## Schedule
BLLIX Project Tracker - Key Dates and Documents
Orientation - Success Criteria/Goals
Goal | Metric | Status
Client Goal #1 | Metric we will use to track
Client Goal #2 | Metric we will use to track
Orientation - Baseline Education Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | n/a
Master Design Document | Link
Configuration and Validation - Delivery and Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | SPS touchpoints - data requirements, troubleshooting steps etc. | In Progress | 0%
Inbound/Putaway | General Receiving(PO, Blind Receipt, Customer Returns), Move Item, Move Stock, Move Container | Completed | 0% | 2025-05-16
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock | Completed | 0% | 2025-05-23
Outbound I | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking | Completed | 0% | 2025-05-30
Outbound II | Packing and Shipping, Repalletize, Rollback After Picking, Void and Reprocess Shipment, Assign Trip to Container | Completed | 0% | 2025-05-30
Reporting | Report Builder, Dashboard Widgets | Open | NA
End to End Testing | Testing all process flows with live data end to end | Open
Validation - User Acceptance Training
Task/Activity | Description | Delivery Date
UAT Onsite Agenda | Link | 6/2/2025 - 6/6/2025 | June 4-6 (Isaac is good)
SOP Documentation | Link to Tango
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 2025-06-11
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps |  | 6/9/2025 - 6/13/2025
Deposco Onsite Support |  | 2025-06-23 | Need to confirm with Jacob
Project Closeout |  | 2025-07-04

## Timeline
| Jan 13 - Mar 7 | Mar 10 - 14 | Mar 17 - 21 | Mar 24 - 28 | Mar 31 - Apr 4 | Apr 7 - 11 | Apr 14 - 18 | Apr 21 - 25 | Apr 28 - May 2 | May 5 - 9 | May 12 - 16 | May 19 - 23 | May 26 - 30 | June 2-6 | June 9-13 | June 16-20 | June 23-27
Project Management
Design
Configuration
Inbound
Inventory Management
Reporting
Outbound
3PL Billing
Validation
Process Testing
Hardware Testing
UAT
Deploy
Cutover
Operational Go live
Post Go Live Support
Project Closeout

## Task Tracker
BLLIX Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | DEP Comments | BLLX Comments
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Setup Client SX Account | Setup Mavenlink with tenant code and General / Project Management tasks | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task |  | FALSE | FALSE | Completed | DEP | Jacob
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task |  | FALSE | FALSE | Completed | DEP | Jacob
Orientation | Begin development for new socket APIs | Deposco Socket team begins development for new socket APIs as per initial project SOW | Task |  | FALSE | FALSE | Closed | DEP | Business Consultant
Orientation | Setup Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network 2) Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task |  | FALSE | FALSE | Completed | DEP/BLLX | Business Consultant / Technical Lead
Orientation | Setup Parcel Carrier Accounts | UPS: Client utilizes Deposco UPS Registration Wizard to setup UPS account FedEx: Clients configures FedEx account and Meter # within Deposco CompanyConfig UI screen | Task |  | FALSE | FALSE | Completed | BLLX | Technical Lead
Orientation | Setup Exisiting Sockets | Client utilizes Deposco help site guides to setup existing socket connections | Task |  | FALSE | FALSE | Completed | BLLX | Technical Lead
Orientation | General Application and UI Overview | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Message Center Overview - Handheld Menu Access | Task |  | FALSE | FALSE | Completed | DEP/BLLX | Full team
Orientation | Begin Master Data Gathering | Sample Master Data templates for items, packs, locations, zones, storages, etc. to be provided by Deposco to be used by client | Task |  | FALSE | FALSE | Completed | BLLX | Client team
Orientation | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task |  | FALSE | FALSE | Completed | BLLX | Warehouse Leads
Orientation | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task |  | FALSE | FALSE | Completed | BLLX | Inbound Lead
Orientation | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task |  | FALSE | FALSE | Completed | BLLX | Outbound Lead / Customer Service Lead
Orientation | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task |  | FALSE | FALSE | Completed | BLLX | Outbound Lead
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | FALSE | Completed | DEP | Solution Lead
Design | Master Design Document Delivery | Deliver master design document for client team to review | Task |  | FALSE | FALSE | Completed | DEP | Solution Lead
Design | Review and Sign Master Design Document | Client to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  | FALSE | FALSE | Completed | DEP/BLLX | Full Team
Configuration | Deliver Inbound Configuration | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Implementation Lead
Configuration | Deliver Inventory Management Configuration | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Implementation Lead
Configuration | Deliver Outbound Configuration Pt 1 | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Implementation Lead
Configuration | Deliver Outbound Configuration Pt 2 | Via demo sessions or loom videos | Task |  | TRUE | TRUE | Completed | DEP | Jacob
Configuration | Deliver Integration Configuration Training | Via demo sessions or loom videos | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-05-30 | 5/27: Jacob working on setting up licensing from DEP side (UPS, FedEx)
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task |  | FALSE | TRUE | Open | DEP | Jacob |  | 2025-06-06
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task |  | TRUE | TRUE | In Progress | BLLX | Amrom |  | 2025-05-23
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task |  | TRUE | TRUE | In Progress | BLLX | Amrom |  | 2025-05-23
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | TRUE | TRUE | In Progress | BLLX | Amrom |  | 2025-05-23
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | TRUE | TRUE | In Progress | BLLX | Amrom |  | 2025-05-23
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab - Setup Amazon, Shopify, Quickbooks | Task |  | TRUE | TRUE | Open | DEP/BLLX | Amrom |  | 2025-05-23
Validation | End to End Test Case Execution | Complete end to end test cases | Task |  | FALSE | TRUE | Open | BLLX | Warehouse Leads + Technical Lead |  | 2025-06-06
Validation | Deliver Onsite UAT Agenda |  | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-05-30
Validation | Train End Users | During UAT and any additional training as needed | Task |  | FALSE | TRUE | Open | BLLX | Amrom |  | TBD | Need to confirm with Isaac on UAT and Go-Live dates
Validation | Review Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task |  | TRUE | TRUE | Open | DEP/BLLX | Full team |  | 2025-06-06 | Need to confirm with Isaac on UAT and Go-Live dates
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-06-06 | Need to confirm with Isaac on UAT and Go-Live dates
Deployment | Execute Cutover Plan Steps |  | Task |  | TRUE | TRUE | Open | DEP/BLLX | Full team |  | 2025-06-13 | Need to confirm with Isaac on UAT and Go-Live dates
Configuration | Confirm Hardware - Printers and Handhelds setup | BLLX to setup majority of Printers and Handhelds and validate | Task |  | TRUE | FALSE | Open | BLLX | Amrom |  | 2025-05-30
Configuration | Outbound: Need DEP to auto send an email | Need DEP to send an email automatically once the Order status changes to "Complete". After Weight and Dims details are entered | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-05-30
Configuration | Receiving: Need DEP to auto send an email | Need DEP to send an email on what has been Received v. Expected. Also include Damaged items. Amron to share detial on what they are looking for | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-05-30
Configuration | Print Box Label | Print Box Label | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-05-30
Configuration | Pallet Label during check-in | Pallet Label during check-in | Task |  | TRUE | TRUE | Open | DEP | Jacob |  | 2025-05-30
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Recordings
BLLIX Demo Videos
# | Date | Category | DESCRIPTION | LINK
Misc DEMOS
1 | 2024-12-20 | Baseline Education Sessions | Deposco User Exerience | https://drive.google.com/file/d/1SDB6gIyKHuCohoLDshXKLuqPny3AR6as/view?usp=drive_link
2 | 2025-01-07 | Baseline Education Sessions | Inbound Overview/Education | https://drive.google.com/file/d/1XkGPhhbOTYm10ij-jHDSLYJy8jVemOiz/view?usp=drive_link
Virtual Design Sessions
1 | 2025-01-13 | Design Sessions | Inbound/Putaway | https://drive.google.com/file/d/18CCGR2ndySP_5iMe-V3K6U7ltRFGXHYh/view?usp=drive_link
2 | 2025-01-14 | Design Sessions |  | https://drive.google.com/file/d/1ZkIWBATHsM4wUHIClFurw-9LFhRsv4eh/view?usp=drive_link
3 | 2025-01-15 | Design Sessions |  | https://drive.google.com/file/d/1F0Qxq5jhngDhQABrM93T0SlM2bRt2rnD/view?usp=drive_link
4 | 2025-01-16 | Design Sessions
Process DEMOS
1 |  | Integrations
2 |  | Inbound/Putaway
3 |  | Inventory Management
4 |  | Outbound I
5 |  | Outbound II
6 |  | Reporting
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## DEP Config Tasks
Deposco Configuration Task List
Product | Task Group | Task | SOW Notes | In Scope | Post Design - Configuration Notes | Owner | Status | % Complete
Bright Warehouse Configuration (T&M) | Inbound | Receiving |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Inbound | Returns |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Inbound | Putaway |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Inventory Management | Item Tracking |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Inventory Management | Kitting |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Inventory Management | Cycle Counting |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Inventory Management | Replenishment |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Outbound | Outbound Order Management |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Outbound | Pickwave Management |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Outbound | Picking |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Outbound | Packing and Shipping |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Outbound | Rate Shopping |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Other | Shipping Documents/Labels |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Other | 3PL Billing |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Setup | System Admin |  | FALSE |  |  |  | 0%
Bright Warehouse Configuration (T&M) | Setup | Data Maintenence |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M) | Configure | Shopify |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M) | Configure | Quickbooks Online |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M) | Configure | UPS |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M) | Configure | FedEx |  | FALSE |  |  |  | 0%
Bright Performance Configuration (T&M) | Standard Dashboard and Reporting | Company Reports / Report Builder |  | FALSE |  |  |  | 0%
Bright Performance Configuration (T&M) | Standard Dashboard and Reporting | Report Scheduling |  | FALSE |  |  |  | 0%
Bright Performance Configuration (T&M) | Standard Dashboard and Reporting | Dashboards |  | FALSE |  |  |  | 0%
Bright Order Configuration (T&M) |  |  |  | FALSE |  |  |  | 0%
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Test Cases - Unit
BLLIX Unit Test Cases
Task | Test # | Scenario | Expected Outcome | Owner | Status | Test Data | Notes
Inbound
Receiving | 1.01.01 | When receiving a purchase order with multiple lines for the same item, the user scans the item to receive in the 'quantity' mode | The user is prompted for the correct order line to receive against. The user selects the specific order line that is being received and proceeds with the receiving process | BLLX Team | Failed
Returns | 1.01.02 | When configured to display notes during receiving, the user scans or enters a purchase order that has notes populated at the header level | The user is displayed the note before the summary screen for the PO is shown | BLLX Team | Invalid
Putaway | 1.01.03 | When configured to display notes during receiving, the user scans or enters a purchase order that has notes populated at the line level | The user is displayed the note after the line item is selected, and before the item is physically received | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.04 | Receive overage against a PO where the overage quantity being received falls below the threshold set up at the item level, regardless of the set up in the workflow process | Able to receive the item and enter the overage quantity. The item setting over rides the workflow setting | BLLX Team | Pass
Inbound/Putaway | 1.01.05 | Receive overage against a PO for an item that does not have the over receipt tolerance set at the item level. Enter a quantity that does not exceed the threshold set at the workflow process level | Able to receive the item and enter the overage quantity. The workflow setting is invoked | BLLX Team | Pass
Inbound/Putaway | 1.01.06 | When prompted to scan the purchase order identifier to receive the purchase, the user scans or enters an invalid purchase order to receive against | The user is displayed an error that the identifier is invalid | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.07 | When prompted to scan the purchase order identifier, the user scans a valid purchase order identifier that exists and has quantity left to receive | The user is taken to the screen to receive the items. The item summary screen is displayed | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.08 | User partially receives the purchase order and hits the 'finish' button to temporarily exit the purchase order | The user is exited from the PO receiving screen. The PO goes to 'Receiving' status | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.09 | User completes receiving the entire purchase order | The user is exited from the PO receiving screen. The PO goes to 'Received' status | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.10 | User scans an item to begin the receiving process | The user is displayed the list of eligible POs for that item. The user selects the PO that the user needs to receive and begins the receiving process | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.11 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.12 | User receives against a non-each pack for a serial tracked item that requires serial capture at picking or packing | The receipt is completed at the non-each pack level. No attributes are captured | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.13 | User receives against a non-each pack for an item that does not have item attribute capture requirements | The receipt is completed at the non-each pack level | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.14 | User receives a item tracked stock | The respective attribute(s) are on the receipt line | BLLX Team | Ready to Test
Inbound/Putaway | 1.01.15 | Receive an item that has an image and confirm that the user is able to see the image on the handheld (adequate size, etc) | The user is able to see the item image on the hand held and complete the receipt | BLLX Team | Ready to Test
Inventory Management |  |  |  | BLLX Team | Invalid
Inventory Management |  |  |  | BLLX Team | Failed
Inventory Management |  |  |  | BLLX Team | Pass
Inventory Management |  |  |  | BLLX Team | Ready to Test
Inventory Management |  |  |  | BLLX Team | Ready to Test
Inventory Management |  |  |  | BLLX Team | In Progress
Inventory Management |  |  |  | BLLX Team | Ready to Test
Inventory Management |  |  |  | BLLX Team | Pass
Inventory Management |  |  |  | BLLX Team | Ready to Test
Inventory Management |  |  |  | BLLX Team | Ready to Test
Outbound I |  |  |  | BLLX Team | Pass
Outbound I |  |  |  | BLLX Team | Pass
Outbound I |  |  |  | BLLX Team | Ready to Test
Outbound I |  |  |  | BLLX Team | Ready to Test
Outbound I |  |  |  | BLLX Team | Ready to Test
Outbound I |  |  |  | BLLX Team | Ready to Test
Outbound I |  |  |  | BLLX Team | Ready to Test
Outbound I |  |  |  | BLLX Team | Ready to Test
Outbound II |  |  |  | BLLX Team | Ready to Test
Outbound II |  |  |  | BLLX Team | Ready to Test
Outbound II |  |  |  | BLLX Team | Ready to Test
Outbound II |  |  |  | BLLX Team | Ready to Test
Outbound II |  |  |  | BLLX Team | Ready to Test
Outbound II |  |  |  | BLLX Team | Ready to Test
Integrations |  |  |  |  | NOT Ready to Test
Integrations |  |  |  |  | NOT Ready to Test
Integrations |  |  |  |  | NOT Ready to Test
Integrations |  |  |  |  | NOT Ready to Test
Integrations |  |  |  |  | NOT Ready to Test
NOT Ready to Test

## Test Cases - End to End
BLLIX End to End Test Cases
Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Receive PO full | Ready to Test | BLLX
Receive partial PO against Inbound Shipment | Ready to Test | BLLX
Receive a customer return from a web order | Ready to Test | BLLX
Receive a customer return for a boutique order | Ready to Test | BLLX
Receive a customer return for an EDI order | Ready to Test | BLLX
Unreceive full PO | Ready to Test | BLLX
Unrecieve partial PO | Ready to Test | BLLX
Unreceive full Inbound Shipment | Ready to Test | BLLX
Unreceive partial Inbound Shipment | Ready to Test | BLLX
Blind receive additional units found after receiving | Ready to Test | BLLX
Putaway
Putaway single item containers | Ready to Test | BLLX
Putaway mixed item containers | Ready to Test | BLLX
Putaway containers to reserve locations | Ready to Test | BLLX
Putaway containers to pickable locations | Ready to Test | BLLX
Putaway loose stock | Ready to Test | BLLX
Outbound
Fulfill single unit web order | Ready to Test | BLLX
Fulfill multi unit web order | Ready to Test | BLLX
Fulfill single unit Boutique order | Ready to Test | BLLX
Fulfill multi unit Boutique order | Ready to Test | BLLX
Fulfill "majors" order under 250 lbs | Ready to Test | BLLX
Fulfill "majors" order greater than or equal to 250 lbs | Ready to Test | BLLX
Fulfill orders that require SSCC Labels on Cartons | Ready to Test | BLLX
Fulfill order with customized product | Ready to Test | BLLX
Fulfill order with "build a bag" product | Ready to Test | BLLX
Fulfill orders with priority ship via | Ready to Test | BLLX
Fulfill orders with generic packing slips | Ready to Test | BLLX
Fulfill orders with customer specific packing slips | Ready to Test | BLLX
Fulfill QVC order | Ready to Test | BLLX
Exception a pick task for a single unit order | Ready to Test | BLLX
Exception a pick task for a multi unit order | Ready to Test | BLLX
Exception a pick task for web order | Ready to Test | BLLX
Exception a pick task for boutique order | Ready to Test | BLLX
Exception a pick task for "majors" order | Ready to Test | BLLX
Cancel an order that has not yet been released | Ready to Test | BLLX
Cancel an order that has been released but not picked | Ready to Test | BLLX
Cancel an order that has been picked but not packed or shipped | Ready to Test | BLLX
Cancel an order that has been packed but not shipped | Ready to Test | BLLX
Roll back an order that has been shipped and cancel it | Ready to Test | BLLX
Roll back an order that has not been shipped and re-ship | Ready to Test | BLLX

## GoNo-Go Decision
BLLIX Go vs No-Go Decision Evaluation
Factors | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 25
Deposco Setup | Label Printers | 10 | Y | BLLX | 0% | 0 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 | Y | BLLX | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful?
Deposco Setup | Scanners and Handheld Devices | 10 | Y | BLLX | 50% | 5 | Are all scanners procured? Deposco app installed? Auto-send features enabled?
Deposco Setup | End users | 10 | Y | BLLX | 75% | 0 | Are all end users configured with user profiles in the system? Logged in successfully?
Deposco Setup | Printer Details | 10 | Y | BLLX | 0% | 0 | Are all printer details configured in Deposco and printer validations passed?
Deposco Setup | Printer Resources | 10 | Y | BLLX | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources?
Deposco Setup | Printer Assignments | 10 | Y | BLLX | 0% | 0 | Are all reports assigned to printers and resources?
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | DEP | 100% | 10 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 |  | DEP | 100% | 10 | Have all jobs have been scheduled and enabled? | not enabled - disabled and run manually
| Warehouse Prep | 40 |  |  |  | 10
Warehouse Prep | Location Labels | 10 | Y | BLLX | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? |  |  | Target to have it setup by next week
Warehouse Prep | Container Labels | 10 | Y | BLLX | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable?
Warehouse Prep | Inventory Labels | 10 |  | BLLX | 100% | 10 | Are all inventory units labeled and scannable?
Warehouse Prep | Network Connectivity | 10 | Y | BLLX | 0% | 0 | Is the internet connectivity strong and cover all necessary scan areas?
| Standard Operating Procedure Documentation | 0 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Create Customer Returns | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Putaway | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Cycle Counting | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Adjust Inventory | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Kitting (Kit To Stock) | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Bulk/FBA Picking | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Batch Picking | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Singles Packing | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | LTL Soft Close Packing | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | LTL Shipping (Wholesale) | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Exceptions in Packing | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
SOP Documents | Customer Order Management | 0 |  | BLLX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members?
| Training & Testing | 50 |  |  |  | 38.5
Training & Testing | Test Case Scenarios Definition | 10 |  | DEP / BLLX | 100% | 10 | Have all unit test cases and end-to end test cases been created and documented for the solution? |  |  | DEP to deliver baseline scenarios and BLLX to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | BLLX | 80% | 8 | Have all unit test cases passed or been marked invalid? Has test data been provided?
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | BLLX | 75% | 7.5 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided?
Training & Testing | Supervisor/Administrator Training | 10 | Y | BLLX | 80% | 8 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes?
Training & Testing | End-user Training | 10 | Y | BLLX | 50% | 5 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes?
| Production Master Data | 60 |  |  |  | 11
Master Data | Cutover Inventory Validation | 10 | Y | BLLX | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? |  |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 | Y | BLLX | 25% | 2.5 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? |  |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 | Y | BLLX | 10% | 1 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? |  |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | BLLX | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? |  |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Kit/Component Relationships | 10 | Y | BLLX | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? |  |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | BLLX | 75% | 7.5 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? |  |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 7.5
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / BLLX | 75% | 7.5 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 34
Interfaces - Imports to Deposco | Carton Types Upload | 10 | Y | BLLX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? |  |  | Jacob to share upload template for this 6/18
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 |  | BLLX | 100% | 10 | Is the Data Exchange accurate and does it meet production needs?
Interfaces - Imports to Deposco | Items/Packs Upload | 0 |  | BLLX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs?
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | BLLX | 100% | 5 | Is the Data Exchange accurate and does it meet production needs?
Interfaces - Imports to Deposco | Trading Partner Upload | 10 |  | BLLX | 90% | 9 | Is the Data Exchange accurate and does it meet production needs? |  |  | Amrom to complete by 6/20
Interfaces - Imports to Deposco | Container Upload | 10 |  | BLLX | 100% | 10 | Is the Data Exchange accurate and does it meet production needs?
| Integrations with Deposco | 40 |  |  |  | 0
Integrations with Deposco | UPS - Get Shipping Label | 10 | Y | BLLX | 0% | 0 | Is the interface accurate and does it meet production needs? |  |  | Jacob and Amrom to review this week
Integrations with Deposco | UPS - Get Rate Shop Request | 10 | Y | BLLX | 0% |  | Is the interface accurate and does it meet production needs? |  |  | Jacob and Amrom to review this week
Integrations with Deposco | FedEx - Get Shipping Label | 10 | Y | BLLX | 0% | 0 | Is the interface accurate and does it meet production needs? |  |  | Jacob and Amrom to review this week
Integrations with Deposco | FedEx - Get Rate Shop Request | 10 | Y | BLLX | 0% |  | Is the interface accurate and does it meet production needs? |  |  | Jacob and Amrom to review this week
| Reports and Labeling | 80 |  |  |  | 51
Reports and Labeling | Shipping Label | 10 | Y | DEP | 0% | 0 | Does the report print from the application accurately and timely?
Reports and Labeling | Packing Slip Report | 10 |  | DEP | 90% | 9 | Does the report print from the application accurately and timely?
Reports and Labeling | Location Label | 10 |  | DEP | 90% | 9 | Does the report print from the application accurately and timely?
Reports and Labeling | Item Label | 10 |  | DEP | 90% | 9 | Does the report print from the application accurately and timely?
Reports and Labeling | FBA Label | 10 | Y | DEP | 90% | 5 | Does the report print from the application accurately and timely?
Reports and Labeling | Carton Type Label | 10 | Y | DEP | 0% | 0 | Does the report print from the application accurately and timely?
Reports and Labeling | LP Label | 10 | Y | DEP | 90% | 9 | Does the report print from the application accurately and timely?
Reports and Labeling | Generic BOL Report | 10 | Y | DEP | 100% | 10 | Does the report print from the application accurately and timely?
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | DEP / BLLX | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? |  |  | Stay on their system
| Total Weighted Score: | 187
| Total Possible Score: | 425
| Total Percentage: | 44%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan
BLLIX Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | BLLX
3 | Set up Shopify | Set up Shopify Instances in Production environment | FALSE | BLLX
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE | DEP/BLLX
5 | Test Order Pull | Create a test order in Shopify and bring order into Deposco | FALSE | BLLX
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify | FALSE
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify | FALSE
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE
10 | Master Data Check - Items | Look through items in production environment | FALSE
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE
18 | Inventory Push to Shopify | Inventory is pushed to shopify | FALSE
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Shopify Instances to bring in orders | FALSE
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE

## Future ItemsParking Lot
BLLIX Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | BLLX Comments

## Open Items
Open Items
TITLE | DESCRIPTION | Date Opened | Priority | Resolution | Done
Views/Filters | BU/Groups specific views/filters | 2025-03-20 |  | One button on Left hand menu. User to toggle between the two views | TRUE
Sales Order Entry | Different required fields for B2B vs B2C orders | 2025-03-20 | Phase 2 |  | FALSE
Check In Process | Listbox of Open IOs | 2025-03-20 | Go live critical | Yes. Using warehouse lookup process | TRUE
Shipping | Close out parcel orders when truck arrives | 2025-03-20 | Go live critical | Yes. Use ATTC, SSPacking with Close Shipment = False | TRUE
PO Entry | Not able to resubmit an PO after initial submit | 2025-03-11 | Phase 2 | Why do we not want to allow changes after initial submit and before BLLIX approval? Make change while "pending". but no change after "approved". What happens if both happen at same time? - DEP to test and confirm | TRUE
Trip Customs Details Process | Adding info for a trip through UI. Want it to be in UI rather than Handheld process. | 2025-03-11 | Phase 2 | Yes. Need custom process | FALSE
Different Outbound Order Entry views per Order Summary | After submit there is second screen - can we control the values here based on order summary |  | Go live critical |  | FALSE
Out The Door Process |  |  | Phase 2 |  | FALSE
Throw error/Remove New button for Order | Client should get an error if they hit New button/remove from screen. If we remove Order create permission, client cannot use Outbound Order Entry |  | Go live critical |  | FALSE
Repalletize rules | Add LPN in listbox showing stock - Validations to ensure no mixed pick details in destination LPN |  | Go live critical |  | TRUE
FALSE
FALSE
Receiving Image Capture | Add image capture rules to receiving - validate in android device that icon is visible on screen for pictures |  | Go live critical | ETA 05-16 | TRUE
Trip Custom Details process | Handheld flow to allow Trip updates to certain attributes and send email to list for BOL upload in DEP |  | Go live critical

## Options
# | Open Item | Resolution | Pros | Cons
1 | Throw error/Remove New button for Order | Remove the Outbound order views completely from the Application menu. Customers can view the orders they have created by clicking into the orders from the Outbound Order Entry UI by either clicking into the order or by clicking the "i" icon to the right of the order | 1. User is forced to use only the Sales Order Entry process, thus resolves the main issue 2. Order information can still be viewed | If the user clicks the order link instead of "i" icon they are taken to this screen that has the "Proceed to Checkout" button. This button only shows more information about the order, nothing can be editted. We are looking to see if this can be greyed out
2 | Different Outbound Order Entry views per Order Summary | This can only be done on a business unit level, not on an order attribute level
Templates can be created for each order summary with pre-filled information, and the user can copy this to create different types of orders
|  | Data Exchange CSV uploads: Define template for both Outbound Orders and Fulfillment Orders. | 1. Can control exactly which attributes we display for user to populate and import. 2. Clients do not need Create Order access and can still upload orders, no risk of clients editing orders. | UI Sales Order Entry application not utilized