## Schedule
ECOATM Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal | Metric | Status
Client Goal #1 | Metric we will use to track | Open
Client Goal #2 | Metric we will use to track | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | https://docs.google.com/document/d/15sqnjN7qtOZoaJ6j11_b4PZn0330JIDEEqUHCyCLDbY/edit?usp=drive_link | 2025-01-31 | 2025-02-06
Master Design Document | LINK
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | API data requirements, troubleshooting steps etc.
Inbound | Receiving(PO, ITO, RMA), Staging, Sortation, Putaway
Inventory Management | Cycle Counts, Adjust Inventory
Outbound | Outbound Order Management, Waving, Picking, Audit, Shipping, Stage/Close
Other - WMS | Transfer orders, 3PL Billing, etc.
Reporting | Report Builder, Dashboard Widgets
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Completion Date
End to End Testing | Testing all process flows with live data end to end
UAT Onsite Agenda | LINK | 0%
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0%
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0%
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned.
Deposco Onsite Support | Travel booked for cutover and go-live week.
Project Closeout | Agreement of final deliverables provided.

## Timeline
| Jan 27 - 31 | Feb 3 - 7 | Feb 10 - 14 | Feb 17 - 21 | Feb 24 - 28 | Mar 3 - 7 | Mar 10 - 14 | Mar 17 - 21 | Mar 24 - 28 | Mar 31 - Apr 4 | Apr 7 - 11 | Apr 14 - 18 | Apr 21 - 25 | Apr 28 - May 2 | May 5 - 9 | May 12 - 16 | May 19 - 23 | May 26 - 30 | Jun 2 - 6 | June 9 - 16 | June 16 - 20
Project Management
Orientation
Design
Onsite Design
Master Design Document
API Support
API Support
Configuration
Inbound
Receiving
Returns
Putaway
Inventory Management
Item Tracking
Cycle Counting
API Development
Outbound
Outbound Order Management
Pick Wave Management
Picking
Packing & Shipping
Rate Shopping
Reporting
Carrier Sockets
SSO Configuration
Validation
Process Testing
Hardware Testing
UAT
Deploy
Cutover
Operational Go live
Post Go Live Support
Project Closeout

## Task Tracker
ecoATM Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | START DATE | DUE DATE | COMMENTS
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Setup Client Mavenlink Account | Setup SX with tenant code and General / Project Management tasks | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task |  | FALSE | FALSE | Completed | DEP | Claire
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  | FALSE | FALSE | Completed | DEP | Steel
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task |  | FALSE | FALSE | Completed | DEP | Steel
Orientation | Setup Users | Deposco guides client super user through user setup with Data Exchange import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task |  | FALSE | FALSE | Completed | DEP | Steel
Orientation | Begin development for new APIs | Stock Update API still pending final design decisions | Task |  | FALSE | FALSE | Completed | DEP | Brian
Orientation | Setup Print Client (Windows) | Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network | Task |  | FALSE | FALSE | Completed | DEP | Daniel |  |  | ECOATM001-2
Orientation | Setup Print Client (Windows) | Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task | 2.High | FALSE | FALSE | Completed | ecoATM | Sudhanshu | 2025-01-31 | 2025-02-28
Orientation | Setup Parcel Carrier Accounts | Client utilizes Deposco help site guides to setup FedEx connection | Task |  | FALSE | FALSE | Completed | ecoATM | Halea | 2025-01-31 | 2025-02-14
Orientation | Setup Parcel Carrier Accounts | Client utilizes Deposco help site guides to setup DHL connection | Task |  | FALSE | FALSE | Closed | ecoATM | Halea | 2025-01-31 | 2025-02-28
Configuration | Inventory API Testing | “customAttribute1” & “customAttribute2” missing from the sample payload on the Developer Portal for this endpoint. This is currently blocking accounting testing. | Issue | 1.Blocker | FALSE | FALSE | Completed | DEP | Brian |  | 2025-06-25 | 5/27/25 [DEP] - Our team has opened a ticket following up on this item internally.
Orientation | General Application and UI Overview | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Data Exchange Overview - Handheld Menu Access | Task |  | FALSE | FALSE | Completed | DEP/ecoATM | Full team | 2025-02-11 | 2025-02-26
Orientation | Begin Master Data Gathering | Sample Master Data templates for items, packs, locations, zones, storages, etc. to be provided by Deposco to be used by client - Item data provided while onsite | Task |  | FALSE | FALSE | Completed | DEP | Johnny | 2025-02-11 | 2025-02-28
Orientation | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task |  | FALSE | FALSE | Completed | ecoATM | Bradley
Orientation | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task |  | FALSE | FALSE | Completed | ecoATM | Bradley
Orientation | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task |  | FALSE | FALSE | Closed | ecoATM | Bradley
Orientation | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task |  | FALSE | FALSE | Completed | ecoATM | Bradley
Orientation | Schedule recurring project calls | Weekly status call Bi-weekly executive steering call | Task |  | FALSE | FALSE | Completed | DEP | Claire
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | FALSE | Completed | DEP | Daniel
Design | Master Design Document Delivery | Deliver master design document for client team to review | Task |  | FALSE | FALSE | Completed | DEP | Daniel
Design | Review and Sign Master Design Document | Client to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  | FALSE | FALSE | Completed | DEP/ecoATM | Full Team |  |  | 5/13 [DEP] Jackie to send integration MDD for signature
Configuration | Deliver Inbound Configuration | Via demo sessions | Task |  | FALSE | FALSE | Completed | DEP | Johnny
Configuration | Deliver Inventory Management Configuration | Via demo sessions | Task |  | FALSE | FALSE | Completed | DEP | Johnny
Configuration | Deliver Outbound Configuration | Via demo sessions | Task |  | FALSE | FALSE | Completed | DEP | Johnny
Configuration | Deliver Integration Configuration Training | Via demo sessions | Task |  | FALSE | FALSE | Completed | DEP | Johnny
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Johnny |  | 2025-05-27
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task | 2.High | FALSE | FALSE | In Progress | DEP/ecoATM | Full team |  | 2025-07-02
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task | 2.High | FALSE | FALSE | Open | DEP | Jackie |  | 2025-07-02 | Track during onsite UAT to ensure no missed on needed setup
Orientation | FedEx Setup | Hazardous items giving error during setup | Task | 2.High | FALSE | FALSE | Completed | ecoATM | Halea |  | 2025-05-30 | 6/24 [ecoATM] Joe followed up, but no response on the signing yet. Updated devices to not be hazardous to complete testing. 6/17 [ecoATM] - Hazard form being signed internally for FedEx to complete setup. 6/3/25 [ecoATM] Escalated with FedEx 5/20/25 [DEP] - Halea to reach out to FedEx rep about error message
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task | 3.Medium | FALSE | FALSE | Completed | ecoATM | Andrew |  | 2025-05-09
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task | 3.Medium | FALSE | FALSE | Completed | ecoATM | Inventory Lead |  | 2025-05-16 | 5/2725 [DEP] Workflow for stock unit verification requires an additional scan.
Validation | Deliver Onsite UAT Agenda | Deliver onsite UAT agenda | Task | 3.Medium | FALSE | FALSE | In Progress | DEP | Implementation Lead |  | 2025-07-31 | Daniel created draft
Validation | Train End Users | During UAT and any additional training as needed | Task | 3.Medium | FALSE | FALSE | Open | ecoATM | Warehouse Leads |  | 2025-07-25
Validation | Unit Test Cases - Outbound | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 3.Medium | FALSE | FALSE | In Progress | ecoATM | Outbound Lead |  | 2025-05-27
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task | 3.Medium | FALSE | FALSE | In Progress | ecoATM | Technical Lead |  | 2025-06-10 | 7/29/25 - POI issue still open
Validation | End to End Test Case Execution | Complete end to end test cases | Task | 3.Medium | FALSE | FALSE | In Progress | ecoATM | Warehouse Leads + Technical Lead |  | 2025-06-13
Deployment | Execute Cutover Plan Steps |  | Task | 3.Medium | FALSE | FALSE | Open | DEP/ecoATM | Full team |  | 2025-08-18 | Reviewed in weekly status on 7/21
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task | 3.Medium | FALSE | FALSE | In Progress | DEP | Implementation Lead |  | 2025-07-31
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task | 3.Medium | FALSE | FALSE | Open | DEP | Jackie |  | 2025-08-04
Configuration | FedEx and Sortation Enhancement | FedEx shipping and sortation enhancement | Task | 3.Medium | FALSE | FALSE | Completed | ecoATM |  |  | 2025-06-20 | Enhancements planned for delivery on Thursday, 6/19.
Orientation | Setup Parcel Carrier Accounts | ecoATM to utilize Deposco help site guides to setup Stamps connection | Task | 4.Low | FALSE | FALSE | Hold | ecoATM | Halea | 2025-01-31 | 2025-02-28
Validation | API 2.0 Ticket - Payment Status | [IMS-400] Deposco API: Unable to Update Payment Status to Approved – Deposco API Rejects Update for Orders in 'Staged' Status - JIRA | Issue | 1.Blocker | FALSE | FALSE | Completed | DEP | Brian |  |  | Work-around in API 1.0
Validation | API 2.0 Ticket - Serial Number instead of the Acquisition Cost | [IMS-413] DEPOSCO: InventoryAdjustment API 2.0 returns Serial Number instead of the Acquisition Cost - JIRA | Issue | 1.Blocker | FALSE | FALSE | Completed | DEP | Daniel
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## RecordingsDemos
ecoATM Demo Videos
Date | Category | DESCRIPTION | LINK
Baseline Education
| Deposco User Exerience | User Experience/Application Overview Demo | https://drive.google.com/file/d/1GSaQQD2g-VQLefRzkri7X2zN-ce3ztC-/view?usp=drive_link
Master Data
| Manifest Upload (Data Exchange/Field Mappings) | Recording on Manifest Upload and general walk through of Data Exchange and Field Mappings | https://www.loom.com/share/9bd12f9797574955b168de0feae714b0
Process Demos
Integrations
2025-04-09 | Inbound/Putaway | Inbound Demo Session | https://drive.google.com/file/d/1S-TE2L4vlKiEfNBZEaLy1gZMx6iTWtYT/view?usp=drive_link
| Inbound/Putaway | Case Lot Direct Putaway | https://www.loom.com/edit/3521717ef953427d9f1428aa40aa70d9
2025-04-22 | Inventory Management | Inventory Management Demo Session | Recap: ECOATM <> DEP Inventory Management Demo Session
| Inventory Management | Requested Error Message Change | https://www.loom.com/share/6d9faf11ceea4400920fa90e517c8ae5
| Outbound - Part 1 | Outbound 1 Demo Session | https://drive.google.com/drive/folders/1YyhgDbdpPXf_A5XGTjlvV3oi1cexYOV8
| Outbound - Part 2 | Outbound 2 Demo Session | https://drive.google.com/drive/folders/1YyhgDbdpPXf_A5XGTjlvV3oi1cexYOV8
| Reporting | Reporting Demo Session | https://drive.google.com/drive/folders/1YyhgDbdpPXf_A5XGTjlvV3oi1cexYOV8
Miscellaneous Session Recordings
Testing/Training Support
| Inbound | Inbound Working Session 4/18/25 | Recap: ECOATM <> DEP Inbound Working Session April 18
| How to test a printer |  | https://www.loom.com/share/8be66022f2e74c298003040ddff1f863
| Inventory Management | Inventory Management Working Session | https://drive.google.com/drive/folders/1YyhgDbdpPXf_A5XGTjlvV3oi1cexYOV8
| Outbound | Outbound Working Session | https://drive.google.com/drive/folders/1YyhgDbdpPXf_A5XGTjlvV3oi1cexYOV8
| Case Lot Picking |  | https://www.loom.com/share/cf84a68a4690429bb81859b362cf6846
Assigned Trip (IMS-509)

## Deposco Configuration Tracker
Deposco Configuration Task List
Product / Task Group | Task | SOW Notes | In Scope | Post Design - Configuration Notes | Owner | Status | % Complete
Bright Warehouse Configuration (T&M)
Inbound | Receiving | Setup & configuration for receiving process | TRUE | Data Exhange Inbound Transfer Order: - Set in similar way to LPN Receiving Template, the only thing that we will change will be the order type (done) -We will need these order statuses and order line statuses to be set "New" status since the initial upload (done) | Johnny | Complete | 100%
Inbound | Receiving | Setup & configuration for receiving process | TRUE | Data Exhange Purchase Order LPN Receiving: - Set the Current Status as New (done) - Default Quantity to 1 (done) - Default Status to New (done) -Set OL Line status to "New" (done) - Default type to Purchase Order (done) Business Rule to Prevent Users from logging into either or if the attribute doesn't match the button they are using (ie: Scan manifest for unit in Case receiving) (done) - import type field: Stamp Either "Case" or "Unit". (done) - We will include the lpn field at the order line level (done) | Johnny | Complete | 100%
Inbound | Receiving | Setup & configuration for receiving process | TRUE | Data Exhange Purchase Order: - Set the Current Status as Draft (done) - Default Quantity to 1 (done) - Default Status to Draft (done) -Set OL Line status to "Draft" (done) - Default type to Purchase Order (done) -Import Type - Case or Unit (done) Business Rule to Prevent Users from logging into either or if the attribute doesn't match the button they are using (done) - We will need to add columns to for import type to Stanp Either "Case" or "Unit". (done) - We wont include the lpn field at the order line level (done) | Johnny | Complete | 100%
Inbound | Receiving | Handheld Rewording Changes | TRUE | -Remove Item Listbox in receivingitemscreen (done) -Rename label “SKU” to “IMEI” in receivingitemscreen (done) - Default Quantity to 1 (done) - Default Status to Draft (done) -Set OL Line status to "Draft" (done) - Default type to Purchase Order (done) - Default Item number to INT101 (done) -ReceiveLPNScreen - edit item listbox to include description instead of item.number (done) -Rename “Total” label in receiveLPNScreen to “# of Boxes” (done) -Default Direct Putaway to NO and remove from screen (done) -Remove Summary from identifier input screen (done) | Johnny | Complete | 100%
Inbound | Receiving | Setup & configuration for receiving process | TRUE | Button #1: Unit Receiving - Receive by serial number in grocery scan fashion (done) - Always auto stage to "Receiving" (done) - Force receiving to a container (done) - Add business rules in the create stock unit post to stamp the serials in the stock unit serial number and in the stock unit inventoryAttribute1 --> We will need to also stamp other attributes outlined in API MDD (done) -- business rule in the post of the first screen to validate that unit import type orders only are using the imei receiving (done) - After receipt of items, stamp acquisition cost on Stock Unit | Johnny | Complete | 100%
Inbound | Receiving | Setup & configuration for receiving process | TRUE | Button #2: Case Lot Receiving - Receive by LPN on order line (done) - Always auto stage to "Receiving" (done) - Add business rules in the create stock unit post to stamp the serials and other attributes in OL to respective fields in SU (done) serials in the stock unit serial number and in the stock unit inventoryAttribute1 (done) --- business rule in the post of the first screen to validate that case import type orders only are using the lpn/box receiving (done) - After receipt of items, stamp acquisition cost on Stock Unit (done) | Johnny | Complete | 100%
Inbound | Receiving | Setup & configuration for receiving process | TRUE | Button #3: Inbound Transfer Receiving - Putaway set to TRUE -- use putaway rules - We will also need to stamp the stock unit with the attributes passed in the OL into the RL and Stock Unit | Johnny | Complete | 100%
Inbound | Repalletize | Will be used to break multi sku case lots (box) | TRUE | Business rule to load the item number once the serial number has been scanned | Johnny | Complete | 100%
Inbound | Returns | Recieve against customer return orders | TRUE | Button: RMA Receiving - Order Type = Customer Return (done) - Customer Return Button (done) - Each Order Lines Needs a Note associated to display to the receiver - Reason Codes Below: - Defect confirmed (no restocking fee) - No defect found (apply restocking fee) - Unexpected device (50% restock fee) - Add field to display the short description | Johnny | Complete | 100%
Inbound | Sortation | Sort Devices into | TRUE | Move Item Process: - See MDD for proposed flow - Boxes will be set as locations (done) - Business Rules to change the suggested putaway screen based on the attributes in the MDD - XAML text field to input the slot number (done) - Business rule to stamp the slot number into the location customAttribute1 after the move has happened (done) | Johnny | Complete
Inbound | Putaway | Setup and configuration of putaway processes with anticipated putaway rules by item attributes. Use of new directed putaway process along with use of existing move processes for different staging steps and sortation processes. | TRUE | - #1: Consolidate by sku and age Consolidate by sku if capacity exists in location and no device in current location is older than x days ( we might need to add a distinct count of item IDs for this) - #2: Empty location in zone Based on product category or based on zone. #3: Capacity checks (We might need to add storage details to get the min/max values of that locaton. Whatever is set as the pack doesn't really matter) : Cannot put more than 5 distinct skus to a location No ability to override suggested location Show any location returned by the above in the picking zone(s) (even if stock already exists there) - Business rule to blank location customAttribute1 from the box used in sortation once the last sku has been moved | Johnny | Complete | 100% | Sort type update back to TINC in move back to DT | Initial scan: Populate Slot Number textbox and box text box If sort exists: populate the existing slot number as message
Inventory Management | Stock Unit Tracking | Use of LPNs, serial number tracking, inventory attribute tracking | TRUE | Stock Unit Attributes That Need Tracking (We need to check If we have enough fields for all of these): number = itemNumber quantity packType = Each actionType = ADJ businessUnitCode = ECOATM processCode: CR = Adds Inventory DR = Deducts Inventory adjustmentFacility = LVL adjustmentLocation = stagingLocation (ie Receiving, Device Testing etc.) effectiveDate (ie 2025-02-26T13:42:32-05:00) serialNumber = ecoATM LPN inventoryAttribute1 = IMEI inventoryAttribute2 = (4) Encumbrance (Use of “Standardized Codes”) BlockList (BL) FMI (FMI) MDM (MDM) CarrierFinancial (CF) BlockList + FMI (BL-FMI) etc. inventoryCondition = Sort Type / Grouping | Johnny | Complete | 0%
Inventory Management | Item Tracking | Use of LPNs, serial number tracking, inventory attribute tracking | TRUE | Inumber = SKU or item number in Oracle businessUnit ID = 73 businessKey code = ECOATM salesEnabled = true (Inventory Item Status) shippableFlag = true inventoryTrackingEnabled = true serialTrackingEnabled = true cycleCount =true originCountry: Populated via “Automations” customAttribute1 = modelYear customAttribute2 = carrier customAttribute3 = capacity customAttribute4 = condition customAttribute5 = Itemtype (i.e. INT, GSB, PWS) size = grade styleName = targetSalesChannel productCategory = category brandName = brand name = model colorName = colorName colorCode = sortableColor Populated via “Automations” longDescription = longDescription shortDescription = model-color externalImageUrl = imageURL | Johnny | Complete | 0%
Inventory Management | Cycle Counting | Setup and configuration for cycle count process. Includes adjust inventory process for inventory transfers. | TRUE | - Cycle Counting will be done using our base processes - The user will scan the serial instead of the item number/upc -Monthly Cycle Counts → Set cycle count frequency to 30 - Serial Cycle Count Enhancements (nice to have): Request: Enhance cycle counting using SUPPORT_SERIAL_NUMBER_SCAN to handle unexpected serial numbers found in a location. (This is on Daniel) - Make sure that you validate scenarios where there are multiple serials for one same SKU. Validate that scanning one serial doesnt count all of them. | Johnny | Complete | 0%
Inventory Management | Adjust Inventory | We will use it to decrement inventory for the system | TRUE | Make The following cosmetic changes to the Buttons: Consume by Item = Consume by Unit Consume by LPN = Consume by Box Consume by Location = Consume by Location Create Inventory → Remove completely from screen We will add the following reason codes in the SI field: Reason Codes: Transfer from Wholesale Write off Etc. We will need to configure the item description to show instead of the item number. This might not be possible through base. Lets assess If this is really necessary because we would need to override the screen | Johnny | Complete
Outbound | Outbound Order Management | - Anticipated support for Automations setup and configuration. - Return to Vendor order creation/processing. | TRUE | - Address Validations -> FedEx setup NTH (The tenant script function only applies to Domestic orders --> The condition should be oh.shipToCountry =="US" - Lookup table to store the different account numbers and write POI rules to trigger stamping different account numbers based on the weight or count of containers Lookup Table Columns: Trading Partner Code, Account Type, Ship Via. Rule for # of containers is = Total Unit Count/50 - Hold status if there is no sale price on the order line (will not use item level unit price) - Automations: Set Country of Origin to CN if Apple, If Samsung then KR - Want unit price to come from Order, not from Item | Johnny |  | 0%
Outbound | Order Release Profile | Order Release Profile Configuration | TRUE | Order Release Profile: Single Order Picking Oldest Stock then Pick Sequence All stock on order to fulfill | Johnny |  | 0%
Outbound | Pickwave Management | One waving profile, work group splits by units and zone (where zone = product category, phones vs tablets), one order per wave | TRUE | - Name: PWS-externalOrderNumber-TPCode-BuildTimeWithSeconds - Split work group by zones - Max 50 tasks in phone zone group all the phone zones so they dont get split - Max 10 tasks in tablet zone. group all the phone zones so they dont get split - Max 3 tasks in case lot zone - Repurpose Description Boolean field to decide if it is priority or not. This will need to bump up the wave if this field is checked - Add External Order Number to the pickwave instead of Deposco Order Number - Cellphone, Tablet & Case Lots Zones to split during waving - Second wave profile: Repicks Back order with wave attached and partial pick | Johnny |  | 0%
Ourbound | Build and Release Scheduler | Build and Release Scheduler | TRUE | Sort orders by created date (oldest to newest) --> You will have to modify the config manager query for this Scheduler to run at 7am daily (ecoATM will change)
Outbound | Picking | Setup and configuration for single scan picking process | TRUE | Pickwave Selection Display Screen: - Sort by created date (oldest to newest) but put orders with “priority” flag ability on pickwave - Single Scan Picking with Split Screen + Image Display - Opportunistic count in single scan picking with threshold of 1 - Picking into the shipping container itself - If there is an exception then we will set the stock unit into a hold status instead of the location -Pregenerate picking LPN numbers -Stage boxes after picking. Step where invoices are sent (Generic Shipping Locations) Screen Changes: - Change item number to description - Remove pick quantity since it will always be 1 - Add color - Remove Available Quantity - Display count of boxes (count of workgroup in the order) - Webhook to trigger message to Oracle --> This will be on Brian to design | Johnny |  | 0%
Outbound | Inbound Transfer Order | Set up Build Transfer Order Process | TRUE | -User will build up the transfer order by scanning individual LPNs to a TO - We will be shipping to facility RTV and the transfer reason code should be Return to Vendor - We need to generate shipping labels for these TOs - Dynamically change the Destination location for the TO based on the Vendor (TP). Still thinking on how to do this
Outbound | Single Scan Packing | - Setup and configuration for packing and shipping processes - Packing w/ a stage option, attc to close out | TRUE | - All else through single scan packing with close ship/generate ship label = false - Stage after pack to a location in PWS Staging Zone – if first work group finished in an order can stage anywhere in zone else stage to location where other boxes for order are staged (We will need to add business rules to tell the user where to stage the box. This will be the auditing step - Screen Change – Add a total count of items in box below the listbox. Just a text field for the count Like Total: 50 in blue makes sense Stage after SSPack with logic identified above Remove dims screen | Johnny |  | 0%
Outbound | Single Container Packing (Parcel Only) | - Setup and configuration for packing and shipping processes - Used for Case Lots | TRUE | - Case Lots will go through single container packing - Create parcel labels but still do not close - Autopopulate carton type - Use weight for scale | Johnny |  | 0%
Outbound | Shipping | - Setup and configuration for packing and shipping processes - Packing w/ a stage option, attc to close out | TRUE | - No signature required - No Saturday Shipping - TP flag for insurance required - LPN and Order Number for label in shipping option (FedEx) - Interrupt/hold flag (Rules to prevent user from shipping an orer that has the interrups/hold flag enabled) - Add “Payment Status” field that validates if an order is ready to be packed (Add rule to prevent order from being packed out if Payment status is not there) - We need to set a dashboard to display which orders can go through the generation of label process | Johnny |  | 0%
Outbound | Assign Trip To Containers | - Process To close out the shipments at the end of day | TRUE | Assign Trip Button #1: “Parcel Assign Trip” → select carrier as dock door, scan box license plate to pallet – keep adding to it throughout the day → close when truck is gone - Add business rules to prevent assigning orders with a specific ship vendor to incorrect door. Eg: Fedex goes to FedEx | Johnny |  | 0%
Outbound | Assign Trip To Containers | - Process To close out the shipments at the end of day | TRUE | Assign Trip Button #2: - “Freight Assign Trip” → more common scenario - Need a button to print BOL outside of Assign Trip based on LPN | Johnny |  | 0%
Outbound | Rate Shopping | Rate shopping at packing across licensed parcel carriers | TRUE | - We need to decide when we need rate shopping to be triggered | Johnny |  | 0%
Outbound | Void Labels | Void Labels | TRUE
Other | Shipping Documents/Labels | (no notes) | TRUE | - Shipping Labels after single container packing - BOL at the end of freight shipping (ATTC Button 2) | Johnny |  | 0%
Setup | System Admin | (no notes) | TRUE |  | Johnny |  | 0%
Setup | Data Maintenence | Support for preliminary master data setup and data exchange import templates. - locations and zones - inbound orders - items and packs | TRUE | Data Exchanges for Manifest especified at the first rows of this file - Storage Upload - Location Zones - Stock Unit Printer Resources and Assignments - Item Upload | Johnny |  | 0%
Bright Socket Configuration (T&M)
Configure | API Support | Support for use of Deposco's REST API by ecoATM team who will be building the connection between Deposco and ecoATM systems. Refer to integration diagram for endpoints in scope. ***Includes an additional 20 hours for new API for serialized item grading conversions. ***Any additional hours needed will require SOW/CR | TRUE | This is on Brian. Once we have the APIs built up we will be able to test some scenarios. We will communicate with you once this is ready for you to test through postman | Brian |  | 0%
Configure | UPS | (no notes) | TRUE | On ecoATM to set up carrier account | ECOATM | In Progress | 50%
Configure | FedEx | (no notes) | TRUE | On ecoATM to set up carrier account | ECOATM | In Progress | 50%
Configure | DHL | (no notes) | TRUE | On ecoATM to set up carrier account | ECOATM | In Progress | 50%
Configure | Stamps.com (USPS) | (no notes) | TRUE | On ecoATM to set up carrier account | ECOATM | In Progress | 50%
Bright Performance Configuration (T&M)
Standard Dashboard and Reporting | Company Reports/Report Builder | (no notes) | TRUE | Scheduled Email Reports Report of encumbrance and count of associated items Aging inventory report for each of the testing locations Report of units/IMEI in contact sales location with the incumbrance detail and Manifest Number Report Builder Reports Orders shipped by date range with filters for zones. Stock on hand reports with filters for zones and locations Count of items on order compared to count of items in container for Items in Contact Sales Location Report |  |  | 0%
Standard Dashboard and Reporting | Report Scheduling | (no notes) | TRUE | ECOATM to decide which reports and when to send the reports |  |  | 0%
Standard Dashboard and Reporting | Dashboards | (no notes) | TRUE | We will need to set the following dashboards: - Inbound - Outbound - Sortation - PAcking/Shipping - Inventory Requests of Widgets Orders Shipped per Day Shipments created per Day Aged Orders Number of units and orders unshipped Open orders Orders on hold Stock Unit On Hold Sale Summary widget Count of items in each process in warehouse (testing, received, sorted) (Report of units/IMEI in contact sales location with the incumbrance detail and Manifest Number) Summary Drilled in version Ready to ship orders |  |  | 0%
Dashboard and Reporting add-on | Report Scheduling | (no notes) | TRUE |  |  |  | 0%
Dashboard and Reporting add-on | Data Archive | (no notes) | TRUE | We will dump data at the EOD to their snowflake instance. We will need to make sure we set up the connection in a successful way. Check CLPK for reference |  |  | 0%

## Unit Test Cases (INTERNAL TEST) (hidden)
eco ATM Unit Test Cases |  | Category | % Complete
|  | Integrations | 0%
|  | Inbound | 0%
|  | Inventory Management | 0%
|  | Outbound | 0%
|  | Other WMS | 0%
|  | Reporting | 0%
|  | TOTAL | 0%
Category | Subcategory | Scenario | Expected Outcome | Owner | Status | Test Data | Comments
Integrations
Integrations | FedEx - Rate Shop | Retrieve rates for domestic shipment |  |  | NOT Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for international shipment |  |  | NOT Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for Saturday Delivery shipment |  |  | NOT Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for all relevant Ship Vias: |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for all relevant Ship Vias: FedEx Ground, FedEx Home Delivery etc. |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve domestic shipping label |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve international shipping label |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label using Prepaid Freight Terms Type |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label using Collect Freight Terms Type |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label using Third Party Freight Terms Type |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for Saturday Delivery shipment |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for Residential shipment |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for shipment where Insurance is required |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for shipment where Delivery Signature is required |  |  | NOT Ready to Test
Integrations | FedEx - Shipping Documents | Retrieve Commercial Invoice for international shipment |  |  | NOT Ready to Test
Inbound
Inbound | Pre Receiving - Manifest Creation | User creates Purchase Order (Manifest) using Manifest Upload Data Exchange | - Purchase order is created successfully in environment (Draft Status) - Order Header Type is stamped onto ol.priceCode (Order Type) | ecoATM Team | Ready to Test | Order: TESTDEMOPO1
Inbound | Pre Receiving - Case Lot Manifest Creation | User creates Case Lots Order using Case Lot Manifest Upload Data Exchange | - Case Lot Purchase order is created successfully in environment (New Status) - Order Header Type is stamped onto ol.priceCode (Order Type) | ecoATM Team | Ready to Test | Order: TESTDEMOCL1
Inbound | Pre Receiving - ITO Creation | User creates Inbound Transfer Orderr using Inbound Transfer Order Upload Data Exchange | - Inbound Transfer Order Uploadr is created successfully in environment (New Status) - Order Header Type is stamped onto ol.priceCode (Order Type) | ecoATM Team | Ready to Test | Order: TESTDEMOITO1
Inbound | Pre Receiving - Customer Return Creation | User creates Customer Return using Inbound Customer Return Upload Data Exchange or via API | Customer return order is created successfilly in environment | ecoATM Team | Ready to Test
Inbound | Pre Receiving - Customer Return Creation | User creates Customer Return via HandHeld process (Create RMA) | User inputs order number and continues throught the receiving process. A new customer return order will be created at the end of the process when items have been received | ecoATM Team | Ready to Test
Inbound | Pre Receiving - Purchase Order Line Cancelation | User cancels Purchase Order manually in the UI using Process Action Link "Cancel Enitre Order" or pushes updated via API | Order status is updated to "Cancelled" and Canceled Pack Quantity is updated | ecoATM Team | Ready to Test | Order: CANCELPOTEST | Order Status must be "New"
Inbound | Pre Receiving - Purchase Order Cancelation | User cancels Purchase Order Line manually in the UI using Process Action Link "Cancel Order Line" or pushes updated via API | Order status is updated to "Partially Cancelled" and Canceled Pack Quantity is updated for associated line | ecoATM Team | Ready to Test | Order: CANCELPOLINETEST Order Line: CANCELPOLINETEST--2, CANCELPOLINETEST--5
Inbound | Receiving - IMEI Receiving | User scans container and manifest number in "IMEI Receiving" button to start receiving process | User is brought to the item list screen and is able to scan IMEIs to start receiving stock into the system | ecoATM Team | Ready to Test | Order: 196
Inbound | Receiving - IMEI Receiving | User scans manifest but not a container | Error message will be displayed | ecoATM Team | Ready to Test | Order: 196
Inbound | Receiving - IMEI Receiving | User scans a manifest with type of "Case" in "IMEI Receiving" | Error message will be displayed | ecoATM Team | Ready to Test | Scanned order: 197
Inbound | Receiving - IMEI Receiving | User scans an IMEI that is NOT on the manifest scanned to start receiving process | User gets an error message saying the item does not belong on the order | ecoATM Team | Ready to Test | Order: 196 IMEI Scanned: 12459412
Inbound | Receiving - IMEI Receiving | User inputs/scans item number instead of IMEI | Error message will be displayed | ecoATM Team | Ready to Test | Order: 196
Inbound | Receiving - IMEI Receiving | User scans an IMEI that is on the manifest | Inventory is received and autostaged into the "Receving" location. user is brought back to the Item list screen to continue receiving process | ecoATM Team | Ready to Test | Order: 196 IMEI Scanned: 1231293
Inbound | Receiving - IMEI Receiving | User selects "New LPN" when box is full | User is able to continue receiving the rest of the items on the manifest in the new container | ecoATM Team | Ready to Test | Order: 196 Container Scanned: JY2
Inbound | Receiving - Case Lots Receiving | User uses "Box Receiving" and inputs a manifest number to start the case lot receiving process | User is brought to the item list screen and is able to scan the containers on the manifest | ecoATM Team | Ready to Test | Order: 197
Inbound | Receiving - Case Lots Receiving | User scans a manifest with type of "Unit" in "Box Receiving" | Error message will be displayed | ecoATM Team | Ready to Test | Order: 197 Scanned: 196
Inbound | Receiving - Case Lots Receiving | User scans an inbound LPN that is NOT on the manifest | Error message will be displayed | ecoATM Team | Ready to Test | Order: 201 Scanned: case1000
Inbound | Receiving - Case Lots Receiving | User scans an inbound LPN that is on the manifest | Inbound LPN will be transported to a container and the container is staged at the "Receiving" location. Order status will be updated to "Received" | ecoATM Team | Ready to Test | Order: 197 Scanned: JYCASE
Inbound | Receiving - Customer Returns | User goes into "Customer Returns" and inputs a container and existing customer return order number | User is brought to item list screen | ecoATM Team | Ready to Test | Order: CRTESTRECEIVE
Inbound | Receiving - Customer Returns | User scans an Customer Return that does not exist in the system | Error message will be displayed | ecoATM Team | Ready to Test | INPUTTED: DEPOSCO999999
Inbound | Receiving - Customer Returns | User scans an Customer Return that is on the manifest | User is brought to the "Reason Code and Credit Screen" where they are asked to select a "No Refund" or "Refund Approved" | ecoATM Team | Ready to Test | Order: CRTESTRECEIVE IMEI: IMEITEST0012
Inbound | Receiving - Customer Returns | Customer return note (posted via API) will be displayed on the screen which will be used to determing if a refund will be processed or not for the order | User is brought to the "Reason Code and Credit Screen" where they are asked to select a "No Refund" or "Refund Approved" | ecoATM Team | Ready to Test | Order: CRTESTRECEIVE
Inbound | Receiving - Customer Returns | User receives an order with a note titled "Return Notes" in the order line level | The note tied to the order line will appear for the user in the "Order Line Notes Screen" | ecoATM Team | Ready to Test | Order: 345 Orderline: 345--1,345--2 Note: "THIS IS A DEFECTIVE ITEM", "THIS ITEM IS THE WRONG COLOR"
Inbound | Receiving - Customer Returns | User selects Refund Approved or No Refund in Reason Code Screen | Customer Return order and order line status are updated to received | ecoATM Team | Ready to Test | Order: CRTESTRECEIVE
Inbound | Receiving - Inbound Transfer Order | User scans Inbound Transfer Order number to start process in "IMEI Receiving" | Error message will be displayed | ecoATM Team | Ready to Test | Order: TESTITOJY0001
Inbound | Receiving - Inbound Transfer Order | User scans Inbound Transfer Order number to start process in "Box Receiving" | User is brought to a screen with listbox of all available inbound LPNs on the order and is able to scan a container to start receiving items | ecoATM Team | Ready to Test | Order: TESTITOJY0001
Inbound | Receiving - Inbound Transfer Order | User scans a inbound LPN not on the order | Error message will be displayed | ecoATM Team | Ready to Test | Order: TESTITOJY0001 Scanned: NOTBOX
Inbound | Receiving - Inbound Transfer Order | User scans inbound LPN on the order | Items are received and can be putaway directly from the receiving location. No additional testing for the item is needed. Order status is updated to "Receivied" | ecoATM Team | Ready to Test | Order: TESTITOJY0001
Inbound | Receiving - Inbound Transfer Order | User partially recieves ITO | Order is updated to partial receipt, and users are able to go back at a later time and continue receiving the order | ecoATM Team | Ready to Test | Order: 328
Inbound | Receiving - Inbound Transfer Order | User comes back to a partially received order at a later time | User is able to contine and finish the receving process for the order | ecoATM Team | Ready to Test | Order: 328
Inbound | Unreceiving | User scans a PO that is not in a "Received" status | Error message will be displayed | ecoATM Team | Ready to Test | Order: 312
Inbound | Unreceiving | User scans PO that is in "Received" status | User is brought to Item list screen with all items on PO available to be unreceived | ecoATM Team | Ready to Test | Order 316
Inbound | Unreceiving | User inputs an item NOT on the PO | Error message will be displayed | ecoATM Team | Ready to Test | Order: 316 Item Inputted: Unknown
Inbound | Unreceiving | User inputs/scans an item on the PO | Item is unreceived and is depreacted from the item listbox. A negative receipt line is created for the order line | ecoATM Team | Ready to Test | Order: 332
Inbound | Move Container to Testing | User inputs a received container to start the move container process | User is brought to the destination location screen | ecoATM Team | Ready to Test | Container: r3412
Inbound | Move Container to Testing | User inputs "Device Testing" into destination location | Stock unts from container are moved to the Device Testing location and the container is disacciated | ecoATM Team | Ready to Test | Conatainer: r3412 Inputted: Device Testing
Inbound | Putaway - Sortation | User scans location/zone that they are currently in on the "Change User Zone Screen" | User is brought to the "Location Input Screen" and is prompted to scan the barcode located at their sortation station | ecoATM Team | Ready to Test | Selected: Sortation2
Inbound | Putaway - Sortation | User scans the barcode at their desk | User is brought to "Move Item Screen" and is able to scan the items that are in the box they brought to their sortation station from the testing zone | ecoATM Team | Ready to Test | Inputted: Device Testing
Inbound | Putaway - Sortation | User scans an available IMEI in the Device Testing location and the box is empty and the sortation station does not have an existing sort type for the item | user will be able to assign a container (box) that the device will be put into as well as a slot location at the sortation station | ecoATM Team | Ready to Test | Serial Scanned: 1245321512
Inbound | Putaway - Sortation | User scans an item with the same sort type as an existing item already sorted in the sort station and the box is not full yet | User is prompted to put the item in the specific sort type combination that exists in the station | ecoATM Team | Ready to Test | Serial Scanned: 1523462462
Inbound | Putaway - Sortation | User scans an item with the same sort type as an existing item already sorted in the sort station and the box is full | The sortation box will not be visible a tthe "Suggested Putaway" screen and is able to assign a new box/slot for the item. User will know to putaway full box when they see the box is full physically | ecoATM Team | Ready to Test | Changed Max Storage for Box01 to 1 and scanned serial 1245321512
Inbound | Putaway - Pickface | User scans full box from sortation station in the "3.Putaway" button in the receiving process | User is brought to "Move Item Screen" where all items in the box will be listed | ecoATM Team | Ready to Test | Location (Box) Scanned: Box01
Inbound | Putaway - Pickface | User scans item that in not in the container | Error message will be displayed | ecoATM Team | Ready to Test | Inputted: NONITEM141241
Inbound | Putaway - Pickface | User scans IMEI that is in the container and there are existing stock of the same item in a Pickface location | User is brought to "Putaway Location Screen" with the location number that has stock of the same item | ecoATM Team | Ready to Test | Scanned: 1523462462
Inbound | Putaway - Pickface | User selects the location that is prompted | Item is moved to the selected location and user is brought back to the "Move Item" screen to continue the process until all items in the box have been putaway | ecoATM Team | Ready to Test | Scanned: PHONEPF05
Inbound | Putaway - Pickface | User scans IMEI that is in the container and there is perexisting stock of the same item, the devices in the location are not "x" days old, and location has available capacity | User will be brought to "Putaway Location Screen" with a list of locations that match the criteria in the scenario | ecoATM Team | Ready to Test
Inbound | Putaway - Pickface | User scans IMEI that is in the container and item does not match any criteria in the previous scenario | User will be brought to "Putaway Location Screen" with a location that shares the same product category name as the zone the location is in | ecoATM Team | Ready to Test
Inbound | Putaway - Pickface | User scans IMEI that is in the container and item does not match any criteria in the previous 2 scenarios | User will be brought to "Putaway Location Screen" with a list of locations that are empty and have a threshold of 5 distinct colors, and the existing sort color does not already belong in the location | ecoATM Team | Ready to Test
Inventory Management
Inventory Management | Cycle Counting - Task Creation - By Location | Scheduled by profile | Locations that do not have stock units and have the field "Cycle Count" is enabled will have a cycle count task created against it with a priority of "5" auto assigned and type as "Count by Location" | ecoATM Team | Ready to Test | Ran scheduler and created 31 new counts
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via HH for location that has Cycle Count = true | Cycle count task created with assigned priority | ecoATM Team | Ready to Test | Tablet PickLoc10
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via HH for location that has Cycle Count = false | Error message will be shown | ecoATM Team | Ready to Test | Phones PickLoc22
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via UI (Process Action Link Button) for location that has Cycle Count = true | Cycle count task will be created with assigned priority | ecoATM Team | Ready to Test | Phones PickLoc15
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via UI (Process Action Link Button) for location that has Cycle Count = false | Error message will be shown | ecoATM Team | Ready to Test | Phones PickLoc22
Inventory Management | Cycle Counting - Task Execution - By Location | User scans a serial for a location with one item in the location | The item/sku associated with the scan will be counted (the item will now have "**" to the left of the item to indicate that the item has been counted | ecoATM Team | Ready to Test | Phones PickLoc1 Serial Scanned: 12523151251
Inventory Management | Cycle Counting - Task Execution - By Location | User scans a serial that was already scanned in the same count task | Error message will be shown | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | User does not count all items in a location and goes to the next location | Cycle count variance will be created against the location and the serial number that was not counted will be asscoiated with the variance | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Count exact quantity that actually exists in the location systematically and user enters "next location" | No variance will be created and the user will be taken to the next location within the cycel count queue task list | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Count different quantity than what actually exists in the location systematicall | Variance is created against the location and the serial number that was not counted in the location will be associated in the variance | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Skip counting an item in a location by hitting "Next Location" before all items are counted | Zero is recorded as count for items not counted and a variance will be created against the serial number | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Scan an item that does not systematically exist in a location when counting | Error Message will be shown | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Variance | User approves variance | Stock unit is deprecated from the location and a record is created in the "Count Variance History" table | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Variance | User rejects variance | Stock unit stays in the location | ecoATM Team | Ready to Test
Inventory Management | Cycle Counting - Variance | User recounts variance | Stock unit stays in the location systematically and a new cycle count is created against the location with a priority of 2 amd a type of "Recount Variants" | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User enters a valid location in the warehouse | User is brought to the :Option Screen" where they can choose the method of adjustment | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User enters a location not in the warehouse | Error message will be shown | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User selects consume by Unit | User is brought to an item selection screen where they are prompted to enter in a serial | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User scans an IMEI that is not in the location | Error message will be shown | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User scans an IMEI that is in the location | Item is added to a pending list and the user is able to continue to scan availble IMEIs to the location | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User selects confirm after scanning available items in the location | User is brought to the "Review Screen" where scanned serials will be shown in a listbox and the user has 4 options to select from for the Reason and is also able to add a Note to the adjustment as well | ecoATM Team | Ready to Test
Inventory Management | Adjust Inventory | User selects commit after inputting reason code and/or note | Stock units are deprecated from the location and records are created in the "InvLedger List" table with associated reason code stamped to the line | ecoATM Team | Ready to Test
Outbound
Outbound | Outbound Order Management - Address Validation | Process order that fails address validation with suggested change | Sales Order goes to status "Hold - AV" and Order Header Note created with suggested address changes - POI Done flag is set to true |  | NOT Ready to Test
Outbound | Outbound Order Management - Address Validation | Process order that fails address validation with NO suggested change | Sales Order goes to status "Hold - AV" and Order Header Note created indicating no suggestions could be found - POI Done flag is set to true |  | NOT Ready to Test
Outbound | Outbound Order Management - Address Validation | Process order that passes address validation | Sales Order stays in New status - POI Done flag is set to true |  | NOT Ready to Test
Outbound | Outbound Order Management - POI Done | POI runs successfully | POI Done flag is set to true |  | NOT Ready to Test
Outbound | Outbound Order Management - POI Done | POI fails | POI Done flag stays false. Waving does not run on the order. |  | NOT Ready to Test
Outbound | Outbound Order Management - Re-run POI | Scheduler re-runs POI on orders where POI Done is not true |  |  | NOT Ready to Test
Outbound | Pickwave Management - Waving Execution | Manually wave one order | Order selected remains in New, moves to Back Ordered, or moves to Released based on profile match and inventory evaluation |  | NOT Ready to Test
Outbound | Pickwave Management - Waving Execution | Manually wave multiple orders | All orders selected remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation |  | NOT Ready to Test
Outbound | Pickwave Management - Waving Execution | Scheduled wave multiple orders | All orders in New or Back Ordered status are waved in order of created date ascending. All orders remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation. |  | NOT Ready to Test
Outbound | Pickwave Management - Pickwave Profile | Order matches large order profile conditions | Order waved on Large Order Wave - can only be picked in Single Scan Picking |  | NOT Ready to Test
Outbound | Pickwave Management - Pickwave Profile | Order matches singles order profile conditions | Order waved on Singles Wave - can only be picked in Single Scan Picking |  | NOT Ready to Test
Outbound | Pickwave Management - Pickwave Profile | Order matches multis order profile conditions | Order waved on Multis Wave - can only be picked in Batch Picking |  | NOT Ready to Test
Outbound | Pickwave Management - Pickwave Profile | Order matches no waving criteria | Order stays in New or Back Ordered status |  | NOT Ready to Test
Outbound | Pickwave Management - Back Order Management | Order waved has sufficient inventory available to release | Order moves to Released and is assigned a Pickwave with work group and pick tasks |  | NOT Ready to Test
Outbound | Pickwave Management - Back Order Management | Order waved as no sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | NOT Ready to Test
Outbound | Pickwave Management - Back Order Management | Order waved as partially sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Singles Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Multis Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Multis Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Multis Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Multis Picking |  |  |  | NOT Ready to Test
Outbound | Picking - Multis Picking |  |  |  | NOT Ready to Test
Outbound | Outbound - Packing and Shipping |  |  |  | NOT Ready to Test
Outbound | Outbound - Rate Shopping |  |  |  | NOT Ready to Test
Outbound | Outbound - EDI Fulfillment |  |  |  | NOT Ready to Test
Other WMS
Other WMS | Other WMS - Transfer Orders |  |  |  | NOT Ready to Test
Other WMS | Other WMS - Shipping Documents/Labels |  |  |  | NOT Ready to Test
Other WMS | Other WMS - 3PL Billing |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Reporting
Reporting | Dashboard - Inbound | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Dashboard - Inventory Management Dashboard | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Dashboard - Outbound | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Dashboard - User Performance | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Report Builder - | -- | Report returns timely and accurately for customer needs

## Unit Test Cases
ecoATM Unit Test Cases |  | Category | % Complete
|  | API | 0%
|  | Inbound | 93.75%
|  | Inventory Management | 96%
|  | Outbound I | 76.19%
|  | Outbound II | 85.19%
|  | Other WMS | 0%
|  | Reporting | 0%
|  | TOTAL | 57.46%
Category | Subcategory | Scenario | Expected Outcome | Owner | Status | Test Data | Deposco Comments | ecoATM Test Data | ecoATM Comments | ecoATM Screenshots | ecoATM JIRA | DEP Comments
API
API | Purchase Order | ecoATM retrieves PO(s) with OrderStatus = "Draft" | Identify all available available PO(s) in a "Draft" status with unknown skus (INT101) | ecoATM | Ready to Test
API | Purchase Order | ecoATM pushes PO/POL status updates with OrderStatus = "Hold" | PO OrderStatus/LineStatus = Hold - When a PO is processing the IMEI and to avoid API calls from retrieving the same PO information in a "Draft" status | ecoATM | Ready to Test
API | Purchase Order | ecoATM pushes PO/POL updates for PO(s) with OrderStatus = "New" | PO OrderStatus/LineStatus = New, acquisitionCost, targetSalesChannel, encumbrance, IMEI, expectedGrade, ignoreEncumbrance are all set - When IMEI processing is complete | ecoATM | Failed |  |  | Order ID 367 | When updating the order with a lower-case "new" value, the UI displays the change but the API response and later GET calls do not work properly | [IMS-350] Deposco: API - Update Order Status - Strange behavior when sending case-insensitive status - JIRA
API | Purchase Order, Customer Return, Inbound Transfer Order | ecoATM POST PO/RMA/ITO with max (100) line(s) in a Single Request | PO/RMA/ITO is successfully created | ecoATM | Ready to Test
API | Purchase Order, Customer Return, Inbound Transfer Order | ecoATM POST PO/RMA/ITO over (100) line(s) in a Single Request | Receive (400) error message for “Line count for order xxx is 101+ which exceeds the limit of 100.” | ecoATM | Ready to Test
API | Purchase Order, Customer Return, Inbound Transfer Order | ecoATM POST PO/RMA/ITO for a Line Item/Pack that does NOT exist in Deposco | Receive error message stating: "Item (or Pack) with id xxxxxx not found." | ecoATM | Ready to Test
API | Customer Return (RMA) | ecoATM POST RMA(s) to create or update Customer Return (RMA) Orders after the RMA process has been started in the sales portal and then communicated to Oracle. | Customer Return (RMA) is created in DEP with an OrderStatus = New | ecoATM | Ready to Test
API | Customer Return (RMA) | ecoATM retrieves RMA(s) with OrderStatus = "New" when uploaded via Data Exchange | Identify all Customer Return (RMA) Orders with OrderStatus = New that were uploaded via Data Exchange. | ecoATM | Ready to Test
API | Customer Return (RMA) | ecoATM retrieves RMA(s) with OrderStatus = "Received" | Identify all RMA(s) that were Received in DEP | ecoATM | Ready to Test
API | Stock Inventory Modification | ecoATM pushes Stock Inventory "Updates" - using Serial Number - after Grading and Testing is Complete | Updates existing Stock Unit and Inventory Adjustment records for: Graded Sku, Encumbrance, Sort Type/Grouping, Battery Health, ecoATM Reason Code, acquisitionCost, Testing Results + Summary Failure Reason | ecoATM | Ready to Test
API | Stock Inventory Modification | ecoATM pushes Stock Inventory "Updates - using "Serial Number" - for a previously modified Item | Updates specified Stock Unit "Attributes" only | ecoATM | Ready to Test
API | Stock Inventory Modification | ecoATM pushes Stock Inventory "Updates for a "Serial Number" that does NOT exist in "Device Testing" Location | "errorMessage": "Cannot find item for the provided serial number and location" | ecoATM | Ready to Test
API | Inventory Adjustment | ecoATM retrieves all required Inventory Modification Updates on the "Inventory Adjustment" created. | Graded Sku, Encumbrance, Sort Type/Grouping, Battery Health, ecoATM Reason Code, acquisitionCost, Testing Results + Summary Failure Reason | ecoATM | Ready to Test
API | Inventory ATP | ecoATM retrieves ATP measures when there is a change in Inventory | Return ATP measures based on the parameters specified using the pageNo for pagination | ecoATM | Ready to Test
API | Inventory ATP | ecoATM retrieves ATP measures when there is NO change in Inventory | Return ATP measures based on the parameters specified using the pageNo for pagination | ecoATM | Ready to Test
Inbound
Inbound | Pre Receiving - Manifest Creation | User creates Purchase Order (Manifest) using Manifest Upload Data Exchange | Purchase order is created successfully in environment (Draft Status) | ecoATM | Pass |  |  | Deposco_Unit_IMEI |  |  |  |  | The below comments are for orders/manifests in general, not to specific ingest types
Inbound | Pre Receiving - Case Lot Manifest Creation | User creates Case Lots Order using Case Lot Manifest Upload Data Exchange | Case Lot Purchase order is created successfully in environment (New Status) | ecoATM | Pass |  |  | Deposco_Unit_CaseLot |  |  |  | JY 4/22: test unit updated to reflect what is in design document | Date fields from Manifest are being saved as 1 day earlier in created Order | [IMS-296] Deposco: Manifest Dates are incorrect in created Purchase Order - JIRA
Inbound | Pre Receiving - ITO Creation | User creates Inbound Transfer Orderr using Inbound Transfer Order Upload Data Exchange | Inbound Transfer Order Uploadr is created successfully in environment (New Status) | ecoATM | Pass |  |  | Deposco_Unit_Transfer |  |  |  |  | IMEI is not being written to IMEI field | [IMS-300] Deposco: IMEI is not being written correctly - JIRA
Inbound | Pre Receiving - Customer Return Creation | User creates Customer Return using Inbound Customer Return Upload Data Exchange or via API | Customer return order is created successfilly in environment | ecoATM | Pass |  |  | Deposco_Unit_RMA |  |  |  |  | add IMEI to DE upload and rules for populating field if the field is blank, if not then stamp ol.serial
Inbound | Pre Receiving - Purchase Order Line Cancelation | User cancels Purchase Order manually in the UI using Process Action Link "Cancel Enitre Order" or pushes updated via API | Order status is updated to "Cancelled" and Canceled Pack Quantity is updated | ecoATM | Pass |  |  | Deposco_Unit_Cancel
Inbound | Pre Receiving - Purchase Order Cancelation | User cancels Purchase Order Line manually in the UI using Process Action Link "Cancel Order Line" or pushes updated via API | Order status is updated to "Partially Cancelled" and Canceled Pack Quantity is updated for associated line | ecoATM | Pass |  |  | Deposco_Unit_PartialCancel
Inbound | Receiving - IMEI Receiving | User scans container and manifest number in "IMEI Receiving" button to start receiving process | User is brought to the item list screen and is able to scan IMEIs to start receiving stock into the system | ecoATM | Pass |  |  | Deposco_Unit_Receiving_IMEI
Inbound | Receiving - IMEI Receiving | User scans manifest but not a container | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_Receiving_IMEI
Inbound | Receiving - IMEI Receiving | User scans a manifest with type of "Case" in "IMEI Receiving" | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_Receiving_IMEI
Inbound | Receiving - IMEI Receiving | User scans an IMEI that is NOT on the manifest scanned to start receiving process | User gets an error message saying the item does not belong on the order | ecoATM | Pass |  |  | Deposco_Unit_Receiving_IMEI
Inbound | Receiving - IMEI Receiving | User inputs/scans item number instead of IMEI | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_Receiving_IMEI
Inbound | Receiving - IMEI Receiving | User scans an IMEI that is on the manifest | Inventory is received and autostaged into the "Receving" location. user is brought back to the Item list screen to continue receiving process | ecoATM | Pass |  |  | Deposco_Unit_Receiving_IMEI
Inbound | Receiving - Case Lots Receiving | User uses "Box Receiving" and inputs a manifest number to start the case lot receiving process | User is brought to the item list screen and is able to scan the containers on the manifest | ecoATM | Pass |  |  | Deposco_Unit_CaseLot_Receiving
Inbound | Receiving - Case Lots Receiving | User scans a manifest with type of "Unit" in "Box Receiving" | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_CaseLot_Receiving
Inbound | Receiving - Case Lots Receiving | User scans an inbound LPN that is NOT on the manifest | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_CaseLot_Receiving
Inbound | Receiving - Case Lots Receiving | User scans an inbound LPN taht is on the manifest | Inbound LPN will be transported to a container and the container is staged at the "Receiving" location. Order Status will be updated to "Received" | ecoATM | Pass |  |  | Deposco_Unit_CaseLot_Receiving
Inbound | Receiving - Customer Returns | User goes into "Customer Returns" and inputs a container and existing customer return order number | User is brought to item list screen | ecoATM | Pass |  |  | Deposco_Unit_RMA_Receiving
Inbound | Receiving - Customer Returns | User scans an Customer Return that does not exist in the system | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_RMA_Receiving
Inbound | Receiving - Customer Returns | User scans an Customer Return that is on the manifest | User is brought to the "Reason Code and Credit Screen" where they are asked to select a "No Refund" or "Refund Approved" | ecoATM | Pass |  |  | Deposco_Unit_RMA_Receiving
Inbound | Receiving - Customer Returns | Customer return note (posted via API) will be displayed on the screen which will be used to determing if a refund will be processed or not for the order | User is brought to the "Reason Code and Credit Screen" where they are asked to select a "No Refund" or "Refund Approved" | ecoATM | Pass |  |  | Deposco_Unit_RMA_Receiving
Inbound | Receiving - Customer Returns | User selects available reason codes on Reason Code Screen | Customer Return order and order line status are updated to received | ecoATM | Pass |  |  | Deposco_Unit_RMA_Receiving | Refund Approved, and No Refund are not options in the reason code dropdown. Options present are: No Defect Found, Unexpected Device, Wrong Serial, Defect Confirmed |  |  | JY 4/22: Reason code should be updated to the ones shown on the screen currently. Test Unit updated to reflect changes
Inbound | Receiving - Inbound Transfer Order | User scans Inbound Transfer Order number to start process in "Inbound Transfer Receiving" | User is able to scan the availble box lpns on the order | ecoATM | Pass |  |  | Deposco_Unit_Receiving_Transfer_2 | Test says Inbound Transfer Order is received in "Box Receiving", but should it not be received in the "Inbound Transfer Receiving"? |  |  | JY 4/22: Test case has been updated
Inbound | Receiving - Inbound Transfer Order | User scans a inbound LPN not on the order | Error message will be displayed | ecoATM | Pass |  |  | Deposco_Unit_Receiving_Transfer_2
Inbound | Receiving - Inbound Transfer Order | User scans inbound LPN on the order | Items are received and can be putaway directly from the receiving location. No additional testing for the item is needed. Order status is updated to "Receivied" | ecoATM | Pass |  |  | Deposco_Unit_Receiving_Transfer_2
Inbound | Receiving - Inbound Transfer Order | User partially recieves ITO | Order is updated to partial receipt, and users are able to go back at a later time and continue receiving the order | ecoATM | Pass |  |  | Deposco_Unit_Receiving_Transfer_2
Inbound | Receiving - Inbound Transfer Order | User comes back to a partially received order at a later time | User is able to contine and finish the receving process for the order | ecoATM | Pass |  |  | Deposco_Unit_Receiving_Transfer_2
Inbound | Move Container to Testing | User inputs a received container to start the move container process | User is brought to the destination location screen | ecoATM | Pass |  |  | Deposco_Unit_Sort | When scanning the box # it always returns this error message: | TypeError: Cannot set property "locations" of null. Error compiling script | [IMS-303] Deposco: Move Container Inbound Action throws an error - JIRA | JY 4/22: This is now patched and ready to be tested again
Inbound | Move Container to Testing | User inputs "Device Testing" into destination location | Stock unts from container are moved to the Device Testing location and the container is disassociated | ecoATM | Pass |  |  | Deposco_Unit_Sort | Stock Units are not disassociated with the container | AR 4/25 : It was explained to me that the issue with the test below and sortation is because of an issue on this unit test, with the devices not being disassociated with their container when moving them to Device Testing | [IMS-315] Deposco: Error when scanning IMEIs at Sortation - JIRA | 4/27: This is now patched and ready to test again
Inbound | Putaway - Sortation | User scans location/zone that they are currently in on the "Change User Zone Screen" | User is brought to the "Location Input Screen" and is prompted to scan the barcode located at their sortation station | ecoATM | Pass |  |  | Deposco_Unit_Sort
Inbound | Putaway - Sortation | User scans the barcode at their desk (Scan "Device Testing") | User is brought to "Move Item Screen" and is able to scan the items that are in the box they brought to their sortation station from the testing zone | ecoATM | Pass |  |  | Deposco_Unit_Sort | Previous error blocked me from moving the items to Device Testing When I tried to set the info myself manually I am getting an error saying the device is not in my location. Either way I can't pass the test | Scanned item [INT101] doesn't exist in location [Device Testing]. |  | JY 4/22: the parameter to scan an item is its serial number. To find the serial number of the item, you can look for the item in the stock unit section within the location entity (Device Testing)
Inbound | Putaway - Sortation | User scans an available IMEI in the Device Testing location and the box is empty and the sortation station does not have an existing sort type for the item | user will be able to assign a container (box) that the device will be put into as well as a slot location at the sortation station | ecoATM | Pass |  |  | Unit_Sortation_IMEI_14_1 |  |  |  |  | AR 4/25: I am using the device SN (which is the same as the IMEI). I'm not sure whether maybe the JIRA ticket was showing the unedited version I cloned but I did not include a screenshot yesterday, just the steps and the entity/field values relevant I just refreshed, resaved, and included a new screenshot with the error. This was after using the SN/IMEI value: Unit_Sortation_IMEI_11 I've also tried other identifiers to be sure like stock unit number, container number, order line number, which didn't work
Inbound | Putaway - Sortation | User scans an item with the same sort type as an existing item already sorted in the sort station and the box is not full yet | User is prompted to put the item in the specific sort type combination that exists in the station | ecoATM | Pass |  |  | Stock Unit's SN: PutFull_IMEI_F_1 - Location: UnitTestSort3 Stock Unit's SN: PutFull_IMEI_Fo_1 - Location: UnitTestSort2 Stock Unit's SN: PutFull_IMEI_S_1 - Location: UnitTestSort4 | This previously was working, but now boxes are not being suggested at Sortation, and I cannot put items into any box that is not empty | [IMS-352] Deposco: At Sortation, unable to put multiple stock units in a single box - JIRA
Inbound | Putaway - Sortation | User scans an item with the same sort type as an existing item already sorted in the sort station and the box is full | The sortation box will not be visible a tthe "Suggested Putaway" screen and is able to assign a new box/slot for the item. User will know to putaway full box when they see the box is full physically | ecoATM | Pass |  |  | Unit_Sortation_IMEI_14_3
Inbound | Putaway - Pickface | User scans full box from sortation station in the "3.Putaway" button in the receiving process | User is brought to "Move Item Screen" where all items in the box will be listed | ecoATM | Pass |  |  | Box01 | When scanning the box number at Putaway, the items in the box are not listed on the Move Item Screen page |  |  | JY 4/29: Checking container Box01 there was no stock in the container to move
Inbound | Putaway - Pickface | User scans item that in not in the container | Error message will be displayed | ecoATM | Pass
Inbound | Putaway - Pickface | User scans IMEI that is in the container and there are existing stock of the same item in a Pickface location | User is brought to "Putaway Location Screen" with the location number that has stock of the same item | ecoATM | Pass |  |  | Unit_Put_IMEI_Color5
Inbound | Putaway - Pickface | User selects the location that is prompted | Item is moved to the selected location and user is brought back to the "Move Item" screen to continue the process until all items in the box have been putaway | ecoATM | Pass |  |  | Unit_Put_IMEI_Color5
Inbound | Putaway - Pickface | User scans IMEI that is in the container and there is perexisting stock of the same item, the devices in the location are not "x" days old, and location has available capacity | User will be brought to "Putaway Location Screen" with a list of locations that match the criteria in the scenario | ecoATM | Pass
Inbound | Putaway - Pickface | User scans IMEI that is in the container and item does not match any criteria in the previous scenario | User will be brought to "Putaway Location Screen" with a location to put the item away into, and the user will not be able to override the suggested location | ecoATM | Pass |  |  | Unit_Put_IMEI_Color1 | Suggested Location given to this unit is "Case Lot PickLock3" The Item is a normal Apple cell phone so I would expect it to suggest one of the phone pick locations, not a case lot location | [IMS-328] Deposco: Individual Unit being suggested Case Lot Pick Location - JIRA
Inbound | Putaway - Pickface | User scans IMEI that is in the container and item does not match any criteria in the previous 2 scenarios | User will be brought to "Putaway Location Screen" with a list of locations that have capacity, does not exceed 5 distinct sortable colors, and does not have an item with the sort color of the item being putaway | ecoATM | Pass |  |  | Unit_Put_IMEI_SameColor
Inbound | Putaway - Pickface | ECO: User processes a device through entire putaway process, and reviews displayed text and labels | References to the Source should be called Boxes References to the Destinatino should be called Locations References to the Stock Unit should use the IMEI/SN, not Item or LPN The Listed Identifier for the Stock Unit after scanning should display the IMEI/SN value, not the Item Number | DEP | NOT Ready to Test |  |  |  | I added this row for better visibility of the task and to track testing the result. If we need to keep these rows specific to the Deposco-Created-Unit-Tests, then we need to decide how best to track change requests and their related tests like these | [IMS-326] Deposco: Single-Item Putaway Changes - JIRA
Inbound | Putaway - Pickface | ECO: User scans a device with a not-allowed Item (SKU) | Error message will be displayed | DEP | NOT Ready to Test |  |  |  | I added this row for better visibility of the task and to track testing the result. If we need to keep these rows specific to the Deposco-Created-Unit-Tests, then we need to decide how best to track change requests and their related tests like these | [IMS-327] Deposco: Input Validation at Putaway - JIRA
Inbound | Putaway - Case Lot Direct Putaway | User scans a container that has multiple different item types in it | Error message will be displayed | ecoATM | Pass |  |  | Unit_MixCase-LPN
Inbound | Putaway - Case Lot Direct Putaway | User scans a container with stock units of the same item and there is eligble locations for putaway | User will be brought to next screen where locations eligible to be putaway will appear in either consolidate or empty | ecoATM | Pass |  |  | Unit_Case_Put-LPN
Inbound | Putaway - Case Lot Direct Putaway | User scans a container with item in it that already exists in a eligible location that matches the zone criteria | Location will appear under "Consolidate" | ecoATM | Pass |  |  | Case LPN: Unit_Case_Put-LPN2 | We don't want multiple cases in the same location period. | [IMS-325] Deposco: No Locations are showing as suggested for Case Lots - JIRA |  | JY 5/2: Updated per request from ecoATM
Inbound | Putaway - Case Lot Direct Putaway | User scans a container with item in it that does not exists in a eligible empty location that matches the zone criteria | Eligible location will appear under "Empty" | ecoATM | Pass |  |  | Unit_Case_Put-LPN | When scanning the first case lot at putaway, no locations showed on the suggested table. After putting that case into a location, scanning the second case does suggest the location that has the first case | [IMS-325] Deposco: No Locations are showing as suggested for Case Lots - JIRA
Inbound | Putaway - Case Lot Direct Putaway | User selects one of the locations on the listbox | Container and stock units will be moved to the location, and the location attribute on the container updates from "receiving" to the putaway location | ecoATM | Pass |  |  | Unit_Case_Put-LPN
Inventory Management
Inventory Management | Cycle Counting - Task Creation - By Location | Cycle count is created through scheduler (user is able to run schedulers manually for testing) | Locations that do not have stock units and have the field "Cycle Count" is enabled will have a cycle count task created against it with a priority of "5" auto assigned and type as "Count by Location". Note the criteria for cycle count creations in the Inventory Management Demo Session (recording in tracker) | ecoATM | Pass |  |  | UnitTestSort2
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via HH for location that has Cycle Count = true | Cycle count task created with assigned priority | ecoATM | Pass |  |  | UnitTestSort2
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via HH for location that has Cycle Count = false | Error message will be shown | ecoATM | Pass |  |  | UnitTestSort3
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via UI (Process Action Link Button) for location that has Cycle Count = true | Cycle count task will be created with assigned priority | ecoATM | Pass |  |  | UnitTestSort2
Inventory Management | Cycle Counting - Task Creation - By Location | Manual via UI (Process Action Link Button) for location that has Cycle Count = false | Error message will be shown | ecoATM | Pass |  |  | UnitTestSort3
Inventory Management | Cycle Counting - Task Execution - By Location | User scans a serial for a location | The item/sku associated with the scan will be counted (the item will now have "**" to the left of the item to indicate that the item has been counted | ecoATM | Pass |  |  | Tablet PickLoc15 | NOTE : the flow works as expected with the Serial Number, but the page text indicates SKU not SN in a way that is confusing | [IMS-329] Deposco: Item Screen on Inventory Cycle Count errors when scanning an SKU - JIRA
Inventory Management | Cycle Counting - Task Execution - By Location | User scans a serial that was already scanned in the same count task | Error message will be shown | ecoATM | Pass |  |  | Tablet PickLoc15
Inventory Management | Cycle Counting - Task Execution - By Location | User does not count all items in a location and goes to the next location | Cycle count variance will NOT be created against the location, and the system will treat it as if the user counted the correct amount | ecoATM | Pass
Inventory Management | Cycle Counting - Task Execution - By Location | Count exact quantity that actually exists in the location systematically and user enters "next location" | No variance will be created and the user will be taken to the next location within the cycel count queue task list | ecoATM | Pass
Inventory Management | Cycle Counting - Task Execution - By Location | Count different quantity than what actually exists in the location systematicall | Variance is created against the location and the serial number that was not counted in the location will be associated in the variance | ecoATM | Pass |  |  | Phones PickLoc3 | extra + and - are created for the device without a variance | [IMS-336] Deposco: Inventory Cycle Count - Variance is creating a plus and minus for the scanned IMEI - JIRA | AR 5-6: Still seeing the issue when retesting | AR 5-9: New accept screen appears and the unexpeted variances are not being created
Inventory Management | Cycle Counting - Task Execution - By Location | Scan an item that does not systematically exist in a location when counting | Error Message will be shown | ecoATM | Pass |  |  | location: Phones PickLoc3 Serial: friday7
Inventory Management | Cycle Counting - Variance | User approves variance | Stock unit is deprecated from the location and a record is created in the "Count Variance History" table | ecoATM | Pass |  |  | Initial Location: Case Lot PickLock1 IMEI: Unit_Case_Put_IMEI_2 | The stock unit appears to be completely deleted from the system, not just deprecated or disassociated
Inventory Management | Cycle Counting - Variance | User rejects variance | Stock unit stays in the location. No new task is created | ecoATM | Pass
Inventory Management | Cycle Counting - Variance | User recounts variance | Stock unit stays in the location systematically and a new cycle count is created against the location with a priority of 2 amd a type of "Recount Variants" | ecoATM | Pass |  |  | UnitTestSort5
Inventory Management | Adjust Inventory | User enters a valid location in the warehouse | User is brought to the "Option Screen" where they can choose the method of adjustment | ecoATM | Pass
Inventory Management | Adjust Inventory | User enters a location not in the warehouse | Error message will be shown | ecoATM | Pass
Inventory Management | Adjust Inventory | User selects consume by Unit | User is brought to an item selection screen where they are prompted to enter in a serial | ecoATM | Pass
Inventory Management | Adjust Inventory | User scans an IMEI that is not in the location | Error message will be shown | ecoATM | Pass |  |  | Location: Case Lot PickLock3 Unit SN: Unit_Put_IMEI_Color1
Inventory Management | Adjust Inventory | User scans an IMEI that is in the location | Item is added to a pending list and the user is able to continue to scan availble IMEIs to the location | ecoATM | Pass
Inventory Management | Adjust Inventory | User selects confirm after scanning available items in the location | User is brought to the "Review Screen" where scanned serials will be shown in a listbox and the user has 4 options to select from for the Reason and is also able to add a Note to the adjustment as well | ecoATM | Pass |  |  | Location: Case Lot PickLock3 Units: Unit_Inventory_IMEI_1_1 to Unit_Inventory_IMEI_1_10 | The Reason dropdown is only populated with a single value, depending on which handheld menu is selected
Inventory Management | Adjust Inventory | User selects commit after inputting reason code and/or note | Stock units are deprecated from the location and records are created in the "InvLedger List" table with associated reason code stamped to the line | ecoATM | Pass |  |  | Location: Case Lot PickLock3 Units: Unit_Inventory_IMEI_1_1 to Unit_Inventory_IMEI_1_10 | I can't view the contents of the invLedger List page to verify
Inventory Management | Additional Request - Scanned IMEI Error Message | User scans an IMEI that does not exist at all in the system (User scans a device that belongs in another location) | error message "Serial Number Doesn't Exist" | ecoATM | Pass |  |  |  |  | [IMS-342] Deposco: Inventory Adjustment - Can't view InvLedger - JIRA
Inventory Management | Additional Request - Scanned IMEI Error Message | User scans an IMEI that exists but does not belong in the location being cycle counted | error message will show where the IMEI should exist | ecoATM | Pass
Inventory Management | Additional Request - Scanned IMEI Error Message | User scans an IMEI that exists and it belongs in the location being counted | message will show that 1 quantity of the item is counted against | ecoATM | Pass
Outbound I
Outbound I | Out Bound Order Management - Post Order Import Run | POI(Post Order Import) will run automatically when orders & items are pushed into the system or through a scheduler. Users have the option to run POI manually through the process action link button | Successful POI runs will be indicated by a checkmark in the "POI" field on the orderheader. If this field is not marked, then this will indicate to the user that POI failed for the order, and based on updated attributes outlined in the following tests, the user will knwo what needs to be updated before POI is ran against the order again | ecoATM | Pass |  |  | LargeOutboundTestSO
Outbound I | Outbound Order Management - Address Validation | Process order that fails address validation without a suggested address | Sales Order goes to status "Hold - AV" and POI field on order is set to true | ecoATM | Pass |  |  | OutboundTestSalesOrder
Outbound I | Outbound Order Management - Address Validation | Process order that passes address validation | Sales Order stays in New status - POI Done flag is set to true | ecoATM | Pass |  |  | LargeOutboundTestSO
Outbound I | Outbound Order Management - POI/Automations | POI is ran against an order that has "2 Day" in the "Ship Via" field | Order "Ship Via" field will be updated to "FedEx 2Day". | ecoATM | Pass
Outbound I | Outbound Order Management - POI/Automation | POI is ran against an order without "Freight Bill To..." fields filled on the order | Fields will be populated with values from the "Ship To..." fields | ecoATM | Pass
Outbound I | Outbound Order Management - POI/Automation | POI is ran against an order that has an order line without a unit price populated or the unit price in the field is "0" | POI will fail, and the order will stay in new status, but "POI" field will be marked as false | ecoATM | Pass
Outbound I | Outbound Order Management - POI/Automation | POI is ran against an order with multiple order lines and quantity (TESTING PURPOSES, THIS CAN BE UPDATED TO A SMALLER QUANTITY) | "# of Shipping Boxes (PHONE)" will be the total amount of items in CellPhone category divided by 50 "# of Shipping Boxes (TABLET)" will be the total amount of items in Tablet category divided by 10 | ecoATM | Pass
Outbound I | Outbound Order Management - POI/Automation | POI is ran against order with values set in the "# of Shipping Boxes" fields | "Freight" vs "Parcel" logic will be based on the summation of the two fields. If the order is or exceeds 30 shipping boxes, then the system will set the account number on the trading partner, if it is under 30, then the account number will be pulled from the lookup table | ecoATM | Pass
Outbound I | Outbound Order Management - POI/Automation | POI is ran against an order that does not have a "ship via" set on the order AND the freight terms type is "prepaid" | "Ship Via" on order will be set to the "ship via" on the trading partner level for the trading partner on the order | ecoATM | Ready to Test |  |  | Sales Order: Unit_Out_POI_Phone | The Ship Via does not change when I run POI after setting Freight Terms Type to Prepaid | [IMS-396] Deposco: Ship Via for Prepaid is not being set - JIRA
Outbound I | Outbound Order Management - POI/Automation | POI is rerun on failed orders either through the scheduler or manually by the user after order attriburtes have been updated | Once order vaules have been updated so that POI can be completed against the order, if the order is successful then "POI" field will be marked as true. | ecoATM | Pass
Outbound I | Pickwave Management - Waving Execution | User manually runs waving scheduler, or runs "Build Pick Wave" through the PAL button in the UI | Order selected remains in New, moves to Back Ordered, or moves to Released based on profile match and inventory evaluation | ecoATM | Pass |  |  | LargeOutboundTestSO
Outbound I | Pickwave Management - Waving Execution | Manually wave multiple orders | All orders selected remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation | ecoATM | Pass |  |  | Orders: Unit_Out_Pick_Mult_Man_Release Unit_Out_Pick_Mult_Man_Back | Pick Waves are created, but not released, so the Order statuses stay in "Wave Built" | [IMS-397] Deposco: Bulk Wave Release Action creates waves but does not release them - JIRA
Outbound I | Pickwave Management - Waving Execution | Scheduled wave multiple orders | All orders in New or Back Ordered status are waved in order of created date ascending. All orders remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation. | ecoATM | Pass
Outbound I | Pickwave Management - Workgroup Management | Any picktasks generated for a pickwave in any CellPhone locatios will be limited to 50 | Orders that exceed the limit will have multiple workgroups split amongst the order | ecoATM | Failed |  |  | LargeOutboundTestSO | Work groups created mix tablets and phones, but don't properly apply either one's limits | [IMS-385] Deposco: Pick Wave is splitting work groups weirdly for mixed orders - JIRA
Outbound I | Pickwave Management - Workgroup Management | Any picktasks generated for a pickwave in any Tablet locatios will be limited to 10 | Orders that exceed the limit will have multiple workgroups split amongst the order | ecoATM | Failed |  |  | LargeOutboundTestSO | Work groups created mix tablets and phones, but don't properly apply either one's limits | [IMS-385] Deposco: Pick Wave is splitting work groups weirdly for mixed orders - JIRA
Outbound I | Pickwave Management - Workgroup Management | Any picktasks generated for a pickwave in any CaseLot locations will be limited to 3 | Orders that exceed the limit will have multiple workgroups split amongst the order | ecoATM | Failed |  |  | LargeOutboundTestSO | all 20 case lot items were added to a single work group | [IMS-385] Deposco: Pick Wave is splitting work groups weirdly for mixed orders - JIRA
Outbound I | Pickwave Management - Pickwave Profile | Order matches no waving criteria | Order stays in New or Back Ordered status | ecoATM | Pass
Outbound I | Pickwave Management - Back Order Management | Order waved has sufficient inventory available to release | Order moves to Released and is assigned a Pickwave with work group and pick tasks | ecoATM | Pass |  |  | OutboundTestSalesOrder2
Outbound I | Pickwave Management - Back Order Management | Order waved as no sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. | ecoATM | Pass |  |  | Retest_398_Enough_ SO | Pick Wave is not removed from the order | [IMS-398] Deposco: Backorder not working as expected - JIRA
Outbound I | Pickwave Management - Back Order Management | Order waved as partially sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. | ecoATM | Pass |  |  | Retest_398_Partial_ SO | Pick Wave is not removed from the order, and status says Partially Released | [IMS-398] Deposco: Backorder not working as expected - JIRA
Outbound II
Outbound II | Picking - IMEI | User goes into Outbound --> Picking in the handheld menu | User is brought to the Picking Menu screen with listbox of pickwaves ordered in ascending order based off of the pick wave created date | ecoATM | Pass
Outbound II | Picking - IMEI | User selects a wave and enters in any value into the "Picking LPN" field | User is borught to the "Select Work Group" with available workgroups listed (user will need to be assigned to the zones the location that the picktasks are in for the workgroups | ecoATM | Pass |  |  | PWS_Order-250429_10
Outbound II | Picking - IMEI | User selects a workgroup availle to start | User is brought to the Picking Screen with information on where to go for the first pick task | ecoATM | Pass |  |  | PWS_Order-250429_10
Outbound II | Picking - IMEI | User inputs the location that is displayed on the screen | User is brought to the next Picking Screen where they will be asked to scan the barcode of the item to pick | ecoATM | Pass |  |  | PHONEPF04
Outbound II | Picking - IMEI | User inputs an invalid location or a different location that is not shown on the screen | Error Message will be displayed | ecoATM | Pass |  |  | aa
Outbound II | Picking - IMEI | User scans a serial that is in the locaiton of the pick task & there are more pick tasks in the workgroup still to be completed | User will be brought to the next pick tasks and will be prompted to scan the next location of the next pick task | ecoATM | Pass |  |  | PWS_Order-250608_2 | Does not let me select either work group for the pick wave I created to follow this scenario | https://gazelle.atlassian.net/browse/IMS-388
Outbound II | Picking - IMEI | User scans a serial that is in the locaiton of the pick task & there are no more pick tasks in the current workgroup the user is in, but there are still inactive pick tasks in the other workgroup of the same pick wave | User will be brought to the "NewPalletInputScreen" where they will be able to scan/input any values to create their next picking container | ecoATM | Pass
Outbound II | Picking - IMEI | User scans a serial that is in the locaiton of the pick task & there are no more pick tasks in the current workgroup the user is in,are there are no more inactive pick tasks in the other workgroup of the same pick wave | User will be brought back to the "Picking Menu" Screen where they can repeat the picking process | ecoATM | Pass |  |  | PWS_Order-250606_1
Outbound II | Picking - IMEI | User inputs scans/inputs a serial that is not in the location of the pick task | Error Message will be displayed | ecoATM | Pass
Outbound II | Picking - Case Lots | User selects a wave that has an open workgroup in the CaseLot zone and inputs a picking container to start the picking process | User is brought to the workgroup screen where they can select any available workgroups that are in open state | ecoATM | Pass |  |  | PWS_Order-250608_2
Outbound II | Picking - Case Lots | User selects a valid workgroup | User is brought to the Picking Screen where they are prompeted to enter in the location of the first pick task | ecoATM | Pass
Outbound II | Picking - Case Lots | User selects location on the screen for the pick task | User is brought to the next picking screen where they are prompted to scan the container displayed on the screen | ecoATM | Pass
Outbound II | Picking - Case Lots | User inputs an invalid location or location not on the screen for the pick task | Error message will be displayed | ecoATM | Pass
Outbound II | Picking - Case Lots | User inputs the container displayed on the screen for the user to pick | User is brought to the "Stage Items" screen. If the an container that shares the same order is existing in a shelf stagin location, then the system will trigger the follow the leader logic and prompt the user to stage the container to the same Shelf location. If it does not have an exisiting container in the shelf location, then the user is able to stage the container to an empty shelf locaiton | ecoATM | Failed |  |  | PWS_Order-250608_2 | Scanning cases does not prompt staging as suggested here. When explicitly clicking for staging, does not behave as said here | [IMS-386] Deposco: Case Lot Picking does not follow listed Staging steps - JIRA
Outbound II | Picking - Case Lots | User inputs a container that is not displayed on the screen for the user to pick | Error message will be displayed | ecoATM | Pass
Outbound II | Picking - Exception | User exceptions a pick during the picking process | User is brought to the next available pick task, the associated stock unit in the pick task will be put on hold, and a cycle count task will be created against the locaiton with type of "Picking Audit" | ecoATM | Pass
Outbound II | Picking - Suspend Task | User suspends a pick during the picking process | User is brought to the next available pick task, and the suspend taks will be pushed to the end of the queue to be actioned on at the end of the workgroup | ecoATM | Pass
Outbound II | Picking - Suspend Workgroup | User suspends the workgroup during the picking process | User is brought back to the new pallet input screen if there are more workgroup to be actioned on in the wave, or the user is brought to the pick wave | ecoATM | Pass
Outbound II | Picking - Stop Work Group | User stops a work group during the picking process | User is brought back to the new pallet screen, and the workgroup the user was in gets disassociated from the user, and a new user is able to go in and continue the workgroup | ecoATM | Failed |  |  | PWS_Order-250608_2 | Stopping a work group brings me back to the same group | https://gazelle.atlassian.net/browse/IMS-387
Outbound II | Packing - Box Audit | User selects a container that was picked for a IMEI picking order | User is brought to the "Items in Order" screen where the user will see a list box of the items that are in the container they picked the order into | ecoATM | Pass
Outbound II | Packing - Box Audit | User selects "Pack Remainder" on the screen if they confirm that all units are in the box in front of them | User is brought to the "Stage LPN" screen where they are able to select an empty "Shelf" location in the system if there is not a container already in a Shelf location that shares the same order number. If there is already a container with matchin order numbers in a shelf location, the textbox will auto populate the suggested shelf location | ecoATM | Pass
Outbound II | Packing - Box Audit | User scans each individual serial number in the container | The associated item to the scanned serial will be deprecated from the listbox, and the user is able to know which item is missing from the picking container. Once containers have been staged to a shelf locaiton, the order status will be updated to "Staged" | ecoATM | Failed |  |  | Container: ARW_Unit_Pick | I am allowed to scan either SKU or SN, and I am able to scan the same SN over and over again, without error | https://gazelle.atlassian.net/browse/IMS-389
Outbound II | Packing - Single Container Packing | User scans a container that has been staged to the shelf location, but the payment status on the order level is "Hold" | Error message will be displayed | ecoATM | Pass
Outbound II | Packing - Single Container Packing | User scans a container that has been staged to the shelf location, but the payment status on the order level is "Payment Received" | User is brought to "Dimension Input Screen" where they are prompted to weigh the shipping container | ecoATM | Pass | [6 empty] | for DEP: Change logic to "Payment Received" - DONE
Outbound II | Packing - Single Container Packing | User scans a container that contains an item that waas picked in a location in the Tablet zone | Box field in the "Dimension Input Screen" should autppopulate to "Tablet Box" | ecoATM | Pass
Outbound II | Packing - Single Container Packing | User scans a container that contains an item that waas picked in a location in the CellPhone zone | Box field in the "Dimension Input Screen" should autppopulate to "Phone Box" | ecoATM | Pass |  |  |  | The containers for picking are being created as Tablet boxes, even when no tablets are in that pick wave | https://gazelle.atlassian.net/browse/IMS-390
Outbound II | Packing - Single Container Packing | User enters "submit" withhout entering a weight | Error message will be displayed | ecoATM | Pass
Outbound II | Packing - Single Container Packing | User enters "submit" after entering a weight | User will be brought back ot the "LPN Input Screen" with a message displaying "Packed [X} containing [x] items". User is able to continue to scan a new container | ecoATM | Pass | [6 empty] | Currently FedEx account not set up for hazaardous item. When testing, please make sure to check the "Hazard" flag on the item level to false before testing this unit case
Outbound II | Assign Trip - Unit/IMEI & Case Lots | User inputs an invalid value in the "Shipping Door" textbox | Error message will be displayed | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Unit/IMEI & Case Lots | User selects or inputs a valid value in the "Shipping Door" textbox | User is brough to the "Pallets Assigned to Trip" screen wheren they are prompted to scan a pallet onto container to build a pallet | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Unit/IMEI & Case Lots | User scans an invalid container to add to the trip | Error message will be displayed | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Unit/IMEI & Case Lots | User scans a container for an order that does not have the same "Ship Vendor" name as the shipping door name. Example: Ship Vendor on order is "FedEx", valid shipping doors will be "FedEx1, FedEx2.. etc" | Error message will be displayed | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Unit/IMEI & Case Lots | User scans a container for an order that has the same "Ship Vendor" name as the shipping door name. Example: Ship Vendor on order is "FedEx", valid shipping doors will be "FedEx1, FedEx2.. etc" | Container will be added to the trip and will be displayed on the listbox | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Unit/IMEI & Case Lots | User scnas same container that they scanned onto the pallet to be added to the trip | Container is removed from the trip and is also removed from the listbox displayed to the user | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Unit/IMEI | User selects "Close Trip" after adding container(s) to the pallet on the trip | User is brought back to the Outbound MainMenu screen with a message displaying trip is closed | ecoATM | Pass |  |  | Sales Order: Unit_Out_Trip_SO_2
Outbound II | Assign Trip - Case Lots | User selects "Close Trip" after adding container(s) to the pallet on the trip | User is brought back to the "Cusotm Details Input Screen" where they are able to enter in additional information about the trip | ecoATM | Failed |  |  | Sales Order: Unit_Out_Trip_Case_SO_2 | Receiving a Quantity mismatch error when attempting to scan the case into the trip | [IMS-405] Deposco: Unable to Assign Trip for Case Lots - JIRA
Outbound II | Assign Trip - Case Lots | User selects "Close" after entering additional information on the "Csutom Details Input Screen" | User is brought back to the Outbound MainMenu screen with a message displaying trip is closed | ecoATM | NOT Ready to Test |  |  | Sales Order: Unit_Out_Trip_Case_SO_2 | Can't reach this test due to the above issue
Outbound II | Build Transfer Order | User selects "RTV" from the listbox | User is brought to the OutboundTranferOrderScreen and is prompted to select the transfer purpose and is prompted to scan the location is which the items will be picked from | ecoATM | Pass
Outbound II | Build Transfer Order | User inputs an invalid Ship To Facility | Error message will be displayed | ecoATM | Pass
Outbound II | Build Transfer Order | User inputs an invalid location or container to pick the items for the OTO | Error message will be displayed | ecoATM | Pass
Outbound II | Build Transfer Order | User selects a Transfer Purpose but not a location or container | Error message will be displayed | ecoATM | Pass
Outbound II | Build Transfer Order | User inputs a location/container but does not input a Transfer Purpose | Error message will be displayed | ecoATM | Pass
Outbound II | Build Transfer Order | User inputs a valid location/container and inputs a Tranfer Purpose | User is brought to the CreateContainerForTransferScreen and is prompted to enter in a container in which the items will go into for the transfer order | ecoATM | Pass
Outbound II | Build Transfer Order | User inputs a value for the container in the screen | User is brough to the ItemToTransferScreen and is shown all unique item types in the location/container | ecoATM | Pass
Outbound II | Build Transfer Order | User scans a valid serial that exists in the location to be added to the transfer order | Item is added to the order, and the quantity next to the item number will be deprecated by 1 and a message will be displayed to the user that the item was moved to the container | ecoATM | Pass
Outbound II | Build Transfer Order | User scans an invalid serial or a serial that does not exist in the location | An error message will be displayed | ecoATM | Pass
Outbound II | Build Transfer Order | User selects "Stage" after adding items into the container for the transfer order | User is brough to the "ContianerToTransferDescriptionScreen" and is shown all of the items that the user picked into the container | ecoATM | Pass
Outbound II | Build Transfer Order | User selects "next" after confirming all items picked are on the screen | User is brought to the "StageTransferContainerScreen" where they are prompted to scan a location to stage the shipping container | ecoATM | Pass
Outbound II | Build Transfer Order | User selects an invalid location for staging | Error message will be displayed | ecoATM | Pass
Outbound II | Build Transfer Order | User inputs "Shipping" as the staging location | User is brought back to the "BuildTransferOrderScreen" where they are able to repeat the process and a message will be displayed indicating the container is staged to the shiupping location. In the desktop UI, a new order is created with a type of "Outbound Transfer Order" | ecoATM | Pass |  |  | Container: Unit_OTO_Box | I was able to chose a staging location that was not Shipping
Outbound II | Build Transfer Order | In the UI, the Ship To information field will be taken from the RTV ship to facility level. The user will select the trading partner that the order will go to | After selecting the trading partern for the order and saving out, the ship to fields will update to the ship to information on the selected trading partner level | ecoATM | Pass
Outbound II | Build Transfer Order | User will go through the assign trip - case lot workflow to pack out the order | the order is successfully packed out and a label is generated for the order | ecoATM | Ready to Test
Outbound II | Void Shipping Labels | After an order is shipped, and a label is generated. The user will go to the Shipment on the Shipment table, and they select the process action link "Void Shipping Labels" (use case for when truck driver does not come in time to pick up packages) | The shipping labels will be removed on the OrderHeader Level | ecoATM | Ready to Test
Other WMS
Other WMS | Other WMS - Transfer Orders |  |  |  | NOT Ready to Test
Other WMS | Other WMS - Shipping Documents/Labels |  |  |  | NOT Ready to Test
Other WMS | Other WMS - 3PL Billing |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Other WMS |  |  |  |  | NOT Ready to Test
Reporting
Reporting | Dashboard - Inbound | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Dashboard - Inventory Management Dashboard | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Dashboard - Outbound | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Dashboard - User Performance | -- | Report returns timely and accurately for customer needs |  | NOT Ready to Test
Reporting | Report Builder - | -- | Report returns timely and accurately for customer needs

## End to End Cases
ecoATM End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 0%
Category | Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Inbound | Receive IMEI PO full | Ready to Test | ecoATM
Inbound | Receive Caselot PO full | Ready to Test | ecoATM
Inbound | Receive Partial PO | Ready to Test | ecoATM
Inbound | Receive Outbound Transfer Order | Ready to Test | ecoATM
Inbound | Create RMA from shipped SO and receive in full | Ready to Test | ecoATM
Inbound | Create RMA from shipped SO and receive partially | Ready to Test | ecoATM
Inbound | Putaway case lot containers to case lot zone pickable locations | Ready to Test | ecoATM
Inbound | Sort Units to correct sort type boxes in sortation process | Ready to Test | ecoATM
Inbound | Putaway sorted units to picking locations | Ready to Test | ecoATM
Outbound
Outbound | Fulfill "Parcel" orders | Ready to Test | ecoATM
Outbound | Fulfill "Freight" orders | Ready to Test | ecoATM
Outbound | Fulfill order with caselot line item | Ready to Test | ecoATM
Outbound | Build RTV Transfer Order in system | Ready to Test | ecoATM
Outbound | Fulfill Transfer Order | Ready to Test | ecoATM
Outbound | Fulfill international orders | Ready to Test | ecoATM
Outbound | Fulfill domestic orders | Ready to Test | ecoATM
Outbound | Exception a pick task | Ready to Test | ecoATM
Outbound | Cancel an order that has not yet been released | Ready to Test | ecoATM
Outbound | Cancel an order that has been released but not picked | Ready to Test | ecoATM
Outbound | Cancel an order that has been picked but not packed or shipped | Ready to Test | ecoATM
Outbound | Cancel an order that has been packed but not shipped | Ready to Test | ecoATM
Outbound | Void Shipping Labels after Single Container Packing | Ready to Test | ecoATM
Outbound | Roll back an order that has been shipped and cancel it | Ready to Test | ecoATM
Outbound | Roll back an order that has not been shipped and re-ship | Ready to Test | ecoATM
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Ready to Test | ecoATM
Inventory Management | Perform on demand cycle counts by location | Ready to Test | ecoATM
Inventory Management | Move Inventory from Contact Sales back to Device Testing | Ready to Test | ecoATM

## Go No-Go Tracker
EcoATM Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 26.5
Deposco Setup | Label Printers | 10 | Y | ecoATM | 25% | 2.5 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 | Y | ecoATM | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | ecoATM | 50% | 5 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 | Y | ecoATM | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | ecoATM | 30% | 3 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | ecoATM | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | ecoATM | 30% | 3 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 50% | 5 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Clean up LPNs - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 80% | 8 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 40 |  |  |  | 19
Warehouse Prep | Location Labels | 10 | Y | ecoATM | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT | 8/1 or 8/8
Warehouse Prep | Container Labels | 10 | Y | ecoATM | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT | 8/1 or 8/8
Warehouse Prep | Inventory Labels | 10 |  | ecoATM | 100% | 10 | Are all inventory units labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 |  | ecoATM | 90% | 9 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 55 |  |  |  | 5.5
SOP Documents | Receiving/Unreceiving | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Wholesale Picking | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | ecoATM | 10% | 0.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 27.5
Training & Testing | Test Case Scenarios Definition | 10 |  | DEP / ecoATM | 100% | 10 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and ecoATM to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | ecoATM | 75% | 7.5 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | ecoATM | 50% | 5 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | ecoATM | 50% | 5 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | ecoATM | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 50 |  |  |  | 34
Master Data | Cutover Inventory Validation | 10 | Y | ecoATM | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Decision: Want to bulk upload stock units to generic location and use Deposco to put away prior to launch
Master Data | Items and Packs | 10 |  | ecoATM | 100% | 10 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 | Y | ecoATM | 70% | 7 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | ecoATM | 70% | 7 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Menu Structures | 10 |  | ecoATM | 100% | 10 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 8
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / ecoATM | 80% | 8 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 55 |  |  |  | 55
Interfaces - Imports to Deposco | Carton Types Upload | 10 |  | ecoATM | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 |  | ecoATM | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 |  | ecoATM | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 | Y | ecoATM | 100% | 5 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Trading Partner | 10 |  | ecoATM | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 |  | ecoATM | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Orders Upload (Manifest Upload) | 10 |  | ecoATM | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 120 |  |  |  | 26
Integrations with Deposco | ecoATM Integration - Item - Push | 10 | Y | ecoATM | 80% | 8 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT | MORE INTERFACES MIGHT BE BUILT OUT TO PULL TRADING PARTNERS ETC
Integrations with Deposco | ecoATM Integration - Purchase Order - Pull | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | ecoATM Integration -Stock Unit - Pull | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | ecoATM Integration - Sales Order - Push | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | ecoATM Integration - Receipt Line - Pull | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | ecoATM Integration - Ship Notice - Push | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | ecoATM Integration - Inventory Ledger - Push | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | ecoATM Integration - Inventory ATP - Push | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 |  | ecoATM | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Rate Shop Request | 10 |  | ecoATM | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Stamps - Get Shipping Label | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Stamps - Get Rate Shop Request | 10 | Y | ecoATM | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 30 |  |  |  | 30
Reports and Labeling | Shipping Label | 10 |  | ecoATM | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT | PENDING SECTION TO DECIDE WHICH REPORTS/LABELS WILL BE PRINTED IN DEPOSCO
Reports and Labeling | Sortation Label | 10 | Y | ecoATM | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Container Label | 10 | Y | ecoATM | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Location Labels | 10 | Y | ecoATM | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 0
Contingency Plans | Contingency Plans | 10 | Y | DEP / ecoATM | 0% | 0 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 231.5
| Total Possible Score: | 510
| Total Percentage: | 45.39%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan
ecoATM Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | ENV | OWNER | DATE | NOTES
Pre-cutover
1 | Create Production Environment | Create ticket to stand up prod environment | TRUE | DEP | PROD | Daniel | 2025-07-11
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | TRUE | ecoATM | PROD | Omar
3 | API Setup | Ensure the facility and location ID(s) are validated when moving to prod since these are hard-coded on the URL - these ID(s) can change when created in the PROD env | TRUE | ecoATM | UA & PROD |  | Completed in UA, but validation required for PROD
4 | Test Item Post | Ensure all items come into Deposco as expected | TRUE | ecoATM | UA & PROD
Smoke Testing Week
5 | Test Order Post | Push Sales Order via API into Deposco | FALSE | ecoATM | UA
6 | Test Manifest Upload and Update | Create and update PO/Manifest | TRUE | ecoATM | UA
7 | Test ShipNotice Webhook | Test shipment | FALSE | ecoATM | UA |  |  | Testing of shipping orders, but need to complete end to end for better idea of status
8 | Test Inventory GET | Send an inventory GET via API from Deposco | FALSE | ecoATM | UA |  |  | ATP still open
9 | Test FedEx Label | Fulfil an order using a FedEx shipping service | TRUE | ecoATM | UA
10 | Master Data Check - Items | Look through items in production environment | TRUE | ecoATM | PROD
11 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | TRUE | ecoATM | PROD
12 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | TRUE | ecoATM | PROD
13 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE | ecoATM | PROD |  |  | One open issue - Question with operations.
14 | Master Data Check - Vendors |  | TRUE | ecoATM | PROD
15 | Master Data Check - Customers |  | FALSE | ecoATM | PROD | Omar |  | Need to add shipping account information
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-11 | Plans for onsite UAT
17 | End to End Testing - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE | DEP/ecoATM | UA |  | 2025-08-11
18 | End to End Testing - Picking | Pick an order, ensure everything behaves as expected | FALSE | DEP/ecoATM | UA |  | 2025-08-11
19 | End to End Testing - Box Audit | Audit an order, ensure everything behaves as expected | FALSE | DEP/ecoATM | UA |  | 2025-08-11
20 | End to End Testing - Packing | Pack an order, ensure everything behaves as expected | FALSE | DEP/ecoATM | UA |  | 2025-08-11
21 | End to End Testing - Assign Trip/Build Pallet | Ship out order(s), ensure everything behaves as expected | FALSE | DEP/ecoATM | UA |  | 2025-08-11
Inbound Launch
22 | Wipe smoke testing data | Remove any stock units or open orders from smoke testing from production. | FALSE | DEP | PROD | Daniel | 2025-08-18
23 | Cut off POs from current system | POs uploaded into Deposco | FALSE | ecoATM | PROD |  | 2025-08-15 | Manual upload, so stopping users from uploading. Just instruction to users.
24 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-11
25 | Validate Each Printer | Ensure that printers are able to print a print validation and correct printer assignments are set up | FALSE | DEP/ecoATM | PROD |  | 2025-08-11
26 | Validate Each Sortation Station | Ensure each sortation station is able to log into Depsoco and scanners/printers are working as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-11
Weekend Inventory and Outbound Cutover
27 | Cut off SOs from current system | Orders start to flow into Deposco | FALSE | ecoATM | PROD |  | 2025-08-21
28 | Inventory count/receipt | Stock received/counted into the facility | FALSE | ecoATM | PROD |  | 2025-08-22 | Getting inventory into Deposco; Create transfer orders on 8/21, then execute on 8/22 & 8/23
Outbound Launch
29 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-11
30 | Validate Audit Station | Ensure each audit station is able to log into Depsoco | FALSE | DEP/ecoATM | PROD |  | 2025-08-11 | Test order for outbound smoke testing
31 | Smoke Test - Transfer Order | Transfer inventory from current system to new system | FALSE | DEP/ecoATM | PROD |  | 2025-08-12
32 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-12
33 | Smoke Test - Picking | Pick an order, ensure everything behaves as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-12
34 | Smoke Test - Box Audit | Audit an order, ensure everything behaves as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-12
35 | Smoke Test - Packing | Pack an order, ensure everything behaves as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-12
36 | Smoke Test - Assign Trip/Build Pallet | Ship out order(s), ensure everything behaves as expected | FALSE | DEP/ecoATM | PROD |  | 2025-08-12

## FutureOpen Items Parking Lot
ecoATM Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | Owner | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | ecoATM Comments
RMA | Decision On RMA Processing flow | 2025-02-05 | ECOATM
Sortation | Deposco to meet with Product Owner to discuss best approach for sortation flow | 2025-02-05 | DEP
Stock Unit Fields | Confirm with DB team to see if we have enough fields to store all the info needed | 2025-02-05 | DEP
Shipping Carriers | Register Shipping Carriers | 2025-02-11 | ECOATM
Print Client | Set up print client | 2025-02-11 | ECOATM

## UAT Open Items
Phase 2 Item Tracker
TITLE | DESCRIPTION | Date Opened | DEP Comments | EcoATM Comments | Completed Date | Status | Owner
Test Progress Report | Report on OrderHeader View | 2025-08-11 | 3 New Additional Columns: - Transferred Units - Sold Units - RTV |  |  | Open | DEP
Storage Logic Set Up | Make storage for locations client facing | 2025-08-11 | set up field & add field to query in rules | IMS-632 |  | Open | DEP
Change Barcode XAML | Change screen XAML postUAT for barcode scanning | 2025-08-11 | Change "barcode" to "text" |  |  | Open | DEP
Disable Putaway Flag Receiving | Either Change the XAML or Add a BU | 2025-08-11 |  |  |  | Open | DEP
Device Testing Validation | add validation to move to device testing | 2025-08-11 | add error Added in UA - Ready for EcoATM to Test |  | 2025-08-11 | Validation | ecoATM
Validate slot number fits on sort label | Change "Slot Number" to "Slot" | 2025-08-11 | Change "Slot Number" to "Slot" | max 6 characters |  | Open | DEP
Validation at sortation to force a slot scan | add logic so that user gets error for null slot at first move | 2025-08-11 | add logic so that user gets error for null slot at first move |  |  | Open | DEP
Free Up Slot Config Change | Change Screen message once done from "Box has been moved to the shelf: [RB-001]" to "Box [RB-001] has been moved to shelf [location]" | 2025-08-11 | Change made in UA |  | 2025-08-11 | Validation | ecoATM
|  | 2025-08-11 | Make sure we dont allow blind receiving |  |  | Open | DEP
Open
Open
Open
Open
Open