## On-site Design AI (hidden)
| On-site Design Action Items |  |  | 1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
ITEM # | DESCRIPTION | CREATE DATE | DUE DATE | OWNER | PRIORITY | STATUS | TEAM | OWNER | CREATED | ETA | NOTES

## Design Parking Lot (hidden)
Design Parking Lot
ITEM # | DETAILS | OWNER | STATUS | PRIORITY | ADDITIONAL DETAILS
1 | NDC Capture. How to track NDC? We will need to validate during picking. | DEP | Complete |  | Manufacturer will be tracked in RX label
2 | Demo kit to stock | DEP | New
3 | Re-send Printer config file - Matt | DEP | Complete
4 | Inventory Adjustment Reason Codes | GOWEST | New |  | To provide inventory adjustment reason codes - e.g., EXP¦Expired,DMG¦Damaged
5 | Blind Counts | GOWEST | New |  | To confirm whether blind counts are required
6 | Cycle Counts | GOWEST | New |  | To confirm whether cycle counts will be done by location/item or both
7 | Address Validation for front end orders | GOWEST | New |  | To confirm whether address validation is required for front end orders (Phone)
8 | How to handle inventory adjustments journals? Current touchpoint is inventory sync only and does not include adjustments | CB | New
9 | How to handle blind receiving? CB creates RTV (return to vendor) and gets pushed | CB | New
10 | What is the API time frame required between RX verification and Deposco order creation? | CB | New
11 | Order translation/shipment code | SHIPIUM | New
12 | Which business key value is required for Parata? NDC? | PARATA | New
13 | Rollback order after picking flow | DEP | New
14 | Required info for QC screen, provide details to DEP team | GOWEST | New
15 | Master data | GOWEST | New |  | To confirm zone names and location types
16 | Provide QC solution | DEP | New

## Waving Flows (hidden)
Category | Profile | Path | Cartonization | Picking | Packing | Min | Max
RX | Mix | Batch Picking > QC > Single Scan Packing | No | Batch Picking | Single Scan Packing | 1 | 12
RX | Parata | Batch Picking > QC > Single Scan Packing | No | Batch Picking | Single Scan Packing | 1 | 12
RX | Hand Count | Batch Picking > QC > Single Scan Packing | No | Batch Picking | Single Scan Packing | 1 | 12
RX | Line | Batch Picking > QC > Single Scan Packing w/ Cartonization | Yes | Batch Picking | Single Scan Packing | 1 | 12
RX | Cold | Batch Picking > QC > Single Scan Packing | No | Batch Picking | Single Scan Packing | 1 | 12
OTC | Line Heavy | Batch Picking > Single Scan Packing w/ Cartonization | Yes | Batch Picking | Single Scan Packing | 1 | 12
OTC | Line Light | Batch Picking > Single Scan Packing w/ Cartonization | Yes | Batch Picking | Single Scan Packing | 1 | 12
OTC | Cold | Batch Picking > Single Scan Packing w/ Cartonization | Yes | Batch Picking | Single Scan Packing | 1 | 12
Mix | RX + OTC | Batch Picking > QC RX > Merge OTC > Single Scan Packing | No | Batch Picking | Single Scan Packing | 1 | 12

## Reporting Requirements (hidden)
Reports
CLIENT REQUESTED REPORTS | TYPE | STATUS | ADDITIONAL DETAILS

## Project Management
Week | Budget Remaining | Milestone | Milestone Achieved?
Week1 7/6-7/12 | 360 | Design Doc draft, review, and agreement | TRUE
Week2 7/13-7/19 | 310 | Configuration, hardware, and enviornment set up | TRUE
Week3 7/20-7/26 | 265 | Super User testing and feedback | TRUE
Week4 7/27-8/2 | 235 | End User training and feedback | TRUE
Week5 8/3-8/9 | 200 | End User training, Production Stand up | TRUE
Week6 8/10-8/16 |  | Go Live | TRUE
Week7 8/17-8/23 |  | Post Go Live Support week 1 | FALSE
Week8 8/24-8/30 |  | Post Go Live Support week 2 | FALSE

## Task Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
CATEGORY | DESCRIPTION | TYPE | STATUS | OWNER | SEVERITY | Remote UAT Critical? | Go Live Critical? | Due Date | DEP Comments | Client Comments
Design | Educational Demo | Task | Closed | DEP | High | TRUE | TRUE
Design | On Site details WMS gathering | Task | Closed | DEP | Medium | TRUE | TRUE | 2025-07-10
Design | Design Documents draft | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-11
Design | Design Documents Review | Task | Closed | DEP/GOWEST | High | TRUE | TRUE | 2025-07-11
Master Data | Location Zone Setup | Task | Closed | GOWEST | High | TRUE | TRUE | 2025-07-16
Master Data | Carton types Setup | Task | Closed | GOWEST | High | TRUE | TRUE | 2025-07-18
Master Data | Containers Setup | Task | Closed | GOWEST | High | TRUE | TRUE | 2025-07-16
Master Data | Suppliers | Task | Closed | GOWEST | High | TRUE | TRUE | 2025-07-18
Integrations | Shopify Socket | Task | Closed | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-11
Integrations | UPS | Task | Closed | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-11
Integrations | Loop | Task | Closed | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-18
Integrations | Integration Testing | Task | In Progress | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-25
Hardware / Physical | Printer Setup | Task | Closed | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-25
Hardware / Physical | Handheld Setup | Task | Closed | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-25
Master Data | Printer Assignment and Testing | Task | Closed | DEP/GOWEST | Critical | TRUE | TRUE | 2025-07-25
Inbound | Inbound Config | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-16
Inventory Management | Inventory Management Config | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-16
Outbound | Outbound Config | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-17
Inbound | Inbound Demo | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-16
Inventory Management | Inventory Management Demo | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-16
Outbound | Outbound Demo | Task | Closed | DEP | High | TRUE | TRUE | 2025-07-17
Testing | Inbound Testing | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-07-25
Testing | Inventory Management Testing | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-07-25
Testing | Outbound - Waving Testing | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-07-25
Testing | Outbound - Order Management Testing | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-07-25
Testing | Outbound - Picking/Packing Testing | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-07-25
Training | Inbound Training | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-08-01
Training | Inventory Management Training | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-08-01
Training | Outbound - Waving Training | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-08-01
Training | Outbound - Order Management Training | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-08-01
Training | Outbound - Picking/Packing Training | Task | In Progress | GOWEST | High | TRUE | TRUE | 2025-08-01
Cutover | Cutover, Go-No Go Decision | Task | Open | DEP/GOWEST | Critical | TRUE | TRUE | 2025-08-04

## Test Case Summary
Client Testing Summary
Client: |  | Go West Supply
Client Code: |  | GOWEST
Test Cases Required: |  | 64
Test Cases Executed: |  | 61
Test Cases Remaining: |  | 24
Test Cases Passed: |  | 40
Test Cases Failed: |  | 0
% Complete: |  | 62.5%
Process | Test Cases Required | Test Cases Complete | Test Cases Failed | % Complete
Receiving | 21 | 0 | 0 | 0%
Inventory Management | 14 | 14 | 0 | 100%
Outbound - Waving | 10 | 10 | 0 | 100%
Outbound - Picking/Packing | 19 | 16 | 0 | 84.21%
Integration | 0
UAT/Go-Live Checklist | Status
Test Cases | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Test Case - Inbound
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Inbound
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 21
Test Cases Executed: |  | 21
Test Cases Not Tested: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | 100%
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Purchase Order Test Cases
1 | Switch User Facility | 1.01 | Confirm that user is located in the correct facility. Navigate to Handheld > Inbound > Change Facility. | Change User Facility Screen pops up. You are presented with a list of all the available facilities. | Cannot change facilite |  | Cade | Pass |  | Currently doesn't apply, but will be using in the future
|  | 1.02 | Select the corresponding facility from the list. Hit "Next". | Screen message will say "Updated user facility to [facility name]."
2 | Create Purchase Orders (Through PO Entry) | 2.01 | Navigate to the "PO Entry" button under Purchasing in UI Application Menu. | After PO is Entered: 1) PO will be created and can be found in "PO Entry". 2) Associated PO lines will be attached with the PO. | PO112 Created |  | Cade | Pass | The bill to supplier went away once i selected it. Is this because it is the same?
|  | 2.02 | Click "New Purchase Order" on top right cornor.
|  | 2.03 | Enter or Select Supplier and Bill to Supplier. Enter optional field including Other Reference Number, Payment Terms, Planned Arrival Date.
|  | 2.04 | Use Item Search to select items that need to be placed in the PO, then enter Planned Arrival Date, Order Quantity.
|  | 2.05 | Keep adding items to the existing PO and Enter optional fields as needed.
|  | 2.06 | Hit Save Draft to work on the PO later or Submit to end entering PO process.
3 | Create Purchase Orders (Through Data Exchange) | 3.01 | Navigate to the "Purchase Order" import template under Data Exchange -> Field Mapping in UI Application Menu. | After PO is Entered: 1) PO will be created and can be found in "PO Entry". 2) Associated PO lines will be attached with the PO. |  |  | Cade | Pass | First attempt i did not delete the empty row or column causing failed upload. Second attempt I 1 of 2 records were processed.... thinking it is due to not filling out all details on each line item. Third attempt i was able to get a success status.
|  | 3.02 | Click "Download Sample CSV".
|  | 3.03 | For each line of records: Enter Purchase Order Number, Supplier, Bill to, Item, and Order Pack Quantity Enter optional field including Other Reference Number, Planned Arrival Date, and Unit Cost.
|  | 3.04 | Use Item Search to select items that need to be placed in the PO, then enter Planned Arrival Date, Order Quantity.
|  | 3.05 | Keep adding new lines with different items to the existing PO and Enter optional fields as needed.
|  | 3.06 | Save excel file and Nevigate "PO Import" under Data Exchange in applicaiton menu, then on the right click 3 dots icon the click "Run". Finally, drop saved file in the portal.
4 | Purchase Orders (Receive in Full) | 4.01 | Navigate to the "PO Receiving" button under Inbound | After PO is Received: 1) A screen message will display on the MainMenu saying "All lines have been received." 2) Updates made to PO and PO Lines 3) Receipt Line record created for each orderline received 4) Stock created in the receiving location 5) Depending on process configuration, Item Label may have printed. | All lines have been received |  | Cade | Pass | When scanning/entering SKU it keeps saying "enter the product number." Is this standard? or do we need to just turn down our volume on the handheld?
|  | 4.02 | Enter/Scan the Order Number under Identifier Number Field. Select Submit or Enter when finished.
|  | 4.03 | Scan/Enter the items you are receiving (list of items on the PO will be provided in the list box)
|  | 4.04 | Keep scanning item number or UPC to receive.
|  | 4.05 | After each scan, QTY will change.
|  | 4.06 | If there are multiple lines on the purchase order, you will be staying the "Receive Item Screen". Repeat the steps above untill all items are received.
5 | Purchase Orders (Partial Receipt) | 5.01 | Navigate to the "PO Receiving" button under Inbound | After PO is Received: 1) A screen message will display on the MainMenu saying "Purchase Order [Purchase Order Number] is received partially." 2) Updates made to PO and PO Lines 3) Receipt Line record created for each orderline received 4) Stock created in the receiving location |  |  | Cade | Pass | Did not get the partially recevied message after clicking finish. Also on the PO Entry page, you cannot see the order total. Why is that?
|  | 5.02 | Enter/Scan the Order Number under Identifier Number Field. Select Submit or Enter when finished.
|  | 5.03 | Scan/Enter the items you are receiving (list of items on the PO will be provided in the list box)
|  | 5.04 | Keep scanning item number or UPC to receive.
|  | 5.05 | After each scan, QTY will change.
|  | 5.06 | Whenever user wish to stop without receiving remainding QTY, hit "Finish".
6 | Purchase Orders (Blind Receipt) | 6.01 | Navigate to the "PO Receiving" button under Inbound | After PO is Received: 1) A screen message will display on the MainMenu saying "Blind Purchase Order [Purchase Order Number] is received." 2) Updates made to Blind PO and PO Lines 3) Receipt Line record created for each orderline received 4) Stock created in the receiving location | Receipt lines 143-147 created |  | Cade | Pass | After each scan, you have to click next. You cannot scan and then scan again causing it to take longer than you would like. Received the "All lines have been received message" instead of "blind Purchase order is received."
|  | 6.02 | Enter Nothing under Identifier Number Field. Select Submit or Enter when finished.
|  | 6.03 | No item will be displayed, but user can scan item to proceed
|  | 6.04 | Keep scanning item number or UPC to receive.
|  | 6.05 | After each scan, QTY will change.
|  | 6.06 | Whenever user wish to stop without receiving remainding QTY, hit "Finish".
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Not Tested/Fail | GOWEST Notes | Deposco Notes
Customer Returns and Damages Receiving Test Cases
1 | Returns Receiving (Receive in Full) | 1.01 | Navigate to the "Return Receiving" button under Inbound | After RMA is Received: 1) A screen message will display on the MainMenu saying "Customer Return [Customer Return Number] is received. All lines have been received." 2) Updates made to Customer Return and Customer Return Lines 3) Receipt Line record created for each orderline received 4) Stock created in the Returns location
|  | 1.02 | Enter/Scan the Customer Return Number under Identifier Number Field.
|  | 1.03 | Scan/Enter the items you are receiving (list of items on the Customer Return will be provided in the list box)
|  | 1.04 | Keep scanning item number or UPC to receive.
|  | 1.05 | After each scan, QTY will change.
|  | 1.06 | If there are multiple lines on the return order, you will be staying the "Receive Item Screen". Repeat the steps above untill all items are received.
2 | Returns Receiving (Partial Receipt) | 2.01 | Navigate to the "Return Receiving" button under Inbound | After RMA is Partially Received: 1) A screen message will display on the MainMenu saying "Customer Return [Customer Return Number] is received. All lines have been received." 2) Updates made to Customer Return and Customer Return Lines 3) Receipt Line record created for each orderline received 4) Stock created in the Returns location
|  | 2.02 | Enter/Scan the Customer Return Number under Identifier Number Field.
|  | 2.03 | Scan/Enter the items you are receiving (list of items on the Customer Return will be provided in the list box)
|  | 2.04 | Keep scanning item number or UPC to receive.
|  | 2.05 | After each scan, QTY will change.
|  | 2.06 | Whenever user wish to stop without receiving remainding QTY, hit "Finish".
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Step Details | Status | GOWEST Notes | Deposco Notes
Putaway Processes
1 | Putaway Single Item | 1.01 | Navigate to "Single Item Putaway" under Inventory on handheld MainMenu | This process allows a user to move unique items individually out of a location and into a different location 1) Stock units that were moved are decremented from their source location, and are created in the destination location | Was able to move 5 pairs of jeans to bin location 16-01-01. Had to remember 160101 instead of dashes |  | Cade | Pass | In the step details it says to go to inventory.... thinking this is supposed to be under inbound instead since that is where single item put away is
|  | 1.02 | Enter the location that contains the stock you want to move
|  | 1.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  | 1.04 | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  | 1.05 | User is prompted to putaway screen and a listbox of suggested locations is displayed. User must scan or select a location in which to put the stock away.
|  | 1.06 | If user wants to continue moving items from this location, user can repeat steps 1.03-1.06
|  | 1.07 | Otherwise, user can exit the process
2 | Putaway Multi Items | 2.01 | Navigate to "Multi items Putaway" under Inventory on handheld MainMenu | This process allows a user to move multiple items using the same process, instead of one unique SKU. 1) When all stock has been moved successfully, a message displays on menu saying "All Items Moved." 2) Picking Cart is now empty and remains in its original location. 3) Stock units that were moved are decremented from their source location, and are created in the destination location. | Was able to get the All items moved messsage at the end of all the steps. Went ahead and tried thr process again to ensure i coudl do it without receiving an error emssage. |  | Cade | Ready for Retest | When you get to 2.03. Should we have a barcode at the receiving location so yoou can just scan the barcode instead of typing it in?
|  | 2.02 | Enter/Scan container in Container field displays the cart in which you want to put the stock you are wanting to move
|  | 2.03 | Enter or scan location with the stock you want to move
|  | 2.04 | A listbox of available SKUs to move display. User must scan or enter Pack UPC to move
|  | 2.05 | Select Pack UOM, enter in quantity to move and select Submit
|  | 2.06 | You will be taken to an Item Capture Screen. Scan the lot number. Enter Quantity.
|  | 2.07 | Repeat steps 2.04-2.06 to move more items in the location into your assigned cart.
|  | 2.08 | User is given a summary of the number of unique Skus and quantity in cart. If user wants to move stock in a different location, User can scan another location.
|  | 2.09 | When finished, select Move Source Screen.
|  | 2.1 | On the Move Source Screen, hit Move to move items in your assigned user cart to a directed location. ** Move Full allows you to move the entire stock in a container. Using this will not give you suggested putaway locations. Please do not use this for Inbound putaway.
|  | 2.11 | User enters quantity and selects/scans item.
|  | 2.12 | A listbox of suggested putaway locations is displayed. User must select or scan a location to move the stock
|  | 2.13 | User repeats 2.10-2.12 to move the rest of the stock, if any
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
PO Receiving Edge Cases
1 | Incorrect PO# Entry | 1.01 | Navigate to Handheld > Inbound > PO Receiving. | Confirm Blind Order Screen will be displayed. "No records found matching that identifier, click Next to continue as Blind Order." Screen Message will be displayed. | All lines have been recieved - badpo321 |  | Cade | Pass
|  | 1.02 | Enter a PO Number that does not exist.
2 | Scanning Already Received PO | 2.01 | Navigate to Handheld > Inbound > PO Receiving. | Error message appears reading, "Purchase Order [] can not be received in because it is in status [Received].". | po69 cannot be received because it is in status received |  | Cade | Pass
|  | 2.02 | User scans a PO that has already been received instead of a new PO.
|  | 2.03 | User will be prevented from continuing with the process
3 | Attempt to Finish PO without Receiving Item | 3.01 | Navigate to Handheld > Inbound > PO Receiving. | If nothing has been received, user will be directed back to Identifier Input Screen. | Tried clicking "finish" kept telling me to enter the item number |  | Cade | Pass
|  | 3.02 | Enter a PO Number.
|  | 3.03 | User hits "Finish/Exit" without receiving an item
|  | 3.04 | If nothing has been received, user will be directed back to Identifier Input Screen.
4 | Receiving an existing Item not on a PO | 4.01 | Navigate to Handheld > Inbound > PO Receiving. | Error message appears reading, "Unable to find order line for item:" | received unable to find order line for item |  | Cade | Pass
|  | 4.02 | User scans/Keys an Item not on PO for receiving.
|  | 4.03 | User will be prevented from receiving the item in the process
5 | Receiving an Item that is not on a PO nor exists in the system | 5.01 | Navigate to Handheld > Inbound > PO Receiving. | Error message appears reading, "Please scan a valid item." | Received please scan a valid item message |  | Cade | Pass
|  | 5.02 | User scans/Keys an Item not on PO for receiving
|  | 5.03 | User will be prevented from receiving the item in the process
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Returns Receiving Edge Cases
1 | Incorrect RMA# Entry | 1.01 | Navigate to Handheld > Inbound > Return Receiving. | A message should dispay reading, "Customer Return _____ does not exist" |  |  | Cade
|  | 1.02 | Enter a Returns Number that does not exist.
2 | Scanning Already Received RMA | 2.01 | Navigate to Handheld > Inbound > Return Receiving. | Error message appears reading, "There are no lines eligible to receive for this order". |  |  | Cade
|  | 2.02 | User scans a Customer Return that has already been received instead of a new Customer Return
|  | 2.03 | User will be prevented from continuing with the process
3 | Attempt to Finish RMA without Receiving Item | 3.01 | Navigate to Handheld > Inbound > Return Receiving. | Message will show nothing has been received from the associated Returns. |  |  | Cade
|  | 3.02 | User hits "Finish/Exit"
|  | 3.03 | If nothing has been received, user will receive message "You have not received any item for order [_____]"
4 | Receiving an existing Item not on an RMA | 4.01 | Navigate to Handheld > Inbound > Return Receiving. | Error message appears reading, "Please enter a valid SKU for [Customer Return]." |  |  | Cade
|  | 4.02 | User scans/Keys an Item not on Customer Return for receiving
|  | 4.03 | User will be prevented from receiving the item in the process
5 | Receiving an Item that is not on an RMA nor exists in user facility | 5.01 | Navigate to Handheld > Inbound > Return Receiving. | Error message appears reading, "Order [Customer Return#] only accepts items in Company [MAIN]. Please enter an item for Company [MAIN] or hit 'Finish' and start a new order for this item." |  |  | Cade
|  | 5.02 | User scans/Keys an Item not on Customer Return for receiving
|  | 5.03 | User will be prevented from receiving the item in the process
6 | Over-Receive | 6.01 | During Receiving, user keys in quantity that is greater than the order pack quantity. | Message should appear reading "Quantity entered is greater than the Inbound Transfer Order Quantity. Please validate the quantity is correct and re-enter it". Email should be sent to merch team to notify of an overreceipt after receiving process has been completed |  |  | Cade
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Putaway Edge Cases
1 | Incorrect Location Entry | 1.01 | Navigate to Handheld > Inbound > Single Item Putaway. | A message should dispay reading, "The location [] could not be found in your current facility." | Received could not be found in facility message |  | Cade | Pass |  | Single Item putaway
|  | 1.02 | Enter a Locator that does not exist.
2 | Moving an item not in scanned location | 2.01 | Navigate to Handheld > Inbound > Single Item Putaway. | Error message appears reading, "Scanned item [] doesn't exist in location [].". | Scanned item doesnt exist message |  | Cade | Pass |  | Single Item putaway
|  | 2.02 | Scan locator
|  | 2.03 | Scan an item not on the list
3 | Moving quantity more than quantity in the location | 3.01 | Navigate to Handheld > Inbound > Single Item Putaway. | Error message appears reading, "The entered quantity exceeds the total movable Each quantity of *". | Quantity exceeds total movable quanitty of 5 |  | Cade | Pass |  | Single Item putaway
|  | 3.02 | Scan locator
|  | 3.03 | Scan an item on the list
|  | 3.04 | Enter quantity more than what's in the screen
4 | Moving to a location not on suggested list | 4.01 | Navigate to Handheld > Inbound > Single Item Putaway. | Move will be completed, selected item with quantity will be moved to the scanned locator | Item moved to 010103 |  | Cade | Pass |  | Single Item putaway
|  | 4.02 | Scan locator
|  | 4.03 | Scan an item on the list then eneter quantity
|  | 4.04 | Scan locator not on the list
5 | Incorrect Location Entry | 5.01 | Navigate to Handheld > Inbound > Multi Items Putaway. | A message should dispay reading, "No such location or LPN in the current facility." |  |  | Cade | Pass |  | Multi Items Putaway
|  | 5.02 | Enter a Locator that does not exist.
6 | Moving an item not in scanned location | 6.01 | Navigate to Handheld > Inbound > Multi Items Putaway. | Error message appears reading, "Please enter a valid item number.". |  |  | Cade | Pass |  | Multi Items Putaway
|  | 6.02 | Scan locator
|  | 6.03 | Scan an item not on the list
7 | Moving quantity more than quantity in the location | 7.01 | Navigate to Handheld > Inbound > Multi Items Putaway. | Error message appears reading, "The entered quantity exceeds the total available quantity for pack type.". |  |  | Cade | Pass |  | Multi Items Putaway
|  | 7.02 | Scan locator
|  | 7.03 | Scan an item on the list
|  | 7.04 | Enter quantity more than what's in the screen
8 | Moving to a location not on suggested list | 8.01 | Navigate to Handheld > Inbound > Multi Items Putaway. | Move will be completed, selected item with quantity will be moved to the scanned locator |  |  | Cade | Pass |  | Multi Items Putaway
|  | 8.02 | Scan locator
|  | 8.03 | Scan an item on the list then eneter quantity then go back to move source screen
|  | 8.04 | Hit move and select item and quantity
|  | 8.05 | Scan locator not on the list
9 | Move all item from the cart | 9.01 | Navigate to Handheld > Inbound > Multi Items Putaway. | Move will be completed, selected item with quantity will be moved to the scanned locator |  |  | Cade | Pass |  | Multi Items Putaway
|  | 9.02 | Scan locator
|  | 9.03 | Scan an item on the list then eneter quantity then go back to move source screen
|  | 9.04 | Hit "Move" then click "All"
|  | 9.05 | Scan locator

## Test Case - Inventory Managemen
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Inventory Management
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 14
Test Cases Executed: |  | 14
Test Cases Passed: |  | 14
Test Cases Failed: |  | 0
% Complete: |  | 100%
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Cycle Count
1 | Create Cycle Count Task by Location | 1.01 | Make sure Cycle Count checkbox is checked for both Item and the Location that contains its stock units (Inventory). | Using the location cycle count creation handheld process will create cycle count tasks for a specific location Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEFORE TESTING. When cycle counting via handheld "Perform Cycle Count" process, user will be prompted to count all specified items in the location. | cycle count task created for 090901 |  |  | Pass
|  | 1.02 | Navigate to "Create Cycle Count By Location" under Inventory in handheld menu
|  | 1.03 | Scan or enter the location to count
|  | 1.04 | Optionally enter a priority for the cycle count. If no priority is entered, then the priority will default to five (Medium).
|  | 1.05 | Cycle count tasks for the location will appear in the Cycle Count Queue table. (located in Inventory Admin menu option on the desktop UI)
2 | Perform Cycle Count | 2.01 | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. More info on this in the next test script. | was able to get the correct cycle count and then move onto the next location - 160202 |  |  | Pass
|  | 2.02 | Scan or enter starting location (any location in the warehouse) and hit enter
|  | 2.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 2.04 | User will scan the location they're directed to
|  | 2.05 | User will be shown a list box with items in location needing to be cycle counted.
|  | 2.06 | User will scan SKU and hit enter
|  | 2.07 | On the next screen, user will select the pack type and enter the quantity they counted.
|  | 2.08 | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  | 2.09 | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  | 2.1 | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
3 | Manage Cycle Count Variances | 3.01 | User (typically a supervisor or manager) will enter the "Approve Variances" UI through a laptop or desktop | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances". | Able to accept variance for ID 20 |  |  | Pass
|  | 3.02 | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system.
|  | 3.03 | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted.
|  | 3.04 | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted).
4 | On Demand Cycle Count | 4.01 | User will select "Perform On Demand Location Cycle Count" from Inventory menu | If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. (ref seq. 7) Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING. | Created cycle count variance for ID 23 |  |  | Pass
|  | 4.02 | User will be prompted to enter a location and priority (1-10 w/1 being highest priority). Priority defaults to 5 if left empty.
|  | 4.03 | User creates cycle count task and will immediately begin task (reference seq. 3, steps 3.04-3.10) and will be assigned to the user to complete.
5 | Physical Count | 5.01 | Select "Physical Count" from Inventory Menu. This is only usable after selecting and activating a physical count via the Admin Menu. | 1) When Physical Count Activity is started from Physical Count Admin button, message will appear saying "[controlled/non-controlled] Physical Count Activity [process name] is started on [date time] and is active". 2) Non-controlled Physical Count Activity will be able to create and delete inventory. Stock units will be updated with whatever is counted for that location. 3) If controlled, discrepancies will be recorded in "Manage Cycle Count Variances" . 4) Once physical count activity is complete, screen will return to MainMenu and will display a message saying "[controlled/non-controlled] Physical Count Activity [process name] is finished at [date time]". 5) Adjustments to item's SU will show up in Inventory General Ledger Table |  |  |  | Pass | Getting an error message when trying to scan items to increase the quantity of what is being scanned for location 080801. Feel like i should have to scan each item instead of type in a quantity-----this method is a physical count meaning you do not scan anything. You do not have to use this option.
|  | 5.02 | Scan/Enter a location
|  | 5.03 | User counts items in location
|  | 5.04 | To go onto the next location, User can select "Next Location"
|  | 5.05 | If phys count activity is non-controlled, user is taken to phys count summary screen and can click "Recount" or "Apply" before finally confirming.
|  | 5.06 | When done with physical count activity, navigate to "Physical Count Admin" button and click "Finish Physical Count Activity"
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Adjust Inventory
1 | Adjust Inventory: Decrement Inventory out of a Location | 1.01 | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 4) Updates made to Item's SU in location |  |  |  | Pass
|  | 1.02 | Scan/key in Location
|  | 1.03 | Select "Consume by Item"
|  | 1.04 | Scan Item SKU
|  | 1.05 | Enter quantity of item's SU you want to consume
|  | 1.06 | If you have more than one item's SU you want to consume in the location, click next and repeat steps 2.04 and 2.05
|  | 1.07 | Once finished, click Confirm
|  | 1.08 | Once final reviewing all items, select Reason Code and click Commit
2 | Adjust Inventory: Add Inventory to a Location | 2.01 | Select "Adjust Inventory" from the Inventory menu | 1) After items have been confirmed and the user clicks commit, user is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" 2) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 3) Updates made to Item's SU in location | Was able to add "found" inventory but still had to manually type in the quantity instead of scanning |  |  | Pass
|  | 2.02 | Scan/key in Location
|  | 2.03 | Select "Create Inventory"
|  | 2.04 | Scan Item SKU
|  | 2.05 | Enter quantity of item's SU you want to create. User can optionally enter serial, lot, and LPN #.
|  | 2.06 | If you have more than one item's SU you want to create, click next and repeat steps 2.04 and 2.05
|  | 2.07 | Once finished, click Confirm
|  | 2.08 | Once final reviewing all items, select Reason Code and click Commit
3 | Adjust Inventory: Consume All Inventory in Location | 3.01 | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location | Was able to get to the commit step but did not want to click the button to remove everything from receiving location |  |  | Pass
|  | 3.02 | Scan/key in Location
|  | 3.03 | Select "Consume All in Location"
|  | 3.04 | Select Reason Code and Click Commit
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Inventory Edge Cases
1 | Ad-Hoc Cycle Count - Counting Less than the Item's Qty | 1.01 | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances" UI for a manager or supervisor to review 2) If qty count entered is less than the system's qty, a negative variance qty will be displayed for that item in "Approve Variances" | Varaince ID 25 created |  |  | Pass
|  | 1.02 | User will enter quantity less than the item's SU quantity currently in Deposco's system
|  | 1.03 | User will be asked to recount and will proceed to re-enter the quantity.
2 | Ad-Hoc Cycle Count - Counting More than the Item's Qty | 2.01 | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances UI for a manager or supervisor to review 2) If qty count entered is more than the system's qty, a positive variance qty will be displayed for that item in "Approve Variances" | Was able to bypass the scanning each item by manually inputting the quantity |  |  | Pass
|  | 2.02 | User will enter quantity more than the item's SU quantity currently in Deposco's system
|  | 2.03 | User will be asked to recount and will proceed to re-enter the quantity.
3 | Perform Cycle Count - Scanning incorrect Location | 3.01 | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) Error message saying "You must cycle count the given location [required location]". 2) User will be prevented from ever counting in an incorrect location. | Received a cycle count must be performed for the 090901 location |  |  | Pass
|  | 3.02 | Scan or enter starting location and hit enter
|  | 3.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 3.04 | User scans an incorrect location
User is prompted to re-enter correct location. Proceed as normal.
4 | Perform Cycle Count - Scanning Item that does not exist in Location | 4.01 | Select Perform Cycle Count button in handheld menu from Inventory | 1) Variance be generated in the "Approve Variances" UI for a manager or supervisor to review | Able to approve cycle count variances |  |  | Pass
|  | 4.02 | Scan or enter starting location and hit enter
|  | 4.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 4.04 | User will incorrectly scan an item not listed nor existing in the location
|  | 4.05 | On the next screen they'll select the pack type and enter the quantity they counted
|  | 4.06 | User will be brought back to the screen displaying the list box of items and can proceed as normal
5 | Physical Count- Physical Count Activity not Started | 5.01 | User makes sure there is no physical count activity started by navigating to Physical Count Admin button In the Admin Menu. If there is one existing, user should select "Finish Physical Count Activity". | 1) User will get an error on MainMenu saying "PHYSICAL_COUNT Activity has not started." 2) User will not be able to start physical count process unless the activity has been started in Physical Count Admin. |  |  |  | Pass
|  | 5.02 | Select "Physical Count" button in Admin Folder
|  | 5.03 | User will not be able to start physical count
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Inventory Adjustment Edge Cases
1 | Adjust Inventory: Decrement Inventory out of a Location | 1.01 | Select "Adjust Inventory" from the Inventory menu | Screen message "Please enter a quantity that is equal to or less than the current consumable inventory [] quantity." will be displayed. |  |  |  | Pass | After the 5th step, you have to hit confirm and then give a reason why you are conusming that inventory
|  | 1.02 | Scan/key in Location
|  | 1.03 | Select "Consume by Item"
|  | 1.04 | Scan Item SKU
|  | 1.05 | Enter quantity of the item that's more than on the screen

## Test Case - Outbound Order Wave
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Outbound - Waving
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 10
Test Cases Executed: |  | 10
Test Cases Passed: |  | 10
Test Cases Failed: |  | 0
% Complete: |  | 100%
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Waving (Build And Release Logic)
1 | Release Single Line Single Quantity Wave | 1.01 | Create Sales Orders with status as New. These Sales orders must follow this specific criteria: Single Line Single Quantity | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table). 2) Depending on the amount of orders released, and the items on the order, one or many waves will be created. Orders with items that have the single line and single item will be grouped in the same wave, max number orders per wave is 20. 3) Wave is available for selection in the handheld menu under Outbound> Single Scan Picking 4) Wave name starts with Single-Singles-${DATE}_${BUILD_TIME}-${COUNTER} | WHen you batch them out, they will automatically go into their designated wave dependent on the line items within order |  |  | Pass | You need to either click into the order or select all of the new orders and then you are able to find the actions drop down to Build and Release Wave
|  | 1.02 | From the actions list on the top right, select Post Order Import - this will bring up a pop-up- when that says completed, you may close the pop up.
|  | 1.03 | Run "Build and Release Wave" manually from the actions drop-down menu. Find this by selecting the actions list on the top right
2 | Release Single Line Multi Quantities Wave | 2.01 | Create Sales Orders with status as New. These Sales orders must follow this specific criteria: Single Line Multi Quantities | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table). 2) Depending on the amount of orders released, and the items on the order, one or many waves will be created. Orders with items that have the single line and single item will be grouped in the same wave, max number orders per wave is 20. 3) Wave is available for selection in the handheld menu under Outbound> Single Scan Picking 4) Wave name starts with Single-Multis-${DATE}_${BUILD_TIME}-${COUNTER} |  |  |  | Pass
|  | 2.02 | From the actions list on the top right, select Post Order Import - this will bring up a pop-up- when that says completed, you may close the pop up.
|  | 2.03 | Run "Build and Release Wave" manually from the actions drop-down menu. Find this by selecting the actions list on the top right
3 | Release Multi Line Wave | 3.01 | Create Sales Orders with status as New. These Sales orders must follow this specific criteria: Multi Lines | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table). 2) Depending on the amount of orders released, and the items on the order, one or many waves will be created. Orders with items that have the single line and single item will be grouped in the same wave, max number orders per wave is 12. 3) Wave is available for selection in the handheld menu under Outbound> Single Scan Picking 4) Wave name starts with Batch-Multis-${DATE}_${BUILD_TIME}-${COUNTER} |  |  |  | Pass
|  | 3.02 | From the actions list on the top right, select Post Order Import - this will bring up a pop-up- when that says completed, you may close the pop up.
|  | 3.03 | Run "Build and Release Wave" manually from the actions drop-down menu. Find this by selecting the actions list on the top right
4 | Release Express Order Wave | 3.01 | Create Sales Orders with status as New. These Sales orders must follow this specific criteria: Order shipvia as UPS Next Day and Express Order Flasg as True | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table). 2) Depending on the amount of orders released, and the items on the order, one or many waves will be created. Orders with items that have the single line and single item will be grouped in the same wave, max number orders per wave is 12. 3) Wave is available for selection in the handheld menu under Outbound> Single Scan Picking 4) Wave name starts with Express-${DATE}_${BUILD_TIME}-${COUNTER} | On this one the pick wave number is the same as a single single. Should it say something about express in the pick wave number?
|  | 3.02 | From the actions list on the top right, select Post Order Import - this will bring up a pop-up- when that says completed, you may close the pop up.
|  | 3.03 | Run "Build and Release Wave" manually from the actions drop-down menu. Find this by selecting the actions list on the top right
5 | Undo Release Entire Wave | 5.01 | Navigate the wave that need to be undone release, wave must be in "Released" status and Orders need to be in "Released" status | 1) Wave is unreleased and status changed to "Plan". 2) Orders status changed from "Released" to "New". | To start out you need to be in pick wave instead of orders |  |  | Pass
|  | 5.02 | On top right, click action and hit "Undo Release"
6 | Undo Release Specific Order from the wave | 6.01 | Navigate the wave that need to be undone release, wave must be in "Released" status and Orders need to be in "Released" status | 1) Orders status changed from "Released" to "New". | 76 changed from released to new |  |  | Pass
|  | 6.02 | On top right, click action and hit "Undo Release Order"
|  | 6.03 | Select the order that need to be unreleased
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Order Management Test Cases
1 | Cancel Entire Order | 1.01 | Navigate the Order in Distribution -> Orders in UI | 1) Entire order will be canceled, status changed to "Canceled" 2) Order lines Cancel Pack Quantity will changed to the same as Order Pack Quantity | Cancelled 1044 |  |  | Pass
|  | 1.02 | Use Action, then click "Cancel Entire Order".
2 | Cancel Order Lines | 2.01 | Navigate the Order in Distribution -> Orders in UI | 1) Order line will be canceled, status changed to "Canceled" if canceled quantity is the ordered quantity 2) Order lines Cancel Pack Quantity will changed to the same as Order Pack Quantity | Partially cancelled 1042 |  |  | Pass
|  | 2.02 | Use Action, then click "Cancel Order Lines".
|  | 2.03 | Find the order line need to be canceled and enter the quantity need to be canceled.
3 | Reset Sales Order | 3.01 | Navigate to Handheld > Admin > Reset Sales Order. | 1) Order rolled back to new, status changed to "New". 2) If the order in an invalid status, then screen message "Invalid order [] to reset: this order has a shipment that is not in status: [New, Rolled Back, Shipping]" will be displayed. | reset 1043 |  |  | Pass
|  | 3.02 | Enter Order Number
|  | 3.03 | Order must be in valid status
4 | Roll Back Order | 4.01 | Navigate to Handheld > Admin > Roll Back Order. Order needs to be in Picking or Comepleted but not Shipped status | 1) Order will be rolled back to new. 2) Picked Skus will be staged in Shipping location | What should i be entering for LPN on screen after clicking roll back order |  |  | Pass | Scan whtever cart or bin the order was picked to
|  | 4.02 | Scan
5 | Void Shipment | 5.01 | Navigate to Handheld > Admin > Void Shipment. Order need to be Completed and Shipped Status. | 1) Order will be rolled back to Completed but not Shipped. 2) Picked Skus will be staged in a LPN in Shipping location. |  |  |  | Pass
|  | 5.02 | Scan the shipment tracking number

## Test Case - Outbound PickingPac
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Picking / Packing
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 19
Test Cases Executed: |  | 16
Test Cases Not Testeded: |  | 16
Test Cases Failed: |  | 0
% Complete: |  | 84.21%
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Picking
1 | Singles Scan Picking - Single line Single Quantity Wave | 1.01 | User will navigate Single Scan Picking under Outbound | 1) Picking cart will be staged to default Shipping Location to be packed out 2) Stock is added to picking container(s) 3) Updates are made to container pick details 4) Entire wave picked into 1 cart, could contains multiple orders | Was able to get back to the menu screen after picking 3 separate orders. Just need to remind myself to scann the LPN of the cart i plan to use for picking |  | Cade | Pass
|  | 1.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single-Singles-${DATE}_${BUILD_TIME}-${COUNTER}.
|  | 1.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 1.04 | Enter and repeate for next task until the entire wave is done.
|  | 1.05 | Once all pick tasks have been completed, user is returned to menu screen
2 | Singles Scan Picking - Single line Multi Quantities Wave | 2.01 | User will navigate Single Scan Picking under Outbound | 1) Picking cart will be staged to default Shipping Location to be packed out 2) Stock is added to picking container(s) 3) Updates are made to container pick details 4) Entire wave picked into 1 cart, could contains multiple orders |  | When you get to the screen where you are scanning the barcode, you need to put the quantity in the quantity section BEFORE scanning the item. | Cade | Pass | After scanning the first item, the next scan changed the location instead of just scanning another product
|  | 2.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single-Multis-${DATE}_${BUILD_TIME}-${COUNTER}.
|  | 2.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 2.04 | Enter and repeate for next task until the entire wave is done.
|  | 2.05 | Once all pick tasks have been completed, user is returned to menu screen
3 | Batch Picking - Multi Lines Multi Quantities | 3.01 | User will navigate Batch Picking under Outbound | 1) Picking cart will be staged to default Shipping location to be shipped 2) Stock is added to picking container(s) 3) Updates are made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location 5) 1 order picked into 1 cart/bin | Is there a way to have the quantity increase when you scan the item? How can you advance to the next task automatically instead of clicking in one of the fillable spaces and clikcing enter? | If there is more than one for the quantity, you need to enter the number of items you are to pick before scanning the item. For going to the next portion of the wave, the handheld setting once updated will move us to the next screen | Cade | Pass | Is there a way to have the quantity increase when you scan the item? How can you advance to the next task automatically instead of clicking in one of the fillable spaces and clikcing enter?
|  | 3.02 | User will see a list of waves specific to Batch Picking process and can select or enter the wave, wave name starts with Batch-Multis-${DATE}_${BUILD_TIME}-${COUNTER}.
|  | 3.03 | User will be taken to picking screen and scan SKU and picking cart, and enter quantity.
|  | 3.04 | Complete the wave by picking all the items on the pick tasks
|  | 3.05 | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity (User will need to refer Suggested Bin to scan the same bin for the same order)
|  | 3.06 | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
4 | Batch Picking - Multi Lines Multi Quantities | 4.01 | User will navigate Batch Picking under Outbound | 1) Picking cart will be staged to default Shipping location to be shipped 2) Stock is added to picking container(s) 3) Updates are made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location 5) 1 order picked into 1 cart/bin |  |  | Cade | Pass | Keeps skipping the quanitty when i scan an item
|  | 4.02 | User will see a list of waves specific to Batch Picking process and can select or enter the wave, wave name starts with Express-${DATE}_${BUILD_TIME}-${COUNTER}.
|  | 4.03 | User will be taken to picking screen and scan SKU and picking cart, and enter quantity.
|  | 4.04 | Complete the wave by picking all the items on the pick tasks
|  | 4.05 | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity (User will need to refer Suggested Bin to scan the same bin for the same order)
|  | 4.06 | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Packing
1 | Consolidation | 1.01 | Select Carton Consolidation from the Outbound menu. | Items are moved to the correct bin and consolidated for next steps |  |  | Cade | Pass |  | Currently doesn't apply, but will be using in the future
|  | 1.02 | Enter the Source Location, which is most likely Shipping or Rx Staging as repalletize will happen after picking, once the bins are staged at shipping.
|  | 1.03 | If the order was picked into separate bins. To consolidate the orders, the user can combine both orders into one bin. For example, if the order is in bins 1 and 2, and they should be consolidated, the user can consolidate both orders in bin 1 using Repalletize. The user should select either order's bin to move the contents of.
|  | 1.04 | Enter the bin# to hold both consolidated orders. Select "move all" in the Items in Source Pallet screen
2 | Singles Packing - For picked Single line Single Quantity Wave | 2.01 | User will navigate Single Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created. |  |  | Cade | Pass
|  | 2.02 | User will be prompted to scan/enter a container (a Cart that was just picked into)
|  | 2.03 | User will then be prompted with a list of items that are in said container.
|  | 2.04 | Scan each item in container, hit Enter.
|  | 2.05 | After one item has been scanned, use one of the following methods to enter dimension information for the shipping box: Enter the dimensions of the box, Select the box from the Box list, or Scan a barcode for the box to populate the Carton Type field.
|  | 2.06 | Rateshop screen will be populated, user wil hit "No Change" to skip rateshop or "Rateshop" for rate shopping.
|  | 2.07 | If user hit "Rateshop", then rateshop carrier call will be made to UPS and list of rates will be ready for user to pick.
|  | 2.08 | User will be returned to the item list screen, finish scaning the items in the container and repeat 2.04 to 2.07
3 | Multi Packing - For picked Single line Multi Quantities Wave | 3.01 | User will navigate Multi Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created. |  |  | Cade |  | Was told UPS Missing or invalid ship to phone number..... this might be an issue as customers are not required to enter their phone number. For other companies, we do not have to provide a phone number for shipping purposes. Can we remove this setting?
|  | 3.02 | User will be prompted to scan/enter a container (a Cart that was just picked into)
|  | 3.03 | User will then be prompted with a list of items that are in said container.
|  | 3.04 | Scan each item in container, hit Enter.
|  | 3.05 | After one item has been scanned, user will be prompted to scan a list of items that belong to the same order
|  | 3.06 | After all item have been scanned, use one of the following methods to enter dimension information for the shipping box: Enter the dimensions of the box, Select the box from the Box list, or Scan a barcode for the box to populate the Carton Type field.
|  | 3.07 | Rateshop screen will be populated, user wil hit "No Change" to skip rateshop or "Rateshop" for rate shopping.
|  | 3.08 | If user hit "Rateshop", then rateshop carrier call will be made to UPS and list of rates will be ready for user to pick.
|  | 3.09 | User will be returned to the item list screen, finish scaning rest of the items in the cart (that belongs to other orders) and repeat 3.04 to 3.08
4 | Multi Packing - For picked Single line Multi Quantities Wave | 4.01 | User will navigate Batch Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created. |  |  | Cade |  | Phone number issue is happening for all orders. Not sure what to do to bypass this
|  | 4.02 | User will be prompted to scan/enter a container (a bin that was just picked into)
|  | 4.03 | User will then be prompted with a list of items that are in said container.
|  | 4.04 | Scan each item in container, hit Enter.
|  | 4.05 | After one item has been scanned, user will be prompted to enter quantity and go back to item list screen to keep scan rest of the items.
|  | 4.06 | After all item have been scanned, use one of the following methods to enter dimension information for the shipping box: Enter the dimensions of the box, Select the box from the Box list, or Scan a barcode for the box to populate the Carton Type field.
|  | 4.07 | Rateshop screen will be populated, user wil hit "No Change" to skip rateshop or "Rateshop" for rate shopping.
|  | 4.08 | If user hit "Rateshop", then rateshop carrier call will be made to UPS and list of rates will be ready for user to pick.
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Picking Edge Case Scenarios
1 | Singles Scan Picking - Scan wrong item | 1.01 | User will navigate Single Scan Picking under Outbound | Screen message will be displayed "The SKU [] could not be found. Please enter a valid SKU." |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 1.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 1.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 1.04 | Scan the SKU not the screen or doesn't exist.
|  | 1.05 | Enter quantity and hit enter.
2 | Singles Scan Picking - Enter more than needed | 2.01 | User will navigate Single Scan Picking under Outbound | Screen Message will be dislayed "The quantity that you entered [] is more than the quantity that is required []." |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 2.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 2.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 2.04 | Scan the SKU.
|  | 2.05 | Enter quantity that's more tha required and hit enter.
3 | Singles Scan Picking - Exception current pick task | 3.01 | User will navigate Single Scan Picking under Outbound | 1) Current task will be exceptioned, task state changed to "Exception" 2) Task related orderline will be "Back Ordered" 3) Task Related Stock Unit will be "On Hold" 4) Cycle Count task will be created with type of Picking Audit |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 3.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 3.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 3.04 | Hit "Exception".
|  | 3.05 | Select a exception code, then click "Exception".
4 | Singles Scan Picking - Pick current pick task partially then exception rest | 4.01 | User will navigate Single Scan Picking under Outbound | 1) Current task will be exceptioned, task state changed to "Complete" with Quantity to Pick as 0 and Quantity Picked as partially picked quantity 2) Task related orderline will be "Back Ordered" 3) Task Related Stock Unit will be "On Hold" 4) Cycle Count task will be created with type of Picking Audit |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 4.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 4.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 4.04 | Pick less than what's required, hit enter then hit "Exception".
|  | 4.05 | Select a exception code, then click "Exception".
5 | Singles Scan Picking - Suspend Pick Task | 5.01 | User will navigate Single Scan Picking under Outbound | 1) Current task will be de-prioritized 2) Next pick task will be displayed if any 3) Current will be displayed once all remaining tasks are done |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 5.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 5.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 5.04 | Hhit "Exception".
|  | 5.05 | Click "Suspend Pick Task".
6 | Singles Scan Picking - Suspend Work Group | 6.01 | User will navigate Single Scan Picking under Outbound | 1) Current task will be stopped 2) User will go back to wave entry screen 3) User will still be assigned in the same wave |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 6.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 6.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 6.04 | Hhit "Exception".
|  | 6.05 | Click "Suspend Work Group".
7 | Singles Scan Picking - Stop Work Group | 7.01 | User will navigate Single Scan Picking under Outbound | 1) Current task will be stopped 2) User will go back to wave entry screen 3) User will not be assigned in the same wave |  |  | Cade | Pass |  | Applies to Batch Picking as well
|  | 7.02 | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking container to be used, wave name starts with Single.
|  | 7.03 | User will be taken to picking screen(Location will be pre-populated) and scan SKU and enter quantity.
|  | 7.04 | Hhit "Exception".
|  | 7.05 | Click "Stop Work Group".
Test Case ID | Test Case Description | Process Steps | Step Details | Expected Result | Actual Result | Test Data | Owner | Status | GOWEST Notes | Deposco Notes
Packing Edge Case Scenarios
1 | Single Packing - Rateshop select a different rate | 1.01 | User will navigate Single Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping labels and Packing slips are printed and visible on Shipment Line. 4) Shipment record is created with the new shipping method. |  |  | Cade | Pass
|  | 1.02 | User will be prompted to scan/enter a container (a Cart that was just picked into)
|  | 1.03 | Scan each item in container, hit Enter.
|  | 1.04 | Enter dimension and choose rateshop.
|  | 1.05 | Select a different rate or shipping method than the current ship via.
2 | Batch Packing/Multi Packing - Pack Remainder | 2.01 | User will navigate Batch Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created. |  |  | Cade | Pass
|  | 2.02 | User will be prompted to scan/enter a container (a bin that was just picked into)
|  | 2.03 | User will then be prompted with a list of items that are in said container.
|  | 2.04 | Instead of scanning each item, do click "Pack Ramainder".
|  | 2.05 | User will be immidately direct to dimension entry screen and pack out the order.
3 | Batch Packing/Multi Packing - Start New Bin | 3.01 | User will navigate Batch Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping labels and Packing slips are printed and visible on Shipment Line. 4) Shipment record is created. 5) Multiple container hist will be created, order will be shipped in seperate boxes. |  |  | Cade
|  | 3.02 | User will be prompted to scan/enter a container (a bin that was just picked into)
|  | 3.03 | User will scan part of the order then click "New Bin".
|  | 3.04 | User will be immidately direct to dimension entry screen and pack out part of the order that was scanned.
|  | 3.05 | Once the part of the order was packed out, user will be directly back to item list screen to finish packing rest part of the order.
4 | Batch Packing/Multi Packing/Single Packing - Select a different Shipping method during rateshop | 4.01 | User will navigate Batch Packing under Outbound | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping labels and Packing slips are printed and visible on Shipment Line. 4) Shipment record is created with the new shipping method. |  |  | Cade | Pass
|  | 4.02 | User will be prompted to scan/enter a container (a bin that was just picked into)
|  | 4.03 | Scan each item in container, hit Enter.
|  | 4.04 | Enter dimension and choose rateshop.
|  | 4.05 | Select a different rate or shipping method than the current ship via.
Cade

## Testing Issue Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
CATEGORY | DESCRIPTION | TYPE | REPORTER | STATUS | OWNER | SEVERITY | ASSIGNED CONTACT | CREATED DATE | COMPLETION DATE | UPDATES | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16
Outbound | Update MO packing slip's expiration date and ship date logic to match generic packing slip | Request |  | Closed | DEP | High | Sam | 2025-02-03
Outbound | Update VA packing slip's expiration date and ship date logic to match generic packing slip | Request |  | Closed | DEP | High | Sam | 2025-02-03
Rx Outbound | Add RX label print once rule | Task |  | Closed | DEP | High | Sam | 2025-02-03 |  | Item Categories good - Change pushed to print at itemTrackingCapture to solve multi prints and ensure correct lots/exp captured - caused unintended issues in other processes so reverted - reassess among team.
Outbound | CB to correct this order’s CA6 | Task |  | Closed | ALLI | High |  | 2025-02-03
Outbound | Remove Price Column from PackSlips | Task |  | Closed | DEP | Low | Sam | 2025-02-03
Rx Outbound | RX Label item barcode not scannable - Packing and QC | Issue | Josephine | In Progress | ALLI | High | Danny/John | 2025-02-03 |  | Needs to be enlarged for printer resolution or scanners with higher resolution. GOWEST to look for resolution similar to honeywell.
Outbound | Add 10x10 and 12x12 carton sizes during packing | Task | Ani | Closed | ALLI | Low | Matt | 2025-02-03
Hardware / Physical | Autoscale Not sending weight to pack screen | Issue | Michelle | Closed | ALLI | Medium |  | 2025-02-03
Outbound | Easier way to Reprint Packing Slip | Request |  | Closed | DEP | Low | Sam/Josephine | 2025-02-03 |  | Added containerHistId to orderLine view. Slightly better, need something scannable.
Rx Outbound | Reprint Rx Label process - Need better access to orderId, scan should be for UPC not itemNumber | Task | Sam | Hold | DEP/ALLI | Medium | Josephine | 2025-02-03 |  | Now done by rxNumber and itemNumber. Seems to be much better. Master data required to complete - putting on hold
Rx Outbound | Validate expiration date logic for RX label | Request | Josephine | Closed | DEP | Medium | Sam | 2025-02-03 |  | Revised label query and rules to ensure pulling from matching rxNumber and stock allocation.
Rx Outbound | 1 RX order with multiple pets - display the correct information | Issue | Josephine | Closed | ALLI | Critical | Quan/Ani/Jawad | 2025-02-03 |  | Revised as part of rxLabel changes. Label now printing off of orderNumber, itemNumber, and rxNumber to ensure consistency Incorrect update - investigate orders with duplicated lines and if this is still happening
Rx Outbound | Need different markings per facility for Rx - Determine which fields can be used to pull in this data from CB | Request |  | Closed | ALLI | High | Cyrus/Jawad | 2025-02-03 |  | Cyrus - 2025-02-10: The following can be found part of Master Item data as CustomFields: Markings_MI Markings_LAS Markings_IND Josephine - 2/10: Deployed and monitored working correctly.
Outbound | Add screen message to display order source (brand) at Packing | Request | Michelle | Closed | DEP | Low | Quan | 2025-02-04
Integrations | Map Shipium's response payload carrierLabelPrice to shipment.TotalCost - need ticket Addtional Shipping call response mapping: - carrier - carrierServiceName - carrierServiceMethodId - serviceMethodName | Request | Cyrus | In Progress | DEP | Medium | Quan | 2025-02-04 |  | Being used for reporting purposes. Deposco to create a mapping ticket Ticket Created by Quan 02/14
Hardware / Physical | Printer assignments need to be fixed across the board | Issue | Ani | Closed | ALLI | High |  | 2025-02-04 |  | I've had to correct resources across Vegas so the user can use multiple printers as is necessary. Resources are labeled as printers which is very confusing.
Outbound | SO-5263903 should've been backordered because there wasn't enough stock available. However, it was waved and allowed users to pick. User then exceptioned before putting the order on backorder. | Issue | Danny | Closed | DEP | Low |  | 2025-02-04 |  | Only one order observed, need to investigate BnR logs to determine how this was allocated and released with short qty at facility
Integrations | Military addresses erroring out in MAIN - SO-5263903, DocStore ID 2069 | Issue | Josephine | Closed | ALLI | High | Josephine/Cyrus | 2025-02-04 |  | Review order data compared to USPS rule config, is it compliant or needs revision? Rule issue or order data issue? 2/4 JG: Need to talk to Indicia representative. This is a USPS error. An indicia company name must be configured by USPS for manifestMID 901614629 in order to create a shipping label. Please contact your postal representative.
Shipium | DocStore ID - 1581 - 400 error- TSO-0151092 | Issue | Ani | Closed | DEP | High | Ani | 2025-02-04 |  | JG: spring branch postal code is 78070.
Outbound | When orderHeader.shipToLine2 == "unknown", then set as "" | Request | Josephine | Closed | DEP | Low | Henry | 2025-02-04 |  | Automation configured and tested in UA - ported to prod and monitoring. All unshipped orders with 'unknown' value have been cleaned up.
Master Data | CB to correct item weight master data. Item's weight is overestimated in the master data, thus throwing error during packing due to the actual weight being lighter than the master data's weight. - e.g. MAIN - AS-6398673, item 28599-2, DS ID:2414 INDY - SO-5266137 - DocStore 2456 - Item 52383 - weight 0.3 INDY - SO-5266474 - DocStore 2507 - Item 49813 - weight 0.25 INDY - SO-5266282 - DocStore 2551 - Item 52383 - weight 0.3 INDY - SO-5265664 - Doc Store 2652 - Item 27135-2 - weight 0.25 |  | Josephine | Closed | ALLI | Medium | Cyrus/Danny | 2025-02-05 |  | 2/5 JG - Deployed in UA - waiting for Cyrus/Shipium to confirm changes Soft pushed to Prod - will turn on once confirmed by Cyrus/Shipium Cyrus - 2025-02-10: The payload looks good to me. Please consult Shipium if errors are still being encountered.
Outbound | Handcount location sequence not working as expected | Issue | Danny/Matt/Quan | Closed | ALLI | High | Quan | 2025-02-05 |  | 2/13: Should be updated over 2/15 weekend Should now grouped by item Sequence to be changed by Danny/Matt
Inbound | Refine putaway logic to display OS location that has inventory and sort by location sequence | Request | Rebecca | Closed | ALLI | Medium | Quan | 2025-02-05
Outbound | Discuss Order Release Profile for Rx HandCount - Currently strict FEFO, request is to not split picks from different stockUnits. Need to assess. | Request | Quan | Closed | ALLI | High | Josephine | 2025-02-05 |  | Logic needs to be if fill with one complete one, then fill that. Need to discuss further. John to discuss with pharm. to determine what's needed.
| CB to call receptline API to update received PO | Question | Craig | Closed | ALLI | High | Cryus/Quan/Danny | 2025-02-06 |  | Validated by Criag
Master Data | Clean up Miami locations and INDY OTC A/B location pick sequence values - currenly pickers are having to go back and forth between lettered sections | Issue | Henry | Closed | ALLI | Medium |  | 2025-02-06 |  | Closing because duplicate
Outbound | SO5265643 - exception suspended task issue | Request |  | Closed | ALLI | Medium |  | 2025-02-06
Outbound | CA3 - AS-6463997 Cold order mapped businessDaysOfTransit (CA3) to 5, so shipment goes through Fedex Ground, DSID 4570. When changed to 2, it ships the correct way. CB needs to change CA3 to 2 | Issue |  | Closed | ALLI | High |  | 2025-02-06 |  | Jawad created CB ticket. GOWEST is working as expected, to be pushed for other brands and validated Cyus - 2025-02-10: Confirmed by Daniel
Outbound | Rx label split - expiration date issue | Issue | Josephine | Closed | DEP | High |  | 2025-02-06
Outbound | Potential duplicate order lines EX. SO-5265573, SO-5265902 | Issue | Quan | Closed | ALLI | Critical |  | 2025-02-06
Integrations | Ensure tracking numbers are being transmitted to CB - CS is frequently reach out to michelle for these missing records | Task | Henry/Michelle | Closed | ALLI | Medium |  | 2025-02-07 |  | Cyurs - 2025-02-10: Jawad to help get example or screenshots
Integrations | Item categories refinement, need to distinguish RX Line and RX handcount items - Currently printing one copy | Task | Quan | In Progress | ALLI | High |  | 2025-02-07 |  | Need categorize handcount for Parata - Jawad to create a ticket. Cyurs - 2025-02-10: Jawad/Ops to share more details in the tickets for the development to start 2/14: Change is complete, but some updates needed. handcount_C
Outbound | Hazard - Limited qty orders not hitting the correct carrier call, order AS-6436371, DSID 6882 | Issue | Josephine | Closed | DEP | Medium |  | 2025-02-07
Outbound | Add Item Description on Carton consolidation | Request | Quan | Validation | ALLI | Medium | Quan | 2025-02-07
Inbound | Add item long desc to ReceiveItemConfigScreen list box | Request |  | Open | DEP | Low |  | 2025-02-07
Outbound | Create new handheld button for heavy packing - tie new packing slip grouped by CH through rules | Request | Josephine | Open | DEP | Low |  | 2025-02-07
Outbound | Work through backorders - Danny and Cyrus to re-run the data tonight and rerun these orders | Task | John | Closed | ALLI | High | Danny | 2025-02-10
Integrations | Hard code Fedex Ground shipment method for limited quantity | Request | Cyrus | Closed | ALLI | High | Josephine | 2025-02-10 |  | Josephine - 2/11: Running into "Could not find a carrier to fulfill the request: ups-2nd-day-air-service-method is not in the allow list: [fedex-ground-service-method] shipmentId: 7a94400d-cc47-4624-a4fc-e7a4873a1307"
Reporting | Meeting to review reporting setup - Example reports needed: Average pick rate by zone widget; Average pick rate per hour widget; Average pick rate per day widget; Average pack rate by zone widget; Average pack rate per hour widget; Average pack rate per day widget | Discussion |  | Open | DEP | Low
Outbound | When shipping a Virginia order, it is printing 2 packing slips. The normal one, and the Virginia Packing List. Packing slip only has one item, not all items listed. Can we make sure that it only prints the Virginia Packing List? | Issue | Danny | Validation | DEP | Medium | Quan |  |  | Quan - Fixed 2/27
Reporting | In the report building, I can't add any of the API fields like CA5, CA6, and CA7. Can you add those so they can be available when I am building reports. | Request | John | Open | DEP | Medium | Ani
Reporting | Create an Executive Dashboard. The dashboard everyone keeps using, keeps getting changed, so John is wasting his time on what changes I make to it. Here's what I want to see in the dashboard to start with Shipments today by facility Open ( not shipped) order count available by facility, ideally with a filter by Order Source Open Order count by Order created date, so we can see how old our orders are. I'm sure you have something like this out of the box Daily/Weekly Packing Performance Daily/Weekly Shipping Performance Daily/Weekly Receiving Performance Shipments and rate by facility - Today | Request |  | Open | DEP | Low
Shipium | I saw a note from Samantha at Shipium, saying there was something wrong with the Hazardous shipping label call. Was that fixed? | Issue |  | Closed | DEP | Low
Outbound | At the end of the day, we are leaving too many orders waved. Is there an easy way to push all waved orders, that have not started being processed, to be pushed back to new? | Question |  | Closed | DEP | Low |  |  |  | You can undo release for the individual waves. Order goes to new status once wave undone.

## GoNo-Go Decision
Go/No-Go Decision
FACTORS | DETAILS | WEIGHT | CRITICAL? | OWNER | % COMPLETE | SCORE | ANALYSIS | DUE DATE | COMMENT | CLIENT TEAM TESTED | DEP TEAM TESTED
| Deposco Setup | 80 |  |  |  | 70
Deposco Setup | Printer Details | 10 |  | Client | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | Client | 100% | 10 | Are all printers staions/resources set up with the appropriate printers? |  |  | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | Client | 100% | 10 | Are all printer assignments set up on the appropriate printers (shipping label, packing slip, customs docs, item label, LPN label)? |  |  | FALSE | FALSE
Deposco Setup | APP on RF Scanners/Handheld Devices | 10 |  | Client | 100% | 10 | Are all handheld units configured? Are all of the handhelds working correctly? |  |  | FALSE | FALSE
Deposco Setup | Label Printers | 10 | Y | Client | 0% | 0 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 |  | Client | 100% | 10 | Are the report documents configured to print on the proper printers? Are some reports configured with device overrides (e.g. processing area printers). |  |  | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | Deposco | 100% | 10 | Have all High and Critical issues from the issues list been resolved? |  |  | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Order Release - Cycle Count | 10 |  | Deposco | 100% | 10 | Backups, day, month end jobs. All jobs have been scheduled. Order Pull, Item Pull, Inventory Sync, Cycle Counts, Replenishments, Waving |  |  | FALSE | FALSE
| Warehouse Prep | 40 |  |  |  | 40
Warehouse Prep | Location Labels | 10 |  | Client | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 10 |  | Client | 100% | 10 | Procure Carts for moving of inventory |  |  | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 10 |  | Client | 100% | 10 | Item inventory barcoded and labeled to scan |  |  | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 |  | Client | 100% | 10 | Is the connectivity strong and cover all necessary scan areas? |  |  | FALSE | FALSE
| Standard Operating Procedure Documentation | 80 |  |  |  | 80
Standard Operating Procedures | Receiving | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Putaway | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Inventory Moves | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Inventory Adjustment | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Waving | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Picking | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Packing | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
| Training & Testing | 140 |  |  |  | 112.5
Training & Testing | Business Scenarios Definition | 10 |  | Client | 100% | 10 | Define all Business scenario including exception processes Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Process Training and Volumn Testing - Receiving - Putaway - Inventory Move - Inventory Adjustment - Cycle Counting - Waving - Picking - Packing - Shipping | 50 | Y | Client | 85% | 42.5 | Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Super-user Testing & Training | 40 | Y | Client | 80% | 32 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | End-user Training | 40 | Y | Client | 70% | 28 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
| Configurations/Master Data | 80 |  |  |  | 58
Configurations | Items - Shopify | 10 |  | Client | 90% | 9 |  |  |  | FALSE | FALSE
Configurations | Packs (UOMs) - Shopify | 10 |  | Client | 90% | 9 | Are all items setup? Are all of the units of measure defined for each item? |  |  | FALSE | FALSE
Configurations | Zones - Data Exchange | 10 |  | Client | 100% | 10 | Have all of the Zone and Zone Location records been set up? Has the pick flow been tested? |  |  | FALSE | FALSE
Configurations | Locations - Data Exchange | 10 |  | Client | 100% | 10 | Are the location types, zones, and location masters configured accurately. |  |  | FALSE | FALSE
Configurations | Item Update - Data Exchange | 10 | Y | Client | 0% | 0 | Have the appropriate menu levels been created for the different departments? |  |  | FALSE | FALSE
Configurations | Stock Unit - Data Exchange | 10 | Y | Client | 0% | 0 | Have the appropriate menu levels been created for the different departments? |  |  | FALSE | FALSE
Configurations | Carton Type - Data Exchange | 10 |  | Client | 100% | 10 | Have all valid pack types been entered into the system? |  |  | FALSE | FALSE
Configurations | Containers - Data Exchange | 10 |  | Client | 100% | 10 | Pallets, bins, carts |  |  | FALSE | FALSE
| Cutover and Conversion Plans | 10 |  |  |  | 10
Cutover and Conversion Plans | Cutover plan developed | 10 |  | Deposco | 100% | 10 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  |  | FALSE | FALSE
| Integrations | 50 |  |  |  | 50
Integrations with Deposco | Shopify | 30 |  | Deposco | 100% | 30 |  |  |  | FALSE | FALSE
Integrations with Deposco | UPS | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Loop | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
| Reports and Labeling | 20 |  |  |  | 30
Reports and Labeling | Shipping Label | 20 |  | Deposco | 100% | 20 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Reports and Labeling | Packing Slip | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | Deposco Client | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? |  |  | FALSE | FALSE
| Total Weighted Score: | 460.5
| Total Possible Score: | 510
| Total Percentage: | 90.29%
| Go Live Recommendation: | Yes | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Go-Live Readiness Plan
Go Live Readiness Plan
Phase | ID | System | Area Owner | Assigned | Status | Process | Task Description | Initial ETA | Created | Target | Finish | Go Live REQUIRED | Comments
Build |  |  | DEP |  | Completed | Environment | Deposco Stand up PROD enviornment |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | Completed | Environment | Check configuration migration, SI, BR, Inbound Mapping |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | Completed | Environment | Check Channel Xref, Cross references, Channel Look Up |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | Completed | Environment | Check JIRA Ticket if need back port to Prod |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Environment | Set up Shopify Prod Account with accurate Data |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Environment | Set up Loop Prod Account with accurate Data |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Environment | Set up UPS Prod Account with accurate Data |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | Completed | Integration | Connect DEP PROD with Shopify Prod |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | Completed | Integration | Connect DEP PROD with Loop Prod |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | In Progress | Integration | Connect DEP PROD with UPS Prod |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Device Config | Printers set up (pdf printer, shipping label printer) & resource assigments |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Device Config | Deposco downloaded on handheld devices |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Device Config | End users set up and logged into handhelds |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Build |  |  | DEP |  | In Progress | Scheduler | Check scheduler frequencies finalized |  | 2025-08-04 |  |  | Go Live REQUIRED
Build |  |  | GOWEST |  |  | Reports/Labels | Check all Labels Printed and finalized |  | 2025-08-04 |  |  | Go Live REQUIRED
Build |  |  | GOWEST |  |  | Access | Permission finalized & created |  | 2025-08-04 |  |  | Go Live REQUIRED
Build |  |  | GOWEST |  | Completed | Process | Create business SOP documentation for Deposco users |  | 2025-08-04 |  |  | Go Live REQUIRED
Data |  |  | GOWEST |  |  | Master Data | Master Data Set up | 01/19-01/21 | 2025-08-04 |  |  | Go Live REQUIRED
Data |  |  | DEP |  | Completed | Master Data | Shopify Items Pull |  | 2025-08-04 | 2025-08-06 |  | Go Live REQUIRED
Data |  |  | GOWEST |  | Open | Master Data | Item Update import - Safety stock and re-order point |  | 2025-08-04 |  |  | Go Live REQUIRED
Data |  |  | GOWEST |  | Completed | Master Data | Supplier import |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Data |  |  | GOWEST |  | Completed | Master Data | Zones Import |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Data |  |  | GOWEST |  | In Progress | Master Data | Locations w Pick Sequence Import |  | 2025-08-04 | 2025-08-06 |  | Go Live REQUIRED
Data |  |  | GOWEST |  | Completed | Master Data | Container Import |  | 2025-08-04 | 2025-08-06 |  | Go Live REQUIRED
Data |  |  | GOWEST |  | Completed | Master Data | Carton Type Import |  | 2025-08-04 | 2025-08-05 |  | Go Live REQUIRED
Data |  |  | GOWEST |  |  | Transactional Data | Stock Unit Import |  | 2025-08-04 | 2025-08-10 |  | Go Live REQUIRED
Data |  |  | GOWEST |  |  | Transactional Data | Prepare smoke testing data |  | 2025-08-04 | 2025-08-11 |  | Go Live REQUIRED
Data |  |  | GOWEST |  |  | Transactional Data | Transactional Data Set Up - PO |  | 2025-08-04 | 2025-08-11 |  | Go Live REQUIRED
Data |  |  | GOWEST |  |  | Transactional Data | Transactional Data Set Up - SO |  | 2025-08-04 | 2025-08-11 |  | Go Live REQUIRED
WMS E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inbound | Smoke Test Inbound Process |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inbound | 1. Receiving PO |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inbound | 2. Receiving RMA |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inbound | 3. Putaway |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inbound | 4. Print Label |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inventory | Smoke Test Inventory Process |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inventory | 1. Inventory Adjustmet |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inventory | 2. Inventory Move |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inventory | 3. Cycle Count |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Inventory | 4. Warehouse Lookup |  | 2025-08-04 |  |  | Go Live REQUIRED
E2E Smoke Testing | [11 empty] | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | Smoke Test Outbound Process |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 1. Waving |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 2. Singles Picking |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 3. Multis Picking |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 4. Singles Packing |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 5. Multis Packing |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 6. Batch Picking |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 7. Batch Packing |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 8. Shipping Label Printing |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Outbound | 9. Packing Slip Printing |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Smoke Testing | [11 empty] | UAT REQUIRED
UPS E2E Smoke Testing |  |  | DEP&GOWEST |  |  | Shipping Carrier | Smoke Test Shipping Carrier |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Testing |  |  | DEP&GOWEST |  |  | UPS | UPS Shipping Label |  | 2025-08-04
E2E Testing |  |  | DEP&GOWEST |  |  | UPS | UPS Rateshop |  |  |  |  | UAT REQUIRED
Shopify E2E |  |  | DEP&GOWEST |  |  | Integration | Smoke Test Shopify |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Testing |  |  | DEP&GOWEST |  |  | Shopify | Order Pull |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Testing |  |  | DEP&GOWEST |  |  | Shopify | Shipnotice |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Testing |  |  | DEP&GOWEST |  |  | Shopify | Inventory Sync |  |  |  |  | UAT REQUIRED
Loop E2E |  |  | DEP&GOWEST |  |  | Integration | Smoke Test Loop |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Testing |  |  | DEP&GOWEST |  |  | Loop | RMA Pull |  | 2025-08-04 |  |  | UAT REQUIRED
E2E Testing |  |  | DEP&GOWEST |  |  | Loop | RMA Receipt Notice |  |  |  |  | UAT REQUIRED

## Go-Live Cutover Plan
Cutover Date | Tasks Activities | Area Owner | Status | Owner | Notes
2025-08-04 | Go or no Go Call | DEP&GOWEST
2025-08-08 | Labeling Warehouse | GOWEST
2025-08-08 | Volume testing | GOWEST
2025-08-08 | End User Training | GOWEST
2025-08-04 | Code Freeze and Stand Up Production | DEP
2025-08-05 | Shopify Master Data Cutover | GOWEST
2025-08-08 | Hardware equipment ready and connected to Deposco (printers, RF devices) | GOWEST
2025-08-05 | Item Master Data pull into Deposco | DEP
2025-08-06 | Master Data Load to Deposco (Location, Zone, Container, Carton Type, Suppliers) | GOWEST
NA | Physical count |  |  |  | NA
8/7/2025-8/8/2025 | Smoke Testing | DEP&GOWEST
2025-08-11 | Inventory Data Load to Deposco | GOWEST
2025-08-11 | Shopify Tansactional data Cutover | DEP
2025-08-11 | Go Live | DEP&GOWEST
2025-08-29 | Post Go Live Support | DEP

## Go-Live Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
CATEGORY | DESCRIPTION | TYPE | REPORTER | STATUS | OWNER | SEVERITY | ASSIGNED CONTACT | CREATED DATE | COMPLETION DATE | UPDATES | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16
Outbound | Update MO packing slip's expiration date and ship date logic to match generic packing slip | Request |  | Closed | DEP | High | Sam | 2025-02-03
Outbound | Update VA packing slip's expiration date and ship date logic to match generic packing slip | Request |  | Closed | DEP | High | Sam | 2025-02-03
Rx Outbound | Add RX label print once rule | Task |  | Closed | DEP | High | Sam | 2025-02-03 |  | Item Categories good - Change pushed to print at itemTrackingCapture to solve multi prints and ensure correct lots/exp captured - caused unintended issues in other processes so reverted - reassess among team.
Outbound | CB to correct this order’s CA6 | Task |  | Closed | ALLI | High |  | 2025-02-03
Outbound | Remove Price Column from PackSlips | Task |  | Closed | DEP | Low | Sam | 2025-02-03
Rx Outbound | RX Label item barcode not scannable - Packing and QC | Issue | Josephine | In Progress | ALLI | High | Danny/John | 2025-02-03 |  | Needs to be enlarged for printer resolution or scanners with higher resolution. GOWEST to look for resolution similar to honeywell.
Outbound | Add 10x10 and 12x12 carton sizes during packing | Task | Ani | Closed | ALLI | Low | Matt | 2025-02-03
Hardware / Physical | Autoscale Not sending weight to pack screen | Issue | Michelle | Closed | ALLI | Medium |  | 2025-02-03
Outbound | Easier way to Reprint Packing Slip | Request |  | Closed | DEP | Low | Sam/Josephine | 2025-02-03 |  | Added containerHistId to orderLine view. Slightly better, need something scannable.
Rx Outbound | Reprint Rx Label process - Need better access to orderId, scan should be for UPC not itemNumber | Task | Sam | Hold | DEP/ALLI | Medium | Josephine | 2025-02-03 |  | Now done by rxNumber and itemNumber. Seems to be much better. Master data required to complete - putting on hold
Rx Outbound | Validate expiration date logic for RX label | Request | Josephine | Closed | DEP | Medium | Sam | 2025-02-03 |  | Revised label query and rules to ensure pulling from matching rxNumber and stock allocation.
Rx Outbound | 1 RX order with multiple pets - display the correct information | Issue | Josephine | Closed | ALLI | Critical | Quan/Ani/Jawad | 2025-02-03 |  | Revised as part of rxLabel changes. Label now printing off of orderNumber, itemNumber, and rxNumber to ensure consistency Incorrect update - investigate orders with duplicated lines and if this is still happening
Rx Outbound | Need different markings per facility for Rx - Determine which fields can be used to pull in this data from CB | Request |  | Closed | ALLI | High | Cyrus/Jawad | 2025-02-03 |  | Cyrus - 2025-02-10: The following can be found part of Master Item data as CustomFields: Markings_MI Markings_LAS Markings_IND Josephine - 2/10: Deployed and monitored working correctly.
Outbound | Add screen message to display order source (brand) at Packing | Request | Michelle | Closed | DEP | Low | Quan | 2025-02-04
Integrations | Map Shipium's response payload carrierLabelPrice to shipment.TotalCost - need ticket Addtional Shipping call response mapping: - carrier - carrierServiceName - carrierServiceMethodId - serviceMethodName | Request | Cyrus | In Progress | DEP | Medium | Quan | 2025-02-04 |  | Being used for reporting purposes. Deposco to create a mapping ticket Ticket Created by Quan 02/14
Hardware / Physical | Printer assignments need to be fixed across the board | Issue | Ani | Closed | ALLI | High |  | 2025-02-04 |  | I've had to correct resources across Vegas so the user can use multiple printers as is necessary. Resources are labeled as printers which is very confusing.
Outbound | SO-5263903 should've been backordered because there wasn't enough stock available. However, it was waved and allowed users to pick. User then exceptioned before putting the order on backorder. | Issue | Danny | Closed | DEP | Low |  | 2025-02-04 |  | Only one order observed, need to investigate BnR logs to determine how this was allocated and released with short qty at facility
Integrations | Military addresses erroring out in MAIN - SO-5263903, DocStore ID 2069 | Issue | Josephine | Closed | ALLI | High | Josephine/Cyrus | 2025-02-04 |  | Review order data compared to USPS rule config, is it compliant or needs revision? Rule issue or order data issue? 2/4 JG: Need to talk to Indicia representative. This is a USPS error. An indicia company name must be configured by USPS for manifestMID 901614629 in order to create a shipping label. Please contact your postal representative.
Shipium | DocStore ID - 1581 - 400 error- TSO-0151092 | Issue | Ani | Closed | DEP | High | Ani | 2025-02-04 |  | JG: spring branch postal code is 78070.
Outbound | When orderHeader.shipToLine2 == "unknown", then set as "" | Request | Josephine | Closed | DEP | Low | Henry | 2025-02-04 |  | Automation configured and tested in UA - ported to prod and monitoring. All unshipped orders with 'unknown' value have been cleaned up.
Master Data | CB to correct item weight master data. Item's weight is overestimated in the master data, thus throwing error during packing due to the actual weight being lighter than the master data's weight. - e.g. MAIN - AS-6398673, item 28599-2, DS ID:2414 INDY - SO-5266137 - DocStore 2456 - Item 52383 - weight 0.3 INDY - SO-5266474 - DocStore 2507 - Item 49813 - weight 0.25 INDY - SO-5266282 - DocStore 2551 - Item 52383 - weight 0.3 INDY - SO-5265664 - Doc Store 2652 - Item 27135-2 - weight 0.25 |  | Josephine | Closed | ALLI | Medium | Cyrus/Danny | 2025-02-05 |  | 2/5 JG - Deployed in UA - waiting for Cyrus/Shipium to confirm changes Soft pushed to Prod - will turn on once confirmed by Cyrus/Shipium Cyrus - 2025-02-10: The payload looks good to me. Please consult Shipium if errors are still being encountered.
Outbound | Handcount location sequence not working as expected | Issue | Danny/Matt/Quan | Closed | ALLI | High | Quan | 2025-02-05 |  | 2/13: Should be updated over 2/15 weekend Should now grouped by item Sequence to be changed by Danny/Matt
Inbound | Refine putaway logic to display OS location that has inventory and sort by location sequence | Request | Rebecca | Closed | ALLI | Medium | Quan | 2025-02-05
Outbound | Discuss Order Release Profile for Rx HandCount - Currently strict FEFO, request is to not split picks from different stockUnits. Need to assess. | Request | Quan | Closed | ALLI | High | Josephine | 2025-02-05 |  | Logic needs to be if fill with one complete one, then fill that. Need to discuss further. John to discuss with pharm. to determine what's needed.
| CB to call receptline API to update received PO | Question | Craig | Closed | ALLI | High | Cryus/Quan/Danny | 2025-02-06 |  | Validated by Criag
Master Data | Clean up Miami locations and INDY OTC A/B location pick sequence values - currenly pickers are having to go back and forth between lettered sections | Issue | Henry | Closed | ALLI | Medium |  | 2025-02-06 |  | Closing because duplicate
Outbound | SO5265643 - exception suspended task issue | Request |  | Closed | ALLI | Medium |  | 2025-02-06
Outbound | CA3 - AS-6463997 Cold order mapped businessDaysOfTransit (CA3) to 5, so shipment goes through Fedex Ground, DSID 4570. When changed to 2, it ships the correct way. CB needs to change CA3 to 2 | Issue |  | Closed | ALLI | High |  | 2025-02-06 |  | Jawad created CB ticket. GOWEST is working as expected, to be pushed for other brands and validated Cyus - 2025-02-10: Confirmed by Daniel
Outbound | Rx label split - expiration date issue | Issue | Josephine | Closed | DEP | High |  | 2025-02-06
Outbound | Potential duplicate order lines EX. SO-5265573, SO-5265902 | Issue | Quan | Closed | ALLI | Critical |  | 2025-02-06
Integrations | Ensure tracking numbers are being transmitted to CB - CS is frequently reach out to michelle for these missing records | Task | Henry/Michelle | Closed | ALLI | Medium |  | 2025-02-07 |  | Cyurs - 2025-02-10: Jawad to help get example or screenshots
Integrations | Item categories refinement, need to distinguish RX Line and RX handcount items - Currently printing one copy | Task | Quan | In Progress | ALLI | High |  | 2025-02-07 |  | Need categorize handcount for Parata - Jawad to create a ticket. Cyurs - 2025-02-10: Jawad/Ops to share more details in the tickets for the development to start 2/14: Change is complete, but some updates needed. handcount_C
Outbound | Hazard - Limited qty orders not hitting the correct carrier call, order AS-6436371, DSID 6882 | Issue | Josephine | Closed | DEP | Medium |  | 2025-02-07
Outbound | Add Item Description on Carton consolidation | Request | Quan | Validation | ALLI | Medium | Quan | 2025-02-07
Inbound | Add item long desc to ReceiveItemConfigScreen list box | Request |  | Open | DEP | Low |  | 2025-02-07
Outbound | Create new handheld button for heavy packing - tie new packing slip grouped by CH through rules | Request | Josephine | Open | DEP | Low |  | 2025-02-07
Outbound | Work through backorders - Danny and Cyrus to re-run the data tonight and rerun these orders | Task | John | Closed | ALLI | High | Danny | 2025-02-10
Integrations | Hard code Fedex Ground shipment method for limited quantity | Request | Cyrus | Closed | ALLI | High | Josephine | 2025-02-10 |  | Josephine - 2/11: Running into "Could not find a carrier to fulfill the request: ups-2nd-day-air-service-method is not in the allow list: [fedex-ground-service-method] shipmentId: 7a94400d-cc47-4624-a4fc-e7a4873a1307"
Reporting | Meeting to review reporting setup - Example reports needed: Average pick rate by zone widget; Average pick rate per hour widget; Average pick rate per day widget; Average pack rate by zone widget; Average pack rate per hour widget; Average pack rate per day widget | Discussion |  | Open | DEP | Low
Outbound | When shipping a Virginia order, it is printing 2 packing slips. The normal one, and the Virginia Packing List. Packing slip only has one item, not all items listed. Can we make sure that it only prints the Virginia Packing List? | Issue | Danny | Validation | DEP | Medium | Quan |  |  | Quan - Fixed 2/27
Reporting | In the report building, I can't add any of the API fields like CA5, CA6, and CA7. Can you add those so they can be available when I am building reports. | Request | John | Open | DEP | Medium | Ani
Reporting | Create an Executive Dashboard. The dashboard everyone keeps using, keeps getting changed, so John is wasting his time on what changes I make to it. Here's what I want to see in the dashboard to start with Shipments today by facility Open ( not shipped) order count available by facility, ideally with a filter by Order Source Open Order count by Order created date, so we can see how old our orders are. I'm sure you have something like this out of the box Daily/Weekly Packing Performance Daily/Weekly Shipping Performance Daily/Weekly Receiving Performance Shipments and rate by facility - Today | Request |  | Open | DEP | Low
Shipium | I saw a note from Samantha at Shipium, saying there was something wrong with the Hazardous shipping label call. Was that fixed? | Issue |  | Closed | DEP | Low
Outbound | At the end of the day, we are leaving too many orders waved. Is there an easy way to push all waved orders, that have not started being processed, to be pushed back to new? | Question |  | Closed | DEP | Low |  |  |  | You can undo release for the individual waves. Order goes to new status once wave undone.

## Phase 1 UAT Readiness Plan (hidden)
UAT Readiness Plan
Phase | ID | System | Area Owner | Assigned | Status | Process | Task Description | Initial ETA | Created | Target | Finish | UAT | Comments
Build | 1 | UAT | DEP | Ani | 100% | Environment | Deposco Stand up UA enviornment |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 2 | UAT | ALLI | ALLI | 100% | Integration | CB Stand Up CB Sandbox |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 3 | UAT | DEP | ALLI | 100% | Integration | Deposco connect CB Sandbox |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 4 | UAT | DEP | Josephine | 100% | Integration | Deposco connect Shipium |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 5 | UAT | ALLI | ALLI/DEP | 0% | Device Config | Printers set up (pdf printer, shipping label printer) & resource assigments |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 6 | UAT | ALLI | ALLI | 100% | Device Config | Deposco downloaded on handheld devices |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 7 | UAT | ALLI | ALLI | 100% | Device Config | End users set up and logged into handhelds |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 8 | UAT | DEP | ALLI/DEP | NA | Scheduler | Check scheduler frequencies finalized |  | 2024-12-23 | 2025-01-03 |  | Go Live REQUIRED
Build | 9 | UAT | ALLI | ALLI/DEP | NA | Reports/Labels | Check all Labels Printed and finalized |  | 2024-12-23 | 2025-01-03 |  | Go Live REQUIRED
Build | 10 | UAT | ALLI | ALLI | 100% | Access | Permission finalized & created |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 11 | UAT | DEP | ALLI | 100% | Process | Deposco Unit Test |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Build | 12 | UAT | ALLI | ALLI | 100% | Process | Create business SOP documentation for Deposco users |  | 2024-12-23 | 2025-01-03 |  | Go Live REQUIRED
Data | 13 | UAT | DEP/ALLI | ALLI | 100% | Master Data | Master Data Set up | 01/19-01/21 | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 14 | UAT | DEP/ALLI | ALLI | 100% | Master Data | Items Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 15 | UAT | DEP/ALLI | ALLI | 100% | Master Data | Kit Items import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 16 | UAT | DEP/ALLI | ALLI | 100% | Master Data | Kit header Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 17 | UAT | ALLI | ALLI | 100% | Master Data | Items Pack Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 18 | UAT | ALLI | ALLI | 100% | Master Data | Items UPC Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 19 | UAT | ALLI | ALLI | 100% | Master Data | Zones Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 20 | UAT | ALLI | ALLI | 100% | Master Data | Locations w Pick Sequence Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 21 | UAT | ALLI | ALLI | 100% | Master Data | Storage Details Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 22 | UAT | ALLI | ALLI | 100% | Master Data | Container Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 23 | UAT | ALLI | ALLI | 100% | Master Data | Carton Type Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 24 | UAT | ALLI | ALLI | 100% | Master Data | Item Components Import |  | 2024-12-23 | 2025-01-03 |  | UAT REQUIRED
Data | 25 | UAT | ALLI | ALLI | 100% | Transactional Data | Stock Unit Import |  | 2024-12-23 | 2025-01-06 |  | UAT REQUIRED
Data | 26 | UAT | ALLI | ALLI | 100% | Transactional Data | Transactional Data Set Up(PO, SO, RMA, OTO, ITO, WO, RTV) |  | 2024-12-23 | 2025-01-06 |  | UAT REQUIRED
WMS E2E Testing | 27 | UAT | ALLI | ALLI | 100% | Inbound | Test Inbound Receiving (PO RMA ITO) |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 28 | UAT | ALLI | ALLI | 100% | Inbound | PO Receiving |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 29 | UAT | ALLI | ALLI | 100% | Inbound | PO Receiving Edge Cases(Receive NDC, Lot, Expiration) |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 30 | UAT | ALLI | ALLI | 100% | Inbound | PO Receiving Direct Putaway |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 31 | UAT | ALLI | ALLI | 100% | Inbound | Return Receiving |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 32 | UAT | ALLI | ALLI | 100% | Inbound | Return Receiving Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 33 | UAT | ALLI | ALLI | 100% | Inbound | Return Receiving Direct Putaway |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 34 | UAT | ALLI | ALLI | 100% | Inbound | ITO Receiving |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 35 | UAT | ALLI | ALLI | 100% | Inbound | ITO Receiving Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 36 | UAT | ALLI | ALLI | 100% | Inbound | ITO Receiving Direct Putaway |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 37 | UAT | ALLI | ALLI | 100% | Inbound | Putaway Processes (Pallet, Stock, Item) |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 38 | UAT | ALLI | ALLI | 100% | Inbound | Singles Putaway Processes (Pallet, Stock, Item) Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 39 | UAT | ALLI | ALLI | 100% | Inbound | Multis Putaway Processes (Pallet, Stock, Item) Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 40 | UAT | ALLI | ALLI | 50% | Inbound | Print Item Label |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 41 | UAT | ALLI | ALLI | 100 | Inventory | Test Inventory Management Processes |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 42 | UAT | ALLI | ALLI | 100% | Inventory | Inventory Moves |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 43 | UAT | ALLI | ALLI | 100% | Inventory | Singles Inventory Moves Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 44 | UAT | ALLI | ALLI | 100% | Inventory | Multis Inventory Moves Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 45 | UAT | ALLI | ALLI | 100% | Inventory | Inventory Adjustments |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 46 | UAT | ALLI | ALLI | 100% | Inventory | Inventory Adjustments Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 47 | UAT | ALLI | ALLI | 100% | Inventory | Cycle Counts |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 48 | UAT | ALLI | ALLI | 100% | Inventory | Cycle Counts by item |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 49 | UAT | ALLI | ALLI | 100% | Inventory | Cycle Counts by location |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 50 | UAT | ALLI | ALLI | 100% | Inventory | Cycle Counts on demand |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 51 | UAT | ALLI | ALLI | 100% | Inventory | Cycle Counts Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 52 | UAT | ALLI | ALLI | 100% | Inventory | Cycle Counts Approvals |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 53 | UAT | ALLI | ALLI | - | Inventory | Physical Counts |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 54 | UAT | ALLI | ALLI | 100 | Inventory | Replenishment |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 55 | UAT | ALLI | ALLI | 100% | Inventory | Replenishment Edge Cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 56 | UAT | ALLI | ALLI | 100 | Inventory | Kit to Stock with Work Order |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 57 | UAT | ALLI | ALLI | 100 | Outbound | Test Outbound Management (SO RTV OTO) |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 58 | UAT | ALLI | ALLI | 100% | Outbound | Post SO to Deposco |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 59 | UAT | ALLI | ALLI | 100% | Outbound | Run POI againist the SO |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 60 | UAT | ALLI | ALLI | 100% | Outbound | Build and Release Wave on single SO |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 61 | UAT | ALLI | ALLI | 100% | Outbound | Build and Release Wave on Mutiple SOs |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 62 | UAT | ALLI | ALLI | 100% | Outbound | SO picking |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 63 | UAT | ALLI | ALLI | 100% | Outbound | SO picking with RX items (Lot and Expiration tracked) |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 64 | UAT | ALLI | ALLI | 100% | Outbound | SO picking Exception |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 65 | UAT | ALLI | ALLI | -% | Outbound | RX Label printing |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 66 | UAT | ALLI | ALLI | -% | Outbound | RX Putwall (Non Parata RX) |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 67 | UAT | ALLI | ALLI | 100% | Outbound | Quality Control |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 68 | UAT | ALLI | ALLI | 100% | Outbound | Quality Control edge cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 69 | UAT | ALLI | ALLI | 100% | Outbound | Carton Consolidation |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 70 | UAT | ALLI | ALLI | 100% | Outbound | SO Packing |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 71 | UAT | ALLI | ALLI | 100% | Outbound | SO Packing edge cases |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 72 | UAT | ALLI | ALLI | -% | Outbound | Cartonization Packing |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
E2E Testing | 73 | UAT | ALLI | ALLI | -% | Outbound | Simple Ship Parata related orders |  | 2024-12-23 | 2025-01-08 |  | UAT REQUIRED
Shipium E2E | 74 | UAT | ALLI | ALLI | 50 | Shipium | Shipium testing |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 75 | UAT | ALLI | ALLI | 50 | Shipium | Hazmat |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 76 | UAT | ALLI | ALLI | 50 | Shipium | Military Address |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 77 | UAT | ALLI | ALLI | 50 | Shipium | Residential and Saturday |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
CB E2E | 78 | UAT | ALLI | ALLI/DEP | 100 | CB Integration | Receipt line API |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 79 | UAT | ALLI | ALLI/DEP | 100% | CB Integration | Inventory API |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 80 | UAT | ALLI | ALLI/DEP | 50 | CB Integration | Shipnotice API (Shipment API) |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
E2E Testing | 81 | UAT | ALLI | ALLI/DEP | 50 | CB Integration | Other Search APIs |  | 2024-12-23 | 2025-01-09 |  | UAT REQUIRED
Volume | 82 | UAT | ALLI | ALLI | 0% | Inbound | Volume test Inbound Receiving |  | 2024-12-23 | 2025-01-24 |  | Volume and Training
Volume | 83 | UAT | ALLI | ALLI | 0% | Inventory | Volume test Inventory Management Processes |  | 2024-12-23 | 2025-01-24 |  | Volume and Training
Volume | 84 | UAT | ALLI | ALLI | 0% | Outbound | Volume test SO Fulfillment (Picking, Packing, Close Trip) |  | 2024-12-23 | 2025-01-24 |  | Volume and Training
Volume | 85 | UAT | ALLI | ALLI | 0% | Scheduler | Volume test Schedulers |  | 2024-12-23 | 2025-01-24 |  | Volume and Training
Volume | 86 | UAT | ALLI | ALLI | 0% | Scheduler | Volume test POI |  | 2024-12-23 | 2025-01-24 |  | Volume and Training
Volume | 87 | UAT | ALLI | ALLI | 0% | Scheduler | Volume test Waving |  | 2024-12-23 | 2025-01-24 |  | Volume and Training
Ops Report | 88 | UAT | DEP | ALLI/DEP | 0% | Report | Provide Deposco Dev Ops Report from Volume Test |  | 2024-12-23 | 2025-01-24 |  | Go Live REQUIRED
Ops Report | 89 | UAT | DEP | DEP |  | Report | Additional Ops report need to be built |  | 2024-12-23 | 2025-01-24 |  | Go Live REQUIRED

## Go Live Prep Plan (hidden)
Cutover Date | Tasks Activities | Area Owner | Owner | Notes
2025-01-23 | Go or no Go Call | ALLI&Deposco
2025-01-24 | Labeling Warehouse | ALLI | Matthew&Dani
2025-01-29 | Volume testing | ALLI
2025-01-24 | End User Training | ALLI
2025-01-24 | Code Freeze and Stand Up Production | Deposco | Quan/Jo/Ani
2025-01-27 | CB Master Data Cutover | ALLI
2025-01-31 | CB Transactional Data Cutover Review | ALLI
2025-01-28 | Hardware equipment ready and connected to Deposco (printers, RF devices) | ALLI
2025-01-28 | Item Master Data push to Deposco | ALLI
2025-01-29 | Master Data Load to Deposco (Location, Zone, Container, Carton Type, Storage Details) | ALLI
2025-01-31 | Smoke Testing | ALLI&Deposco
2025-02-01 | **Physical Inventory Count | ALLI
TBD | Inventory Data Load to Deposco | ALLI
2025-02-02 | CB Tansactional data Cutover | ALLI
2025-02-03 | Go Live | ALLI&Deposco
2025-02-07 | Post Go Live Support | ALLI&Deposco

## Pre-Cutover Activities (hidden)
PRE-CUTOVER ACTIVITIES
CLIENT PRE-CUTOVER STEPS
Purpose: Organize all tasks that are to be executed in preparation for deployment.
ITEM # | TEAM OWNER | ASSIGNED RESOURCE | % COMPLETE | TASK DESCRIPTION | INITIAL ETA | TARGET DATE | COMPLETION DATE | REQUIRED COMPLETION DATE | DEPENDENCIES | COMMENTS
CLIENT
1 | Client |  | 0% | Upload/Create all Locations to Deposco
2 | Client |  | 0% | Scanners at each workstation
3 | Client |  | 0% | Validate Pack Station laptops
4 | Client |  | 0% | Validate Scales
5 | Client |  | 0% | Set up pack stations
6 | Client |  | 0% | Set up printers (Print Client is setup, printers are on same device)
7 | Client |  | 0% | Set up wifi
8 | Client |  | 0% | Configure packstations as a resource and assign printers
9 | Client |  | 0% | Shipping Label - print out and validate
10 | Client |  | 0% | Packing Slip - print out and validate
11 | Client |  | 0% | End User Configuration
12 | Client |  | 0% | Continued Super User Training
13 | Client |  | 0% | User Training (Happy Path and Exception Scenarios)
14 | Client |  | 0% | Validate/Test integration schedulers for Deposco are working
15 | Client |  | 0% | Review Scheduler Frequencies
16 | Client |  | 0% | Review Waving Logic
17 | Client |  | 0% | Build SOP document for entire solution. Leave a relevant copy at each given area (packing sections for pack stations)
18 | Client |  | 0% | Validate all Locations in proper zones
19 | Client |  | 0% | Test with all set-up Printers
20 | Client |  | 0% | Repull product data into production
DEPOSCO
1 | DEP |  | 0% | Build system monitoring queries
2 | DEP |  | 0% | Wipe out test orders
3 | DEP |  | 0% | Review each packstation is configured as a resource
4 | DEP |  | 0% | Validate all master data has been configured
5 | DEP |  | 0% | Review Waving Logic
6 | DEP |  | 0% | Purge Transactional Data
7 | DEP |  | 0% | Validate all schedulers are enabled for production environment
8 | DEP |  | 0% | Validate all Integration changes needed are in production environment
9 | DevOps |  | 0% | Build Production environment
10 | DevOps |  | 0% | Add socket credientals to Production environment
11 | DEP |  | 0% | Wipe product data

## Cutover Activities (hidden)
CUTOVER ACTIVITIES
CLIENT CUTOVER TASKS
CUTOVER DAY
ITEM # | TASK OWNER | ASSIGNED RESOURCE | STATUS | TASK DESCRIPTION | PLANNED COMPLETION DATE | ACTUAL FINISH DATE | DEPENDENCIES | COMMENTS
1 | Client |  | Open | Validate each pack station is setup to coresponding printers
2 | Client |  | Open | Upload inventory into Deposco
3 | Client |  | Open | Enable Sockets and Schedulers
4 | DEP |  | Open | Enable all socket endpoints in each direction
5 | DEP |  | Open | Enable Client endpoints
6 | Client |  | Open | Pull open Sales Orders into Deposco
7 | Client |  | Open | Create open Purchase Orders into Deposco
8 | Client |  | Open | Do and end to end smoke tests with some POs and SOs
9 | DEP |  | Open | Wipe out end to end test orders
10 | DEP |  | Open | Remove non-admin users from UA Environment

## Demo & Meeting Recordings
Recordings
DATE | TOPIC | LINK | PASSWORD | COMMENTS
2025-07-16 | Inbound&Inventory Recording | Recap: Go West Inbound&Inventory Demo July 16
2025-07-17 | Weekly Status Call | Recap: Gowest Weekly Status Call July 17
2025-07-17 | Outbound Demo Part1 | Recap: Gowest Outbound Demo July 17
2025-07-21 | Outbound Demo Part2 | Recap: Gowest Outbound demo Part 2 July 21
2025-07-25 | Loop Return Demo | Recap: GOWEST Testing Support July 25
2025-07-31 | Weekly Status Call | Recap: Gowest Weekly Status Call July 31
2025-08-07 | Go No Go Call | Recap: GOWEST Testing Support August 4

## UAT Tracker (hidden)
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
CATEGORY | DESCRIPTION | TYPE | STATUS | OWNER | SEVERITY | CONTACT | CREATION DATE | COMPLETION DATE | NOTES
Master Data | Facilities in Deposco have been named/renamed: Indiana is now called "INDY" and Las Vegas is now "LAS". Are those changed by Deposco and are they going to remain like these? | Question | Closed | DEP | Low |  | 2025-01-09
Master Data | Clarification on startActivityTime and endActivityTime for this call link. The goal here for us is to get all Inventory records that have been updated after (and equal) to a certain date, thus limiting the return. Share an example call using the above params. | Question | Closed | ALLI | Medium | Quan/Cyrus | 2025-01-09
Master Data | Enable search for the following (goal is to limit the records returned): 1. order (Sales Order) with createdDate, createdDateOp, updatedDate, updatedDateOp and currentStatus 2. order (Purchase Order) same as above. | Request | Closed | ALLI | High | Quan/Cyrus | 2025-01-09
Outbound | Shipment data response query: The response has two different shipVia values: Shipium and Shipium - Shipium, which one is the correct value to map to? Example shipment Id 52 and 39. | Question | Closed | ALLI | High | Josephine/Cyrus | 2025-08-12 |  | As of this on-site UAT, we will be using "Shipium" shipVia value.
Outbound | Shipment data is missing Shipium service method type selected. Can it be added in the response e.g. "usps-ground-advantage-service-method" | Request | Closed | DEP | High | Josephine/Cyrus | 2025-01-13 |  | Can you please clarify which field you want mapped? - "carrierServiceMethodId": "fedex-ground-service-method" or - "serviceMethodName": "GOWEST - FedEx Ground" Cyrus: The following: carrierServiceMethodId shipiumShipmentId labelUrl Cyrus: Has a separate email thread and additional issues highlighted are: 1. Missing dynamic tenantId and fulfillmentContext 2. APO/FPO customsInfo handling 3. Setting up and finalizing shipOption and/or businessDaysOfTransit Quan: No longer needed, confirmed with Cyrus 1/15/2025
Outbound | Some shipments has "nullnull" as trackingNumber. Should we skip those shipments even if they are mapped to the correct order? E.g. shipment Id: 41 | Issue | Closed | DEP | High | Quan/Cyrus | 2025-08-12
Master Data | Items. Missing item attributes, incomplete SKU push from CB. | Issue | Closed | ALLI | High | Josephine/Cyrus | 2025-01-13 |  | We are running into errors while updloading stock information because of missing items. Please make sure all SKUs are imported. We also saw a few items that are not marked as lot number enabled/expiration date enabled. These have to be labeled Cyrus: Can you share with us a list of SKUs you are getting the error for? When the issue with Lot/Expiration fields was highlighted the first time, we re-pushed all SKUs with the fix. All the SKUs should now be reflecting the settings we have in CB. So please, share SKU examples so we can check and open internal ticket. Thanks 01/22 - Cyrus: Filter information shared by Quan to identify these. GOWEST Ops has confirmed we should send all flags as true.
Master Data | Packs. Missing packs, incomplete pack push from CB. | Issue | Closed | ALLI | Critical | Josephine/Cyrus | 2025-01-13 |  | 01/23 - Cyrus - Matt opened an internal ticket and shared data on Dims/UPC to be updated in CB database
Inventory Management | Workorder creation. To determine whether to create from handheld or data exchange upload. | Discussion | Closed | DEP | Critical |  | 2025-01-13 | 2025-01-16 | To be completed via CSV upload
Hardware / Physical | Printer configuration | Discussion | Closed | ALLI | Blocker | Matt N | 2025-01-13 |  | 1/24/25 - 95% complete - Most printers set up in facilities 1/16/25 - Printers came in at noon. Working to complete setup/testing
Outbound | RX label verification with printers. | Task | In Progress | DEP/ALLI | Critical | Josephine/Matt/Danny | 2025-01-13 |  | Indy and Vegas still pending testing
Hardware / Physical | Shipping label verification with printers. | Task | Closed | ALLI | Critical | Josephine/Matt | 2025-01-13
Outbound | QC - add lot number and expiration date. | Request | Closed | ALLI | High | Ani | 2025-01-13 |  | GOWEST need to check and confirm
Outbound | QC - change "Pack" button to "QC" | Request | Closed | DEP | Low | Ani | 2025-01-13 |  | Within the process on the screen message - XML
Outbound | RX/OTC hold rule - move logic to the end of QC | Task | Validation | ALLI | High | Ani/Danny | 2025-01-13
Outbound | Picking - remove "stage" button from ItemEntryBinScreen | Request | Closed | ALLI | Medium |  | 2025-01-13
Outbound | Add "All Mix" test cases | Task | Closed | ALLI | High | Ani | 2025-01-13 |  | Requested change at end of December
Outbound | Complete "All Mix" test cases | Task | Validation | ALLI | Critical | Danny | 2025-01-13
Outbound | Data for fields seem to be mapped to incorrect entity (OrderHeader) in Deposco. If I open an SO in Deposco, I see fields like Pet Weight, Pet Name etc under Order Header (Header Info). As was highlighted in one of previous emails and mentioned in the mapping doc, these values needs to be at the OrderLine level. E.g. if an SO has multiple SKUs ordered for multiple pets, then how are the multiple Pet mapping is handled on the Order Header level in Deposco? | Issue | Closed | ALLI | Low | Ani | 2025-01-15 |  | Any fields marked (API) are custom fields. This is placed in order header for ease of configuration. Their values are still pulling directly from your mapping document, so there are no changes on this end. Cyrus: So if a new SO is pushed from CB GOWEST, and that SO has 5 medications/RX and are prescribed to 3 different pets. If the fields are being pulled to OrderHeader and we want to see all 3 pets get populated for each RX, how is it achieved in Deposco?
Reporting | Packing Slip adjustments - 8 trading partners - x20 states | Request | Pending SOW Signature | DEP | High | Josephine | 2025-01-15 |  | We have received notification of changes by four different states. On copy, I have sent the current mock-up along with the additions required by the state of Missouri. What we need, is to create additional templates of our packing slip with the changes in language necessary to be compliant in these states. On copy is Ani, our compliance director. She can add the language for the other three states, and Danny can fill you in on the details of how we can make this work.
Reporting | rx label adjustments - 8 trading partners - Not needed currently | Request | Closed | DEP | High | Josephine | 2025-01-15 |  | I know that we mapped out an RX label template. One thing we need to discuss is the label based on which brand we are fulfilling orders for. For example, an GOWEST order has the GOWEST name in the corner. On other brands, like Tractor supply, it would need to say Tractor supply RX. We need to make that corner label a dynamic field that changes based on what brand the order originates from. I can provide a list of what should be in that corner. Label is attached on copy for reference.
Reporting | UAT Reports List - Go-Live Critical & Prioritize remaining | Request | Pending SOW Signature | DEP | High | Matt N | 2025-01-15 |  | Blind PO and Blind Returns
Misc | Standard Operating Procedure Documentation | Task | Closed | ALLI | Critical |  | 2025-01-15
Reporting | Update location label - show locator |  | Closed | ALLI | Medium |  | 2025-01-15 |  | Yes, location labels show locators.
Integrations | Remove date fields from Shipium | Task | Closed | ALLI | Critical | Cyrus | 2025-01-17 |  | "desiredDeliveryDateLocal": "2025-01-20T23:59:59.999999999", "estimatedDeliveryDateLocal": "2025-01-23T20:00:00", "desiredDeliveryDate": "2025-01-20T23:59:59.999999999-08:00", "estimatedDeliveryDate": "2025-01-24T04:00:00Z", "effectiveShipDateTime": "2025-01-17T18:12:12.959Z" 1/21 Josephine: This is ready for testing.
Integrations | Remove shipOption fields from Shipium | Task | Closed | ALLI | Critical | Josephine | 2025-01-17 |  | "shipOption": "Standard" 1/21 Josephine: This is ready for testing. Check DocStore #48.
Integrations | Map businessDaysOfTransit to customAttribute3 | Task | Closed | ALLI | Critical | Josephine | 2025-01-17 |  | 1/21 Josephine: This is ready for testing. Check Docstore #50
Integrations | Map tenantId, fulfillmentContext on orderHeader custom fields | Task | Closed | ALLI | Critical | Cyrus | 2025-01-17 |  | To map tenantId and fulfillmentContext to order header custom fields, with the same naming convention 1/21 Josephine: Mapping to new custom fields are completed
Outbound | Sales Orders throwing error on some data but it is not clear which field | Issue | Closed | ALLI | High | Cyrus/Ani | 2025-01-21 |  | Cyrus: We tried to push some SO and we get these errors in response. Can you help idenfity the fields with issue? Error creating Sales Order/SO-5191176: Data truncation: Data too long for column 'VALUE' at row 1 and Error creating Sales Order/SO-5191186: Column 'ITEM_ID' cannot be null I have shared payload request/response example in Teams meeting. 01/24 - Cyrus: Still getting error > Error creating Sales Order/SO-5191177: Data truncation: Data too long for column 'VALUE' at row 1 1/27/25 - Ani - Working with Dev on currect ticket
Master Data | Where do we map the NDC value in Items entity? | Question | Closed | ALLI | Medium | Cyrus | 2025-01-21 |  | Josephine: NDC is mapped on the stock unit level rather than the individual items' level. The field is called stockUnit.inventoryAttribute1
Reporting | Reprint label button | Request | Closed | ALLI | Medium |  | 2025-01-21 |  | Matthew requested a way to reprint a label if wifi goes out during process 01/23 - Josephine: Outbound > Reprint RX Label. Current parameter is set to order ID, so may need to change to order number
Outbound | Waving is taking back to wave selection screen | Issue | Closed | DEP | Medium |  | 2025-01-21 |  | Danny ran into this issue during testing
Misc | Deposco to extend the "inactive" timeout on user if they do not log in to Deposco | Request | Hold | DEP | Medium | Cyrus | 2025-01-21 |  | Cyrus: As discussed in meeting, this request is to avoid having an issue on Production where the user credentials are reset (or the user inactive) for the API user.
Outbound | In an SO, the OrderLine should have the information for Pets (like Pet Name, Weight etc) | Issue | Closed | ALLI | High | Cyrus/Quan | 2025-01-21
Integrations | Shipium customsInfo changes | Request | Closed | DEP | High |  | 2025-01-23 |  | In CustomsInfo section: - customsValue: hardcode to 0.01 - commodityDescription: item.shortDescription - customsValueCurrency: hardcode to USD 01/24 - Cyrus: API call should have info for Customs with some static values, sameple payload has been shared. 1/28/25 - Josephine making latest update
Integrations | Shipium carrierSpecialServices confirmation | Task | Closed | ALLI | High | Cyrus | 2025-01-23 |  | To confirm if carrierSpecialServices can be picked up directly from order header 01/24 - Cyrus: Please note, if the order has Mix data (e.g. Cold Item/Dangerous Item), each of these will have a separate attribute in the Shipium call (sample payload shared). The data for the flags should be picked from the OrderLine in this case.
Integrations | Shipium: Cold Item generation of label missing information and failing | Issue | Validation | ALLI | Critical | Cyrus | 2025-01-24 |  | 01/24 - Cyrus: API call should have info as Item "perishable", sample payload has been shared. 01/24 - Item IsCold_C
Integrations | Shipium: Dangerous Item generation of label missing information | Issue | Needs Info | ALLI | High | Cyrus | 2025-01-24 |  | 01/24 - Cyrus: API call should have info as Item "limited_quantity", sameple payload has been shared. 01/30 - Josephine: Item master data must be updated. Hazmat flag in Deposco should be marked false for Dangerous Goods. Create a new customField called "DangerousGoods" in place.
Integrations | Shipium: Saturday flag needs to be part of the mapping for an order with Saturday delivery set to true - confirm if it's enabled | Issue | Closed | ALLI | Low | Cyrus | 2025-01-24 |  | 01/24 - Cyrus: Sample payload has been shared
Outbound | Shipium: All dates within the call for the Shipium API needs to be UTC | Issue | Hold | DEP/ALLI | Medium | Josephine/Cyrus | 2025-01-24 |  | 01/24 - Cyrus: All dates needs to be UTC to stay persistent with what we have in CB
Integrations | Deposco to confirm if we can send bigger payloads in a single call. | Question | Closed | DEP | High | Quan/Cyrus | 2025-01-24 |  | 1/24 - Quan: This is a system limitation, but Quan asking devops to see if there are any potential changes. 01/24 - Cyrus: Right now if we try to send a single call (e.g Item POST) with count of Items > 500, Deposco returns a Gateway error. We need to find out if Deposco can allow or extend the payload size acceptance rate.
Integrations | Deposco to confirm why we get only 200 records at a time when do a search call for SO with updatedDate and how to get different records for each call? | Question | Closed | DEP | High | Quan/Cyrus | 2025-01-24 |  | 01/24 - Cyrus: Example call: https://sandboxapi.deposco.com/ua/integration/alli/search/order?type=Sales Order&updatedDateOps=>&updatedDate=2024-12-01
Reporting | Convert RX label format to landscape | Request | Closed | ALLI | High | Matt/Danny | 2025-01-23 |  | 01/24 - Josephine: This is ready for testing, however, you will need to switch the printer formats to landscape
Outbound | Ship to Attention is not mapped to name | Issue | Closed | ALLI | Critical | Quan/Cyrus | 2025-01-27 |  | 01/27 - Cyrus: Name needs to get filled in Ship to Attention for the shipment process.
Integrations | Carrier Special Services and Dry Ice | Task | Closed | ALLI | Critical | Cyrus | 2025-01-28
Outbound | UPC NOT WORKING email | Issue | Closed | ALLI | High | Matt | 2025-01-28 |  | Resolved over call with Ani and Matt
Inventory Management | ORDERS NOT GOING TO HOLD WHEN FAILED ON QC email | Issue | Closed | ALLI | High | Ani/Matt | 2025-01-28
Outbound | Orders being packed without QC | Issue | Validation | ALLI | High | Matt | 2025-01-29 |  | The payload response shows "GOWEST - USPS Priority Mail Express" being selected by Shipium, which I think is fine (@Matthew Noland Can you confirm if this carrier service type is okay for a Military Address?) But when I view the label by clicking Show, it shows the label below. I am not sure if I have seen this label before. @Matthew Noland Does this look good to you?
Outbound | All Mix - stays in QC staging rather than shipping | Issue | In Progress | DEP | High | Ani/Danny | 2025-01-31

## On-site UAT Issue Log (hidden)
On-site UAT Issue Log
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
DATE REPORTED | ISSUE DESCRIPTION | TYPE | STATUS | TEAM | OWNER | SEVERITY | PRIORITY | GO LIVE CRITICAL? | DUE DATE | DEP COMMENTS | CLIENT COMMENTS
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Go Live Issue Log (hidden)
Go - Live Issue Log
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
DATE REPORTED | ISSUE DESCRIPTION | TYPE | STATUS | TEAM | OWNER | SEVERITY | PRIORITY | EXPECTED DELIVERY DATE | DEP COMMENTS | CLIENT COMMENTS

## Future (hidden)
Potential Future Cases
ITEM # | DETAILS | NOTES | TIMELINE

## Data Exchange (hidden)
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Imports
Date Updated:
Test Cases Required: |  | 5
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | 0%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Test Notes | Pass/Fail | Tester
1 | Container Import | 1.01 |  | In the application menu, navigate to the Field Mapping tab under Data Exchange | 1) Containers/LPN's should be created in 'Ready' status in the location specified (if applicable) | CSV Imported as Expected
|  | 1.02 |  | Select the "Container Import" field mapping and select 'Download Sample CSV'
|  | 1.03 |  | Complete the template. Required fields: Container Number, LPN Number, Location, Type
|  | 1.04 |  | Save the template to your local device
|  | 1.05 |  | In the application menu, navigate to the Data Exchange tab under Data Exchange
|  | 1.06 |  | Select the "3 dots" at the end of the row for 'Picking Container/LPN Import' and select 'Run'
|  | 1.07 |  | Select the saved template from the local device and select 'Upload'
|  | 1.08 |  | In the application menu, navgate to the Transmission tab under Data Exchange
|  | 1.09 |  | Verify the import's status by checking the 'Status' column
2 | Zone Import | 2.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Zones should be created | CSV Imported as Expected
|  | 2.02 |  | Select the Zone Import field mapping and select 'Download Sample CSV'
|  | 2.03 |  | Complete the template. Required fields: Code
|  | 2.04 |  | Save the template to your local device
|  | 2.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 2.06 |  | Select the "3 dots" at the end of the row for 'Product Category Import' and select 'Run'
|  | 2.07 |  | Select the saved template from the local device and select 'Upload'
|  | 2.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 2.09 |  | Verify the import's status by checking the 'Status' column
3 | Location Import | 3.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Locations should be created as 'Ready' type with corresponding Zones (if applicable) | CSV Imported as Expected
|  | 3.02 |  | Select the Location Import field mapping and select 'Download Sample CSV'
|  | 3.03 |  | Complete the template. Required fields: Location(l) Number, l.Facility, l.Locator, l.storageType, l.Type, l.multiItemThreshold, l.Pickable Optional: Zone(z) Facility, z.Name, Storage(s)
|  | 3.04 |  | Save the template to your local device
|  | 3.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 3.06 |  | Select the "3 dots" at the end of the row for 'Location Import' and select 'Run'
|  | 3.07 |  | Select the saved template from the local device and select 'Upload'
|  | 3.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 3.09 |  | Verify the import's status by checking the 'Status' column. Reference the 'Errors' column if status is 'Failed'
4 | Pack Import | 4.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Packs should be created with corresponding Items | CSV Imported as Expected
|  | 4.02 |  | Select the Pack Import field mapping and select 'Download Sample CSV'
|  | 4.03 |  | Complete the template. Required fields: Item Number, Pack Quantity
|  | 4.04 |  | Save the template to your local device
|  | 4.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 4.06 |  | Select the "3 dots" at the end of the row for 'Item/Pack Import' and select 'Run'
|  | 4.07 |  | Select the saved template from the local device and select 'Upload'
|  | 4.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 4.09 |  | Verify the import's status by checking the 'Status' column
5 | Purchase Order Import | 5.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) OrderHeaders should be created as 'Purchase Order' type with corresponding OrderLines | Initial upload attempts were failures due to an incorrect Business Unit.
|  | 5.02 |  | Select the Purchase Order Import field mapping and select 'Download Sample CSV'
|  | 5.03 |  | Complete the template. Required fields: OrderHeader(oh) Number, oh.currentStatus, OrderLine (ol) Number, ol.customerLineNumber, ol.orderLineStatus
|  | 5.04 |  | Save the template to your local device |  | Single line PO uploaded successfully
|  | 5.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export |  | Multi-line PO failure due to Customer Line Number being set as a Business Key
|  | 5.06 |  | Select the "3 dots" at the end of the row for 'Purchase Order Import' and select 'Run' |  | Multi-line PO uploaded successfully
|  | 5.07 |  | Select the saved template from the local device and select 'Upload'
|  | 5.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 5.09 |  | Verify the import's status by checking the 'Status' column. Reference the 'Errors' column if status is 'Failed'

## Packing (hidden)
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Packing
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
1 | Build Transfer Order | 1.01 |  | Select Build Outbound Transfer Order from Store Operations menu | 1)Ensure your user's Facility is set to the DPR or STPR facility. Screen should read 'Ship-To Facility'
|  | 1.02 |  | Enter the Ship-To Facility Number
|  | 1.03 |  | Select a Transfer Purpose and scan the location with the stock to transfer
|  | 1.04 |  | Scan the container user will be picking into
|  | 1.05 |  | Scan the Items and on the next screen, enter the Quantity that user intends to transfer
|  | 1.06 |  | User will be brought to a sumamry screen showing all items added to the Transfer Order. Confirm order by selecting "Next."Stage your container to a location | User will see the following message: "Container (Container#) staged to (StagingLocation) for ship-to HZLHQ"
|  | 1.07 |  | Pack out the Transfer Order using the Transfer Order Packing button from the Store Operations menu
|  | 1.08 |  | Scan the LPN label of the picking container, and select Next.
|  | 1.09 |  | The Item Screen appears with a list of items in the container. Scan an item in container OR select the "Pack Remainder" button to pack out all items in the container
1.1
2 | Cubed Packing | 2.01 |  | Select Cubed Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container.
|  | 2.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 2.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container.
|  | 2.04 |  | Shipping label and packing list will print
|  | 2.05 |  | User will be returned to the Scan Container Screen and see the following message: "Order [ ] has been successfully packed."
3 | Single Scan Packing | 3.01 |  | Select Single Scan Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container.
|  | 3.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 3.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container, then enter the quantity that will be packed on the next screen
|  | 3.04 |  | Select the box from the Box list
|  | 3.05 |  | Shipping label and packing list will print
|  | 3.06 |  | If there are more items in the picking bin, then you are returned to the Item Screen to scan/select another item.
4 | Outbound Transfer Packing | 4.01 |  | Select Outbound Transfer Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order and an Inbound Transfer Order is created for the store to receive against
|  | 4.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 4.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container or use the pack remainder button to pack out all items in the container
|  | 4.04 |  | Packing list will print once all items are packed
|  | 4.06 |  | User will then be brought back to the Scan Container screen
5 | Bulk Packing | 5.01 |  | Select Bulk Packing from the Outbound Menu | User will see the following message at the end of packing: [The request has been placed to ship orders.] Please check the notification center for error messages. | Receiving an error on the Scan Container step stating, "For input string: "" ' Used BIN-060 for testing
|  | 5.02 |  | User will be prompted to scan/enter a container (a container that was just picked into)
|  | 5.03 |  | User will see an order summary screen showing all orders in the container, as well as the items that those orders have in common
|  | 5.04 |  | Select Enter CLIENTnsions
|  | 5.05 |  | Weight will autopopulate, but select the carton type to pack the order out into
|  | 5.06 |  | Select Ship All
|  | 5.07 |  | User will be returned to the container entry screen
6 | BOPIS Packing | 6.01 |  | Select BOPIS Packing from Outbound Menu | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's status shows status "Staged" and Order's shipping status shows "Not Shipped" | Re-tested with SO630
|  | 6.02 |  | User will be prompted to scan/enter a container (a container that was just picked into)
|  | 7.03 |  | User will then be prompted with a list of items that are in said container.
|  | 7.04 |  | Scan each item in container or use the Pack Remainder button to pack all items
|  | 7.05 |  | After all items have been scanned, Select a box from the Box list to pack your order into
|  | 7.06 |  | User will be returned to the container entry screen
| Move Container | 7.07 |  | Navigate to "Move Container" under Inventory on handheld MainMenu | Because BOPIS will be picked and packed through the main warehouse facility, and then moved to the store- this will be the next step. The order will be transported outside system. The "mover" will need to enter the device, and go to move container- where they will enter the container number and be given the option to change facility. Operator must change to destination facility, in order to receive product. From there, scan the location to drop off, and proceed to next step.
|  | 7.08 |  | Enter/Scan the container (LPN) that contains the stock (inventory) you want to move.
|  | 7.09 |  | User will change their facility to the facility the order is going to, then enter a store location (ex. Receiving)
| BOPIS Pickup | 7.1 |  | Select Close BOPIS Order from Store Operations Menu | 1) Screen message should appear saying "Packed [Order] containing x items.." 2) Order's status shows status "Complete" and Order's shipping status shows "Ship Complete"
|  | 7.11 |  | User will be prompted to scan/enter a container (the container that was packed)
|  | 7.12 |  | User will enter the CLIENTnsions of the box,
|  | 7.13 |  | User will be returned to the container entry screen
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Packing Edge Cases
1 | Single Scan Packing - Scanning a Non Existing Container | 1.01 |  | User enters Single Scan Packing process from facility menu | 1) Screen message should appear saying "Cannot find container [#]." 2) User will always be prevented from starting the packing process if they scan a non existent container
|  | 1.02 |  | User enters a container that does not exist in the system
|  | 1.03 |  | User is prevented from proceeding
2 | Single Scan Packing - New Bin | 2.01 |  | During packing, the user may select New Bin if items in picking container cannot be shipped in one shipping box | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created.
|  | 2.02 |  | On item screen, user will select New Bin
|  | 2.03 |  | User will be prompted to enter the CLIENTnsions of the first shipping box
|  | 2.04 |  | Process will return back to items screen to now pack remaining items in new shipping box
|  | 2.05 |  | This process can be repeated as many times as needed
3 | Single Scan Packing - Scanning an Empty Container | 2.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "There are no items to pack." 2) User will always be prevented from starting the packing process if they scan an empty container
|  | 2.02 |  | User is prevented from proceeding
4 | Single Scan Packing - Scanning Wrong Item | 3.01 |  | User scans item that is not on the listbox / not in the container that the user scanned | 1) Screen message should appear saying "Item scanned does not exist in this Order" 2) User should not be able to scan a non existing item for the order and container
|  | 3.02 |  | User is prevented from proceeding
|  | 3.03 |  | User scans the correct item and proceeds as normal
5 | Batch Packing - Scanning a Container with a Partially Picked Order (unfinished pick task) | 4.01 |  | User enters a container that does not have all items picked into it | 1) Screen message should appear saying "Order not fully picked." 2) User will always be prevented from starting the packing process if they scan an incomplete container
|  | 4.02 |  | User is prevented from proceeding
6 | Singles Packing - Scanning a Non Existing Container | 6.01 |  | User enters Singles Packing from facility menu | 1) Screen message should appear saying "Container does not exist or data issue." 2) User will always be prevented from starting the packing process if they scan a non existent container
|  | 6.02 |  | User enters a container that does not exist in the system
|  | 6.03 |  | User is prevented from proceeding
7 | Singles Packing - Scanning an Empty Container | 7.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "Scanned container contains no items" 2) User will always be prevented from starting the packing process if they scan an empty container
|  | 7.02 |  | User is prevented from proceeding
8 | Singles Packing - Scanning Wrong Item | 8.01 |  | User scans item that is not on the listbox / not in the container that the user scanned | 1) Screen message should appear saying "Invalid item number" 2) User should not be able to scan a non existing item for the order and container
|  | 8.02 |  | User is prevented from proceeding
|  | 8.03 |  | User scans the correct item and proceeds as normal
9 | Batch Packing - Scanning an Empty Container | 9.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "Container [#] does not have any stock units." 2) User will always be prevented from adding the empty container to the trip
|  | 9.02 |  | User is prevented from proceeding

## Integration (hidden)
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Integration
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Integration
1 | - Item Pull | 1.01
1.02
1.03
1.04
1.05
1.06
2 | Sales Order Pull | 2.01
2.02
2.03
2.04
2.05
2.06
3 | Inventory Sync | 3.01
3.02
3.03
3.04
3.05
3.06
3.07
4 | Ship Notice | 4.01
4.02
4.03
5 | - Item Pull | 5.01
5.02
5.03
5.04
5.05
5.06
16 | RTV Picking - User Enters too Much Quantity | 16.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Not Tested
|  | 16.02 |  | User accidentally enters more than the pick quantity
|  | 16.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 16.04 |  | User will again be prompted to enter location, SKU, and quantity.
17 | RTV Picking - Scanning Incorrect Container/Bin | 17.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Not Tested
|  | 17.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
18 | RTV Picking - Exceptions (no stock, damaged, etc.) | 18.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Not Tested
|  | 18.02 |  | User can select "exception" button
|  | 18.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 18.04 |  | Select "exception" again from that screen after selecting a reason
|  | 18.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 18.06 |  | If no other stock exists for that item, it will go to back ordered status.
19 | RTV Picking - Suspend Task | 19.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Not Tested
|  | 19.02 |  | User can select "exception" button
|  | 19.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 19.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
20 | RTV Picking - Suspend Workgroup | 20.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Not Tested
|  | 20.02 |  | User can select "exception" button
|  | 20.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 20.04 |  | User is taken back to MainMenu screen
|  | 20.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
21 | RTV PIcking - Suspend Workgroup and Keep Assigned User | 21.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Not Tested
|  | 21.02 |  | User can select "exception" button
|  | 21.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 21.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 21.05 |  | Assigned user can select wave again to continue picking
6 | POS Order Pull | 6.01
6.02
6.03
6.04
6.05
6.06
7 | Inventory Sync | 7.01
7.02
7.03
7.04
7.05
7.06
7.07

## Picking (hidden)
Client: |  | Go West Supply
Client Code: |  | GOWEST
Process: |  | Picking
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking
1 | Batch Picking | 1.01 |  | User will select Batch Picking button from Outbound menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 1.02 |  | User will see a list of waves and can select or enter the wave
|  | 1.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 1.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 1.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 1.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
2 | High Value Orders | 2.01 |  | User will select High Value Orders button from Admin menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 2.02 |  | User will see a list of waves and can select or enter the wave
|  | 2.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 2.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 2.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 2.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
3 | Single Scan Picking | 3.01 |  | User will select Singles Picking in corresponding facility menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location | Good | selcted works bundle sku to test item componets imported
|  | 3.02 |  | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking cart to be used |  | Good
|  | 3.03 |  | User will scan location, SKU, bin and enter in quantity to complete pick task(s). |  | Good
|  | 3.04 |  | Once all pick tasks have been completed, user is returned to the wave selection screen |  | Good
4 | Outbound Transfer Picking | 4.01 |  | User will select Outbound Transfer Picking button from Outbound menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 4.02 |  | User will see a list of waves and can select or enter the wave
|  | 4.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 4.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 4.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 4.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
5 | Single Scan Picking (with Item Image Display) | 5.01 |  | User will select Singles Picking in corresponding facility menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 5.02 |  | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 5.03 |  | User will see picking screen and item image
|  | 5.04 |  | User will scan location, item SKU, and quantity
|  | 5.05 |  | Once all pick tasks have been completed, user is returned to the wave selection screen
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking Edge Cases
1 | Batch Picking - New Bin | 1.01 |  | During picking, if a picking container becomes too full to put any more items in, the user can select the New Bin button to continue the picking process | Current picking bin will unassign from the order to allow the user to pick into a new container. Picking will proceed as expected | Received an error stating, "Using multi-bins is not allowed." **Resolved** Tested on SO614 with no issues.
|  | 1.02 |  | Selecting New Bin will unassign the current picking bin from the order to allow the user to pick into a new container
|  | 1.03 |  | The picking screen should update to show no suggested bin to pick into
|  | 1.04 |  | User will proceed to complete the pick task in any empty container available
2 | Singles Picking - Stage | 2.01 |  | During picking, if the picking container becomes too full to put any more items in, the user can stage the bin to be packed. | Pick wave can be completed with multiple picking carts that are staged to the Shipping location upon completion | I initially picked x6 of x10 copies of AMGSWL89 from SO468 into BIN-022. I then selected "Stage", which took me to the screen to select a new container. I selected BIN-023, but the picking screen had me pick the original x10 copies into this bin. Looking at the data on SO468, there is only product located in BIN-023.
|  | 2.02 |  | Selecting Stage will prompt the user to select a new cart to continue picking
|  | 2.03 |  | User can proceed with picking as expected in new container
3 | Batch Picking - Entering Less Quantity | 3.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed
|  | 3.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
4 | Singles Picking - Entering Less Quantity | 4.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed
|  | 4.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
5 | Batch Picking - User Scans Incorrect Location | 5.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen | Message notes: please scan a valid location
|  | 5.02 |  | User scans a location other than the one listed on the screen during picking
|  | 5.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 5.04 |  | User should proceed to correct location and continue as normal
6 | Batch Picking - User Scans Incorrect Item | 6.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. | Message notes: please scan valid item
|  | 6.02 |  | User scans the wrong item
|  | 6.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
7 | Batch Picking - User Enters too Much Quantity | 7.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left.
|  | 7.02 |  | User accidentally enters more than the pick quantity
|  | 7.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 7.04 |  | User will again be prompted to enter location, SKU, and quantity.
8 | Batch Picking - Scanning Incorrect Container/Bin | 8.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin
|  | 8.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
9 | Batch Picking - Exceptions (no stock, damaged, etc.) | 9.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from.
|  | 9.02 |  | User can select "exception" button
|  | 9.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 9.04 |  | Select "exception" again from that screen after selecting a reason
|  | 9.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 9.06 |  | If no other stock exists for that item, it will go to back ordered status.
10 | Batch Picking - Suspend Task | 10.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped.
|  | 10.02 |  | User can select "exception" button
|  | 10.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 10.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
11 | Batch Picking - Suspend Workgroup | 11.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete"
|  | 11.02 |  | User can select "exception" button
|  | 11.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 11.04 |  | User is taken back to MainMenu screen
|  | 11.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
12 | Batch PIcking - Suspend Workgroup and Keep Assigned User | 12.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group.
|  | 12.02 |  | User can select "exception" button
|  | 12.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 12.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 12.05 |  | Assigned user can select wave again to continue picking
13 | Singles Picking - User Scans Incorrect Location | 13.01 |  | During picking, the user will see the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen
|  | 13.02 |  | User scans a location other than the one listed on the screen during picking
|  | 13.03 |  | Error message will appear "Please scan a valid location."
|  | 13.04 |  | User should proceed to correct location and continue as normal
14 | Singles Picking - User Scans Incorrect Item | 14.01 |  | During picking, the user scans the wrong item | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item.
|  | 14.02 |  | Screen message will appear stating "Please scan a valid item"
15 | Singles Picking - User Enters Too Much Quantity | 15.01 |  | User enters locatiton and SKU | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left.
|  | 15.02 |  | User accidentally enters more than what is called for to pick
|  | 15.03 |  | Screen message will appear as follows: "Quantity entered is greater than required."
|  | 15.04 |  | User will again be prompted to enter location, SKU, and quantity.
16 | Singles Picking - Exceptions (no stock, damaged, etc.) | 16.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order will go to back ordered status. Also, the stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from.
|  | 16.02 |  | User can select "exception" button
|  | 16.03 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 16.04 |  | If no other stock exists for that item, it will go to back ordered status.
17 | Singles Suspend WorkGroup | 17.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete"
|  | 17.02 |  | User can select "exception" button
|  | 17.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 17.04 |  | User is taken back to MainMenu screen
|  | 17.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
14 | RTV Picking - User Scans Incorrect Location | 14.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen |  |  | Not Tested
|  | 14.02 |  | User scans a location other than the one listed on the screen during picking
|  | 14.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 14.04 |  | User should proceed to correct location and continue as normal
15 | RTV Picking - User Scans Incorrect Item | 15.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. |  |  | Not Tested
|  | 15.02 |  | User scans the wrong item
|  | 15.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
16 | RTV Picking - User Enters too Much Quantity | 16.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Not Tested
|  | 16.02 |  | User accidentally enters more than the pick quantity
|  | 16.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 16.04 |  | User will again be prompted to enter location, SKU, and quantity.
17 | RTV Picking - Scanning Incorrect Container/Bin | 17.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Not Tested
|  | 17.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
18 | RTV Picking - Exceptions (no stock, damaged, etc.) | 18.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Not Tested
|  | 18.02 |  | User can select "exception" button
|  | 18.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 18.04 |  | Select "exception" again from that screen after selecting a reason
|  | 18.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 18.06 |  | If no other stock exists for that item, it will go to back ordered status.
19 | RTV Picking - Suspend Task | 19.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Not Tested
|  | 19.02 |  | User can select "exception" button
|  | 19.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 19.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
20 | RTV Picking - Suspend Workgroup | 20.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Not Tested
|  | 20.02 |  | User can select "exception" button
|  | 20.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 20.04 |  | User is taken back to MainMenu screen
|  | 20.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
21 | RTV PIcking - Suspend Workgroup and Keep Assigned User | 21.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Not Tested
|  | 21.02 |  | User can select "exception" button
|  | 21.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 21.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 21.05 |  | Assigned user can select wave again to continue picking