## Schedule
OMNI Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal | Metric | Status
OMNI Goal #1 | Metric we will use to track | Open
OMNI Goal #2 | Metric we will use to track | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | LINK
Master Design Document | LINK
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | ERP/WebStore/ShippingCarrier/ChannelAggregator/EDI - data requirements, troubleshooting, mapping updates, steps etc. |  | 0%
Order Orchestration | Sourcing, Routing, Exception and Backorder Management |  | 0%
Inbound | General Receiving (PO, Blind Receipt, Customer Returns), Move Item, Move Stock, Move Container |  | 0%
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock |  | 0%
Outbound | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking, Packing, Shipping |  | 0%
Other - WMS | Transfer orders, 3PL Billing, etc. |  | 0%
Reporting | Report Builder, Dashboard Widgets |  | 0%
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Completion Date
End to End Testing | Testing all process flows with live data end to end | 0%
UAT Onsite Agenda | LINK | 0%
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0%
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0%
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned.
Deposco Onsite Support | Travel booked for cutover and go-live week.
Project Closeout | Agreement of final deliverables provided.

## Task Tracker
OMNI Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | Comments
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  | FALSE | Completed | DEP | Hannah
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  | FALSE | Completed | DEP | Hannah
Orientation | Setup Confluence and JIRA Project | Setup OMNI confluence and JIRA Project | Task |  | FALSE | Completed | DEP | Hannah
Orientation | OMNI UA Env. | Deposco to setup OMNI UA environment with OMNI code chosen by OMNI during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  | FALSE | Completed | DEP | Business Consultant
Orientation | Company & Facility | Deposco to coordinate with OMNI to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task |  | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Users | Deposco guides OMNI super user through user setup with Message Center import or copying admin user from user UI. OMNI can choose to setup only super users or all users during this phase. Password reset emails are sent to OMNI users to complete final step for Deposco access | Task |  | FALSE | Completed | DEP | Business Consultant
Orientation | Begin development for new socket APIs | Deposco Socket team begins development for new socket APIs as per initial project SOW | Task |  | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Print OMNI (Windows) | Multi-Step: 1) Deposco Devops team sets up OMNI print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to OMNI to complete setup on their server/network 2) OMNI completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task |  | FALSE | In Progress | DEP/OMNI | Business Consultant / Technical Lead |  |  | 8/1 - procuring printers for pack stations
Orientation | Setup Parcel Carrier Accounts | UPS: OMNI utilizes Deposco UPS Registration Wizard to setup UPS account USPS: | Task |  | FALSE | Completed | OMNI | Technical Lead
Orientation | Setup Exisiting Sockets | OMNI utilizes Deposco help site guides to setup existing socket connections | Task |  | FALSE | Completed | OMNI | Technical Lead |  |  | 8/1 - have one instance for each socket type, still getting credentials from customers
Orientation | General Application and UI Overview | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Message Center Overview - Handheld Menu Access - Master data and Data Exchange application | Task |  | FALSE | Completed | DEP/OMNI | Fany |  |  | 7/14 - scheduled for Thurs 7/17
Orientation | Begin Master Data Gathering | Sample Master Data templates for items, packs, locations, zones, storages, etc. to be provided by Deposco to be used by OMNI | Task |  | FALSE | Completed | OMNI | OMNI team
Orientation | Create Specialized Process Flows | OMNI creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task |  | FALSE | Closed | OMNI | Warehouse Leads |  |  | 8/1 - not needed
Orientation | Create Inbound Process Flows | OMNI creates process flows for inbound handling of product (unloading, receiving, putaway) | Task |  | FALSE | Closed | OMNI | Inbound Lead |  |  | 8/1 - not needed
Orientation | Create Order Management Process Flows | OMNI creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task |  | FALSE | Closed | OMNI | Outbound Lead / Customer Service Lead |  |  | 8/1 - not needed
Orientation | Create Outbound Process Flows | OMNI creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task |  | FALSE | Closed | OMNI | Outbound Lead |  |  | 8/1 - not needed
Orientation | 3PL Client Matrix | Complete spreadsheet with specific customer data | Task |  | FALSE | Completed | OMNI
Orientation | Schedule recurring project calls | Weekly status call Bi-weekly executive steering call | Task |  | FALSE | In Progress | DEP | Hannah
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | Completed | DEP | Fany
Design | SKU Exception List Handling | Ensure that SKU exclusion handling for WooCommerce & Shopify is designed for | Request |  | FALSE | Completed | DEP/OMNI
Design | Master Design Document Delivery | Deliver master design document for OMNI team to review | Task |  | FALSE | Open | DEP | Solution Lead
Design | Review and Sign Master Design Document | OMNI to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  | FALSE | Open | DEP/OMNI | Full Team
Configuration | Deliver Inbound Configuration | Via demo sessions or loom videos | Task |  | FALSE | Open | DEP | Implementation Lead
Configuration | Deliver Inventory Management Configuration | Via demo sessions or loom videos | Task |  | FALSE | Open | DEP | Implementation Lead
Configuration | Deliver Outbound Configuration Pt 1 | Via demo sessions or loom videos | Task |  | FALSE | Open | DEP | Implementation Lead
Configuration | Deliver Outbound Configuration Pt 2 | Via demo sessions or loom videos | Task |  | FALSE | Open | DEP | Implementation Lead
Configuration | Deliver Integration Configuration Training | Via demo sessions or loom videos | Task |  | FALSE | Open | DEP | Implementation Lead
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task |  | FALSE | Open | DEP | Implementation Lead
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task |  | FALSE | Open | OMNI | Inbound Lead
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task |  | FALSE | Open | OMNI | Inventory Lead
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | FALSE | Open | OMNI | Outbound Lead
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | FALSE | Open | OMNI | Outbound Lead
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task |  | FALSE | Open | OMNI | Technical Lead
Validation | End to End Test Case Execution | Complete end to end test cases | Task |  | FALSE | Open | OMNI | Warehouse Leads + Technical Lead
Validation | Deliver Onsite UAT Agenda |  | Task |  | FALSE | Open | DEP | Implementation Lead
Validation | Train End Users | During UAT and any additional training as needed | Task |  | FALSE | Open | OMNI | Warehouse Leads
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task |  | FALSE | Open | DEP/OMNI | Full team
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task |  | FALSE | Open | DEP | PM
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task |  | FALSE | Open | DEP | Implementation Lead
Deployment | Execute Cutover Plan Steps |  | Task |  | FALSE | Open | DEP/OMNI | Full team
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task |  | FALSE | Open | DEP | PM
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Recordings
OMNI Demo Videos
Date | Category | DESCRIPTION | LINK
Baseline Education
| Deposco User Exerience |  | OMNI - Deposco UI & Master Data Demo - 7.17.25
Master Data / Data Exchange
Process Demos
Integrations
Inbound/Putaway
Inventory Management
Outbound I
Outbound II
Reporting
Miscellaneous Demos
Testing/Training Support

## Config Tasks
Deposco Configuration Task List | [9 empty] | 2025-08-12
Product / Task Group | Task | Task Details | Out of Scope (SOW001) | Phase 2 Item | Comments | Owner | Status | % Complete | Locked | Due date | Delivery Date
Pre-Design Tasks | [6 empty] | Complete
Master Data | Item/Pack Field Mapping and DE template |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-17
Master Data | Locations, Zones and Storages Field Mapping and DE template |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-17
Master Data | Company Field Mapping and DE template |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Master Data | Trading Partner Field Mapping and DE template |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Master Data | Components Field Mapping and DE |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Master Data | Container Field mapping and DE template |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Master Data | Carton type Field mapping and DE template |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Master Data | Initial Item and Pack Upload |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-07-25
Master Data | Initial Locations/zones/storages data upload |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-07-25
Master Data | Initial Company data upload |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-07-25
Receiving | Receiving V2 workflow process SIs (PO, Blind PO) and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Receiving | Receiving V2 workflow process SIs ( RMA receiving) and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Receiving | Unreceiving workflow process SIs and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Returns | Create RMA workflow process SIs and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Putaway | Move item workflow SIs |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Kit to Stock | Kit to Stock base configuration and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Cycle Counts | Workflow SIs |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Physical Counts | Workflow SIs |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Inventory adjustments | Workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Warehouse lookup | Workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
OFP | OFP for SLSU | Base Config | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
OFP | OFP for SLMU | Base Config | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
OFP | OFP for MLMU | Base Config | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
OFP | OFP for freight | Base Config | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Picking | Single Scan picking workflow SIs config and process validation | Base Config | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Picking | Batch picking workflow SIs config and process validation | Base Config | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Packing | Pack Order by item workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Packing | Single Scan Packing workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Packing | Bulk Packing workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Packing | Assign trip to container workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Packing | Repalletize workflow SIs config and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-07-25
Other
Printers | Look into autobagger support/references to connect with Deposco |  | FALSE | FALSE | Autobagger has been set up | Omnipress | Complete | 100% | FALSE
Scale | Shipping scale setup |  | FALSE | FALSE | 8/7 - Deciding if they need to purchase or not | Omnipress | To-Do |  | FALSE
Shipping | Look into UPS WorldEase integration |  | TRUE | TRUE | Not supported at this time Eric looking into other options with UPS | Deposco | Closed | 0% | FALSE
|  |  | FALSE | FALSE |  |  |  |  | FALSE
Warehouse setup
Labels | Ensure that all locations are labeled and the barcode is scannable using the handheld |  | FALSE | FALSE |  | Omnipress | In Progress | 50% | FALSE | 2025-08-15
Labels | Label all containers/carts/bins/totes | Label all containers that will be used and validate that the barcodes are scannable using the handheld | FALSE | FALSE |  | Omnipress | In Progress | 50% | FALSE | 2025-08-15
Hanheld devices | Procure all hanheld devices |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-08-15
Printers | ZPL/PDF Printer setup and validation | Set up and validate all printers that will print Deposco reports | FALSE | FALSE | 8/7 - still need to purchase a couple more printers, label & document printers are setup & working | Omnipress | In Progress | 75% | FALSE | 2025-08-15
Printer Resources | Printing Resources | Set up printing Resources | FALSE | FALSE |  | Omnipress | To-Do | 0% | TRUE | 2025-08-15
Printer Assignments | Item label | Create item label printer assignments. Report name: Item Label (4X8) | FALSE | FALSE |  | Omnipress | To-Do | 0% | TRUE | 2025-08-15
Printer Assignments | Shipping labels | Create shipping label printer assignments | FALSE | FALSE |  | Omnipress | To-Do | 0% | TRUE
Printer Assignments | Packing Slips | Create packing slip printer assignments | FALSE | FALSE |  | Omnipress | To-Do | 0% | TRUE
Hanheld devices | DEP app has been downloaded in hh devices |  | FALSE | FALSE |  | Omnipress | To-Do | 0% | FALSE
Bright Warehouse Configuration
Master Data | Image | Upload BU/family logo images for branded label and other reports | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-08-15
Master Data | Zones | Delete zones created during the inital master data upload. Create zones by BU | FALSE | FALSE | Will not create per BU. Zones created to cover needs based on process involved. FL: Is the Omnipress team okay with deleting the zones created during the inital upload? | DEP & OMNI | Complete | 100% | FALSE | 2025-08-15
Master Data | Locations | Update attributes: Pickable and Reserve flags, cycle counts, set status to Ready, add pick sequence, add Skid location flag,update zone assignment. Add a quarantine location for items that are not available for fulfillment. | FALSE | FALSE | 8/7 - Deposco to update field mapping to skip creation 8/8 - New fieldmapping ready | DEP & OMNI | In Progress | 75% | FALSE | 2025-08-15
Master Data | Containers | Upload container data (carts, bins, totes) | FALSE | FALSE |  | Omnipress | In Progress | 50% | FALSE | 2025-08-15
Master Data | Storages | Create and upload Storage data to define the home picking location of items including minimum and maximun quantities at the location. This information will be needed to feed the suggested location logic in the Putaway process, and to create replenishment tasks. | FALSE | FALSE |  | Omnipress | To-Do | 0% | FALSE | 2025-08-15
Master Data | Items | Generate/extract item identifiers to use as UPCs. This is necessary for users to scan item barcodes for all handheld processes. | FALSE | FALSE | 8/7 - Fany to add to MDD that Dep will generate a new item UPC when a new item is created | Omnipress | Closed | 0% | FALSE | 2025-08-15
Master Data | Items | Update item attributes: UPC, Kit Stock, Kit Order, HS codes, Unit Price (customs value), Purchase Cost (production cost), reorder point. | FALSE | FALSE | 8/11 - New field mapping updated to include reorder point and skip new record creation | DEP & OMNI | To-Do | 0% | FALSE | 2025-08-15
Master Data | Items | Ensure that labels for all current items are available to scan using Veracore identifier as the UPC | FALSE | FALSE |  | DEP & OMNI | To-Do | 0% | FALSE | 2025-08-15
Master Data | Packs | Generate and upload dimensions and weight data. This is needed for international shipments and for cartonization after phase 1 | FALSE | FALSE |  | DEP & OMNI | In Progress | 50% | FALSE | 2025-08-15
Master Data | Components | Generate and upload component data for kits. This information is required for both Kit to Stock and Kit to Order items. | FALSE | FALSE |  | Omnipress | In Progress | 25% | FALSE | 2025-08-15
Master Data | Carton Types | Upload carton types using data exchange. Consider defining a Business Unit for family-specific cartons to narrow down the list of suggested cartons during packing. | FALSE | FALSE | No specific cartons per BU | Omnipress | Complete | 100% | FALSE | 2025-08-15
Master Data | Shipping Door | Create shipping doors using in the UI. Navigate to :shipping door and select New. This is needed to the Assign Trip to Container flow (freight orders) | FALSE | FALSE | 8/7 - Deposco to share steps on how to create shipping doors. LINK TO INSTRUCTIONS: https://drive.google.com/file/d/1SJonVZ-XwB4TASjbsM8VjDLiET-ia9FG/view?usp=drive_link | Omnipress | To-Do | 0% | FALSE | 2025-08-15
Receiving | Print Report workflow process configuration and item label creation | This process can be used to print item labels before receiving inventory | FALSE | FALSE | label size : 4x8 | Deposco | To-Do | 0% | FALSE | 2025-08-18
Receiving | Receiving V2 workflow process SIs (PO, Blind PO) and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-08-18
Receiving | Receiving V2 workflow process SIs ( RMA receiving) and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-08-18
Receiving | Unreceiving workflow process SIs and process validation |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-08-18
Receiving | Adjust all screen flows to show location number, instead of location locator |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Returns | Provide return reasons to include in the Create RMA process |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-08-18
Returns | Create RMA workflow process SIs and process validation | Add return reasons | FALSE | FALSE |  | Deposco | In Progress | 100% | TRUE | 2025-08-18
Putaway | Move item workflow SIs |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-08-18
Putway | Configure suggested Putaway logic |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Putaway | Adjust all screen flows to show location number, instead of location locator |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Replenishments | Replenishments workflow SIs and testing (manual and directed) |  | FALSE | FALSE |  | Deposco | In Progress | 100% | FALSE | 2025-08-18
Replenishments | Adjust all screen flows to show location number, instead of location locator |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Cycle Counts | Workflow SIs for create CC by item and location | Hide quantity at the location and ignore zero variances | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Cycle Counts | Workflow SIs for perform CC |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Cycle Counts | Record selectors, profiles, schedulers | Help site link | FALSE | FALSE |  | Deposco | In Progress | 0% | FALSE | 2025-08-18
Cycle Counts | Enable/validate cycle count task creation during picking exceptions and replenishment exceptions and set stock unit status on hold |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Cycle Counts | Validate only admin users have access to manage CC variances |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Physical Counts | Workflow SIs |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE | 2025-08-18
Inventory Adjustments | Enable process to admin users only |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Inventory Adjustments | Provide reason codes for inventory adjustments |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-08-18
Inventory Adjustments | Configure reason codes for inventory adjustments |  | FALSE | FALSE |  | Deposco | To-Do | 0% | TRUE | 2025-08-18
Kit to Stock | Kit to Stock base configuration and process validation |  | FALSE | FALSE |  | Deposco | To-Do | 0% | FALSE | 2025-08-18
Users | Create Omnipress users and groups | Assign groups to Omnipress users and permissions | FALSE | FALSE |  | Omnipress | Not assigned yet | 0% | FALSE
Users | Create external users and groups | Assign groups to external users and permissions | FALSE | FALSE |  | Omnipress | Not assigned yet | 0% | FALSE
|  |  | FALSE | FALSE |  |  | Not assigned yet |  | FALSE
POI | Configure POI rules |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE | TBD
Automations | Configure SO automations |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE | TBD
Packing | Rules to prevent partial kit shipments |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
3PL Billing
3PL Billing | Config transaction billing profile template |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
3PL Billing | Billing configs templates |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
3PL Billing | AdHoc Billing workflow process config |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Bright Order Configuration (T&M)
Daily Item Facility History | Request Snowflake DB setup for prod |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Outbound Order Management | CoHeader field mapping and DE template |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Outbound Order Management | Customer Order - Custom integration | Omnipress team to look into how 'custom integration' orders are being pulled into Veracore | FALSE | FALSE |  | Omnipress | Closed | 0% | FALSE
CO Workbench | CO workbench Application settings |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
CO Workbench | Shipping rate lookup values DE template and Field mapping for CO Workbench |  | FALSE | FALSE |  | Deposco | Complete | 100% | FALSE
CO Workbench | Shipping rate lookup values upload per BU | This will be used to display the applicable shipping services per BU | FALSE | FALSE |  | Omnipress | To-Do | 0% | FALSE
CO Workbench | Page layout |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Co-preprocessing | Configure rules to prevent order updates |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Bright Socket Configuration (T&M)
Shopify | Shopify instances Setup |  | FALSE | FALSE |  | Omnipress | In Progress | 50% | FALSE
WooCommerce | WooCommerce instances Setup |  | FALSE | FALSE |  | Omnipress | In Progress | 11.11% | FALSE
Magento | Magento intances Setup |  | FALSE | FALSE |  | Omnipress | In Progress | 50% | FALSE
Shopify | Shopify instances touchpoint config and testing |  | FALSE | FALSE |  | DEP & OMNI | To-Do | 0% | TRUE
WooCommerce | WooCommerce instances touchpoint config and testing |  | FALSE | FALSE |  | DEP & OMNI | To-Do | 0% | TRUE
Magento | Magento intances touchpoint config and testing |  | FALSE | FALSE |  | DEP & OMNI | To-Do | 0% | TRUE
UPS | Initial UPS account Setup |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE | 2025-07-25
USPS | Initial USPS account Setup |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE
R+L | Initial R+L account Setup |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE
Shipping Carriers | Enable/disable applicable shipping services per carrier |  | FALSE | FALSE |  | Omnipress | Complete | 100% | FALSE
Shipping Carriers | Shipping options |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Shipping Carriers | International shipping validation |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Shipping Carriers | Configure ship from information on label | Shipping options or tradingPartner.useShipFromForShipments | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Shipping Carriers | Ship Via translations | Cross references | FALSE | FALSE |  | Omnipress | Not assigned yet | 0% | TRUE
Sockets | Validate shipnotice ATP query to consider facility and kit components |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Salesforce | Configuration for billing data export file |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Other | Custom integrations to pull orders (23 customers) |  | FALSE | FALSE |  |  |  |  | FALSE
Bright Performance Configuration (T&M)
Global Reports | Create branded shipping label report |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Global Reports | Generic Packing slip |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0% | TRUE
Company Reports/Report Builder | Company reports setup |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Report Scheduling | Report scheduling setup |  | FALSE | FALSE |  | Omnipress | Not assigned yet | 0% | TRUE
Dashboards | Dashboards setup |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Client Portal | Dashboards setup |  | FALSE | FALSE |  | DEP & OMNI | Not assigned yet | 0% | TRUE
Client Portal | User setup |  | FALSE | FALSE |  | Omnipress | Not assigned yet | 0% | TRUE
Phase 2 Items
Integrations | API integrations to retrieve billing data for Salesforce |  | TRUE | TRUE |  | DEP & OMNI |  | 0%
Packing | Cartonization at packing (cubed packing process) |  | FALSE | FALSE |  | Deposco | Not assigned yet | 0%
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE

## Test Cases - Unit
| OMNI Unit Test Cases |  | Category | % Complete
|  |  | Integrations | 0%
|  |  | Order Orchestration | 0%
|  |  | Inbound | 0%
|  |  | Inventory Management | 0%
|  |  | Outbound | 0%
|  |  | Other WMS | 0%
|  |  | Reporting | 0%
|  |  | TOTAL | 0%
Test Case ID | Category | Process Step | Step Details | Expected Outcome | Owner | Status | Comments | Setup Required
Integrations
| Integrations | Shopify - Item Pull | Execute: scheduled run at 00:00:00 nightly | Doc Store created at time of scheduled run. Doc Store status is Success, Failed, or INFO based on results of api search. Only items created or updated since last runtime of the scheduler are returned. |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with no entries into pop-ups | Doc Store created at time of manual run. Doc Store status is Success, Failed, or INFO based on results of api search. |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with one valid product ID | Doc Store created at time of manual run. Doc Store status is Success. Item is created if not already in Deposco and updated if already in Deposco. |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with multiple valid product IDs | Doc Store created at time of manual run. Doc Store status is Success. Items are created if not already in Deposco and updated if already in Deposco. |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with one invalid product ID | Doc Store created at time of manual run. Doc Store status is Failed. Item is not found by Shopify and nothing is created/updated in Deposco. |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with mix of valid/invalid product IDs | Doc Store created at time of manual run. Doc Store status is Failed. Items that are found by Shopify are created or updated in Deposco and items that are not found by Shopify are not. Failures/successes per item are visible in Doc Store Details |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to valid number greater than 0 | Doc Store created at time of manual run. Doc Store status is Success, Failed, or INFO based on results of api search. Only items created or updated in number of days entered are returned. |  | Ready to Test
| Integrations | Shopify - Item Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to invalid number (non-numeric or <=0) | Doc Store created at time of manual run. Doc Store status is |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: "How Do You Want to Handle Items?" set to "Create Item and Channel Listing If Not Found and Only Allow Channel Listing Updates" - Pull item that does NOT yet exist in Deposco | Doc Store status is Success, Failed, or INFO based on results of api search. Item and channel listing are created if returned by Shopify. |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: "How Do You Want to Handle Items?" set to "Create Item and Channel Listing If Not Found and Only Allow Channel Listing Updates" - Pull item that DOES already exist in Deposco | Doc Store status is Success, Failed, or INFO based on results of api search. Only channel listing is updated if Item is returned by Shopify. |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: "Update Pack Weight" set to true |  |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: "Map Inventory Item Fields" set to true |  |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: Throttle Group Configured |  |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: Page Size set to 250 when more than 250 products are returned in the search |  |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: Page Size set to 250 when less than or equal to 250 products are returned in the search |  |  | Ready to Test
| Integrations | Shopify - Item Pull | Criteria: "Shopify Product Status" set to "Active" only | Only "Active" products in Shopify returned and created/updated as necessary. |  | Ready to Test
| Integrations | Shopify - Item Pull | Data: Pull product with a UPC that is already tied to another item in Deposco. | Doc Store status is Failed. |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one valid order ID |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with multiple valid order IDs |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one invalid order ID |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with mix of valid and invalid order IDs |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to valid number greater than 0 |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to invalid number (non-numeric or <=0) |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Shopify Status" set to Any |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Financial Status" have Paid, Partially Refunded, and Refunded checked |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Fulfillment Status" set to Unfulfilled |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Order Number Convention" set to order_number--id |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Since ID" left blank |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Intangible Line Item Status" set to Complete |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Tag Filter" set to ______ |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Enable OMS" set to true |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Ignore Existing" set to true where order already exists |  |  | Ready to Test
| Integrations | Shopify - Order Pull | Criteria: "Ignore Existing" set to true where order does not already exist |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship full order at one time - single tracking number |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship full order at one time - multiple tracking numbers |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship partial order - single tracking number |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship partial order - multipile tracking numbers |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship kit to order products on full order at one time - single tracking number |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship kit to order products on full order at one time - multiple tracking numbers | Fail |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship order that was manually marked as fulfilled in Shopify | Fail |  | Ready to Test
| Integrations | Shopify - Ship Notice | Data: Ship quantity greater than quantity order line in Shopify | Fail |  | Ready to Test
| Integrations | Shopify - Ship Notice | Criteria: Notify Customer set to false |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Execute: Re-generate ship notice for failed transaction |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Execute: Re-process ship notice event for failed transaction |  |  | Ready to Test
| Integrations | Shopify - Ship Notice | Execute: Scheduled re-process of ship notice event for failed transactions that have been retied less than 3 times |  |  | Ready to Test
| Integrations | Shopify - Outbound Inventory Sync | Execute: Scheduled inventory sync nightly |  |  | Ready to Test
| Integrations | Shopify - Outbound Inventory Sync | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to true |  |  | Ready to Test
| Integrations | Shopify - Outbound Inventory Sync | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to false |  |  | Ready to Test
| Integrations | Shopify - Outbound Inventory Sync | Criteria: "Measure Name" set to Total ATP Qty API |  |  | Ready to Test
| Integrations | Shopify - Outbound Inventory Sync | Criteria: "Page Size" set to 200 with more than 200 items to sync |  |  | Ready to Test
| Integrations | Shopify - Outbound Inventory Sync | Criteria: "Page Size" set to 200 with less than or equal to 200 items to sync |  |  | Ready to Test
| Integrations | Quickbooks Online |  |  |  | Ready to Test
| Integrations | Quickbooks Online |  |  |  | Ready to Test
| Integrations | Netsuite |  |  |  | Ready to Test
| Integrations | Netsuite |  |  |  | Ready to Test
| Integrations | UPS - Rate Shop | Retrieve rates for domestic shipment |  |  | Ready to Test
| Integrations | UPS - Rate Shop | Retrieve rates for international shipment |  |  | Ready to Test
| Integrations | UPS - Rate Shop | Retrieve rates for Saturday Delivery shipment |  |  | Ready to Test
| Integrations | UPS - Rate Shop | Retrieve rates for all relevant Ship Vias: UPS Ground, UPS 2Day etc. |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label for all relevant Ship Vias: UPS Ground, UPS 2Day etc. |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve domestic shipping label |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve international shipping label |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label using Prepaid Freight Terms Type |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label using Collect Freight Terms Type |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label using Third Party Freight Terms Type |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label for Saturday Delivery shipment |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label for Residential shipment |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label for shipment where Insurance is required |  |  | Ready to Test
| Integrations | UPS - Shipping Label | Retrieve shipping label for shipment where Delivery Signature is required |  |  | Ready to Test
| Integrations | UPS - Shipping Documents | Retrieve Commercial Invoice for international shipment |  |  | Ready to Test
| Integrations | FedEx - Rate Shop | Retrieve rates for domestic shipment |  |  | Ready to Test
| Integrations | FedEx - Rate Shop | Retrieve rates for international shipment |  |  | Ready to Test
| Integrations | FedEx - Rate Shop | Retrieve rates for Saturday Delivery shipment |  |  | Ready to Test
| Integrations | FedEx - Rate Shop | Retrieve rates for all relevant Ship Vias: |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label for all relevant Ship Vias: FedEx Ground, FedEx Home Delivery etc. |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve domestic shipping label |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve international shipping label |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label using Prepaid Freight Terms Type |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label using Collect Freight Terms Type |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label using Third Party Freight Terms Type |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label for Saturday Delivery shipment |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label for Residential shipment |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label for shipment where Insurance is required |  |  | Ready to Test
| Integrations | FedEx - Shipping Label | Retrieve shipping label for shipment where Delivery Signature is required |  |  | Ready to Test
| Integrations | FedEx - Shipping Documents | Retrieve Commercial Invoice for international shipment |  |  | Ready to Test
Order Orchestration
| Order Orchestration | Preprocessing - Data Validations | Ship Via missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
| Order Orchestration | Preprocessing - Data Validations | Ship To Address info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
| Order Orchestration | Preprocessing - Data Validations | Trading Partner missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
| Order Orchestration | Preprocessing - Data Validations | Line Item info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
| Order Orchestration | Preprocessing - Data Validations | Multiple data validations are triggered on CO | Order goes to Review status until all data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
| Order Orchestration | Preprocessing - Data Validations | Duplicate order warning is triggered | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
| Order Orchestration | Preprocessing - Data Validations | No data validation is triggered | Order is either Back Ordered or Released automatically upon creation |  | Ready to Test
| Order Orchestration | Order Sourcing - Sourcing Group Selection | Order/order line meets ____ criteria | Order sources to Sourcing Group A based on sourcing profile. |  | Ready to Test
| Order Orchestration | Order Sourcing - Sourcing Group Selection | Order/order line meets no matching Sourcing Selection Criteria | Order goes to Review with CoNotice message that sourcing could not be completed |  | Ready to Test
| Order Orchestration | Order Routing - Routing Selection Profile | Order meets ____ criteria | Order uses Routing Profile A based on routing selection profile. |  | Ready to Test
| Order Orchestration | Order Routing - Routing Selection Profile | Order meets no matching Routing Selection Criteria | Order goes to Back Order |  | Ready to Test
| Order Orchestration | Order Release - Available Inventory | Inventory not available to fulfill entire CO in facility A | CO Back Orders |  | Ready to Test
| Order Orchestration | Order Release - Available Inventory | Inventory is available to fulfill entire CO in facility A | CO Releases to facility A and creates an SO |  | Ready to Test
| Order Orchestration | Order Management - Scheduled Routing | Scheduled re-route attempt on orders in Back Order status | Orders in Back Order automatically re-routed ever x hours. Order either stays in Back Order or moves to Released if inventory now available. |  | Ready to Test
| Order Orchestration | Order Exception Management - Reprocess | Manual Reprocess CO in Review status | Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | Ready to Test
| Order Orchestration | Order Exception Management - Reprocess | Scheduled Reprocess CO in Review status | Orders in Review automatically reprocessed every x hours. Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | Ready to Test
| Order Orchestration | Enterprise Inventory Management | Inventory by Facility | Reports execute timely and accurately for all skus |  | Ready to Test
| Order Orchestration | Inventory Segmentation - Manage Segments |  |  |  | Ready to Test
Inbound
1 | Print item label Process to print an item label if needed | 1.01 | Navigate to the "Print item label" button under Inbound in the handheld menu |  | OMNI Team | Ready to Test |  | - Printers -Printer Resources - Printer Assignment for Item Label (4X8)
|  | 1.02 | Enter or scan the item number for which a label should be printed |  | OMNI Team | Ready to Test
|  | 1.03 | A confirmation message appears: Report [Item Label (4X8)] succesfully printed. And a label is printed |  | OMNI Team | Ready to Test
2 | Receiving Process to receive new inventory | 2.01 | Navigate to the "Receiving" button under Inbound |  | OMNI Team | Ready to Test |  | - Item master data - Location master data
|  | 2.02 | Leave the Identifier field blank and hit the Sumit button |  | OMNI Team | Ready to Test
|  | 2.03 | Click on Next to confirm to continue as Blind Order. |  | OMNI Team | Ready to Test
|  | 2.04 | Scan/Enter the Item to receive. |  | OMNI Team | Ready to Test
|  | 2.05 | Key in the quantity being received |  | OMNI Team | Ready to Test
|  | 2.06 | If the pack for the item is a New Pack (flag checked at the pack level) then the user must enter dimensions for the pack. |  | OMNI Team | Ready to Test
|  | 2.07 | Keep repeating step 1.04 to 1.06 if there are multiple items in the order that the user is receiving until all items have been received. When done, you are returned to the Identifier input screen and a confirmation message appears reading "All lines have been received." |  | OMNI Team | Ready to Test
3 | UnReceiving Process to create negative receipt lines due to regular inventory receiving errors. To un-receive the inventory must be located in the Receiving location | 3.01 | Navigate to "UnReceiving" under Inbound in the handheld menu |  | OMNI Team | Ready to Test |  | - Item master data - Location master data
|  | 3.02 | Enter/scan the Blind Order number with lines to unreceive |  | OMNI Team | Ready to Test
|  | 3.03 | Scan the item to unreceive and enter quantity. A confirmation message appears indicating that the item was successfully unreceived |  | OMNI Team | Ready to Test
|  | 3.04 | If there are more items available to un-receive, the user is returned to the Item screen, where they can choose another item to unreceive, otherwise the user is returned to the inbound menu. To stop unreceiving click on "back" |  | OMNI Team | Ready to Test
|  | 3.05 | If the PO is fully unreceived, its status is updated to "New", otherwise it is updated to "Partial Receipt" |  | OMNI Team | Ready to Test
4 | CreateRMA This process allows users to associate the customer return to an existing Sales Order | 4.01 | Select Create RMA under Inbound in the handheld menu |  | OMNI Team | NOT Ready to Test |  | - Outbound configuration
|  | 4.02 | Enter the Sales Order number related to the customer return |  | OMNI Team | NOT Ready to Test
|  | 4.03 | Choose if returning ALL or PARTIAL |  | OMNI Team | NOT Ready to Test
|  | 4.04 | Select Return All to create an RMA for all items in the order or Partial Return to indicate specific items and quantities that are being returned. |  | OMNI Team | NOT Ready to Test
|  | 4.05 | If user selects Partial return, all items in the order are displayed |  | OMNI Team | NOT Ready to Test
|  | 4.06 | Select the item being returned, click Next, and enter the quantity in the next screen |  | OMNI Team | NOT Ready to Test
|  | 4.07 | Repeat if more items need to be included in the RMA, otherwise click on Finish. The RMA is created |  | OMNI Team | NOT Ready to Test
|  | 4.08 | Click on "Add Note" and select reason for return from the drop down list. (This list can be configured to show the values you need) Optionally enter a reason in the blank box and click "Save". |  | OMNI Team | NOT Ready to Test
|  | 4.09 | Select Finish - will bring you back to the main returns screen. |  | OMNI Team | NOT Ready to Test
5 | Receive an RMA Process to receive inventory for previously created RMAs | 5.01 | Select "Returns Receiving" from Inbound menu on Handheld |  | OMNI Team | NOT Ready to Test |  | - Outbound configuration
|  | 5.02 | Enter/Scan the Customer Return number created in the CreateRMA process. |  | OMNI Team | NOT Ready to Test
|  | 5.03 | A list of items to receive appear on the screen. Scan/Enter the Item to receive. |  | OMNI Team | NOT Ready to Test
|  | 5.04 | Key in the quantity being received |  | OMNI Team | NOT Ready to Test
|  | 5.05 | Repeat steps 5.03 - 5.04 if there are multiple items to receive. When done, you are returned to the Identifier input screen and a confirmation message appears reading "All lines have been received." |  | OMNI Team | NOT Ready to Test
6 | Receive a Blind Customer Return Process to receive customer returns without RMA creation, AKA blind customer returns | 6.01 | Navigate to the "Returns Receiving" button under Inbound |  | OMNI Team | Ready to Test |  | - Item master data - Location master data
|  | 6.02 | Leave the Identifier field blank and hit the Sumit button |  | OMNI Team | Ready to Test
|  | 6.03 | Click on Next to confirm to continue as Blind Order. |  | OMNI Team | Ready to Test
|  | 6.04 | Scan/Enter the Item to receive. |  | OMNI Team | Ready to Test
|  | 6.05 | Key in the quantity being received |  | OMNI Team | Ready to Test
|  | 6.06 | If the pack for the item is a New Pack (flag checked at the pack level) then the user must enter dimensions for the pack. |  | OMNI Team | Ready to Test
|  | 6.07 | Keep repeating the steps above if there are multiple items in the order that the user is receiving until all items have been received. When done, you are returned to the Identifier input screen and a confirmation message appears reading "All lines have been received." |  | OMNI Team | Ready to Test
7 | Putaway process - Move Item This process is used to putaway stock after receiving. It can also be used for general inventory movement | 7.01 | Navigate to "Move Item" under Inbound on handheld MainMenu |  | OMNI Team | Ready to Test |  | - Item master data - Location master data - Storage records for the item to display suggested putaway locations
|  | 7.02 | Enter/scan the location that contains the inventory (stock units) you want to move. For putaway after receiving, the source location is the Receiving location. |  | OMNI Team | Ready to Test
|  | 7.03 | A listbox of available SKUs to move display (skus in the scanned location). User must scan or select the item number to move. |  | OMNI Team | Ready to Test
|  | 7.04 | User enters quantity of how much stock to move |  | OMNI Team | Ready to Test
|  | 7.05 | User is prompted to putaway screen and a listbox of suggested locations is displayed. The suggested locations should be ordered by the following logic agreed upon in the MDD: 1) Locations with Storage record (min/max) for that item where the current inventory is below the maximum value defined. 2) Permanent locations that do not have a Storage record for the item but that contain inventory for the item User must scan or enter a location in which to put the stock away. |  | OMNI Team | Ready to Test
|  | 7.06 | If user wants to continue moving items from this location, user can repeat steps 7.03-7.05 |  | OMNI Team | Ready to Test
|  | 7.07 | Otherwise, user can exit the process |  | OMNI Team | Ready to Test
Inventory Management
1 | Move Stock This process can be used for general inventory movement e.g changing an item from location A to location B. This process enables you to use a cart and select multiple SKUs from different source locations and move them to multiple destination locations. | 1.01 | Navigate to "Move Stock" under Inventory on the handheld menu |  | OMNI Team | Ready to Test |  | - Item master data - Location master data - Container master data
|  | 1.02 | User scans the cart in which they want to put the stock to move |  | OMNI Team | Ready to Test
|  | 1.03 | Enter or scan the location with the stock to move |  | OMNI Team | Ready to Test
|  | 1.04 | A listbox of available SKUs at the location displays. User must scan or select item to move to cart |  | OMNI Team | Ready to Test
|  | 1.05 | Select Pack UOM and enter the quantity to move to the cart and select Submit |  | OMNI Team | Ready to Test
|  | 1.06 | Repeat steps 2.04-2.05 to select more items from the same location, if applicable |  | OMNI Team | Ready to Test
|  | 1.07 | When finished moving items from the source location to the cart, select Move Source Screen |  | OMNI Team | Ready to Test
|  | 1.08 | User is given a summary of the number of unique Skus and the total quantity of items in the cart. If the user wants to move more items onto their cart from a different source location, the user can scan another source location and repeat the same steps above (2.03-2.07). |  | OMNI Team | Ready to Test
|  | 1.09 | Otherwise, if the user is ready to move the stock in the cart to destination locations, then select the "Move" button |  | OMNI Team | Ready to Test
|  | 1.1 | User enters the quantity and the item to move |  | OMNI Team | Ready to Test
|  | 1.11 | User enters or scan a location to move the stock. |  | OMNI Team | Ready to Test
|  | 1.12 | User repeats 2.10-2.11 if more items need to be moved. |  | OMNI Team | Ready to Test
|  | 1.13 | To move any remaining stock for a single item, the user can select "All" and then scan the destination location of where the stock should be moved |  | OMNI Team | Ready to Test
|  | 1.14 | When all stock has been moved successfully, a message displays on menu saying "All Items Moved." |  | OMNI Team | Ready to Test
2 | Create Replenishment Tasks (scheduler) Process to generate replen tasks based on configured criteria. All replenishment config must be ready for this to work as expected. | 2.01 | User navigates to the 'Scheduler' entity and select "Create Replenishment Tasks". |  | OMNI Team | Ready to Test |  | - Item master data - Location master data - Replen from locations - Storage Type: Reserve Storage - Status: Ready - Reserve flag is enabled - Replen to locations - Storage Type: Split Case Picking - Storage records for locations to replenish
|  | 2.02 | Run the scheduler manually by clicking on the "Run" button located at the top right of the screen. |  | OMNI Team | Ready to Test
|  | 2.03 | Replen tasks will be generated to fill the locations to the maximum defined in the storage records. |  | OMNI Team | Ready to Test
3 | Perform Replenishment tasks Process to replenish picking locations from reserve locations after replenishments tasks have been created | 3.01 | Naviagte to Inventory in the handheld menu. Then select Replenishments and then Directed Replenishments |  | OMNI Team | Ready to Test |  | - Item master data - Location master data - Container master data
|  | 3.02 | Scan/enter the name of the picking cart that will be used to move the inventory from picking locations to the destination locations |  | OMNI Team | Ready to Test
|  | 3.03 | If there are open replenishment tasks, the user is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next |  | OMNI Team | Ready to Test
|  | 3.04 | The user will be taken to "Picking Screen" to scan and pick the item and quantity to replenish. |  | OMNI Team | Ready to Test
|  | 3.05 | Repeat to complete all picks needed for all replenishment tasks. |  | OMNI Team | Ready to Test
|  | 3.06 | Once all picks are complete or if the user selects 'Cart full', the user is directed to "Replenishment Entry Screen" to replenish the picking locations with the picked items. |  | OMNI Team | Ready to Test
|  | 3.07 | The user will be taken to "Pull Summary Screen" if any replenishment tasks are pending, else the user exits the process and a message is thrown saying: "Nothing to Replenish" |  | OMNI Team | Ready to Test
4 | Create and perform Replenishement Tasks (select specific locations) Process to generate replenishment tasks for locations that the user selects, and immediatly complete the tasks | 4.01 | In the handheld menu go to inventory, the click on Replenishments, then on Manual replenishments |  | OMNI Team | Ready to Test |  | - Item master data - Location master data - Replen from locations - Storage Type: Reserve Storage - Status: Ready - Reserve flag is enabled - Replen to locations - Storage Type: Split Case Picking - Storage records for locations to replenish
|  | 4.02 | Scan the picking cart to use for transporting the stock from source locations to destination locations |  | OMNI Team | Ready to Test
|  | 4.03 | Scan the locations that require to be replenished |  | OMNI Team | Ready to Test
|  | 4.04 | When you finish identifying the locations that require replenishment, select Done |  | OMNI Team | Ready to Test
|  | 4.05 | If no available inventory to replenish is found, then you are returned to the Move Type Screen and a "Nothing to replenish message appears on the screen." If available inventory is found, then the Pull Summary Screen appears with a list of available inventory that can be used to replenish the scanned locations. |  | OMNI Team | Ready to Test
|  | 4.06 | Select Next. A replenishment task is generated for each location and item that require replenishment and where there is available stock. |  | OMNI Team | Ready to Test
|  | 4.07 | Perform all replenishments following the same logic as in the Directed Replenishments process |  | OMNI Team | Ready to Test
5 | Unassign Replenishment Tasks Process to unassign replenishment tasks from your user | 5.01 | Select "Unassign My Tasks" button under Inventory -> Replenishments |  | OMNI Team | Ready to Test
|  | 5.02 | Screen message confirms that the user has been unassigned from their tasks |  | OMNI Team | Ready to Test
|  | 5.03 | The user is unassigned from replenishment tasks that are not in Complete status |  | OMNI Team | Ready to Test
6 | Replenishements - Cart is full | 6.01 | Use the "Directed Replenishment" or "Manual Replenishment" process |  | OMNI Team | Ready to Test
|  | 6.02 | If the container/cart is full before you finish picking all items, then select Cart Is Full instead of picking another item |  | OMNI Team | Ready to Test
|  | 6.03 | The remaining pick tasks are skipped and the user is asked to replenish only the locations for which picks have been completed |  | OMNI Team | Ready to Test
|  | 6.04 | After putting away the stock, you are prompted to continue picking stock for the assigned replenishment tasks that you could not complete. |  | OMNI Team | Ready to Test
7 | Replenishments picking exceptions (no stock/stock damaged) Process to create a picking exception during replenshments when the user is unable to pick the items from the source location | 7.01 | Use the "Directed Replenishment" or "Manual Replenishment" process |  | OMNI Team | Ready to Test
|  | 7.02 | In the Picking screen, select "Exception" |  | OMNI Team | Ready to Test
|  | 7.03 | The user is directed to "Replenishment Picking Exception" screen |  | OMNI Team | Ready to Test
|  | 7.04 | Select a either No Stock or Stock Damaged to exception from the drop down list and hit Exception |  | OMNI Team | Ready to Test
|  | 7.05 | If available stock is found in other reserve locations, then a new replenishment task is generated, and you are prompted to pick the stock from the alternate location. If other replenishment tasks have been assigned to you, then you may be directed to pick stock for those tasks before picking stock for the newly generated task. |  | OMNI Team | Ready to Test
|  | 7.06 | The stock unit is set to On Hold status. |  | OMNI Team | Ready to Test
|  | 7.07 | A cycle count with a type of Picking Audit is generated for the location, if cycle counts are enabled for the location. |  | OMNI Team | Ready to Test
8 | Replenishments picking exceptions (stock unreachable) Process to create a picking exception during replenshments when the user is unable to pick the items from the source location | 8.01 | Use the "Directed Replenishment" or "Manual Replenishment" process |  | OMNI Team | Ready to Test
|  | 8.02 | In the Picking screen, select "Exception" |  | OMNI Team | Ready to Test
|  | 8.03 | The user is directed to "Replenishment Picking Exception" screen |  | OMNI Team | Ready to Test
|  | 8.04 | Select Stock Unreachable and hit Exception |  | OMNI Team | Ready to Test
|  | 8.05 | The replenishment task is skipped and the user is taken to the next replenishment task |  | OMNI Team | Ready to Test
|  | 8.06 | Replenishment tasks where Stock Unreachable is selected are skipped, and the task is NOT marked with a status of "Exception", since the user is still expected to pick from this location eventually |  | OMNI Team | Ready to Test
9 | Replenishments putaway exception Proces to create a putaway exception when the user is unable to put away items to the destination location | 9.01 | Use the "Directed Replenishment" or "Manual Replenishment" process |  | OMNI Team | Ready to Test
|  | 9.02 | If you cannot put away (replenish) the specified quantity of items to the destination location during replenishment, then select Exception on the Replenish Entry Screen. |  | OMNI Team | Ready to Test
|  | 9.03 | The Replenishment Putaway Exception screen appears. Select LOCATION FULL from the list. Then click on exception |  | OMNI Team | Ready to Test
|  | 9.04 | The replenishment task is set to a status of Destination Full. |  | OMNI Team | Ready to Test
|  | 9.05 | A new (reverse) replenishment task is created to return the stock to the source reserve location. |  | OMNI Team | Ready to Test
|  | 9.06 | You are returned to the Replenish Entry Screen and are prompted to scan the source reserve location, the item, and the quantity that is being returned. (If other replenishment tasks have been assigned to you, then you may be directed to put away stock for those tasks before returning stock to the source reserve location for the newly generated task.) |  | OMNI Team | Ready to Test
10 | On Demand Location Cycle Count This process allows a user to scan a location to cycle count and immediatly begin counting. The user will be required to count all items in the location. | 10.01 | Select "On Demand Cycle Count" from Inventory menu |  | OMNI Team | Ready to Test |  | - Item master data - Cycle count flag is enabled - Location master data - Cycle count flag is enabled
|  | 10.02 | User will be prompted to enter a location and priority for the task (1-10 w/1 being highest priority). Priority defaults to 5 if left empty. |  | OMNI Team | Ready to Test
|  | 10.03 | Cycle count task is created and the user immediately begins task. |  | OMNI Team | Ready to Test
|  | 10.04 | User will be shown a list box with items in the location to count |  | OMNI Team | Ready to Test
|  | 10.05 | Scan first SKU to count and hit enter |  | OMNI Team | Ready to Test
|  | 10.06 | Enter the quantity physically counted. The screen never shows the quantity recorded in the system. |  | OMNI Team | Ready to Test
|  | 10.07 | If the quantity entered matches the quantity recorded in the system, the user be returned to the previous screen with the list of items to be counted. |  | OMNI Team | Ready to Test
|  | 10.08 | If a different quantity than what is recorded in the system is entered, the user will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity recorded in the system. |  | OMNI Team | Ready to Test
|  | 10.09 | After the item has been fully counted in a location, "**" will appear left to the item number in the screen |  | OMNI Team | Ready to Test
|  | 10.1 | User will be returned to the item listbox screen to select another item at that location if necessary. When done counting all items, select "Next Location" |  | OMNI Team | Ready to Test
11 | Create Item Cycle Count via Scheduler | 11.01 | Run the scheduler "Create Cycle Count Tasks by Item" under SchedulerTask application (under Setup in the application Menu) |  | OMNI Team | Ready to Test
|  | 11.02 | Cycle count tasks for items that require a cycle count based on the configured critetia will appear in the Cycle Count Queue table with status NEW |  | OMNI Team | Ready to Test
12 | Create Item Cycle Count using the handheld | 12.01 | Identify the item(s) to create cycle counts for |  | OMNI Team | Ready to Test
|  | 12.02 | In the handheld menu go to Inventory and then to Create Item Cycle Count |  | OMNI Team | Ready to Test
|  | 12.03 | Enter the item number/UPC and priority (1-10 w/1 being highest priority) for the cycle count. Priority defaults to 5 if left empty. |  | OMNI Team | Ready to Test
|  | 12.04 | Hit enter |  | OMNI Team | Ready to Test
|  | 12.05 | Repeat steps if more items need to be cycle counted. |  | OMNI Team | Ready to Test
|  | 12.06 | A screen message will show saying "The Item [item] is schedluled for Cycle Count". The tasks have been created and users can start couting using the Perform Item Cycle Count Process |  | OMNI Team | Ready to Test
|  | 12.07 | Cycle count task(s) with status NEW should be generated for the specified location with the specified priority. |  | OMNI Team | Ready to Test
13 | Perform Item Cycle Count | 13.01 | Select "Perform Item Cycle Count" button in handheld menu from Inventory |  | OMNI Team | Ready to Test
|  | 13.02 | Scan or enter any starting location and hit enter. This can be any location, as the system will direct the user to the closest location for which a cycle count task exists |  | OMNI Team | Ready to Test
|  | 13.03 | User is directed to the nearest location that has a cycle count task waiting to be executed |  | OMNI Team | Ready to Test
|  | 13.04 | User scans the location they're directed to |  | OMNI Team | Ready to Test
|  | 13.05 | User will be shown a list box with items in location needing to be cycle counted. |  | OMNI Team | Ready to Test
|  | 13.06 | User will scan SKU and hit enter |  | OMNI Team | Ready to Test
|  | 13.07 | On the next screen, user will select the pack type and enter the quantity they counted |  | OMNI Team | Ready to Test
|  | 13.08 | If they enter the quantity that is in the system, they'll be returned to the previous screen with the list of items to be counted. |  | OMNI Team | Ready to Test
|  | 13.09 | If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected. User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity recorded in the system. |  | OMNI Team | Ready to Test
|  | 13.1 | After each item has been counted in a location, ** will appear left to the item number |  | OMNI Team | Ready to Test
|  | 13.11 | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks |  | OMNI Team | Ready to Test
|  | 13.12 | The task in CycleCountQueue will be changed to "Completed" status. |  | OMNI Team | Ready to Test
|  | 13.13 | Tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review if the counted quantity differed from the quantity in the sytem and if an item that is in the system wasn't counted. |  | OMNI Team | Ready to Test
14 | Manage Cycle Count Variances | 14.01 | User (typically a supervisor or manager) will navigate the "Manage Cycle Count Variances" in the desktop UI |  | OMNI Team | Ready to Test
|  | 14.02 | A list of variances is displayed. A variance recors is created any time the counted quantity of an item at a specific location differs from the quantity recorded in the sytem |  | OMNI Team | Ready to Test
|  | 14.03 | For each record you will see the item, counted qty, variance qty and other relevant data. The columns listed can be adjusted. |  | OMNI Team | Ready to Test
|  | 14.04 | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted). |  | OMNI Team | Ready to Test
15 | Physical Count | 15.01 | Start physical count (Admin user): Select "Physical Count Admin" from Admin Menu. Enter process name and keep the "Controlled" box unchecked if user wants to bypass the approval needed for "Manage Cycle Count Variances" and click "Start". Otherwise, select "controlled" to require variance approval. |  | OMNI Team | Ready to Test
|  | 15.02 | Message will appear saying "[controlled/non-controlled] Physical Count Activity [process name] is started on [date time] and is active". |  | OMNI Team | Ready to Test
|  | 15.03 | Perform physical count (any user): Select "Physical Count" button from Inventory Menu |  | OMNI Team | Ready to Test
|  | 15.04 | Scan/Enter a location |  | OMNI Team | Ready to Test
|  | 15.05 | User counts items in location |  | OMNI Team | Ready to Test
|  | 15.06 | To go onto the next location, User can select "Next Location" |  | OMNI Team | Ready to Test
|  | 15.07 | If physical count activity is non-controlled, user is taken to physical count summary screen and can click "Recount" or "Apply" before finally confirming. |  | OMNI Team | Ready to Test
|  | 15.08 | Finish physical count. (Admin user): When done with physical count activity, navigate to "Physical Count Admin" button and click "Finish Physical Count Activity" |  | OMNI Team | Ready to Test
|  | 15.09 | User will be returned to MainMenu and will display a message saying "[controlled/non-controlled] Physical Count Activity [process name] is finished at [date time]". |  | OMNI Team | Ready to Test
16 | Adjust Inventory Consume by item | 16.01 | Select "Adjust Inventory" from the Admin menu |  | OMNI Team | Ready to Test
|  | 16.02 | Scan/key in Location where stock will be decremented |  | OMNI Team | Ready to Test
|  | 16.03 | Select "Consume by Item" |  | OMNI Team | Ready to Test
|  | 16.04 | Scan Item to consume |  | OMNI Team | Ready to Test
|  | 16.05 | Enter quantity of item's Stock Unit you want to consume. Hit next. A confirmation message appears |  | OMNI Team | Ready to Test
|  | 16.06 | If you have more than one item that you want to consume in the same location repeat steps |  | OMNI Team | Ready to Test
|  | 16.07 | Once finished, click Confirm |  | OMNI Team | Ready to Test
|  | 16.08 | Review items being consumed and select the reason code from the drop down |  | OMNI Team | Ready to Test
|  | 16.09 | Once final reviewing all items, click Commit |  | OMNI Team | Ready to Test
|  | 16.1 | User will be returned to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". |  | OMNI Team | Ready to Test
17 | Adjust Inventory Create inventory | 17.01 | Select "Adjust Inventory" from the Admin menu |  | OMNI Team | Ready to Test
|  | 17.02 | Scan/key in Location |  | OMNI Team | Ready to Test
|  | 17.03 | Select "Create Inventory" |  | OMNI Team | Ready to Test
|  | 17.04 | Select business unit from drop down |  | OMNI Team | Ready to Test
|  | 17.05 | Scan Item SKU to create |  | OMNI Team | Ready to Test
|  | 17.06 | Enter quantity of items to create and select pack type. User can optionally enter LPN # where the stock needs to be created. |  | OMNI Team | Ready to Test
|  | 17.07 | If you have more than one item's SU you want to create, click next and repeat steps |  | OMNI Team | Ready to Test
|  | 17.08 | Once finished, click Confirm |  | OMNI Team | Ready to Test
|  | 17.09 | Review items being created and select the reason code from the drop down |  | OMNI Team | Ready to Test
|  | 17.1 | Once final reviewing all items, click Commit |  | OMNI Team | Ready to Test
|  | 17.11 | User is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" |  | OMNI Team | Ready to Test
18 | Adjust Inventory Consume all in location | 18.01 | Select "Adjust Inventory" from the Inventory menu |  | OMNI Team | Ready to Test
|  | 18.02 | Scan/key in Location |  | OMNI Team | Ready to Test
|  | 18.03 | Select "Consume All in Location" |  | OMNI Team | Ready to Test
|  | 18.04 | Once final reviewing all items, click Commit |  | OMNI Team | Ready to Test
|  | 18.05 | User will be returned to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". |  | OMNI Team | Ready to Test
19 | Kit to Stock This process is used to assemble kit products that will be picked already built | 19.01 | Users navigate to Inventory in the handheld menu and select Kit to Stock |  | OMNI Team | Ready to Test |  | - Item master data - Component master data - Printer Assignment for Item Label (4x8)
|  | 19.02 | Enter the location where kitting will take place and the Kit item number |  | OMNI Team | Ready to Test
|  | 19.03 | In the Kit Item Config screen, a suggested quantity is displayed based on the total quantity of item components at the kitting location. Enter the quantity ot build in the Kit Qty field. |  | OMNI Team | Ready to Test
|  | 19.04 | The Kitting Summary screen shows the previously entered Build Quantity and details for the kit components at the kitting location. |  | OMNI Team | Ready to Test
|  | 19.05 | Optionally print item labels and enter the number of copies required. |  | OMNI Team | Ready to Test
Outbound
| Outbound | Outbound Order Management - Address Validation | Process order that fails address validation with suggested change | Sales Order goes to status "Hold - AV" and Order Header Note created with suggested address changes - POI Done flag is set to true |  | Ready to Test
| Outbound | Outbound Order Management - Address Validation | Process order that fails address validation with NO suggested change | Sales Order goes to status "Hold - AV" and Order Header Note created indicating no suggestions could be found - POI Done flag is set to true |  | Ready to Test
| Outbound | Outbound Order Management - Address Validation | Process order that passes address validation | Sales Order stays in New status - POI Done flag is set to true |  | Ready to Test
| Outbound | Outbound Order Management - POI Done | POI runs successfully | POI Done flag is set to true |  | Ready to Test
| Outbound | Outbound Order Management - POI Done | POI fails | POI Done flag stays false. Waving does not run on the order. |  | Ready to Test
| Outbound | Outbound Order Management - Re-run POI | Scheduler re-runs POI on orders where POI Done is not true |  |  | Ready to Test
| Outbound | Pickwave Management - Waving Execution | Manually wave one order | Order selected remains in New, moves to Back Ordered, or moves to Released based on profile match and inventory evaluation |  | Ready to Test
| Outbound | Pickwave Management - Waving Execution | Manually wave multiple orders | All orders selected remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation |  | Ready to Test
| Outbound | Pickwave Management - Waving Execution | Scheduled wave multiple orders | All orders in New or Back Ordered status are waved in order of created date ascending. All orders remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation. |  | Ready to Test
| Outbound | Pickwave Management - Pickwave Profile | Order matches large order profile conditions | Order waved on Large Order Wave - can only be picked in Single Scan Picking |  | Ready to Test
| Outbound | Pickwave Management - Pickwave Profile | Order matches singles order profile conditions | Order waved on Singles Wave - can only be picked in Single Scan Picking |  | Ready to Test
| Outbound | Pickwave Management - Pickwave Profile | Order matches multis order profile conditions | Order waved on Multis Wave - can only be picked in Batch Picking |  | Ready to Test
| Outbound | Pickwave Management - Pickwave Profile | Order matches no waving criteria | Order stays in New or Back Ordered status |  | Ready to Test
| Outbound | Pickwave Management - Back Order Management | Order waved has sufficient inventory available to release | Order moves to Released and is assigned a Pickwave with work group and pick tasks |  | Ready to Test
| Outbound | Pickwave Management - Back Order Management | Order waved as no sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
| Outbound | Pickwave Management - Back Order Management | Order waved as partially sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Singles Picking |  |  |  | Ready to Test
| Outbound | Picking - Multis Picking |  |  |  | Ready to Test
| Outbound | Picking - Multis Picking |  |  |  | Ready to Test
| Outbound | Picking - Multis Picking |  |  |  | Ready to Test
| Outbound | Picking - Multis Picking |  |  |  | Ready to Test
| Outbound | Picking - Multis Picking |  |  |  | Ready to Test
| Outbound | Outbound - Packing and Shipping |  |  |  | Ready to Test
| Outbound | Outbound - Cartonization |  |  |  | Ready to Test
| Outbound | Outbound - Rate Shopping |  |  |  | Ready to Test
| Outbound | Outbound - EDI Fulfillment |  |  |  | Ready to Test
Other WMS
| Other WMS | Other WMS - Transfer Orders |  |  |  | Ready to Test
| Other WMS | Other WMS - Shipping Documents/Labels |  |  |  | Ready to Test
| Other WMS | Other WMS - 3PL Billing |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
| Other WMS |  |  |  |  | Ready to Test
Reporting
| Reporting | Dashboard - Inbound | -- | Report returns timely and accurately for customer needs
| Reporting | Dashboard - Inventory Management Dashboard | -- | Report returns timely and accurately for customer needs
| Reporting | Dashboard - Outbound | -- | Report returns timely and accurately for customer needs
| Reporting | Dashboard - User Performance | -- | Report returns timely and accurately for customer needs
| Reporting | Report Builder - | -- | Report returns timely and accurately for customer needs

## Test Cases - End to End
OMNI End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 0%
Category | Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Inbound | Receive PO full | Ready to Test | OMNI
Inbound | Receive Partial PO | Ready to Test | OMNI
Inbound | Create RMA from shipped SO and receive in full | Ready to Test | OMNI
Inbound | Create RMA from shipped SO and receive partially | Ready to Test | OMNI
Inbound | Create RMA from shipped SO and do not receive immediately | Ready to Test | OMNI
Inbound | Unreceive full PO | Ready to Test | OMNI
Inbound | Unrecieve partial PO | Ready to Test | OMNI
Inbound | Blind receive additional units found after receiving | Ready to Test | OMNI
Inbound | Over receive PO | Ready to Test | OMNI
Inbound | Over receive RMA | Ready to Test | OMNI
Inbound | Putaway single item containers | Ready to Test | OMNI
Inbound | Putaway mixed item containers | Ready to Test | OMNI
Inbound | Putaway containers to reserve locations | Ready to Test | OMNI
Inbound | Putaway containers to pickable locations | Ready to Test | OMNI
Inbound | Putaway loose stock to reserve locations | Ready to Test | OMNI
Inbound | Putaway loose stock to pickable locations | Ready to Test | OMNI
Outbound
Outbound | Fulfill "large" orders | Ready to Test | OMNI
Outbound | Fulfill single unit orders | Ready to Test | OMNI
Outbound | Fulfill multi unit orders | Ready to Test | OMNI
Outbound | Fulfill international orders | Ready to Test | OMNI
Outbound | Fulfill domestic orders | Ready to Test | OMNI
Outbound | Exception a pick task for "large" order | Ready to Test | OMNI
Outbound | Exception a pick task for a single unit order | Ready to Test | OMNI
Outbound | Exception a pick task for a multi unit order | Ready to Test | OMNI
Outbound | Cancel an order that has not yet been released | Ready to Test | OMNI
Outbound | Cancel an order that has been released but not picked | Ready to Test | OMNI
Outbound | Cancel an order that has been picked but not packed or shipped | Ready to Test | OMNI
Outbound | Cancel an order that has been packed but not shipped | Ready to Test | OMNI
Outbound | Roll back an order that has been shipped and cancel it | Ready to Test | OMNI
Outbound | Roll back an order that has not been shipped and re-ship | Ready to Test | OMNI
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Ready to Test | OMNI
Inventory Management | Perform scheduled cycle counts by item | Ready to Test | OMNI
Inventory Management | Perform on demand cycle counts by location | Ready to Test | OMNI
Inventory Management | Perform scheduled replenishment tasks | Ready to Test | OMNI
Inventory Management | Perform on demand replenishment tasks | Ready to Test | OMNI
Inventory Management | Over-replenish | Ready to Test | OMNI
Inventory Management | Perform exception during replenishment | Ready to Test | OMNI

## Go-Live Cutover Check List
0 |  |  | Phase | Team | Dept | Owner | % Complete | Step | Description | Days Remaining | Start | Finish | Delivery date
|  |  | 00: Configuration | DEP | Pros | Deposco | 0% | Configuration | Inbound Configuration and test cases |  | 2025-08-04 | 2025-08-08 | 2025-08-18 | 18 | 10
| -29 | -7 | 00: Configuration | OMNI | Warehouse | Omni | 0% | Configuration | Inbound Configuration: Unit Testing |  | 2025-08-18 | 2025-08-21
|  |  | 00: Configuration | DEP | Pros | Deposco |  | Configuration | Inventory Configuration and test cases |  | 2025-08-11 | 2025-08-15 | 2025-08-18 | 18 | 18
|  |  | 00: Configuration | OMNI | Warehouse | Omni |  | Configuration | Inventory Configuration: Unit Testing |  | 2025-08-18 | 2025-08-21
|  |  | 00: Configuration | DEP/OMNI | DEP/OMNI | Omni |  | Configuration | Socket Configuration |  | 2025-07-21 | 2025-08-15
|  |  | 00: Configuration | DEP | Pros | Deposco |  | Configuration | Socket Configuration: Demo/Unit test cases |  | 2025-08-18 | 2025-08-22 | 2025-09-25 | 33 | 33
|  |  | 00: Configuration | OMNI | Warehouse | Omni |  | Configuration | Socket Configuration: Unit Testing |  | 2025-08-25 | 2025-08-10
|  |  | 00: Configuration | DEP | Pros | Deposco |  | Configuration | Outbound Configuration and test cases |  | 2025-08-18 | 2025-08-29 | 2025-09-01 | 54 | 54
|  |  | 00: Configuration | OMNI | Warehouse | Omni |  | Configuration | Outbound Configuration: Unit Testing |  | 2025-09-01 | 2025-09-10
|  |  | 00: Configuration | DEP | Pros | Deposco |  | Configuration | Reporting Configuration |  | 2025-08-25 | 2025-08-29 | 2025-09-01 | 34 | 34
| -22 | -2 | 00: Configuration | OMNI | Warehouse | Omni | 0% | Configuration | Reporting Configuration: Unit Testing |  | 2025-09-01 | 2025-09-10
|  |  | 00: Configuration | DEP/OMNI | DEP/OMNI | Deposco |  | Configuration | Shipping Carriers validation and unit test cases |  | 2025-08-25 | 2025-08-29 | 2025-09-01 | 31 | 31
| -20 | -3 | 00: Configuration | OMNI | Warehouse | Omni | 0% | Configuration | Shipping Carriers: Unit Testing |  | 2025-09-01 | 2025-09-05
|  |  | 00: Configuration | DEP | Pros | Deposco |  | Configuration | Billing Configuration and test cases |  | 2025-09-01 | 2025-09-05 | 2025-09-08 | 40
| -20 | -3 | 00: Configuration | OMNI | Warehouse | Omni | 0% | Configuration | Billing Configuration: Unit Testing |  | 2025-09-08 | 2025-09-12
| -16 | 0
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0 | Validate UA Data | Locations uploaded and validated. Location barcodes in place |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0 | Validate UA Data | Zones uploaded and validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Storages uploaded and validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0 | Validate UA Data | Containers uploaded and validated. Labels in place |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Items, Packs, UPCs uploaded and validated. Item labels in place |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Shipping Doors uploaded and validated. Optional labels in place |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Components uploaded and validated |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Item UPCs uploaded and validated. Multiple UPC scenario addressed |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0 | Validate UA Data | Order Release Profiles set up |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Automation set up(if needed) and validated |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Shipping Service Cross References set up and validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Channel Listings established and validated for Shopping Carts |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 90% | Validate UA Data | Business Units uploaded and validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Sample PROD Stockunits uploaded and validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Document printers validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Label printers validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Resources configured for Printers and reports assigned |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Packing slips validated |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Shipping Options created and validated |  |  | 2025-09-12
| -14 | -3 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Wifi tested and connected on each Handheld device |  |  | 2025-09-12
| -9 | 0 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Users created and able to log into UA environment (Omnipress) |  |  | 2025-09-12
|  |  | 02: Pre-UAT | OMNI | Warehouse |  | 0 | Validate UA Data | Users created and able to log into UA environment (Customers) |  |  | 2025-09-12
| -9 | 0 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Handhelds signed in to UA environment |  |  | 2025-09-12
| -9 | 0 | 02: Pre-UAT | OMNI | Warehouse |  | 0% | Validate UA Data | Import live orders into Deposco UA environment |  |  | 2025-09-12
| -9 | 0 | [8 empty] | 2023-03-18
| -9 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -8 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -8 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -8 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -8 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -7 | -1 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -7 | -1 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -7 | -1 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -7 | -1 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -5 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
|  |  | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -5 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -5 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -7 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -9 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -6 | 0 | 03: UAT | OMNI | Warehouse |  | 0% | Validate UA Data
| -6 | 0 | [8 empty] | 2023-03-23
no | -4 | 0 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Inbound UAT: Validate Receiving Process for all BUs
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Inbound UAT: Validate Putaway Process for all BUs
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | SOPs | Inbound UAT: Create SOPs for floor users
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Inventory UAT: Validate Replenishments Process
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Inventory UAT: Validate Cycle Counting Process
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Inventory UAT: Validate Adjust Inventory Process
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | SOPs | Inventory UAT: Create SOPs for floor users
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Outbound UAT: Validate POI/Waving Process
|  |  | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Outbound UAT: Review Scheduler Frequencies
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Outbound UAT: Validate Picking Process
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Outbound UAT: Validate Packing Process
|  |  | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Outbound UAT: Validate Freight Processes
no | -4 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | SOPs | Outbound UAT: Create SOPs for floor users
no | -2 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Billing UAT: Validate Billing Process
no | -2 | -2 | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | SOPs | Billing UAT: Create SOPs for billing users
|  |  | 04: Pre-Cutover | OMNI | Warehouse |  | 0% | User Training | Integrations UAT: Validate/Test integration schedulers
no | -2 | -2
no | -2 | -2 | 05: Go No-Go | DEP | Pros |  | 0% | Code Freeze | Deposco: Code Freeze
no | -2 | -2 | 05: Go No-Go | DEP / OMNI | DEP / OMNI |  | 0% | Go No-Go Decision | Reflect on UAT and determine Go-Live Readiness
no | -2 | -2 | 05: Go No-Go | DEP / OMNI | DEP / OMNI |  | 0% | Go-Live Debrief | Establish Go-Live Communication Channel
|  |  | 06: Cutover | DEP | DevOps |  | 0% | Validate Prod Data | Stand up Production Environment from UA configuration and Master Data
no | -2 | -1 | 06: Cutover | DEP | Pros |  | 0% | Validate Prod Data | Validate Production Environment is clean
no | -2 | -2 | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Locations uploaded and validated
no | -2 | -2 | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Storages uploaded and validated
no | -2 | -2 | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Containers uploaded and validated
no | -2 | -2 | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Items, Packs and Channel Listings uploaded and validated
no | -2 | -1 | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Item UPCs uploaded and validated
|  |  | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Components for kits uploaded and validated
|  |  | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Channel Listings uploaded and validated
|  |  | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Validate Prod Data | Trading Partners uploaded and validated
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Document printers validated
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Label printers validated
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Resources configured for Printers and reports assigned
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Wifi tested and connected on each Handheld device
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Weight scales validated
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Users created and able to log into PROD environment
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Verify user permissions and groups assigned properly
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Handhelds signed into PROD environment
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Validate Prod Data | Carrier Accounts set up and validated
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Socket Config | Validate PROD credentials
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | Cross References | Validate cross references
no | -2 | -1 | 06: Cutover | DEP / OMNI | DEP / OMNI |  | 0% | Smoke Tests | Identify Smoke Test Scenarios
no | -2 | 0 | 06: Cutover | OMNI | Warehouse |  | 0% | Stop Order Export | Stop Sending Orders to old system
no | -1 | 0 | 06: Cutover | OMNI | Warehouse |  | 0% | Cutover | Stop fulfillment in InfoPlus
no | 0 | 0 | 06: Cutover | OMNI | Warehouse |  | 0% | System Config | Record last Sales Order ID in Shopify
|  |  | 06: Cutover | OMNI | Warehouse |  | 0% | System Config | Record last Sales Order ID in WooCommerce
no | 0 | 0 | 06: Cutover | OMNI | Warehouse |  | 0% | Open Orders | Reconcile open orders between Shopping Carts and previous system
no | 0 | 0 | 06: Cutover | OMNI | Warehouse |  | 0% | Load Inventory | Execute plan for loading stockunits into WMS (csv)
no | 0 | 0 | 06: Cutover | OMNI | Warehouse |  | 0% | Confirmation | Confirmation from Rosa that stockunits have been uploaded successfully
no | 0 | 0 | 07: Go-Live | DEP / OMNI | DEP / OMNI |  | 0% | Smoke Tests | PROD Smoke Tests: Review Smoke Test Scenarios
|  |  | 07: Go-Live | OMNI | Warehouse |  | 0% | System Config | PROD Smoke Tests: Turn on Item touchpoint. Import new/live Items into WMS
|  |  | 07: Go-Live | OMNI | Warehouse |  | 0% | System Config | PROD Smoke Tests: Update Item Master Data through Data Exchange
no | 0 | 0 | 07: Go-Live | OMNI | Warehouse |  | 0% | Smoke Tests | PROD Smoke Tests: Begin importing Smoke Test Orders via Shopping Carts
no | 0 | 0 | 07: Go-Live | DEP / OMNI | Warehouse |  | 0% | Smoke Tests | PROD Smoke Tests: D2C Singles
no | 0 | 0 | 07: Go-Live | DEP / OMNI | Warehouse |  | 0% | Smoke Tests | PROD Smoke Tests: D2C Multis
no | 0 | 0 | 07: Go-Live | DEP / OMNI | Warehouse |  | 0% | Smoke Tests | Validate data received in Shopify
no | 0 | 0 | 07: Go-Live | DEP / OMNI | DEP / OMNI |  | 0% | Smoke Tests | PROD Smoke Tests: POI translation/Automation
no | 0 | 0 | 07: Go-Live | DEP | Pros |  | 0% | System Config | Confirmation all Schedulers Turned On
no | 0 | 0 | 07: Go-Live | DEP | Pros |  | 0% | System Config | Turn On Daily item History Scheduler
createmanifest | 0 | 0 | 07: Go-Live | OMNI | Warehouse |  | 0% | Ramp up | Remind BU End Users Omni is no Longer on old system
|  |  | 07: Go-Live | DEP / OMNI | DEP / OMNI |  | 0% | Ramp up | Turn on Wave Scheduler
|  |  | 07: Go-Live | DEP / OMNI | DEP / OMNI |  | 0% | Ramp up | Turn on Billing Scheduler
|  |  | 07: Go-Live | DEP | Pros |  | 0% | Smoke Tests | PROD Smoke Tests: Receiving
no | 0 | 0 | 07: Go-Live | OMNI | IT |  | 0% | Smoke Tests | PROD Smoke Tests: Import PO Receipts
no | 0 | 0 | 07: Go-Live | DEP | Pros |  | 0% | Smoke Tests | PROD Smoke Tests: Inventory Movements
no | 0 | 0 | 07: Go-Live | DEP | Pros |  | 0% | Smoke Tests | PROD Smoke Tests: Replenishments
no | 0 | 0 | 07: Go-Live | DEP | Pros |  | 0% | Smoke Tests | PROD Smoke Tests: Cycle Counts
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | PROD Smoke Tests: E2E batch orders
no | 0 | 0 | 07: Go-Live | DEP | Pros |  | 0% | Smoke Tests | PROD Smoke Tests: Picking
no | 5 | -4 | 07: Go-Live | DEP | Pros |  | 0% | Smoke Tests | PROD Smoke Tests: Packing/Shipping
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Review Tasks/Released/Backorders Orders
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Review Generated Billing Transactions for the previous days
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Engage the Pickers
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Engage Packers
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Confirm Cycle Counts
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Confirm Replenishments
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Enable Replenishments Scheduler
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Ramp up | Monitor & Update SOPs
|  |  | 07: Go-Live | DEP / OMNI | All |  | 0% | Decision | Daily HyperCare Meetings
no | 0 | 0 | 07: Go-Live | DEP | DevOps |  | 0% | Decision | Perform a DB Backup from PROD to UA
no | 0 | 0 | 10: Ticket Monitoring | DEP | Pros |  | 0% | Ticket | Create ticket for receiving V2. After an item is scanned the PO options include fully received ones

## GoNo-Go Decision
OMNI Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 0
Deposco Setup | Label Printers | 10 | Y | OMNI | 0% | 0 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 | Y | OMNI | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | OMNI | 0% | 0 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 | Y | OMNI | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | OMNI | 0% | 0 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | OMNI | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | OMNI | 0% | 0 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 0% | 0 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 0% | 0 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 40 |  |  |  | 0
Warehouse Prep | Location Labels | 10 | Y | OMNI | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Container Labels | 10 | Y | OMNI | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Inventory Labels | 10 | Y | OMNI | 0% | 0 | Are all inventory units labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 | Y | OMNI | 0% | 0 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 65 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Kitting (Kit To Stock) | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | LTL Shipping (Wholesale) | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | OMNI | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 0
Training & Testing | Test Case Scenarios Definition | 10 | Y | DEP / OMNI | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and OMNI to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | OMNI | 0% | 0 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | OMNI | 0% | 0 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | OMNI | 0% | 0 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | OMNI | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 60 |  |  |  | 0
Master Data | Cutover Inventory Validation | 10 | Y | OMNI | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 | Y | OMNI | 0% | 0 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 | Y | OMNI | 0% | 0 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | OMNI | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Kit/Component Relationships | 10 | Y | OMNI | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | OMNI | 0% | 0 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / OMNI | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 55 |  |  |  | 0
Interfaces - Imports to Deposco | Carton Types Upload | 10 | Y | OMNI | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 | Y | OMNI | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 | Y | OMNI | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | OMNI | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Item Vendor Upload | 10 | Y | OMNI | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 | Y | OMNI | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Exports from Deposco | Email confirmation upon shipment | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 110 |  |  |  | 0
Integrations with Deposco | Netsuite - Item - Pull | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Trading Partner - Pull | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Sales Order - Pull | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order - Pull | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Customer Return - Pull | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Ship Notice - Push | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order Receipt - Push | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 10 | Y | OMNI | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 | Y | OMNI | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Rate Shop Request | 10 | Y | OMNI | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 80 |  |  |  | 0
Reports and Labeling | Shipping Label | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Packing Slip Report | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Location Label | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Item Label | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Cartonized Container Label | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Carton Type Label | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Container Label | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Generic BOL Report | 10 | Y | OMNI | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 0
Contingency Plans | Contingency Plans | 10 | Y | DEP / OMNI | 0% | 0 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 0
| Total Possible Score: | 570
| Total Percentage: | 0%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan
OMNI Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | OMNI
3 | Set up Shopify | Set up Shopify Instances in Production environment | FALSE | OMNI
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE | DEP/OMNI
5 | Test Order Pull | Create a test order in Shopify and bring order into Deposco | FALSE | OMNI
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify | FALSE
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify | FALSE
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE
10 | Master Data Check - Items | Look through items in production environment | FALSE
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE
18 | Inventory Push to Shopify | Inventory is pushed to shopify | FALSE
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Shopify Instances to bring in orders | FALSE
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE

## Future ItemsParking Lot
OMNI Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | OMNI Comments