## PAT Project Tracker.xlsx - DEP
robin
|  | CONFIG TASK TRACKER |  |  | Task Summary
[5 empty] | Total Count | In Validation | In Progress | Complete | % of Tasks Complete | % of Hours Complete
[5 empty] | 74 | 7 | 4 | 16 | 21.62% | 13.96%
# | CATEGORY | SUB CATEGORY | DESCRIPTION | SCOPE | ESTIMATE | PRIORITY | OWNER | STATUS | ETA | NOTES | Congifuration Notes
1 | Inbound | LPN Receiving | LPN Number is auto generated based on Deposco Sequence | SIs | 1 |  | Brandon | Complete |  | This will be a dedicated LPN Receiving Button. Reach out to others using these SIs based on the SI lookup tool | Completed by using Deposco Sequence and setting container number attribute + prefix
2 | Inbound | LPN Receiving | LPN Number is required | SIs | 0.5 |  | Brandon | Complete |  | This will be a dedicated LPN Receiving Button. Reach out to others using these SIs based on the SI lookup tool | Set on the SI
3 | Inbound | LPN Receiving | Print LPN Label after stock has been received onto the LPN | Rules | 4 |  | Brandon | Complete |  | This will be a dedicated LPN Receiving Button. Work with Neovia team to determine best time to print using the "Receiving" workflow process | Added rules to Receiving_ReceiveItemScreen-post2 Needed rules as the SI only prints a label list label
4 | Inbound | LPN Receiving | Configure 4x3 LPN Label: - Business Unit - Container # - Date Received - Item # - Qty on the LPN | Report | 4 |  | Sara | Complete |  |  | "LPN Label 4x3" is configured in labelList
5 | Inbound | LPN Receiving | Locations for putaway will be only in the "Receiving Zone" | Query Override | 4 |  | Sara | Complete |  | Determine if this is base logic (it most likely is) if it is not then override using the Putaway Query SI in Receiving | Determine if this is base logic (it most likely is) if it is not then override using the Putaway Query SI in Receiving Putaway Query SI: SuggestedPutatway
6 | Inbound | LPN Receiving | Validation to only allow one lot per LPN captured during receiving. This should be an investigation first if this is base, can be handled via configuration, or if rules are needed. If rules are needed scope with Josiah or Brandon before beginning configuration | Rules | 1 |  | Brandon | Hold |  | This is just an investigation/scoping for the requirement. JIRA ticket created - https://deposco.atlassian.net/browse/PATSUP-16
7 | Inbound | LPN Receiving | Validatio to ensure only one item per lpn | Rules | 2 |  | Brandon | Complete |  |  | Completed using rules on Receiving_ReceiveItemScreen-post
8 | Inbound | Loose Stock Receiving | This will be a dedicated Loose Stock Receiving Button. Straightforward base configuration. Same putaway as LPN Receiving | Query Override | 1 |  | Sara | Complete |  | This is a dedicated Loose Stock Receiving button | Handheld button: Loose Stock Receiving Putaway Query SI: SuggestedPutatwayLoose
9 | Inbound | Damages Receiving | Configure using a dedicated "Damages Receiving" button. Rule prop will be needed to mark receiptLine.disposition == "Damaged" receiptLine.damaged = "true" | Rules | 4 |  | Sara | Complete |  | These rules exist in Verst GeneralReceiving_LPNIdentifierScreen-post but will need to be in a different subcat since these will be received as loose stock. | Rules configured in GeneralReceiving_CreateStock-post
10 | Inbound | Damages Receiving | Configure Image capture and save to OrderHeader | Rules | 2 |  | Sara | Complete |  | Rules exist in DRF, HSW , save to orderHeader not orderLine. | Rules configured in GeneralReceiving_IdentifierInputScreen-post
11 | Inbound | Returns Receiving | Configure "Returns Receiving" handheld process. Blind RMAs and RMAs are eligible for this workflow. Stock will be received loosely and putaway to locations in the returns zone | Rules | 2 |  | Sara | In Progress
12 | Inbound | All receiving | Work with Patterson to get specifications of the Receivng level report that is to be sent after PO is received | Report | 4 |  | Sara | Open |  | Scale example
13 | Reporting | Labels | Pallet Label | Report | 4
14 | Reporting | Labels | Carton Label | Report | 4
15 | Inventory | Move Container | Generic Move Container Process - base suggestions - detach stock from split case picking | SIs | 1 |  | Brandon | Validation
16 | Inventory | Move Item | Generic Move Item Process - base suggestions | SIs | 1 |  | Brandon | Validation
17 | Inventory | Move Stock | Generic Move Stock Process - base suggestions | SIs | 1
18 | Inventory | Directed Putaway | Configure and test Directed Putaway Process - same validations need to exist as in Move Container but a different workflow | SIs | 4 |  | Brandon | In Progress |  | This is a new process so this must be tested thoroughly. Expect issues and document them appropriately - potentially need tickets for putaway
19 | Inventory | Cycle Counts | Configure Generic Cycle Count Profile by Location for the HKC facility | SIs | 1 |  |  |  |  | Plenty of environments to emulate this with. No need to re-invent the wheel here.
20 | Inventory | Cycle Counts | Configure Generic Cycle Count Profile by Item for the HKC facility | SIs | 1 |  |  |  |  | Plenty of environments to emulate this with. No need to re-invent the wheel here.
21 | Inventory | Cycle Counts | Configure Cylce Count by Location Workflow Process | SIs | 2 |  |  |  |  | Plenty of environments to emulate this with. No need to re-invent the wheel here.
22 | Inventory | Cycle Counts | Configure Cylce Count by Item Workflow Process | SIs | 2 |  |  |  |  | Plenty of environments to emulate this with. No need to re-invent the wheel here.
23 | Inventory | Adjust Inventory | Configure base adjust inventory process. | SIs | 2 |  |  |  |  | Use reason codes defined in the MDD otherwise good to pull from another ENV
24 | Inventory | Replenishments | Configure base storage based replenishment process. Will need to evaluate eligible stockUnit and override query if needed. | Query Override | 4 |  | Brandon |  |  | Use MDD for defined eligible stockUnit and replen logic. Many SIs can be re-used from other storage based replen processes.
25 | Inventory | Replenishments | Configure base storage based replenishment process. | SIs | 2 |  | Brandon |  |  | Use MDD for defined eligible stockUnit and replen logic. Many SIs can be re-used from other storage based replen processes.
26 | Inventory | Replenishments | Configure Product Conversion with workorder replens. Look at VERST for this logic | Query Override | 2 |  | Brandon |  |  | Use VERST environment for a template here
27 | Inventory | Replenishments | Configure demand based replenishments. This is not outlined in the design document BUT this has been needed by almost all clients come go live. | SIs | 4 |  | Brandon |  |  | Use VERST environment for a template here
28 | Inventory | Replenishments | Configure Top off replens | SIs | 2 |  | Brandon |  |  | Use VERST environment for a template here. This is base and only generation of tasks
29 | Inventory | Kitting | Configure Kit-to-stock workflow process: Product conversion w/ workorder workflow | SIs | 4 |  |  |  |  | Use MDD for key assumptions
30 | Inventory | ATP Calculations | Verify and make changes to ATP calculations as defined in MDD | Query Override | 2
31 | Outbound | Pre Processing | The Ship To contact name and Ship To address must be populated for the order. The validation is dependent on the Trading Partner code provided on the order. This logic is detailed above. | Rules | 2 |  |  |  |  | Use MDD
32 | Outbound | Pre Processing | If Ship To Country is not ‘US’ then the following fields must be populated on all CoLines: HTS code: CoLine.item.harmonizedCode (this validation is evaluating the Item master data) Customs value: coLine.unitPrice When values are blank on the CoLine then set these values based on item master data. If data is still unavailable then order is set to “Review” Users are able to view the customer orders in review on their dashboard for visibility and timely resolutions. | Rules | 6 |  |  |  |  | Verst has the majority of rules - but will need to write the SET rules from scratch. test thoroughly
33 | Outbound | Pre Processing | Map | Rules | 6 |  |  |  |  | Verst has the majority of rules - but will need to write the SET rules from scratch. test thoroughly
33 | Outbound | Pre Processing | Validate and test Co Revision modes defined in MDD | UI Configuration | 4 |  |  |  |  | This will involve some API testing - define scenarios and test cases. Report back to patterson so they understand the functionality fully
34 | Outbound | Order Routing | Create default order routing profile | UI Configuration | 2
35 | Outbound | Order Routing | Create default Customer Order Management Profile | UI Configuration | 2
36 | Outbound | Order Routing | create routing scheduler | UI Configuration | 1 |  |  |  |  | Pull from a number of OMS envs. All base
37 | Outbound | Order Routing | create retry scheduler | UI Configuration | 1 |  |  |  |  | Pull from a number of OMS envs. All base
38 | Reporting | Co Management | A dashboard widget is created to show all customer orders in a review status. | Report | 2
39 | Outbound | Automations | Determine if the automations outlined in MDD can be handled via API or if truly needed | UI Configuration | 2 |  |  |  |  | Add tasks below as needed for automations
40 | Outbound | POI | Set “POI Complete” (orderHeader.complete) = “True” at the end of Post Order Import processing to confirm POI is executed properly on all orders. | Rules | 0.5 |  | Brandon | Closed
41 | Outbound | POI | OrderLines are evaluated to determine if the order is Ready to Ship (RTS) or Not Ready To Ship (NRTS) The Value RTS or NRTS is set on the orderHeader.customAttribute1 (Order Type) | Rules | 3 |  | Brandon | Closed
42 | Outbound | POI | Ship Vias are evaluated to determine if the shippingService.freightType == “Parcel”. If this is true orderHeader.customAttribute2 (Fulfillment Type) is set to “Parcel”. | Rules | 1 |  | Brandon | Closed
43 | Outbound | POI | Fedex AV | Rules | 2 |  |  |  |  | Pull a generic version that is being used in other environments. Ensure this is set up for the REST FedEx integration
44 | Outbound | POI | trading Partner = “Parts Orders” Orders come down with SCAC code= AM24 and if order exceeds 5 pounds and is a ceiling fan then ship Fedex Home Delivery If commercial ship as Fedex Ground, if residential ship Fedex Home Delivery. | Rules | 3
45 | Outbound | ORP | Configure three ORPs for waving. These are defined in the MDD | UI Configuration | 3 |  | Brandon | In Progress
46 | Outbound | Waving | Configure RTS Delegator and scheduler | UI Configuration | 4 |  | Brandon | Validation |  | This task needs to test cartonization of RTS items, ensure carrier calls are being made, SSCC Numbers genrerated, and shiping labels are generate.
47 | Outbound | Waving | Configure NRTS Delegator and scheduler | UI Configuration | 1 |  | Brandon | Validation
48 | Outbound | Waving | Configure Undo Release WFP | UI Configuration | 0.5 |  | Brandon | Closed
49 | Outbound | Waving | Validate / Configure Stock Rollup functionality | UI Configuration | 1 |  | Brandon | Validation
50 | Outbound | Waving | Configure RTS Pick Wave Profiles | UI Configuration | 2 |  | Brandon | Validation
51 | Outbound | Waving | Configure NRTS Pick Wave Profiles | UI Configuration | 2 |  | Brandon | Validation
52 | Outbound | Waving | Configure Exception / Repick waves | UI Configuration | 0.5
53 | Outbound | Picking | Configure RTS picking (base SIs) | UI Configuration | 2 |  | Brandon | Complete
54 | Outbound | Picking | Configure RTS Picking - Prepopulate cartonized container | Rules | 2 |  | Brandon | Complete |  | Pulled from Gerber BatchPicking_ItemEntryBinQtyScreen-pre
55 | Outbound | Picking | Configure RTS Picking - Print LPN label after scanning RTS container | Rules | 2 |  | Brandon | Complete |  | Added rules to BatchPicking_ItemEntryBinQtyScreen-post
56 | Outbound | Picking | Configrure RTS Picking LPN Label for printing | Report | 2 |  |  |  |  | Awaiting specs from PAT team
57 | Outbound | Picking | Configure NRTS, Singles Picking | SIs | 2 |  |  |  |  | This should be your standard Bulk item pick done across many Deposco envs Key assumptions defined in MDD
58 | Outbound | Picking | Configure NRTS, Multis Picking | SIs | 2 |  |  |  |  | This is your standard batch picking flow Key assumptions defined in MDD
59 | Outbound | Picking | Configure Exception / Repick picking process | SIs | 2 |  |  |  |  | This should be a batch picking flow Key assumptions defined in MDD
60 | Outbound | Packing | Configure RTS Packing Process | SIs | 8 |  | Brandon | In Progress |  | This process will print off SSCC labels using rules This process will prompt user to scan associated LPNs on the order This process will have validations defined in MDD
61 | Outbound | Packing | Configure NRTS, Singles Packing Process | SIs | 4 |  |  |  |  | This is your standard POBI workflow. Needs to be retailer compatible ability to print packing slips and sscc labels
62 | Outbound | Packing | Configure NRTS, Multis Packing Process | SIs | 4 |  |  |  |  | This is your standard SingleScanPacking workflow. Needs to be retailer compatible ability to print packing slips and sscc labels Defined in MDD
63 | Outbound | Packing | Configure Hazmat Packing across all workflows | UI Configuration | 10 |  |  |  |  | Defined in MDD
64 | Outbound | Packing | Configure Stamps integration | UI Configuration | 8
65 | Outbound | Packing | Configure UPS integration | UI Configuration | 8
66 | Outbound | Packing | Configure FedEx Integration | UI Configuration | 8
67 | Outbound | Freight | Configure Create Trip PAL | Rules | 4 |  | Brandon |  |  | Use environments like SCALE, VERST, GULF, GERBER
68 | Outbound | Freight | Configure Freight Picking Process | SIs | 12 |  | Brandon |  |  | Use environments like SCALE, VERST, GULF, GERBER Staging logic / follow the leader included
69 | Outbound | Freight | Configure Print And Apply Process | SIs | 4 |  | Brandon |  |  | Use environments like SCALE, VERST, GULF, GERBER
70 | Outbound | Freight | Configiure ATTC and add validations | Rules | 8 |  | Brandon |  |  | Use environments like SCALE, VERST, GULF, GERBER
71 | Outbound | Freight | Configure Close Trip process and accompanying validations | Rules | 8 |  | Brandon |  |  | Use environments like SCALE, VERST, GULF, GERBER
72 | Outbound | Freight | Configure OFP for Reset Orders | UI Configuration | 8 |  |  |  |  | This will require heavy testing and validations since this process is new
73 | Inventory | Freight | Configure Reset Order Replenishments | UI Configuration | 8 |  |  |  |  | This will require heavy testing and validations since this process is new
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201