## Schedule
RBW Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal | Metric | Status
Client Goal #1 | Metric we will use to track | Open
Client Goal #2 | Metric we will use to track | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions | 2025-06-19
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports | 2025-06-19
Deposco University | Customer completes Deposco University training courses for relevant subjects. | 2025-06-27
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | LINK | 2025-06-25
Master Design Document | LINK | TBD
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | ERP/WebStore/ShippingCarrier/ChannelAggregator/EDI - data requirements, troubleshooting, mapping updates, steps etc. |  | #REF!
Order Orchestration | Sourcing, Routing, Exception and Backorder Management |  | #REF!
Inbound | General Receiving(PO, Blind Receipt, Customer Returns), Move Item, Move Stock, Move Container |  | #REF!
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock |  | #REF!
Outbound | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking, Packing, Shipping |  | #REF!
Other - WMS | Transfer orders, 3PL Billing, etc. |  | #REF!
Reporting | Report Builder, Dashboard Widgets |  | #REF!
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Completion Date
End to End Testing | Testing all process flows with live data end to end | #REF!
UAT Onsite Agenda | LINK | 0%
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0%
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0%
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned.
Deposco Onsite Support | Travel booked for cutover and go-live week.
Project Closeout | Agreement of final deliverables provided.

## Task Tracker
RBW Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Due Date | DEP Comments | RBW Comments
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | FALSE | Completed | DEP
Design | Deposco Email Distro Group | RBW to create a Deposco email distribution group. All emails from the Deposco team will be sent to this distro group |  |  | FALSE | FALSE | Completed | RBW
Design | Printing | RBW to install Deposco print client once Deposco sends the printer conf files. RBW to establish connection to print server and add both ZPL and PDF printers. RBW to send all questions regarding printing set up to Deposco via email. Printing documentation can be found in the help site > search for Printing > click on first link titled "Install the Deposco Print Client on a print server" | Task |  | FALSE | FALSE | Open | RBW | Susan
Design | Integration Set Up | RBW to register scoped parcel integrations (UPS and FedEx). Registration steps can be found in the help site. After accessing the help site, search for UPS and FedEx in the search bar and click on the result that reads UPS and FedEx. | Task |  | FALSE | FALSE | Open | RBW | Susan
Design | 3PL Matrix | RBW team to fill out the 3PL Customer Matrix. This can be found in email subject "Re: Detailed Project Plan - RBW". This can also be found here (in the shared google drive) | Task |  | FALSE | FALSE | Open | RBW | Susan
Design | Integrations | RBW team to work on an updated integration diagram detailing the required EDI and API workflows that need to be included in scope | Task |  | FALSE | FALSE | Open | RBW
Design | Integrations | RBW team to organize a call with Cleo to align on required EDI workflows and API endpoints required for initial scope | Task |  | FALSE | FALSE | Open | RBW
Design | Integrations | RBW team to confirm if Amazon Vendor Central will be leveraged - conversation between RBW and SimpliHome will need to be organized to make this decision | Task |  | FALSE | FALSE | Open | RBW
Design | Integrations | Deposco to create an api mapping document which includes all scoped api endpoints and field mappings for each which can be shared with the Cleo team when ready | Task |  | FALSE | FALSE | Open | DEP
Design | Integrations | Deposco to review supported TMS integrations | Task |  | FALSE | FALSE | Open | DEP
Design | Master Data | DEP to outline required fields for item, pack, location, zone, container entities. DEP to review post inbound + inventory design sessions. | Task |  | FALSE | FALSE | Open | DEP
Design | Labels/Reports | RBW to gather all required labels their current system is printing that they expect Deposco to emulate (e.g. SSCC labels, BOLs, packing slips, customer specific reports, etc.) Once RBW gathers examples of each label/report, they will reach out to Deposco to schedule a call to review together | Task |  | FALSE | FALSE | Open | RBW
Design | Labels/Reports | RBW to send requirements and examples of customers who have customized packing slips/BOLs | Task |  | FALSE | FALSE | Open | RBW
Design | 3PL Billing | RBW team to send Deposco a detailed list of all Billing Configs (each indiivdual transaction they charge their customers) with definitions. Once compelte, Deposco will schedule a call to review together and determine logic required to generate the desired transactions | Task |  | FALSE | FALSE | Open | RBW
Design | Inbound/Inventory Topics | Deposco to schedule a call to review and finalize design approach for the following Inbound/Inventory topics: 1) QC process 2) Suggested Putaway logic 3) Replenishment logic | Task |  | FALSE | FALSE | Completed | DEP
Design | Return Reasons | RBW team to send all reason codes they would like captured as part of the RMA receipt process | Task |  | FALSE | FALSE | Open | RBW
Design | Adjustment Reasons | RBW team to send all reason codes they would like captured when using the Adjust Inventory process to create or deplete inventory (example: Damaged, Client Request etc.) | Task |  | FALSE | FALSE | Open | RBW
Design | OMS | Deposco to review OMS backorder functionality and behavior with non each packs (alternate UOMs) | Task |  | FALSE | FALSE | Open | DEP
Design | Data Considerations | Deposco to send database length constraints for required fields on the following entities: 1) Purchase Order (orderHeader) 2) Customer Order (orderHeader) 3) Item (Item) 4) Facility 5) Location | Task |  | FALSE | FALSE | Completed | DEP
Design | Waving Topics | Deposco to schedule a call to review and finalize design approach for waving for SimpliHome and Aldi | Task |  | FALSE | FALSE | Open | DEP
Design | Outbound Topics | Deposco to schedule a call to review and finalize design approach for the following B2B Outbound Topics: 1) Advanced Trip creation (creation of the trip prior to order being waved/picked) and advanced shipping door assignment 2) Zone based picking (multiple pickers picking a single order) 3) Necessity of having users log into a piece of equipment "fork lift" to drive potential handheld funcitons 4) Pick drop location logic 5) BOL capture and printing 6) End to end fulfillment (picking, staging, assign trip, close trip) | Task |  | FALSE | FALSE | Open | DEP
Design | Master Design Document | Deposco to draft initial Master Design Document in the following sections: - Master Data - Inbound - Inventory - Outbound - Integrations & 3PL Billing - OMS | Task |  | FALSE | FALSE | In Progress | DEP | Laukya | 2025-07-28
Design | Design Review | RBW team to review the drafts and add all feedback directly to the google doc in the form of comments. Once done, Deposco will schedule calls to review each section and the RBW team's comments | Task |  | FALSE | FALSE | In Progress | RBW | Laukya | 2025-07-28
Design | Review and Sign Master Design Document | RBW to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  | FALSE | FALSE | Open | DEP/RBW | Priyesh | 2025-08-06
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Recordings
RBW Demo Videos
Date | Category | Config Code | DESCRIPTION | LINK
Baseline Education
Deposco User Exerience
Master Data / Data Exchange
Process Demos
Integrations
Inbound
Inventory Management
Outbound
Reporting
Miscellaneous Demos
Testing/Training Support

## DEP Config Tasks
Deposco Configuration Task List
Product / Task Group | Task | SOW Notes | In Scope | Complete | Config Code | Post Design - Configuration Notes | Owner | Status | % Complete | Due Date
Bright Warehouse Configuration (T&M)
Inbound | Pre-receiving | DE Field Mapping | FALSE | FALSE
Inbound | Pre-receiving | Purchase Order Entry | FALSE | FALSE
Inbound | Standard Receiving | Confirmation for partial receipts (Under-receipts are allowed but will require a confirmation/screen message acknowledgment) | FALSE | FALSE
Inbound | Standard Receiving | LPN Label config + printing | FALSE | FALSE |  |  |  |  | 0%
Inbound | Standard Receiving | Putaway to receiving lanes | FALSE | FALSE
Inbound | Standard Receiving | QC Putaway - to be configured as a part of inventory management demo | FALSE | FALSE
Inbound | Standard Receiving | Item Tracking Capture - screen message for expiration date format. This should only apply to receiving process. Look at item tracking capture pre process data | FALSE | FALSE
Inbound | Customer Returns | DE Field Mapping | FALSE | FALSE |  |  |  |  | 0%
Inbound | Customer Returns | GPCreateRMA | FALSE | FALSE |  |  |  |  | 0%
Inbound | Customer Returns | General Receiving > Receiving Main screen > xaml > update Indentifier Number to Identifier Number (RMA Number) | FALSE | FALSE
Inbound | Customer Returns | Returns Receiving - Autogenerate LPN | FALSE | FALSE |  |  |  |  | 0%
Inbound | Customer Returns | LPN label printing | FALSE | FALSE |  |  |  |  | 0%
Inbound | Customer Returns | ReceivingItemConfigScreen - add Next button | FALSE | FALSE |  |  |  |  | 0%
Inbound | Customer Returns | Reason codes config | FALSE | FALSE |  |  |  |  | 0%
Inventory Management | Move Item | Happy path move item flow, no special SIs needed. Ensure suggested locations logic is not invoked in this process. | FALSE | FALSE |  |  | Erica |  | 0%
Inventory Management | Move Container | Create new SI prop group and call it Default. Ensure the HH button (button name = Move Container - Putaway) is tied to this SI group. Mimic the "Move Container Properties" SI group for SI setup. | FALSE | FALSE |  |  | Erica |  | 0%
Inventory Management | Move Container - Rack Putaway | Rack Putaway Logic: Condition 1 AND Condition 2 need to be met for suggested locations. This can be configured as one query. Max results = 10. 1) Item Velocity matches Location Velocity and Location is empty. RBW will populate an item’s velocity as A (fast mover), B (medium mover), and C (slow mover). They will do so on a repurposed field on the item entity (item.customAttribute4). RBW will do the same on a repurposed field on Location (location.customAttribute3), designating some Locations to hold A, B, and C movers. Deposco will only suggest A Locations for A items etc. Locations must be tied to a Rack zone. 2) Item needs to be marked as Rack. Deposco will repurpose an item attribute to note if the item is a Rack item (item.customAttribute5). RBW is responsible for using this attribute on the Item entity to designate it for Rack or Bulk putaway (example shown below). If this field reads “Rack”, only Locations in the Rack zone will be suggested. Rack Putaway Assumptions: - One pallet per location (No mixing of customers/BUs within a single location and No mixing of lot/expiration) - Locations are lpn controlled (i.e. no loose stock) - The suggested locations in the screen dropdown can be ordered by the Location > Putaway Sequence attribute. | FALSE | FALSE |  | Putaway - pages 8-10 in design doc | Erica |  | 0%
Inventory Management | Move Container - Bulk Putaway | Logic: All conditions in a single query, max results = 10 1) Non-full locations where item already exists. The system will not suggest locations if it holds same item but different lot and expiration. --> Need to consider volume. Formula: (Location Volume - Volume of Existing Stock) > Volume of Qty to Put Away 2) Empty locations --> Need to consider volume. Formula: Location Volume > Volume of Qty to Put Away 4) Item needs to be marked as Bulk (item.customAttribute5) 5) Item Velocity (item.customAttribute4) needs to match Location Velocity (location.customAttribute3). 6) Locations must be tied to a Bulk zone. Assumptions: - No mixing of customers/BUs within in a single location - The suggested locations in the screen dropdown can be ordered by the Location > Putaway Sequence attribute. Testing Considerations: - When putting away pallet, ensure the Move button moves the stock with the container. | FALSE | FALSE |  | Putaway - pages 8-10 in design doc | Erica |  | 0%
Inventory Management | Move Stock - Rack Putaway | Rack Putaway Logic: Condition 1 AND Condition 2 need to be met for suggested locations. This can be configured as one query. Max results = 10. 1) Item Velocity matches Location Velocity and Location is empty. RBW will populate an item’s velocity as A (fast mover), B (medium mover), and C (slow mover). They will do so on a repurposed field on the item entity (item.customAttribute4). RBW will do the same on a repurposed field on Location (location.customAttribute3), designating some Locations to hold A, B, and C movers. Deposco will only suggest A Locations for A items etc. Locations must be tied to a Rack zone. 2) Item needs to be marked as Rack. Deposco will repurpose an item attribute to note if the item is a Rack item (item.customAttribute5). RBW is responsible for using this attribute on the Item entity to designate it for Rack or Bulk putaway (example shown below). If this field reads “Rack”, only Locations in the Rack zone will be suggested. Rack Putaway Assumptions: - One pallet per location (no mixing of customers/BUs within a single location and No mixing of lot/expiration) - Locations are lpn controlled (i.e. no loose stock) - The suggested locations in the screen dropdown can be ordered by the Location > Putaway Sequence attribute. | FALSE | FALSE |  | Putaway - pages 8-10 in design doc | Erica
Inventory Management | Move Stock - Bulk Putaway | Logic: All conditions in a single query, max results = 10 1) Non-full locations where item already exists. The system will not suggest locations if it holds same item but different lot and expiration. --> Need to consider volume. Formula: (Location Volume - Volume of Existing Stock) > Volume of Qty to Put Away --> Location Volume = location.volume attribute. Volume of Existing Stock/Volume of Qty to Put Away = qty x (Pack LxWxH) 2) Empty locations --> Need to consider volume. Formula: Location Volume > Volume of Qty to Put Away 4) Item needs to be marked as Bulk (item.customAttribute5) 5) Item Velocity (item.customAttribute4) needs to match Location Velocity (location.customAttribute3). 6) Locations must be tied to a Bulk zone. Assumptions: - No mixing of customers/BUs within in a single location - Locations are lpn controlled - The suggested locations in the screen dropdown can be ordered by the Location > Putaway Sequence attribute. | FALSE | FALSE |  | Putaway - pages 8-10 in design doc | Erica
Inventory Management | QC Putaway (ReceivingV2) | - Rename item.customAttribute3 and orderLine.customAttribute3 to "FDA Check Required". Set as boolean. Ensure checking flag sets DB value to true. Logic: - If item.customAttribute3 or orderLine.customAttribute3 = true, then override Receiving Direct Putaway screen > suggested locations to only query for location.storageType = Quarantine. There's already a default putaway query in place via SIs so the QC suggested location putaway needs to be done in rules. - The user will scan the QC location in putaway and the inventory is systematically tied to the QC location. The stock unit status will be automatically set to “On Hold” (i.e. ineligible for allocation). Need to do this via rules. The RBW team is then responsible for setting status back to Ready once FDA check is complete (no need for DEP to configuring status update in this scenario). | FALSE | Y |  | QC and Damages Putaway design: https://docs.google.com/document/d/1y8h4K54E_On8MD1xwS9XOjkurtm_K1ToBBeqnSjgGkM/edit?tab=t.0 | Zach Barnitt | Complete | 100%
Inventory Management | Move Container - Damages Putaway | Create new SI prop group and call it Adhoc. Mimic the current default SI group for SIs. Ensure the HH button (button name = Move Container - Adhoc/Damages) is tied to this SI group. No fancy SIs needed. The suggested putaway logic is not invoked for this version of Move Container. Expectation is the user in the process keys in/scans the QC location. Test with both moving only stock to destination location and with "Move" button where the container moves with the stock. | FALSE |  |  | QC and Damages Putaway design: https://docs.google.com/document/d/1y8h4K54E_On8MD1xwS9XOjkurtm_K1ToBBeqnSjgGkM/edit?tab=t.0 | Zach Barnitt | Complete | 100%
Inventory Management | Move Stock - Damages Putaway | Create new SI prop group and call it Adhoc. Ensure the HH button (button name = Move Stock - Adhoc/Damages) is tied to this SI group. No fancy SIs needed. The suggested putaway logic is not invoked for this version of Move Stock. Expectation is the user in the process keys in/scans the QC location. | FALSE |  |  | QC and Damages Putaway design: https://docs.google.com/document/d/1y8h4K54E_On8MD1xwS9XOjkurtm_K1ToBBeqnSjgGkM/edit?tab=t.0 | Erica |  | 0%
Inventory Management | Adjust Inventory | - Existing button is under Inventory group. No need for additional SI prop group. Nothing fancy in terms of SI config. Leave reason code SI as is (need to get confirmation on reason codes from RBW team). Ensure to test with item tracking capture (lot/exp enabled) where the system will prompt you to enter/confirm lot and exp. - Run through a high-level test for Create Inventory, Consume by Item, Consume by Location, Consume by LPN scenarios. | FALSE |  |  | Inventory Adjustments Design: https://docs.google.com/document/d/1y8h4K54E_On8MD1xwS9XOjkurtm_K1ToBBeqnSjgGkM/edit?tab=t.0 | Zach Barnitt |  | 0%
Inventory Management | Replen - Storage Based (Top off/Static) |  | FALSE
Inventory Management | Replen |  | FALSE
Inventory Management | Replen |  | FALSE
Inventory Management | Replen |  | FALSE
Inventory Management | Cycle Count |  | FALSE |  |  |  | Erica
Inventory Management | Warehouse Lookup |  | FALSE |  |  |  | Erica
Inventory Management | Kit to Stock process | - Read design doc for this process. All base functionality. Test with item tracking capture items and without. - Create and test Assembly Data Exchange Import by listing the subcomponents (assembly items) that make up the parent SKU. | FALSE |  |  |  | Zach Barnitt | Complete | 100%
Outbound | POI | Rule Category 1 (BU=Aldi): - Set orderHeader.customAttribute1 to "PIPO" Rule Cateogry 2 (BU SimpliHome): - Set orderHeader.customAttribute1 to "Parts" if customAttribute1 = 505 and orderHeader.tradingPartner.code = "Y77524" and orderHeader.shipVendor = "UPS" or "FedEx" - Set | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Other | Shipping Documents/Labels |  | FALSE | [5 empty] | 0%
Other | 3PL Billing |  | FALSE | [5 empty] | 0%
Setup | System Admin |  | FALSE | [5 empty] | 0%
Setup | Data Maintenence |  | FALSE | [5 empty] | 0%
Bright Socket Configuration (T&M)
Configure | Web Store |  | FALSE | [5 empty] | 0%
Configure | Retailer |  | FALSE | [5 empty] | 0%
Configure | EDI Fulfillment |  | FALSE | [5 empty] | 0%
Configure | Marketplace |  | FALSE | [5 empty] | 0%
Configure | ERP/Accounting |  | FALSE | [5 empty] | 0%
Configure | Carrier |  | FALSE | [5 empty] | 0%
Configure | Shopify |  | FALSE | [5 empty] | 0%
Configure | Quickbooks Online |  | FALSE | [5 empty] | 0%
Configure | UPS |  | FALSE | [5 empty] | 0%
Configure | FedEx |  | FALSE | [5 empty] | 0%
Bright Performance Configuration (T&M)
Standard Dashboard and Reporting | Global Reports |  | FALSE | [5 empty] | 0%
Standard Dashboard and Reporting | Company Reports/Report Builder |  | FALSE | [5 empty] | 0%
Standard Dashboard and Reporting | Report Scheduling |  | FALSE | [5 empty] | 0%
Standard Dashboard and Reporting | Dashboards |  | FALSE | [5 empty] | 0%
Dashboard and Reporting add-on | Report Models |  | FALSE | [5 empty] | 0%
Dashboard and Reporting add-on | Report Scheduling |  | FALSE | [5 empty] | 0%
Dashboard and Reporting add-on | Data Archive |  | FALSE | [5 empty] | 0%
Bright Order Configuration (T&M)
Configure - Order Orchestration | Preprocessing |  | FALSE | [5 empty] | 0%
Configure - Order Orchestration | Order Sourcing |  | FALSE | [5 empty] | 0%
Configure - Order Orchestration | Order Routing |  | FALSE | [5 empty] | 0%
Configure - Order Orchestration | Order Release |  | FALSE | [5 empty] | 0%
Configure - Order Processing | Order Management |  | FALSE | [5 empty] | 0%
Configure - Order Processing | Order Exception Management |  | FALSE | [5 empty] | 0%
Configure - Enterprise Inventory | Enterprise Inventory Management |  | FALSE | [5 empty] | 0%
Configure - INventory Segmentation | Manage Segments |  | FALSE | [5 empty] | 0%

## GoNo-Go Decision
RBW Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 0
Deposco Setup | Label Printers | 10 | Y | XXX | 0% | 0 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 | Y | XXX | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | XXX | 0% | 0 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 | Y | XXX | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | XXX | 0% | 0 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | XXX | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | XXX | 0% | 0 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 0% | 0 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 0% | 0 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 40 |  |  |  | 0
Warehouse Prep | Location Labels | 10 | Y | XXX | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Container Labels | 10 | Y | XXX | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Inventory Labels | 10 | Y | XXX | 0% | 0 | Are all inventory units labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 | Y | XXX | 0% | 0 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 65 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Kitting (Kit To Stock) | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | LTL Shipping (Wholesale) | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 0
Training & Testing | Test Case Scenarios Definition | 10 | Y | DEP / XXX | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and XXX to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | XXX | 0% | 0 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | XXX | 0% | 0 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | XXX | 0% | 0 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | XXX | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 60 |  |  |  | 0
Master Data | Cutover Inventory Validation | 10 | Y | XXX | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Kit/Component Relationships | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | XXX | 0% | 0 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / XXX | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 55 |  |  |  | 0
Interfaces - Imports to Deposco | Carton Types Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Item Vendor Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Exports from Deposco | Email confirmation upon shipment | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 110 |  |  |  | 0
Integrations with Deposco | Netsuite - Item - Pull | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Trading Partner - Pull | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Sales Order - Pull | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order - Pull | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Customer Return - Pull | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Ship Notice - Push | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order Receipt - Push | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 10 | Y | XXX | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Rate Shop Request | 10 | Y | XXX | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 80 |  |  |  | 0
Reports and Labeling | Shipping Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Packing Slip Report | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Location Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Item Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Cartonized Container Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Carton Type Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Container Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Generic BOL Report | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 0
Contingency Plans | Contingency Plans | 10 | Y | DEP / XXX | 0% | 0 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 0
| Total Possible Score: | 570
| Total Percentage: | 0%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan
RBW Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | XXX
3 | Set up Shopify | Set up Shopify Instances in Production environment | FALSE | XXX
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE | DEP/XXX
5 | Test Order Pull | Create a test order in Shopify and bring order into Deposco | FALSE | XXX
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify | FALSE
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify | FALSE
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE
10 | Master Data Check - Items | Look through items in production environment | FALSE
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE
18 | Inventory Push to Shopify | Inventory is pushed to shopify | FALSE
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Shopify Instances to bring in orders | FALSE
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE