## Schedule
RAD3PL Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal | Metric | Status
Goal #1 | Automate billing that takes 30-40 hrs in their current system | Open
Goal #2 | Remove system performance lag of 4-6 secs for every transaction | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | https://drive.google.com/drive/folders/1ZepH-3BmwwSNQCW_nXqCbuu4q9aBTMje | 2025-02-06 | 2025-02-06
Master Design Document | https://drive.google.com/drive/folders/1ZepH-3BmwwSNQCW_nXqCbuu4q9aBTMje | 2025-02-28
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Demo Delivery | Testing Due Date
Inbound/Putaway | Receiving (Purchase Order, Customer Return, Blind RMA), Move Item/Container/Stock, Unreceive | 2025-03-07 |  | 2025-03-10 | 2025-03-13
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Product Conversion with Workorder, Kit to Stock | 2025-03-11 |  | 2025-03-17 | 2025-03-20
Outbound I | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking, Kit to Order, Kit To Stock | 2025-03-20 |  | 2025-03-24 | 2025-03-27
Outbound II | Packing and Shipping, Repalletize, Rollback After Picking, Void and Reprocess Shipment, Assign Trip to Container, Packing Slip | 2025-03-24 |  | 2025-03-31 | 2025-04-03
3PL Billing | Billing Profiles, Configs, and Invoices | 2025-03-26 | 0% | 2025-04-07 | 2025-04-10
Integrations - Sockets | All endpoints/user scenarios for Shipping Carriers (UPS, FedEX, DHL), Quickbooks Online | 2025-03-24 | 94.29%
Integrations - DEP API | CartRover setup | 2025-03-24 | 25.64%
Reporting | Report Builder, Dashboard Widgets (typically completed post UAT) |  | #DIV/0!
End to End Testing | Testing all process flows with live data end to end | 2025-03-25 | 0% |  | 2025-04-10
0%
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Completion Date
End to End Testing | Testing all process flows with live data end to end | 0% | 2025-04-04
UAT Onsite Agenda | LINK | 0% | 2025-04-08
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0%
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0% | 2025-04-16
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned.
Deposco Onsite Support | Travel booked for cutover and go-live week.
Project Closeout | Agreement of final deliverables provided.
Go live Agenda | Link - Schedule for 4 day Deposco onsite visit to Pitted for Go live
Go live | Implement Deposco with a phased rollout (phase 1, first group of customers on date in column C) | 2025-04-28

## Task Tracker
RAD3PL Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | DEP Comments | RAD3PL Comments
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Setup Client SX Account | Setup SX with tenant code and General / Project Management tasks | Task |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network 2) Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task | 2.High | TRUE | TRUE | Completed | DEP | Keegan
Orientation | Setup Parcel Carrier Accounts | UPS: Client utilizes Deposco UPS Registration Wizard to setup UPS account Stamps: Clients configures FedEx account and Meter # within Deposco CompanyConfig UI screen | Task |  | FALSE | FALSE | Completed | DEP | Technical Lead
Orientation | Setup Exisiting Sockets | Client utilizes Deposco help site guides to setup existing socket connections | Task |  | FALSE | FALSE | Completed | RAD3PL | Matt
Orientation | General Application and UI Overview | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Message Center Overview - Handheld Menu Access | Task |  | FALSE | FALSE | Completed | DEP/RAD3PL | Full team
Orientation | Begin Master Data Gathering | Sample Master Data templates for items, packs, locations, zones, storages, etc. to be provided by Deposco to be used by client | Task |  | FALSE | FALSE | Completed | DEP | Erica
Orientation | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task |  | FALSE | FALSE | Closed | DEP | Warehouse Leads
Orientation | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task |  | FALSE | FALSE | Closed | DEP | Inbound Lead
Orientation | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task |  | FALSE | FALSE | Closed | DEP | Outbound Lead / Customer Service Lead
Orientation | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task |  | FALSE | FALSE | Closed | DEP | Outbound Lead
Orientation | Schedule recurring project calls | Weekly status call Bi-weekly executive steering call | Task |  | FALSE | FALSE | Completed | DEP | Priyesh
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | FALSE | Completed | DEP | Solution Lead
Design | Master Design Document Delivery | Deliver master design document for client team to review | Task |  | FALSE | FALSE | Completed | DEP | Isaac | 2025-02-16 | 2025-02-28
Design | Review and Sign Master Design Document | Client to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  | FALSE | FALSE | Closed | DEP/RAD3PL | Full Team | 2025-02-20 | 2025-02-28
Configuration | Upload Items for Phase 1 BUs | Upload Items into Deposco via Data Exchange | Task |  | TRUE | TRUE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-06
Configuration | Upload Items for Phase 2 BUs | Upload Items into Deposco via Data Exchange | Task |  | TRUE | TRUE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-06
Configuration | Upload Items for Phase 3 BUs | Upload Items into Deposco via Data Exchange | Task |  | TRUE | TRUE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-06
Configuration | Component Upload for Kitted SKUS for Phase 1 BUs | Upload via Data Exchange after you have uploaded the related items | Task |  | TRUE | TRUE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-06
Configuration | Component Upload for Kitted SKUS for Phase 2 BUs | Upload via Data Exchange after you have uploaded the related items | Task |  | TRUE | TRUE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-06
Configuration | Component Upload for Kitted SKUS for Phase 3 BUs | Upload via Data Exchange after you have uploaded the related items | Task |  | TRUE | TRUE | Closed | RAD3PL | Matt | 2025-02-16 | 2025-03-06
Configuration | Printer Setup - Resources, Assignments, Details | Setup all printers in Deposco and assign them to appropriate resources and reports | Task |  | FALSE | TRUE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-07 | Three Zebra printers have been setup and tested with successful Bluetooth capabilities
Configuration | UPS - configure and test all shipping services | Add shipping services into Deposco per email: RAD3PL - Shipping Services | Task |  | FALSE | FALSE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-07
Configuration | Stamps - configure and test all shipping services | Add shipping services into Deposco per email: RAD3PL - Shipping Services | Task |  | FALSE | FALSE | Completed | RAD3PL | Matt | 2025-02-16 | 2025-03-07
Configuration | DHL - configure and test all shipping services | Add shipping services into Deposco per email: RAD3PL - Shipping Services | Task |  | FALSE | TRUE | Closed | RAD3PL | Matt | 2025-02-16 | 2025-03-07
Configuration | Deliver Inbound Configuration | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Erica | 2025-03-03 | 2025-03-07
Configuration | Deliver Inventory Management Configuration | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Erica | 2025-03-07 | 2025-03-11
Configuration | Deposco API - CartRover setup - Phase 1 BUs | Setup up and validate required touchpoints for the CartRover integration | Task |  | FALSE | TRUE | Closed | RAD3PL | Matt | 2025-02-16 | 2025-03-14
Configuration | Deliver Outbound Configuration Pt 1 | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Erica | 2025-03-17 | 2025-03-20
Configuration | Deliver Outbound Configuration Pt 2 | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Erica | 2025-03-20 | 2025-03-31
Configuration | Deliver Integration Configuration Training | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Closed | DEP | Erica | 2025-03-20 | 2025-03-31
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task |  | FALSE | FALSE | Closed | DEP | Implementation Lead | 2025-03-20 | 2025-04-14
Validation | Deliver Onsite UAT Agenda |  | Task |  | FALSE | FALSE | Closed | DEP | Erica | 2025-04-02 | 2025-04-04
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Completed | RAD3PL | Inbound Lead |  | 2025-03-13
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Completed | RAD3PL | Inventory Lead |  | 2025-03-20
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Closed | RAD3PL | Outbound Lead |  | 2025-03-27
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Closed | RAD3PL | Outbound Lead |  | 2025-04-03
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task |  | FALSE | FALSE | Closed | RAD3PL | Matt |  | 2025-04-10
Validation | End to End Test Case Execution | Complete end to end test cases | Task |  | FALSE | FALSE | Closed | RAD3PL | Matt |  | 2025-04-18
Validation | Train End Users | During UAT and any additional training as needed | Task |  | FALSE | TRUE | Completed | RAD3PL | Warehouse Leads |  | 2025-04-18
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task |  | FALSE | TRUE | Completed | DEP | Priyesh |  | 2025-04-11
Validation | Receiving / Receiving LPN barcodes |  | Task |  | FALSE | FALSE | Completed | RAD3PL | Matt
Validation | Kit Header upload | Kit Header upload | Task |  | FALSE | TRUE | Completed | RAD3PL | Matt |  | 2025-04-18
Validation | Blacklist shipping insurance | Blacklist shipping insurance | Task |  | FALSE | TRUE | Completed | RAD3PL | Andrew |  | 2025-04-18
Validation | Shipping Tiers + Rate shopping automation | Shipping Tiers + Rate shopping automation | Task |  | FALSE | TRUE | Completed | RAD3PL | Matt |  | 2025-04-18
Validation | Conditional Rate Shopping | Conditional Rate Shopping | Task |  | FALSE | FALSE | Completed | DEP | Erica |  |  | Completed during UAT onsite
Validation | Testing ship confirmation from Cart Rover | Test for pallet compantibility | Task |  | FALSE | TRUE | Completed | RAD3PL | Andrew |  | 2025-04-18 | LoveBird BU - Confirmed, Additional BUs pending
Validation | Set up Billing for other customers | Set up Billing for other customers | Task |  | FALSE | TRUE | Completed | RAD3PL | Andrew |  | 2025-04-18
Validation | Billing: Profile to add cost to workorders/kitheaders | Billing: Profile to add cost to workorders/kitheaders | Task |  | FALSE | TRUE | Closed | DEP | Isaac |  | 2025-04-18 | Need to follow up with Josiah
Validation | B2B vs B2C automation | Finalize logic to identify B2B vs B2C orders | Task |  | FALSE | TRUE | In Progress | DEP | Erica |  | 2025-04-18 | Erica - still need additional details from Tiffany
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task |  | FALSE | FALSE | Completed | DEP/RAD3PL | Isaac |  | 2025-04-16
Validation | ATTC | Do not want to reuse bins, Type = pallet ideally | Task |  | FALSE | FALSE | Completed | DEP | Erica |  |  | Erica to verify, confirmed
Validation | Why is order in partially shipped? | SO-04385 | Issue |  | FALSE | FALSE | Completed | DEP | Erica |  | 2025-04-18 | In progress with Erica, was able to reproduce in a new order, figured out that the reason why the order was showing as Partially Shipped was due to the orderLine's pickTasks being associated with component assembly items while the orderLine maintains the parent item; currently trying to figure out how to resolve if AssignTripToContainer process is the cause Figured out B2B Wholesale orders in this situation was displaying as Partially Shipped when pallets are getting picking separately into multiple picking containers and then taken through ATTC, each picking container would correspond to a generated Shipment --> the shipped quantity would only display as the first picking container - or pallet quantity of 432, which would correspond to a shipped quantity of 72 of the parent item; in order to account for the multiple shipments, ATTC SI BATCH_CLOSE_SHIPMENT consolidates all of the picking containers onto one shipment with each of them displaying as a ContainerHist, so they don't lose any tracking visibility
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task |  | FALSE | FALSE | Completed | DEP | Erica | 2025-04-15 | 2025-04-17 | Erica to reivew 4/16 before sending to client
Deployment | Execute Cutover Plan Steps |  | Task |  | FALSE | TRUE | Open | DEP/RAD3PL | Erica |  | 2025-04-15
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task |  | FALSE | FALSE | Open | DEP | Priyesh |  | 2025-04-11 | Go-Live scheduled for May 1st (team onsite Wed - Fri)
Configuration | BOL Number Generation in ATTC |  | Task |  | FALSE | TRUE | Completed | DEP | Erica |  | 2025-04-18 | Sending Example Generated BOL File to Matt to Review
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Recordings
RAD3PL Demo Videos
Date | Category | DESCRIPTION | LINK
Baseline Education
2025-01-03 | Deposco User Exerience
2025-01-03 | Master Data / Data Exchange
Process Demos
2025-03-20 | Integrations
2025-03-04 | Inbound/Putaway |  | RAD3PL _ DEP_ Inbound Demo-20250310_160358-Meeting Recording.mp4
2025-03-06 | Inventory Management |  | RAD3PL _ DEP_ Inventory Management Demo-20250317_150333-Meeting Recording.mp4
2025-03-13 | Outbound I |  | Outbound I Demo Session-20250324_140603-Meeting Recording.mp4
2025-03-18 | Outbound II |  | Outbound II Demo Session-20250331_150602-Meeting Recording.mp4
2025-03-25 | Reporting
Miscellaneous Demos
TBD | Testing/Training Support
Billing Profiles and Billing Config |  |  | RAD3PL _ DEP_ Billing Review-20250416_140940-Meeting Recording.mp4
Billing Invoices |  |  | RAD3PL _ DEP Billing Discussion JOIN THIS ONE!-20250424_130209-Meeting Recording.mp4

## DEP Config Tasks
Deposco Configuration Task List
Product / Task Group | Task | SOW Notes | In Scope | Post Design - Configuration Notes | Owner | Status | % Complete
Bright Warehouse Configuration (T&M)
Inbound | Pre Receiving |  | TRUE | Tested Canceling Entire PO, Entire PO Lines, Partially Cancel PO Lines |  | Complete | 100%
Inbound | Receiving |  | TRUE | Successfully Received Purchase Orders, Blind Orders to loose stock and By LPN |  | Complete | 100%
Inbound | Returns |  | TRUE | Successfully Able to CreateRMA As Needed to Receive and Blind RMA through General Receiving |  | Complete | 100%
Inbound | Putaway |  | TRUE | Successfully Tested Move Processes - Move Container, Move Item, Move Stock |  | Complete | 100%
Inventory Management | Inventory Inquiry View |  | TRUE | Total On-Hand Qty, Total ATP Qty, Total ATR Qty, WhSE on BackOrder Qty, Reserve Loc Qty, Pickable Loc Qty, Open Pick Task Qty, Open Order Line Qty, Purchase Order Qty |  | Complete | 100%
Inventory Management | Item Tracking | Lot Tracking and Expiration Date Tracking | TRUE | Lot Tracking and Expiration Date Tracking |  | Complete | 100%
Inventory Management | Kitting |  | TRUE | Kit to Order & Kit to Stock Waving Pick Tasks Creations, ProductConversionw/&w/oWorkOrders |  | Complete | 100%
Inventory Management | Cycle Counting |  | TRUE | Cycle Count Task Creations - Scheduler, Location PAL, and Handheld Cycle Count By Location; Variance Management, and Exception Count Task |  | Complete | 100%
Inventory Management | Replenishment |  | TRUE | Manual Replenishment & Directed Replenishment Tasks |  | Complete | 100%
Outbound | Outbound Order Management |  | FALSE |  |  |  | 0%
Outbound | Pickwave Management |  | FALSE |  |  |  | 0%
Outbound | Picking |  | FALSE |  |  |  | 0%
Outbound | Packing and Shipping |  | FALSE |  |  |  | 0%
Outbound | Rate Shopping |  | FALSE |  |  |  | 0%
Other | Transfer Orders |  | FALSE |  |  |  | 0%
Other | Shipping Documents/Labels |  | FALSE |  |  |  | 0%
Other | 3PL Billing |  | FALSE |  |  |  | 0%
Setup | System Admin |  | FALSE |  |  |  | 0%
Setup | Data Maintenence |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M)
Configure | Web Store |  | FALSE |  |  |  | 0%
Configure | Retailer |  | FALSE |  |  |  | 0%
Configure | EDI Fulfillment |  | FALSE |  |  |  | 0%
Configure | Marketplace |  | FALSE |  |  |  | 0%
Configure | ERP/Accounting |  | FALSE |  |  |  | 0%
Configure | Carrier |  | FALSE |  |  |  | 0%
Configure | Shopify |  | FALSE |  |  |  | 0%
Configure | Quickbooks Online |  | FALSE |  |  |  | 0%
Configure | UPS |  | FALSE |  |  |  | 0%
Configure | FedEx |  | FALSE |  |  |  | 0%
Bright Performance Configuration (T&M)
Standard Dashboard and Reporting | Global Reports |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Company Reports/Report Builder |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Report Scheduling |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Dashboards |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Report Models |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Report Scheduling |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Data Archive |  | FALSE |  |  |  | 0%
Bright Order Configuration (T&M)
Configure - Order Orchestration | Preprocessing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Sourcing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Routing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Release |  | FALSE |  |  |  | 0%
Configure - Order Processing | Order Management |  | FALSE |  |  |  | 0%
Configure - Order Processing | Order Exception Management |  | FALSE |  |  |  | 0%
Configure - Enterprise Inventory | Enterprise Inventory Management |  | FALSE |  |  |  | 0%
Configure - INventory Segmentation | Manage Segments |  | FALSE |  |  |  | 0%

## Test Cases - Unit
RAD3PL Unit Test Cases |  | Category | % Complete
|  | Integrations | 0%
|  | Order Orchestration | 0%
|  | Inbound | 94.29%
|  | Inventory Management | 25.64%
|  | Outbound | #DIV/0!
|  | Other WMS | 0%
|  | Reporting | 0%
|  | TOTAL | 18.86%
Category | Subcategory | Scenario | Expected Outcome | Owner | Status | Test Data | Comments
Integrations
Integrations | Shopify - Item Pull | Execute: scheduled run at 00:00:00 nightly | Doc Store created at time of scheduled run. Doc Store status is Success, Failed, or INFO based on results of api search. Only items created or updated since last runtime of the scheduler are returned. |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with no entries into pop-ups | Doc Store created at time of manual run. Doc Store status is Success, Failed, or INFO based on results of api search. |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with one valid product ID | Doc Store created at time of manual run. Doc Store status is Success. Item is created if not already in Deposco and updated if already in Deposco. |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with multiple valid product IDs | Doc Store created at time of manual run. Doc Store status is Success. Items are created if not already in Deposco and updated if already in Deposco. |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with one invalid product ID | Doc Store created at time of manual run. Doc Store status is Failed. Item is not found by Shopify and nothing is created/updated in Deposco. |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with mix of valid/invalid product IDs | Doc Store created at time of manual run. Doc Store status is Failed. Items that are found by Shopify are created or updated in Deposco and items that are not found by Shopify are not. Failures/successes per item are visible in Doc Store Details |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to valid number greater than 0 | Doc Store created at time of manual run. Doc Store status is Success, Failed, or INFO based on results of api search. Only items created or updated in number of days entered are returned. |  | Ready to Test
Integrations | Shopify - Item Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to invalid number (non-numeric or <=0) | Doc Store created at time of manual run. Doc Store status is |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: "How Do You Want to Handle Items?" set to "Create Item and Channel Listing If Not Found and Only Allow Channel Listing Updates" - Pull item that does NOT yet exist in Deposco | Doc Store status is Success, Failed, or INFO based on results of api search. Item and channel listing are created if returned by Shopify. |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: "How Do You Want to Handle Items?" set to "Create Item and Channel Listing If Not Found and Only Allow Channel Listing Updates" - Pull item that DOES already exist in Deposco | Doc Store status is Success, Failed, or INFO based on results of api search. Only channel listing is updated if Item is returned by Shopify. |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: "Update Pack Weight" set to true |  |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: "Map Inventory Item Fields" set to true |  |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: Throttle Group Configured |  |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: Page Size set to 250 when more than 250 products are returned in the search |  |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: Page Size set to 250 when less than or equal to 250 products are returned in the search |  |  | Ready to Test
Integrations | Shopify - Item Pull | Criteria: "Shopify Product Status" set to "Active" only | Only "Active" products in Shopify returned and created/updated as necessary. |  | Ready to Test
Integrations | Shopify - Item Pull | Data: Pull product with a UPC that is already tied to another item in Deposco. | Doc Store status is Failed. |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one valid order ID |  |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with multiple valid order IDs |  |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one invalid order ID |  |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with mix of valid and invalid order IDs |  |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to valid number greater than 0 |  |  | Ready to Test
Integrations | Shopify - Order Pull | Execute: manual run with "Number of Days To Go Back (Number)" populated to invalid number (non-numeric or <=0) |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Shopify Status" set to Any |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Financial Status" have Paid, Partially Refunded, and Refunded checked |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Fulfillment Status" set to Unfulfilled |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Order Number Convention" set to order_number--id |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Since ID" left blank |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Intangible Line Item Status" set to Complete |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Tag Filter" set to ______ |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Enable OMS" set to true |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Ignore Existing" set to true where order already exists |  |  | Ready to Test
Integrations | Shopify - Order Pull | Criteria: "Ignore Existing" set to true where order does not already exist |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship full order at one time - single tracking number |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship full order at one time - multiple tracking numbers |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship partial order - single tracking number |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship partial order - multipile tracking numbers |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship kit to order products on full order at one time - single tracking number |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship kit to order products on full order at one time - multiple tracking numbers | Fail |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship order that was manually marked as fulfilled in Shopify | Fail |  | Ready to Test
Integrations | Shopify - Ship Notice | Data: Ship quantity greater than quantity order line in Shopify | Fail |  | Ready to Test
Integrations | Shopify - Ship Notice | Criteria: Notify Customer set to false |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Execute: Re-generate ship notice for failed transaction |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Execute: Re-process ship notice event for failed transaction |  |  | Ready to Test
Integrations | Shopify - Ship Notice | Execute: Scheduled re-process of ship notice event for failed transactions that have been retied less than 3 times |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync | Execute: Scheduled inventory sync nightly |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to true |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to false |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync | Criteria: "Measure Name" set to Total ATP Qty API |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync | Criteria: "Page Size" set to 200 with more than 200 items to sync |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync | Criteria: "Page Size" set to 200 with less than or equal to 200 items to sync |  |  | Ready to Test
Integrations | Quickbooks Online |  |  |  | Ready to Test
Integrations | Quickbooks Online |  |  |  | Ready to Test
Integrations | Netsuite |  |  |  | Ready to Test
Integrations | Netsuite |  |  |  | Ready to Test
Integrations | UPS - Rate Shop | Retrieve rates for domestic shipment |  |  | Ready to Test
Integrations | UPS - Rate Shop | Retrieve rates for international shipment |  |  | Ready to Test
Integrations | UPS - Rate Shop | Retrieve rates for Saturday Delivery shipment |  |  | Ready to Test
Integrations | UPS - Rate Shop | Retrieve rates for all relevant Ship Vias: UPS Ground, UPS 2Day etc. |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label for all relevant Ship Vias: UPS Ground, UPS 2Day etc. |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve domestic shipping label |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve international shipping label |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label using Prepaid Freight Terms Type |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label using Collect Freight Terms Type |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label using Third Party Freight Terms Type |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label for Saturday Delivery shipment |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label for Residential shipment |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label for shipment where Insurance is required |  |  | Ready to Test
Integrations | UPS - Shipping Label | Retrieve shipping label for shipment where Delivery Signature is required |  |  | Ready to Test
Integrations | UPS - Shipping Documents | Retrieve Commercial Invoice for international shipment |  |  | Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for domestic shipment |  |  | Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for international shipment |  |  | Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for Saturday Delivery shipment |  |  | Ready to Test
Integrations | FedEx - Rate Shop | Retrieve rates for all relevant Ship Vias: |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for all relevant Ship Vias: FedEx Ground, FedEx Home Delivery etc. |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve domestic shipping label |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve international shipping label |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label using Prepaid Freight Terms Type |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label using Collect Freight Terms Type |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label using Third Party Freight Terms Type |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for Saturday Delivery shipment |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for Residential shipment |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for shipment where Insurance is required |  |  | Ready to Test
Integrations | FedEx - Shipping Label | Retrieve shipping label for shipment where Delivery Signature is required |  |  | Ready to Test
Integrations | FedEx - Shipping Documents | Retrieve Commercial Invoice for international shipment |  |  | Ready to Test
Order Orchestration
Order Orchestration | Preprocessing - Data Validations | Ship Via missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | Ship To Address info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | Trading Partner missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | Line Item info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | Multiple data validations are triggered on CO | Order goes to Review status until all data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | Duplicate order warning is triggered | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | No data validation is triggered | Order is either Back Ordered or Released automatically upon creation |  | Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection | Order/order line meets ____ criteria | Order sources to Sourcing Group A based on sourcing profile. |  | Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection | Order/order line meets no matching Sourcing Selection Criteria | Order goes to Review with CoNotice message that sourcing could not be completed |  | Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile | Order meets ____ criteria | Order uses Routing Profile A based on routing selection profile. |  | Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile | Order meets no matching Routing Selection Criteria | Order goes to Back Order |  | Ready to Test
Order Orchestration | Order Release - Available Inventory | Inventory not available to fulfill entire CO in facility A | CO Back Orders |  | Ready to Test
Order Orchestration | Order Release - Available Inventory | Inventory is available to fulfill entire CO in facility A | CO Releases to facility A and creates an SO |  | Ready to Test
Order Orchestration | Order Management - Scheduled Routing | Scheduled re-route attempt on orders in Back Order status | Orders in Back Order automatically re-routed ever x hours. Order either stays in Back Order or moves to Released if inventory now available. |  | Ready to Test
Order Orchestration | Order Exception Management - Reprocess | Manual Reprocess CO in Review status | Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | Ready to Test
Order Orchestration | Order Exception Management - Reprocess | Scheduled Reprocess CO in Review status | Orders in Review automatically reprocessed every x hours. Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | Ready to Test
Order Orchestration | Enterprise Inventory Management | Inventory by Facility | Reports execute timely and accurately for all skus |  | Ready to Test
Order Orchestration | Inventory Segmentation - Manage Segments |  |  |  | Ready to Test
Inbound
Inbound | Pre Receiving - Inbound Cancelation | Cancel entire PO/RMA before receiving has started | PO will show up as canceled status | Matt | Pass | PO05 - order was canceled before it was checked-in
Inbound | Pre Receiving - Inbound Cancelation | Cancel some PO/RMA lines before receiving has started | A single SKU should be removed from purchase order | Matt | Pass | PO05 - cancelled LBC-SB SKU while receipt was still in new status
Inbound | Pre Receiving - Inbound Cancelation | Cancel part of PO/RMA line before receiving has started | " | Matt | Pass | PO05 - strawberry item removed from PO
Inbound | Pre Receiving - Inbound Cancelation | Cancel entire remaining PO/RMA after some receiving has been completed | User should receive a partial quantity and the remaining units will be canceled | Matt | Pass | PO68 - YoFiit - Received in 30 units to A-01-03, the remaining 10 units were canceled
Inbound | Pre Receiving - Inbound Cancelation | Cancel some PO/RMA lines after some receiving has been completed | One receipt is complete, cancel a specific line item | Matt | Pass | PO-120 - User canceled the cacaoitem
Inbound | Pre Receiving - Inbound Cancelation | Cancel part of PO/RMA line after some receiving has been completed | Cancel a partiqal quantity of a specific SKU | Matt | Pass | PO-120 Canceled 50 units of the cacaoitem
Inbound | Pre Receiving - Inbound Cancelation | Cancel part of PO/RMA while receiving is occurring |  | Matt | Pass | 114 - canceled 100 units of LBC-SB1oz while PO was line item is in "receiving" stage
Inbound | Receiving - Receive by Item | Scan item not on PO/RMA | Deposco will prompt a blind receipt creation | Matt | Pass | scanned "pbsnacksample" and was asked if I would like to create a blind receipt
Inbound | Receiving - Receive by Item | Scan item on PO/RMA | User will be sent to the next screen to select a PO | Matt | Pass | Scanned "YFVANU121" and was given a list of POs to choose from
Inbound | Receiving - Receive by Item | Scan item that doesn't exist in the system at all | User will create a blind receipt | Matt | Pass | BLind receipt was created for a new item
Inbound | Receiving - Receive by Item | Enter quantity less than quantity on PO/RMA | A lesser quantity will be received in | Matt | Pass | PO92 - only 10 units of YFVANU121 is checked in
Inbound | Receiving - Receive by Item | Enter quantity equal to quantity on PO/RMA | The quanity will be received, then that SKU will no longer appear on receive item screen | Matt | Pass | PO92 - all 30 units of YFVACS122 were received to R-10-02
Inbound | Receiving - Receive by Item | Enter quantity greater than quantity on PO/RMA to Demonstrate Overreceiving tolerance up to double the Order Pack Quantity | Up to double quantity will be allowed to receive | Matt | Pass | PO92 - received in 35 units of YFVANU121, even though inly 20 untis remained on PO
Inbound | Receiving - Receive by Item | Enter quantity less than quantity on PO/RMA for a Partial Receipt Status | Receipt will show "partial receipt" status | Matt | Pass | PO-79 - received in only 50 units of honey and partial receipt is displayed
Inbound | Receiving - Misc Receiving Scenarios | Receive damaged products | Items will be virtually in damaged location | Matt | Pass | PO-79 - 25 units were received into damaged location
Inbound | Receiving - Misc Receiving Scenarios | Receive Lot Tracked products |  | Matt | Pass | Order 2040 blind receipt was received by lot
Inbound | Receiving - Misc Receiving Scenarios | Receive Expiration Date tracked products |  | Matt | Pass | Order 2040 blind receipt was received by expiration date
Inbound | Receiving - Misc Receiving Scenarios | Receive an item with an Each Pack Type |  | Matt | Pass | 1 LBC-SB unit was received in (Blind 2040)
Inbound | Receiving - Misc Receiving Scenarios | Receive an Item with a non-Each Pack Type |  | Matt | Pass | PO-78 - received 3 bundles of cacao into receiving location
Inbound | Receiving - Misc Receiving Scenarios | Receive using item UPC |  | Matt | Pass | Item received by unit UPC
Inbound | Receiving - Misc Receiving Scenarios | Receive using pack UPC |  | Matt | Pass | Item received by pack UPC
Inbound | Returns - Create RMA | Create RMA for full SO |  | Matt | Pass | SO142 was returned in full due to damage, note added
Inbound | Returns - Create RMA | Create RMA for some lines of SO |  | Matt | Pass | SO136, SKU "YFORGU122" was returned due to damage
Inbound | Returns - Create RMA | Create RMA for partial SO line |  | Matt | Pass | SO32 - 10 out of a possible 20 units of "cacaoitem" were returned
Inbound | Putaway - Move Item | Putaway single sku from receiving to suggested putaway location (Choose from Location in Displayed Listbox if any) |  | Matt | Pass | Moved 10 units of YFVANU121 from receiving to a suggested location (A-01-03)
Inbound | Putaway - Move Item | Putaway single sku from receiving to non-suggested putaway location (Location doesn't display on listbox when prompted) |  | Matt | Pass | Moved 10 units of YFVANU121 from receiving to a random flow location
Inbound | Putaway - Move Item | Putaway a sku that has other units existing in reserve and/or picking locations |  |  | Pass
Inbound | Putaway - Move Item | Putaway a sku that has no other units existing in reserve and/or picking locations (Find an Empty Location) |  |  | Pass
Inbound | Putaway - Move Container | Putaway LPN from Receiving to location - maintain LPN structure in putaway location |  |  | Pass
Inbound | Putaway - Move Container | Putaway contents from LPN from Receiving-LPN location |  |  | Pass
Inbound | Putaway - Move Stock | Putaway loose contents from Receiving Location or content in assigned LPN to move to designated Locations |  |  | Pass
Inbound | UnReceiving | Unreceive PO from Receiving Location |  |  | Pass
Inbound | UnReceiving | Unreceive PO from LPN-Controlled Location and Perform Primary Steps Needed to Perform This |  |  | Pass
Inbound | Blind Receipt |  |  |  | Failed |  | When using the handheld, user is not prompted to enter an item quantity when creating a blind receipt
Inventory Management
Inventory Management | Inventory Inquiry - Quantities | Total On-Hand Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Total ATP Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Total ATR Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | WhSE on BackOrder Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Reserve Loc Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Pickable Loc Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Open Pick Task Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Open Order Line Qty Example |  | Matt | Pass
Inventory Management | Inventory Inquiry - Quantities | Purchase Order Qty Example |  | Matt | Pass
Inventory Management | Kitting - Kit to Order | Attempt Building a pickwave for Parent Item OrderLine with Kit To Order Checked with sufficient inventory of component Items in a picking location |  |  | Ready to Test
Inventory Management | Kitting - Kit to Order | Attempt Building a pickwave for Parent Item OrderLine with Kit To Order Checked with sufficient inventory of only Parent Items in a picking location | Should Backorder |  | Ready to Test
Inventory Management | Kitting - Kit to Stock | Attempt Building a pickwave for Parent Item OrderLine with Kit To Stock Checked with sufficient inventory of only Parent Items in a picking location |  |  | Ready to Test
Inventory Management | Kitting - Kit to Stock | Attempt Building a pickwave for Parent Item OrderLine with Kit To Stock Checked with sufficient inventory of only Component Items in a picking location | Should Backorder |  | Ready to Test
Inventory Management | Kitting - Kit to Stock - Product Conversion w/o Workorder | Create a Workorder with Pre-Defined Kit Header and Details |  |  | Ready to Test
Inventory Management | Kitting - Kit to Stock - Product Conversion w/o Workorder | Attempt createing a Workorder with No Pre-Defined Kit Header and Details | Should Fail |  | Ready to Test
Inventory Management | Kitting - Product Conversion w Workorder | Build a Workorder with enough input stock at a Workcell Location |  |  | Ready to Test
Inventory Management | Kitting - Product Conversion w Workorder | Attempt to Build a Workorder without enough input stock at a Workcell Location | Should Fail |  | Pass
Inventory Management | Cycle Counting - Task Creation - By Location | Create Cycle Count Tasks by Location Scheduler - Cycle Count Task Created Based on Location's Cycle Count Frequency and Last Counted Date |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Creation - By Location | Create Cycle Count Task Ad-hoc Through Location PAL where Cycle Count = true |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Creation - By Location | Create Cycle Count Task Ad-hoc Through Location PAL where Cycle Count = false | Fail or Nothing Should Happen |  | Ready to Test
Inventory Management | Cycle Counting - Task Creation - By Location | Create Cycle Count Task Through Handheld By Using Cycle Count By Location where Location Cycle Count = true |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Creation - By Location | Create Cycle Count Task Through Handheld By Using Cycle Count By Location where Location Cycle Count = false | Fail or Nothing Should Happen |  | Ready to Test
Inventory Management | Cycle Counting - Task Creation - By Item | Create Cycle Count Tasks by Item Scheduler - Cycle Count Task Created Based on Item's Cycle Count Frequency and Last Counted Date |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Count location with one item |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Count location with multiple items |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Count exact quantity that actually exists in the location systematically |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Count different quantity than what actually exists in the location systematically | Recount is required |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Skip counting an item in a location by hitting "Next Location" before all items are counted | Zero is recorded as count for items not counted |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Scan an item that does not systematically exist in a location when counting |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Approve a variance that's different from the current stock quantity |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Reject a variance that's different from the current stock quantity |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Force a Recount on a variance that's different from the current stock quantity |  |  | Ready to Test
Inventory Management | Cycle Counting - Task Execution - By Location | Force an Exception Task By Selecting NO_STOCK in the Picking Process |  |  | Ready to Test
Inventory Management | Replenishment | Perform a Manual Replenishment Task |  |  | Ready to Test
Inventory Management | Replenishment | Perform a Directed Replenishment Task |  |  | Ready to Test
Inventory Management | Inventory Adjustments | Consume By Item |  |  | Ready to Test
Inventory Management | Inventory Adjustments | Consume By LPN |  |  | Ready to Test
Inventory Management | Inventory Adjustments | Create Stock |  |  | Ready to Test
Outbound I
Outbound I | Outbound Order Management - POI Done | POI runs successfully | POI Done flag is set to true - POI Complete? field should display true |  | Ready to Test
Outbound I | Pickwave Management - Waving Execution | Manually wave one order | Order selected remains in New, moves to Back Ordered, or moves to Released based on profile match and inventory evaluation |  | Ready to Test
Outbound I | Pickwave Management - Waving Execution | Manually wave multiple orders | All orders selected remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation |  | Ready to Test
Outbound I | Pickwave Management - Pickwave Profile | Order matches no waving criteria | Order stays in New or Back Ordered status |  | Ready to Test
Outbound I | Pickwave Management - Back Order Management | Order waved has sufficient inventory available to release | Order moves to Released and is assigned a Pickwave with work group and pick tasks |  | Ready to Test
Outbound I | Pickwave Management - Back Order Management | Order waved as no sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
Outbound I | Pickwave Management - Back Order Management | Order waved as partially sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
Outbound I | Outbound I - Singles Order Management | Manually wave multiple singles orders on one pickwave |  |  | Ready to Test
Outbound I | Picking - Singles Picking | Complete picking of Singles pickwave through SIngles Scan Picking |  |  | Ready to Test
Outbound I | Packing - Singles Packing | Complete packing of SIngles pickwave through Pack Order By Item |  |  | Ready to Test
Outbound I | Outbound I - Multis Orders Management | Manually wave multiple multis orders on one pickwave |  |  | Ready to Test
Outbound I | Picking - Multis Picking | Complete picking of Multis pickwave through Batch Picking |  |  | Ready to Test
Outbound I | Packing - Multis Packing | Complete packing of Multis pickwave through Single Scan Packing |  |  | Ready to Test
Outbound I | Outbound I - Large B2C Order Management | Manually wave one Large B2C order on one pickwave |  |  | Ready to Test
Outbound I | Picking - Large B2C Picking | Complete picking of Large B2C pickwave through SIngles Scan Picking |  |  | Ready to Test
Outbound I | Packing - Large B2C Packing | Complete packing of Large B2C pickwave through Single Scan Packing |  |  | Ready to Test
Outbound I | Outbound I - Undo Wave Release | Undo Wave Release of a Singles Pick wave and Re-release |  |  | Ready to Test
Outbound I | Outbound I - Undo Wave Release | Undo Wave Release of a Multis Pick wave and Re-release |  |  | Ready to Test
Outbound I | Outbound I - Undo Wave Release | Undo Wave Release of a Large B2C Pick wave and Re-release |  |  | Ready to Test
Outbound II
Outbound II | Outbound II - B2B Wholesale Order Management | Manually wave multiple B2B Wholesale orders on one pickwave
Outbound II | Picking - B2B Wholesale Picking | Complete picking of B2B Wholesale pickwave through SIngles Scan Picking
Outbound II | Packing - B2B Wholesale Packing | Complete packing of B2B Wholesale pickwave through Assign Trip to Container
Outbound II | Roll Back After Picking | Complete Rollback after Picking for Any Pickwave Type
Outbound II | Void and Reprocess Shipment | Complete the Void and Reprocess Shipment Process and Display Both Shipment Tracking Numbers After Completion
Outbound II | Repalletize | Combine multiple pallets across multiple orders onto one pallet before shipping out
Outbound II | Rate Shopping | Confirm the Cheapest shipping service is selected in Single Scan Packing with no Order Shipping Tiers specified
Outbound II | Rate Shopping | Confirm that the Cheapest Tier 1 shipping service is selected in Single Scan Packing
Outbound II | Packing Slips | Generate Packing Slip for Any Chosen Business Unit After Completing Picking for an Order
Outbound II | Standard BOL | Generate Standard BOL for Any Chosen Business Unit After Completing Picking for an Order
Other WMS
Other WMS | Other WMS - Transfer Orders |  |  |  | Ready to Test
Other WMS | Other WMS - Shipping Documents/Labels |  |  |  | Ready to Test
Other WMS | Other WMS - 3PL Billing |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Other WMS |  |  |  |  | Ready to Test
Reporting
Reporting | Dashboard - Inbound | -- | Report returns timely and accurately for customer needs
Reporting | Dashboard - Inventory Management Dashboard | -- | Report returns timely and accurately for customer needs
Reporting | Dashboard - Outbound | -- | Report returns timely and accurately for customer needs
Reporting | Dashboard - User Performance | -- | Report returns timely and accurately for customer needs
Reporting | Report Builder - | -- | Report returns timely and accurately for customer needs

## Test Cases - End to End
RAD3PL End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 0%
Category | Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Inbound | Receive PO full | Ready to Test | RAD3PL
Inbound | Receive Partial PO | Ready to Test | RAD3PL
Inbound | Create RMA from shipped SO and receive in full | Ready to Test | RAD3PL
Inbound | Create RMA from shipped SO and receive partially | Ready to Test | RAD3PL
Inbound | Create RMA from shipped SO and do not receive immediately | Ready to Test | RAD3PL
Inbound | Unreceive full PO | Ready to Test | RAD3PL
Inbound | Unrecieve partial PO | Ready to Test | RAD3PL
Inbound | Blind receive additional units found after receiving | Ready to Test | RAD3PL
Inbound | Over receive PO | Ready to Test | RAD3PL
Inbound | Over receive RMA | Ready to Test | RAD3PL
Inbound | Putaway single item containers | Ready to Test | RAD3PL
Inbound | Putaway mixed item containers | Ready to Test | RAD3PL
Inbound | Putaway containers to reserve locations | Ready to Test | RAD3PL
Inbound | Putaway containers to pickable locations | Ready to Test | RAD3PL
Inbound | Putaway loose stock to reserve locations | Ready to Test | RAD3PL
Inbound | Putaway loose stock to pickable locations | Ready to Test | RAD3PL
Outbound
Outbound | Fulfill "large" orders | Ready to Test | RAD3PL
Outbound | Fulfill single unit orders | Ready to Test | RAD3PL
Outbound | Fulfill multi unit orders | Ready to Test | RAD3PL
Outbound | Fulfill international orders | Ready to Test | RAD3PL
Outbound | Fulfill domestic orders | Ready to Test | RAD3PL
Outbound | Exception a pick task for "large" order | Ready to Test | RAD3PL
Outbound | Exception a pick task for a single unit order | Ready to Test | RAD3PL
Outbound | Exception a pick task for a multi unit order | Ready to Test | RAD3PL
Outbound | Cancel an order that has not yet been released | Ready to Test | RAD3PL
Outbound | Cancel an order that has been released but not picked | Ready to Test | RAD3PL
Outbound | Cancel an order that has been picked but not packed or shipped | Ready to Test | RAD3PL
Outbound | Cancel an order that has been packed but not shipped | Ready to Test | RAD3PL
Outbound | Roll back an order that has been shipped and cancel it | Ready to Test | RAD3PL
Outbound | Roll back an order that has not been shipped and re-ship | Ready to Test | RAD3PL
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Ready to Test | RAD3PL
Inventory Management | Perform scheduled cycle counts by item | Ready to Test | RAD3PL
Inventory Management | Perform on demand cycle counts by location | Ready to Test | RAD3PL
Inventory Management | Perform scheduled replenishment tasks | Ready to Test | RAD3PL
Inventory Management | Perform on demand replenishment tasks | Ready to Test | RAD3PL
Inventory Management | Over-replenish | Ready to Test | RAD3PL
Inventory Management | Perform exception during replenishment | Ready to Test | RAD3PL

## GoNo-Go Decision
RAD3PL Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 81
Deposco Setup | Label Printers | 10 | Y | RAD | 80% | 8 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 |  | RAD | 100% | 10 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 |  | RAD | 100% | 10 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 |  | RAD | 90% | 9 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | RAD | 80% | 8 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | RAD | 80% | 8 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | RAD | 80% | 8 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | DEP | 100% | 10 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 |  | DEP | 100% | 10 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 40 |  |  |  | 38
Warehouse Prep | Location Labels | 10 |  | RAD | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Container Labels | 10 | Y | RAD | 80% | 8 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Inventory Labels | 10 |  | RAD | 100% | 10 | Are all inventory units labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 |  | RAD | 100% | 10 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 12 |  |  |  | 1
SOP Documents | Receiving/Unreceiving | 1 |  | RAD | 100% | 1 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Kitting (Kit To Stock) | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | LTL Shipping (Wholesale) | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Picking | 1 |  | RAD | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 48
Training & Testing | Test Case Scenarios Definition | 10 |  | DEP / RAD | 100% | 10 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and XXX to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 |  | RAD | 100% | 10 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 |  | RAD | 100% | 10 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 |  | RAD | 100% | 10 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | RAD | 80% | 8 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 60 |  |  |  | 53
Master Data | Cutover Inventory Validation | 10 |  | DEP | 100% | 10 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 |  | RAD | 90% | 9 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 |  | RAD | 100% | 10 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | RAD | 80% | 8 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Kit/Component Relationships | 10 | Y | RAD | 70% | 7 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 |  | RAD | 90% | 9 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
Master Data | Billing | 10 | Y | RAD | 20% | 2
| Cutover Plan | 10 |  |  |  | 6
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / RAD | 60% | 6 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 45
Interfaces - Imports to Deposco | Carton Types Upload | 10 |  | RAD | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 |  | RAD | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 |  | RAD | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | RAD | 100% | 5 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 |  | RAD | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Exports from Deposco | Email confirmation upon shipment | 10 |  | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 90 |  |  |  | 90
Integrations with Deposco | CartRover - Order Push | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | CartRover - Shipment pull | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | CartRover - Inventory pull | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | DHL - Get Shipping Label | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | DHL - Get Shipping Label | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Stamps - Get Shipping Label | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Stamps - Get Rate Shop Request | 10 | Y | RAD | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 70 |  |  |  | 55
Reports and Labeling | Shipping Label | 10 |  | RAD | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Packing Slip Report | 10 | Y | RAD | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | Nothing using DEP packing slip report but DEP will need to test/validate image that is coming in
Reports and Labeling | Location Label | 10 |  | RAD | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Item Label | 10 |  | RAD | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Carton Type Label | 10 | Y | RAD | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Container Label | 10 | Y | RAD | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Generic BOL Report | 10 | Y | RAD | 70% | 7 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | DEP / RAD | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 427
| Total Possible Score: | 477
| Total Percentage: | 89.52%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan R1
RAD3PL Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE | TIME
1 | Create Production Environment | Create ticket to stand up prod environment | TRUE | DEP | Erica | 2025-04-28 | 6:00
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | RAD3PL |  | 2025-04-28
3 | Set up Shopify/Cin7/CartRover Accounts | Set up Shopify/Cin7/CartRover Instances in Production environment | FALSE | RAD3PL |  | 2025-04-28
4 | Test Item Pull | Ensure all items come into Deposco as expected or re-upload Items through Data Exchange | TRUE | DEP/RAD3PL |  | 2025-04-28
5 | Test Orders Pull | Create a test order in Shopify/CartRover and Cin7/CartRover and bring orders into Deposco | FALSE | RAD3PL |  | 2025-04-28
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify/CartRover | FALSE | DEP/RAD3PL |  | 2025-04-28
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify/CartRover | FALSE | DEP/RAD3PL |  | 2025-04-28
8 | Test UPS shippingLabel | Fulfil an order using all UPS shipping services | FALSE | RAD3PL |  | 2025-04-28
9 | Test STAMPS shippingLabel | Fulfil an order using all STAMPS shipping services | FALSE | RAD3PL |  | 2025-04-28
10 | Test DHL shippingLabel | Fulfil an order using all DHL shipping services | FALSE | RAD3PL |  | 2025-04-28
10 | Master Data Check - Items | Look through items in production environment | TRUE | RAD3PL |  | 2025-04-28
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | TRUE | RAD3PL |  | 2025-04-28
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions and a weight | TRUE | RAD3PL |  | 2025-04-28
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every Location has an applicable zone | TRUE | RAD3PL |  | 2025-04-28
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack/location pair has storage record if applicable | TRUE | RAD3PL |  | 2025-04-28
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE | DEP/RAD3PL |  | 2025-04-28
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE | RAD3PL |  | 2025-04-30 | 19:00
18 | Inventory Push to Deposco | Inventory is cycleCounted Directly in Deposco or StockUnit Data Exchange is executed | FALSE | RAD3PL |  | 2025-05-01 | 5:00
19 | Inventory Push to Shopify | Inventory is pushed to Shopify/CartRover | FALSE | RAD3PL
20 | Turn on Order Pull in Deposco | Turn on scheduler for CartRover Instances for Phase One Customers to bring in orders | FALSE | RAD3PL
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE or confirm the cycleCounted stock depending on inventory strategy decided from line 18 | FALSE | RAD3PL
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE | RAD3PL
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE | RAD3PL
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE | RAD3PL
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | TRUE | RAD3PL |  | 2025-04-29
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | TRUE | RAD3PL |  | 2025-04-29
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
32 | Smoke Test - International Fulfillment | Pack an international order, order is shipped outside system or an international shipping service | FALSE | RAD3PL |  | 2025-04-30 | 17:00
33 | Smoke Test - Wholesale Picking | Pick for a B2B Wholesale order, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
34 | Smoke Test - Wholesale Packing | Pack a B2B Wholesale Order through Assign Trip, ensure everything behaves as expected | FALSE | RAD3PL |  | 2025-04-30 | 17:00
35 | Begin Fulfilling Orders |  | FALSE | RAD3PL |  | 2025-05-01 | 6:00

## Go Live Notes
Day | Process | Description | Changed By | Request/Issue? | Requested By | Team | Status | Comments
Tuesday | Billing | Add Config for per order shipped - ecomm | Josiah | Request | Andrew | NA | Complete
| Billing | Add config for per unit picked - ecomm | Josiah | Request | Andrew | NA | Complete
| Reporting | Customer inventory report showing on hand and atp | Erica | Request |  | NA | Complete
| Billing | Combine international upcharge to be used for domestic and international | Josiah | Request | Andrew | NA | Complete
|  | Prepopulated Bin in BatchPicking - Follow-up with Matt for more details? |  | Issue | Matt | RAD3PL | Validation
| Billing | Add config that just stamps the shipping cost as the totalprice for all shipping services where freight type = 'freight' | Josiah | Request | Andrew | NA | Complete
| Shipping | UPS Access Token | Andrew | Issue | Matt | NA | Complete
| API | Add facility to all sales orders (wait for orders to come in from Andrew adding field in cartrover) | Andrew | Issue | Josiah | NA | Complete | Coming in from cartrover
| Shipping | Transient bins are shipping, prevent those from leaving | Josiah | Issue | Josiah | NA | Complete
Wednesday | Packing | Changed COMMIT_ON_NEW_BIN, ALWAYS_CREATE_NEW_BIN, KEEP_ORIGINAL_CONTAINER_NUMBER | Josiah |  |  | NA | Complete
| Reporting | Expired stock report | Josiah | Request | Matt | NA | Complete
| Automations | Add tiers in lookup record for AK and HI and automation rules to set for all bu's |  |  |  | RAD3PL | Open | 5/13: Need to follow up with RAD3PL team on the details
| Billing | Adjusted oversized pallet and pallet location billing queries to bill if stock is in those locations instead of stock on a container of type pallet | Josiah | Request | Andrew | NA | Complete
| SSpicking | flipped qty and sku text fields in picking | Josiah | Request | Matt | NA | Complete
| Packing | pack order by item creates order number as container and dhl uses that as package id - causing issues so need to strip the # | Josiah | Issue | Matt | NA | Complete | Added rules in dhl label to strip the # for dhl orders to stop error from showing
| POI | Total Order Qty Calculation in POI updated to now take into consideration KitToOrder/KitToStock OrderLineItems | Erica | Request |  | NA | Complete
Thursday | Waving | Remove logic requiring pickwave to be null and add a waving scheduler that will rewave only backorders |  | Request | Matt | NA | Complete
| Shipping | Orders that pull in with blank shipVias end up failing during rateShopping, added automation rules to set as "Ship Outside System" in these cases | Erica | Issue | Matt | NA | Complete | Now sets to ship outside system
| Stamps | Added stamps label rules to set the order number at the bottom of the label | Josiah | Request | Matt | NA | Complete
Friday | Waves | Added build time with seconds to names | Josiah |  |  | NA | Complete
| Picking | Adjusted batchpicking from pick sequence to be expiration then location pick sequence | Josiah | Request |  | NA | Complete | singles picking had biggest pack first, fefo then location pick sequence. Needed batchpicking and singles to match
| Picking | sspicking - qty text field shows up twice during pallet picks |  |  |  | RAD3PL | Validation
| Picking | Pallet picking - adjusted scan item or pallet si to be dynamic item and pallet until they can get lpn labels onto their pallets | Josiah | Request | Matt | NA | Complete
| poi | Add logic to stamp earliest exp date onto order ship by date |  | Request | Matt | Erica | Open
| sspicking | Allow them to create a container in sspicking to pick into for the pallet picking flow |  | Request |  | Erica | Open
| Batchpicking | Do not allow items to be placed in a bin if items for another order exist (Happened to bin 9) |  | Issue |  | Erica | Open | 5/13: There is a workaround available for when/if this occurs
| SsPacking | Orders with po boxes cannot be rateshopped, need to set these to usps during automations |  | Request |  | Erica | Validation | 5/13: In validation

## Future ItemsParking Lot
RAD3PL Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | RAD3PL Comments
Pre-kitting or work order kitting | Adding Pre-kitting or work order kitting | 2025-02-12 |  |  |  | Current not in scope under SOW001. If needed, we would need SOW to support this. DEP can provide estimation to implement this.