## Task Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
| Client: | Sunrise Brands | Sunrise Brands
| Client Code: | SRB | SRB
| Tasks Required: | 108 | 111
| Test Cases Executed: | 72 | 59
| Test Cases Passed: | 47 | 54
| Test Cases In Progress: | 4 | 0
| % Complete: | 43.52% | 48.65%
Task No. | TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Due Date | DEP Comments | SRB Comments | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | ETA | LINK TASK
1 | Provide EDI Retailer List of trading partners and documents |  | Task | High | 3 | FALSE | FALSE | Closed | SRB | Liza | 2024-03-21 | 2024-04-12
2 | Print Server Setup | SRB to install Deposco Print Client and test Printers in Deposco | Task | High | 3 | FALSE | FALSE | Closed | SRB | Galeb | 2024-03-21
3 | Ship Via Mappings | SRB to provide list of shipVia and setup in Decision Service | Task | High | 3 | FALSE | FALSE | Completed | SRB | Liza | 2024-03-21 |  |  |  | done
4 | Setup/Register UPS Accounts |  | Task | High | 3 | FALSE | FALSE | Completed | SRB | deposco | 2024-03-21 | 2024-04-12 | Dep Dev ticket: https://deposco.atlassian.net/browse/SYMSUP-385 |  | need Deposco help with generation, all accounts ready for that
5 | Setup/Register Fedex Accounts |  | Task | High | 3 | FALSE | FALSE | Completed | SRB | liza, done | 2024-03-21 | 2024-04-12 | Each account needs to be validated during Outbound validation |  | done
6 | Setup/Register OnTrac Account | Confirm whether SRB uses OnTrac | Task | High | 3 | FALSE | FALSE | In Progress | SRB | Liza / Maria | 2024-03-21 | 2024-08-30 |  |  | we do not have an Ontrac account
7 | Setup/Register DHL Account | Per Maria, this is applicable | Task | High | 3 | FALSE | FALSE | In Progress | SRB | Liza / Maria | 2024-03-21 | 2024-08-30 |  |  | DHL account only used by NYDJ which is separate business unit
8 | Inventory Adjustment Reason Codes | SRB to provide list of codes (DMG, LOST, EXP ie) | Task | High | 3 | FALSE | FALSE | Closed | SRB |  | 2024-03-21
9 | Upload Current Locations and Zones into Deposco | Use Depsoco Data Exchange Tool to upload all locations into Deposco | Task | High | 3 | FALSE | FALSE | Completed | SRB | Maria | 2024-03-21 | 2024-04-19 | DEP to review Maria's changes
10 | Create all Users into Deposco | Upload all users into Deposco, Data Exchange Template. All UAT users should be created in the system before UAT | Task | Low | 3 | FALSE | FALSE | Open | SRB | Maria | 2024-03-21 | 2024-09-13
11 | Set up Deposco on all devices | Set up Deposco on all devices | Task | High | 3 | FALSE | FALSE | Open | SRB | Maria | 2024-03-21 | 2024-09-13
12 | Add outbound client-specific test cases to the Project Tracker | Add any additional test cases that need to be tested in the Unit Test Cases tab | Task | High | 1 | TRUE | TRUE | Completed | SRB | Amber/Martha | 2024-06-24 | 2024-08-28 |  | Additional scenarios beside what we already presented will be show during the training at the warehouse
13 | NB - Inbound Shipment PUT - Gateway Timeout | https://deposco.atlassian.net/browse/SRBSUP-1 | Issue | High | 2 | TRUE | TRUE | Hold | DEP | Owen | 2024-06-24 | 2024-06-28 |  |  | putting on hold as they are now using CSV import
14 | Validate ALL inbound test case scenarios | Validate ALL inbound test case scenarios | Task | High | 1 | TRUE | TRUE | Completed | DEP | Amber/Martha | 2024-07-02 | 2024-08-28 |  | We validate this one except that we are waiting on answere on the cancelations or partial cancellation on FGPO
15 | Inbound Demo Post Callouts/Updates | Review internal notes and make any updates/resolve issues following demo | Task | High | 2 | TRUE | TRUE | Completed | SRB |  | 2024-07-02 | 2024-07-12
16 | Add Print LPN Logic to GR | GeneralReceiving_CompleteReceipt-post | Task | High | 3 | TRUE | TRUE | Hold | DEP |  | 2024-07-19 | 2024-08-28 |  |  | no longer needed if just using ASN receiving
17 | Inventory Configurations |  | Task | High | 1 | TRUE | TRUE | Closed | DEP | OZ | 2024-07-02 | 2024-07-22
18 | Outbound Configurations |  | Task | High | 1 | TRUE | TRUE | Closed | DEP | OZ/Nidhi | 2024-07-02 | 2024-08-12
19 | Printer Assignment Setup | Set up which reports go to which printers | Task | Low | 4 | TRUE | TRUE | Completed | SRB | Maria | 2024-07-16 | 2024-09-13 | Only stations 1-3 are set up correctly, awaiting PDF printers to be set up as well as the additional assignments for packing slips to be set up.
20 | SSCC Label. Custom Field document | Fill out required fields for SSCC labels: https://docs.google.com/spreadsheets/d/1Z2Gw-ZY85aEZZd58LF148YvuIAGgzoMAXceTGReqUG4/edit?gid=0#gid=0 | Task | High | 2 | TRUE | TRUE | Completed | SRB | what further info do you need | 2024-07-19 | 2024-08-09
21 | SSCC Label Formatting |  | Task | High | 2 | TRUE | TRUE | Completed | DEP |  | 2024-07-19 | 2024-08-16
22 | SSCC Label Formatting Validations (UCC Label) |  | Task | High | 2 | TRUE | TRUE | Closed | SRB | Liza | 2024-07-19 | 2024-08-23
23 | Over Receiving Callouts | DEP to look into preventing over receipt based on OL qty | Task | High | 3 | FALSE | FALSE | Validation | SRB | Maria/Jesus | 2024-07-19 | 2024-08-23
24 | Inventory Callouts | open tasks from inventory demo | Task | High | 2 | FALSE | FALSE | Validation | SRB | Maria | 2024-07-23 | 2024-08-23
25 | Unable to update customer order | DEV ticket: https://deposco.atlassian.net/browse/SRBSUP-3 | Task | High | 2 | FALSE | FALSE | Validation | SRB | ? | 2024-07-26 | 2024-08-23
26 | Upload Future Locations and Zones into Deposco | Use Depsoco Data Exchange Tool to upload all locations into Deposco | Task | High | 3 | TRUE | TRUE | Completed | SRB | Maria | 2024-07-26 | 2024-09-06
27 | Update Item Shippable flag in Deposco | This field determines if an item can be shipped | Task | High | 2 | TRUE | TRUE | Completed | SRB |  | 2024-07-29 | 2024-09-06
28 | Packing Slip Configurations |  | Task | High | 2 | TRUE | TRUE | Validation | SRB | Liza | 2024-07-29 | 2024-09-13
29 | Import Stock Units/Inventory |  | Task | High | 3 | TRUE | TRUE | Completed | DEP/SRB | Maria | 2024-07-29 | 2024-08-30
30 | Update Locations LPN Controlled | SRB to determine which locations need to be lPN controlled and which do not | Task | High | 3 | TRUE | TRUE | Completed | SRB | Maria | 2024-08-01 | 2024-08-23
31 | Carton Type Uploads | SRB to upload this so they can select from drop down for priority orders | Question | Low | 3 | FALSE | FALSE | Open | SRB |  | 2024-07-29 | 2024-09-13
32 | General Receiving: loses Order info after receiving | Deposco to advise | Task | High |  | FALSE | FALSE | Validation | SRB |  | 2024-08-05 | 2024-08-23
33 | Single Scan Packing: Auto populate dimensions for non priority services |  | Task | Low |  | TRUE | TRUE | Completed | SRB | Liza | 2024-08-16 | 2024-08-23
34 | Non auto populated services | SRB to add DS comments for shipping services that do not require ship services | Task |  |  | TRUE | TRUE | Completed | SRB |  | 2024-08-16 | 2024-08-20
35 | Set TP on shipping carriers |  | Task | Low |  | FALSE | FALSE | Open | SRB |  | 2024-08-19 | 2024-09-13
36 | Printer assignment data exchange |  | Task | Low |  | TRUE | TRUE | Completed | SRB |  | 2024-08-19 | 2024-08-23 | Nidhi Patel could you help with this one?
37 | Shipping service data exchange | Upload LTL carriers | Task | Low |  | TRUE | TRUE | Completed | SRB |  | 2024-08-20 | 2024-08-29
38 | Development - SRB to not allow extra cartons to not get created in ERP |  | Task | High |  | FALSE | FALSE | Open | SRB |  | 2024-08-21 | 2024-09-06
39 | Development - SRB to update shipment numbers | PONumber+CreatedDate | Task | High |  | FALSE | FALSE | Open | SRB |  | 2024-08-21 | 2024-09-06
40 | Inbound Shipment Data Exchange Issue | Example, RAAZIA92. Multiple PO/shipment relationships. | Task | Low | 5 | TRUE | TRUE | Closed | DEP | Owen | 2024-08-21 | 2024-09-06 |  |  |  |  | closing as this is not causing issues
41 | Stamping new values on Shipment/Trip for LTL Hard Close | see values on custom field mapping document, hard close process screen | Task | High | 3 | TRUE | TRUE | Validation | SRB | Amber | 2024-08-22 | 2024-09-13 | OZ added these rules and tested
42 | Import shipping service records for LTL truck services |  | Task | High | 3 | TRUE | TRUE | Completed | SRB |  | 2024-08-22 | 2024-09-06
43 | Unflag active shipping services that SRB does not utilize |  | Task | High | 3 | TRUE | TRUE | Closed | SRB |  | 2024-08-22 | 2024-08-29
44 | Add validation during LTL Hard Close so that ship via can not be SRG/Truck |  | Task | High | 3 | TRUE | TRUE | Validation | SRB | Amber | 2024-08-22 | 2024-09-13
45 | Add POI rules for third party vs. prepaid | Add POI rule to set third party if oh.freightBillToAccount is not null or oh.consigneePartner.ups/fedex is not null, else prepaid | Task | High | 3 | TRUE | TRUE | Completed | SRB |  | 2024-08-22 | 2024-09-06
46 | Update customers (trading partners) with the Prepaid account name |  | Task | High | 3 | TRUE | TRUE | Completed | SRB |  | 2024-08-22 | 2024-09-06
47 | Configure Special zone prepick scheduler | 1. Maria to update location/zones 2. validate the replenishments | Task | High | 3 | TRUE | TRUE | Completed | SRB | Maria | 2024-08-22 | 2024-09-09 | Maria & Amber to finish today (9/9)
48 | Add all printers in Deposco |  | Task | High | 3 | TRUE | TRUE | Completed | SRB |  | 2024-08-27 | 2024-09-03
49 | Trading Partner EDI Updates | SRB needs to update all TPs to have packing slip report, zpl label report, packing slip levele, uccean company number | Task | High | 3 | TRUE | TRUE | Open | SRB | Maria/Liza | 2024-08-27 | 2024-09-13 | Opening up to have ecomm PS added to TPs.
50 | UAT Agenda | Send UAT agenda to Maria | Task | High | 3 | TRUE | FALSE | Closed | DEP | OZ | 2024-08-30 | 2024-08-30
50 | API for third party shipping | Ensure API is sending third party information correctly | Task | High | 3 | TRUE | TRUE | Completed | SRB |  | 2024-08-27 | 2024-09-03
51 | Packing Printing | Ensure packing slip/SSCC prints during ss packing. | Task | High | 3 | TRUE | TRUE | Completed | SRB | Nidhi | 2024-08-28 | 2024-09-03
52 | Expeceted Qty API | Create API SQL for stock unit qty on approve variances table | Task | NTH | 5 | FALSE | FALSE | Closed | DEP |  | 2024-08-29 | 2024-09-13 | unable to do this as this requires 2 inputs, which is not supported with api sql
53 | Receipt Summary - Report Builder | Provide training to SRB on how to create this report in Report Builder. | Task | NTH | 5 | FALSE | FALSE | Open | DEP/SRB |  | 2024-09-03 | 2024-09-13
54 | Wave screen updates | SRB wants to manually assign all pick waves to users for all order types. Update wave screen BR to only show waves assigned to user. | Task | High | 3 | FALSE | TRUE | Completed | SRB |  | 2024-09-04 | 2024-09-13
55 | SOP - Waving | Create SOPs for wave mgmt, assigning users to pick waves via WorkGroup view. | Task | High | 3 | FALSE | TRUE | Open | SRB | Amber/Martha | 2024-09-04 | 2024-09-13
56 | Manifest report | Update manifest report input to the query. Needs to be Customer Order #. | Task | High | 3 | FALSE | FALSE | In Progress | DEP | NP | 2024-09-04 | 2024-09-30
57 | SRB Pallet Scan - Receiving | Validation on pallet scan to ensure they are scanning a pallet number that starts with SRB. Ex: SRB-1,SRB-2,SRB-3... | Task | High |  | FALSE | FALSE | Validation | SRB |  | 2024-09-04 | 2024-09-13
58 | Permissions | Update permissions for each Group | Task | High |  | FALSE | FALSE | Open | SRB |  | 2024-09-04 | 2024-09-13 | Help Site: https://docs.deposco.com/docs/html/Content/Administration/Users_and_groups/Groups/Application_permissions_for_a_group.htm?tocpath=Administration%7CUsers%20and%20groups%7CGroups%7CCreate%20a%20group%7C_____4
59 | Lookup Process | Investigate if there is a lookup process that can be used to scan a pallet and get the count of inner cotnainers scanned onto the pallet during ASN receiving | Task | High |  | FALSE | FALSE | Validation | DEP | JM | 2024-09-04 | 2024-09-13 | 9/12 JM - configured ASN Receiving rules to perform screen overrides to show the count of containers already received onto the scanned pallet. Flipping to SRB team to test
60 | API SQL | API SQL: Total Carton Count and Units Received on the PO to show how many LPNS and units were recevied during ASN receiving | Task | Low |  | FALSE | FALSE | Validation | SRB | OZ | 2024-09-04 | 2024-09-13
61 | SOP - Outbound | Create SOPs for outbound. | Task | Blocker | 1 | FALSE | TRUE | Open | SRB | Amber/Martha | 2024-09-04 | 2024-09-13
62 | Physical Equipment Readiness | Receiving pallets need labeled Outbound singles pallets need identified and labeled Outbound multis bins need created (physically) and labeled | Task | Blocker | 1 | FALSE | TRUE | Completed | SRB | Liza | 2024-09-04 | 2024-09-13 | 3 label types created and printing
63 | Wifi Deadspots | Several occassions of long load times in whse due to wifi dead spots | Issue | High | 3 | FALSE | TRUE | Open | SRB | Jesus | 2024-09-04 | 2024-09-13
64 | Parking Lot | Pick by zone - sky pick/floor zone | Request | NTH | 5 | FALSE | FALSE | Open | DEP/SRB |  | 2024-09-04 | 2024-11-04
65 | Batch Picking Screen xml updtaes | Update Batch Picking screen, item number is getting cut off | Request | High |  | FALSE | TRUE | Completed | DEP |  | 2024-09-04 | 2024-09-13
66 | Batch Picking Bin Assignment | turn off Bin Assignment | Request | Low |  | FALSE | FALSE | Validation | SRB |  | 2024-09-04 | 2024-09-13
67 | Shipping Account | Not calling correct shipping carrier account, check findByType config mgr query. | Issue | High |  | FALSE | TRUE | Validation | SRB | NP | 2024-09-04 | 2024-09-13 | some specifics on this
68 | User Setup | Upload all pack users | Task | High |  | FALSE | TRUE | Open | SRB | Maria | 2024-09-04 | 2024-09-13 | I finished the test users, we will do the real ones in production
69 | Void And Reprocess Shipment | Set up process | Request | High |  | FALSE | TRUE | Validation | SRB | Amber | 2024-09-04 | 2024-09-13
70 | SS Packing | remove pack remiander button in the GS ss packing process | Request | High |  | FALSE | TRUE | Completed | DEP | NP | 2024-09-04 | 2024-09-13
71 | SS Packing | SS Packing slip printing rules. Ensure packing slip was printing | Issue | High |  | FALSE | TRUE | Validation | SRB | Amber | 2024-09-04 | 2024-09-13
72 | Ecom packing slip | resolve issues with packing slip for ecom, Nidhi has callouts | Issue | High |  | FALSE | TRUE | Validation | SRB | Amber | 2024-09-04 | 2024-09-13
73 | Reprint PAL | set up reprint trading partner packing slip PAL on shipment based on trading partner on the shipment | Request | High |  | FALSE | FALSE | Validation | DEP | JM | 2024-09-05 | 2024-09-13 | 9/12 JM - configured and internally validated a Process Action Link on Shipment which will allow re-printing the trading partner packing slip associated with a shipment
74 | Inventory Prepick Report | Add warehouse location to style detail report (this report lives outside of Deposco) | Task | Critical |  | TRUE | TRUE | Open | SRB | SRB Team | 2024-09-05 | 2024-09-13
75 | API SQL on Work Group | Create API SQL on Work Group to show OH.SHIP_TO_LINE_1 | Task | High |  | FALSE | FALSE | Completed | DEP
75 | Create labels | Create pregenerated labels to be used during prepick picking | Task | Critical |  | FALSE | FALSE | Open | SRB |  | 2024-09-05 | 2024-09-13
76 | Batch Picking | Using New Bin functoinality switches you out of grocery scan | Task | Critical |  | FALSE | TRUE | Open | DEP | NP | 2024-09-05 | 2024-09-13
77 | Weight scale | validate that weight scales are connected and working during packing | Issue | High |  | FALSE | FALSE | Open | SRB |  | 2024-09-05 | 2024-09-13
78 | Shipping service set up | Review the ship vendors on the shipping services | Issue | Critical |  | FALSE | FALSE | Open | SRB |  | 2024-09-05 | 2024-09-13
79 | Printing rules | SS Packing rules are not loading containerHist correctly to print SSCC labels | Issue | Critical |  | FALSE | FALSE | Completed | DEP |  | 2024-09-05 | 2024-09-13
80 | Cycle counting | Ensure all locations that will be cycle counted have Cycle Count = true | Task | High |  | FALSE | FALSE | Open | SRB |  | 2024-09-05 | 2024-09-13
81 | Pick wave profile | Add Account Number (otherReference2) to pick wave name | Task | Low |  | FALSE | FALSE | Completed | DEP |  | 2024-09-05 | 2024-09-13
82 | API SQL | Add API SQL to show Brand on Work Group | Task | Low |  | FALSE | FALSE | Completed | DEP |  | 2024-09-05 | 2024-09-14
83 | SS Picking Screen xml | Adding 2 qty boxes during wholesale picking, just on 1st pick | Issue | Low |  | FALSE | TRUE | Hold | DEP | NP | 2024-09-05 | 2024-09-14 | 9/16 NP- Cannot reproduce. Putting on Hold for now until we see this in testing again
84 | Add shipping doors | Add Shipping Doors | Task | High |  | FALSE | FALSE | Open | SRB |  | 2024-09-05 | 2024-09-14
85 | Manifest Report (pre) | Need a view on order line to show order number, line qty's, filter for numbers. | Task | Low |  | FALSE | TRUE | Completed | DEP | NP | 2024-09-05 | 2024-09-14 | 9/13 - Liza and Nidhi discussed Pre-Manifest document requirements, will need more than just a view, should very similar to actual manifest that is generated during hard close
85 | ATTC Screen Update | Remove SCAC from the attc screen | Task | Low |  | FALSE | FALSE | Completed | DEP |  | 2024-09-05 | 2024-09-14
86 | Order Consolidation | SRB to investigate order consolidation coming from ERP | Discussion | NTH |  | FALSE | FALSE | Open | SRB |  | 2024-09-05 | 2024-09-30
87 | Printer Detail field mapping | Create Printer upload data exchange | Task | High |  | FALSE | FALSE | Completed | DEP | NP | 2024-09-09 | 2024-09-09
88 | Printing rules | Pack Order By Item printing rules | Task | High |  | TRUE | TRUE | Validation | SRB
86 | UPS testing | Test UPS accounts | Task | High |  | FALSE | TRUE | Open | SRB
87 | Fedex testing | Test Fedex accounts | Task | High |  | FALSE | TRUE | Open | SRB
88 | Waving | Wave different brands/PT together when on same PO | Task |  |  | FALSE | TRUE | Open | DEP
89 | Scanning screen view | add view to see # of cartons and units scanned to a pallet during scanning by PO | Task |  | see liza's email for this one | FALSE | TRUE | Validation | SRB
90 | Validate mappings | Check if the CD and PRD arre mapping to SO | Task |  |  | FALSE | TRUE | Validation | SRB
92 |  | Deposco to schedule meeting to understand Group Access/Permissions | Task |  |  | FALSE | FALSE | Open | DEP
93 |  | Deposco to add 'Account Name' column on the Work Groups List | Task |  |  | FALSE | FALSE | Closed | DEP |  |  |  | Done by Maria
95 |  | Deposco to add Master Pallet validation to always start with "SRB" | Task |  |  | FALSE | TRUE | Validation | SRB
96 |  | Where does Deposco use the SCAC? Why do we need to have those determined in Deposco, since we are asking the warehouse only for the ship VIA | Question |  |  | FALSE | FALSE | Resolved | DEP/SRB
97 |  | Can we shorten the PickWave name, how do we modify it ourselves? | Question |  |  | FALSE | TRUE | Resolved | SRB |  |  |  | 9/13 resolved by Nidhi
98 |  | Configure trip-based manifest | Task |  |  | FALSE | TRUE | In Progress | DEP
99 |  | Configure seperate soft close and hard close phases for wholesale | Task |  |  | FALSE | TRUE | Open | DEP
100 |  | Configure PAL on Trip to Print Manifest | Task |  |  | FALSE | TRUE | Validation | SRB
101 |  | Add OH.shipToContactName to the wave number of the Prepick and Wholesale waving rules. This field is used to store the DC idenitifer being shipped to and will group waves by the destination DC | Task |  |  | FALSE | FALSE | Open | DEP
102 |  | Map Earliest Ship Date from Coheader to Orderheader using POI rule | Task
103 |  | Add | Task
104 |  | Deposco to look into options for integrating Fairbanks scales | Task

## Schedule
SRB Project Tracker - Key Dates and Documents
Demos/Training Schedule
Demo Topic | Description | Demo/Training Date | Goal Action Item Completion Date | Training Recording Link | Password
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions | 2023-03-04 | 2023-03-04 | https://drive.google.com/drive/folders/1C6YqUY_nLuqNQ-2CQugcX2hiiZV73QEw | N/A
Data Exchange Introduction | Data Exchange/Field Mapping/Transmission training + troubleshooting | 2023-03-04 | 2023-03-04 | https://drive.google.com/drive/folders/1C6YqUY_nLuqNQ-2CQugcX2hiiZV73QEw | N/A
Inbound/Putaway | General Receiving(PO, Blind Receipt, Customer Returns, Create RMA), Move Item, Move Stock, Move Container | 2024-07-02 | 2024-07-02 | https://drive.google.com/drive/folders/1Im2xDSxlc7GfJmk6Pbvq8DbXtblDvPFd | N/A
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Product Conversion |  |  |  | N/A
Outbound I | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking |  |  |  | N/A
Outbound II | Packing and Shipping (Singles,Multis,Bulk) Repalletize, Assign trip ,Rollback After Picking, Void and Reprocess Shipment |  |  |  | N/A
Reporting | Report Builder, Dashboard Widgets |  |  |  | N/A
Integrations | API touchpoints - data requirements, troubleshooting steps etc. | Ongoing | Ongoing | https://drive.google.com/drive/folders/1dLFSsIcNyn0K6X_6xYiGnevV1IAURWfa | N/A
Other Key Activities
Task/Activity | Description | Status | Start Date | Completion Date
Unit Testing | Testing specific processes in the Test Script | Open
End to End Testing | Testing all processes with live data end to end | Open
Pre-Cutover Activities | Completion of all Pre-Cutover Steps | Open
UAT - User Acceptance Training | Training of all superusers and end users - Dep onsite support 3 days | Open
Go/No-Go Decision Tracker | Complete evaluation of Go/No-Go Decision Plan | Open
Cutover | Operational Go-Live - Dep onsite support full week | Open
Important Document Links
Document Name | Description | Link
SOP Document | Owned by SRB team to document standard operating proceedures for all major Deposco functions. To be printed and stationed at various places thorughout the warehouse during Go-Live and for onboarding new associates.
Master Design Document | In-depth outline of solution design agreed upon by SRB and Deposco during the Design phase of the implementation
Capability Map | Document outlining configuration decisions made by SRB and Deposco during the Design Phase

## EDI Retailer List
Task Tracker | EDI Document Link: https://drive.google.com/drive/folders/10PruQu0D3YYrf_eJZ_5czB4OewjGpbgB
Retailer | Image Name | SSCC Label? | Packing Slip? | Notes
Nordstrom/Nordstrom Rack |  | TRUE | FALSE | NORDST, NORRAK
Macys/Bloomingdales/Blommingdales Outlet |  | TRUE | FALSE | MAYCS, BLOOMINGDALES, B0023, BLOMOT, BLMOUT
Saks/BRiley,Hudson Bay |  | TRUE | FALSE | SAK5TH, SAK392, SAKSRM, BRILEY | HUDSON, THEBA
VonMaur |  | TRUE | FALSE | VMAUR, VON520
Bealls |  | TRUE | FALSE | BEALLS
Bealls Outlet |  | TRUE | FALSE | BEALOT, BEALLS
Amazon |  | TRUE | FALSE | AMAZON, AMA981, 15228
Belk |  | TRUE | FALSE | BELK, BELKRM
Burlington |  | TRUE | FALSE | BURLIN
Dillards |  | TRUE | FALSE | DIL203
https://docs.google.com/spreadsheets/d/1Mz5weX-R1PpkZQ-SDYukFyMLZc_sRjX_pEHbyNK8DMA/edit#gid=186639706 |  | FALSE | FALSE
Neiman Marcus |  | TRUE | FALSE | NEIMAN, NEI752
Zappos |  | TRUE | FALSE | ZAPPOS, 90225
DSW |  | TRUE | FALSE | 21083
Garnet Hill |  | TRUE | FALSE | 50229
Shopbop |  | TRUE | FALSE | BOP
|  | FALSE | FALSE
bloomingdales drop ship |  | FALSE | TRUE | BLMDIR all brands
ECOM for all brands |  | FALSE | TRUE
Macys drop ship |  | FALSE | TRUE | MACYS2
Nordstrom drop ship |  | FALSE | TRUE | NORDIR, NORPLI, NORRM
Joie drop ship |  | FALSE | TRUE | same but for each brand logo, name
Current Elliot drop ship |  | FALSE | TRUE | " "
Equipment drop ship |  | FALSE | TRUE | " "
Nordstrom Rack drop ship |  | FALSE | TRUE | NRHL, NRHLPL
Neiman Marcus drop ship |  | FALSE | TRUE | NMGRM, NMPLI
Sears/KMart |  | TRUE | FALSE | SEA06 | needs different V# even tho same code
Anthropolotie drop ship |  | FALSE | TRUE | ANTHDS
Stitchfix |  | TRUE | FALSE | STITCH
GovX drop ship |  | FALSE | TRUE | GOVX
Nexdr drop ship |  | FALSE | TRUE | NEXCR
Sams/Walmart |  | TRUE | FALSE | SMCLUB

## Unit Test Cases
Client: |  | Sunrise Brands
Client Code: |  | SRB
Test Cases Required: |  | 111
Test Cases Executed: |  | 69
Test Cases Passed: |  | 68
Test Cases Failed: |  | 0
% Complete: |  | 61.26%
Test Number | Scenario | Assignee | Status | Test Data | Date Complete | SRB Comments | Deposco Comments | In SOP Document?
| Inbound |  |  | 2024-11-13
1 | Receive full PO into 1 LPN | SRB Team | Pass | RARM224313 | 2024-07-09 | Received Complete |  | Yes
2 | Over receive PO, send over receipt on inbond shipment/PO API and perform receipt | SRB Team | Pass | RARM224314 | 2024-07-17 | RAMY19959-600-08 | OZ put fix in for this, please retest.
3 | Receive partial PO and leave open - receive more product later | SRB Team | Pass | RAMY1995 | 2024-07-09 | Receive more in the same FGPO to test - RAMY1995
4 | Receive partial PO and leave open - rcv more product for the same line different shipmnt/bol | SRB Team | Pass | RAMY1995 | 2024-07-17 | BOL # SRBTEST4
5 | Multiple styles in one LPN | SRB Team | Pass | RAAZIA11 | 2024-07-18 | BOL # SRBTEST9
6 | Receive Customer Return - Returns Receiving Button | SRB Team | Pass |  |  | We need to wait for Outbound Orders, Deposco will provide shipped orders. | Validated on ecomm order RATESTREGULAR.
7 | Create one Master/Bulk Carton Label to receive to a Staging Location. | SRB Team | Pass |  |  | Liza working through test data to be able to test this.
8 | Receive damaged products Putaway - Damaged Button Putaway | SRB Team | Pass | RAAZIA09 |  | Moved cont./lpn 000001014361 to IN3
9 | Receive product to a container (LPN) receive the other items into a different container (LPN) - multi LPN test case | SRB Team | Pass | RAMY1995 |  | Is this the same as Row5? We tested receiving more product with a different container for this same FGPO
10 | Reprint LPN labels | SRB Team | Pass | SRB008 | 2024-07-26 | successfully reprinted LPN labels.
| Receive PO for customer that does not use inbound shipments/cartons. (General Receiving) | SRB Team | Invalid |  |  | Maria said to use ASN receiving for this and will not utilize GenRec.
11 | Validate receipt line GETs | SRB Team | Pass |  |  | Marlon/Ephraim working on it.
12 | Perform PO receipt line GETs | SRB Team | Pass |  |  | Marlon/Ephraim working on it.
13 | Perform cancellations via API on a PO | SRB Team | Pass |  |  | Marlon/Ephraim working on it.
| Move Stock |  |  | 2024-04-04
14 | Putaway from Receiving | SRB Team | Pass | SRB002 |  | Moved to: 050010A01
15 | Move stock - add multiple units of different products to cart and put away to the same location | SRB Team | Pass | SRB004 | 2024-07-22 | Moved units in LPN 000000994361/62 to 050016A01
16 | Move stock - add multiple units of different products to cart and put away to two different locations | SRB Team | Pass | SRB001 | 2024-07-29 | 000000994351/52/53 moved to 050020A01, 000000994354/55/56 to 050021A01
17 |  | SRB Team | Pass | martha1 | 2024-07-22 | Moved units in SRB008 to 050010A01 and 050012A01 But I can't see both locations when viewing SRB005 | Martha/Amber to revisit?
| Move Container |  |  | 2024-04-04
18 | Putaway from Receiving | SRB Team | Pass | RAAZIA09 | 2024-07-12 | We moved a comp pallet to a location |  | Yes
19 | Move container - use move only stock to move contents of the pallet into to a new location | SRB Team | Pass | RARM224313 | 2024-07-15 | Moved ALL to: 050010A01
| Cycle Count |  |  | 0/10
20 | Create Cycle Count task via scheduler - Count by Location | SRB Team | Open |  |  | MIS Function, need to test
21 | Create Cycle Count task manually via Handheld to be performed later - Count by Location | SRB Team | Open |  |  | MIS Function, need to test
22 | Create Cycle Count task manually via Handheld and perform immediately (on demand) | SRB Team | Pass
23 | Create Cycle Count task manually via UI PAL on Item | SRB Team | Open
24 | Perform a cycle count and capture same value found in location | SRB Team | Pass
25 | Perform a cycle count and capture value different from quantity found in location (double confirm) | SRB Team | Pass
26 | Perform a cycle count and skip a location that you are prompted to count | SRB Team | Pass
27 | Accept cycle count variances | SRB Team | In Progress
28 | Reject cycle count variances | SRB Team | Pass
29 | Trigger a recount of a completed cycle count task via Manage Cycle Count Variances | SRB Team | Pass
| Adjust Inventory |  |  | 2024-04-04
30 | Consume all in location | SRB Team | Pass |  |  | Not an option under the Adjust Inventory.
31 | Consume some quantity of a particular item in a location | SRB Team | Pass |  |  | Martha completed.
32 | Consume all inventory in a specific container (LPN) | SRB Team | Pass |  |  | Martha completed.
33 | Returns***Interim solution | SRB Team | Pass |  |  | Can you please elaborate?
34 | Create inventory in a specific location | SRB Team | Pass |  |  | Martha completed.
| Replenishment |  |  | 2024-02-05
35 | Create a storage Replenishment task via scheduler | SRB Team | Pass |  |  | On location view, replenishment report
36 | Perform replenishment move | SRB Team | Pass |  |  | On location view, replenishment report
37 | Create a demand prepick Replenishment task via scheduler | SRB Team | Pass |  |  | done
38 | Perform demand prepick replenishment | SRB Team | Pass |  |  | done
39 | Perform exception during Replenishment Putaway | SRB Team | Pass |  |  | done
40 | Inventory Adjustments GET | SRB Team | Open |  |  | Marlon/Ephraim working on it.
| Build and Release Wave |  |  | 2024-08-09
41 | Build and Release wave manually by selecting orders | SRB Team | Pass |  |  | Manually waved SO192, SO189.
42 | Build and Release wave automatically via scheduler | SRB Team | Pass |  |  | Auto waved SO192, SO189.
43 | Build and Release wave where some orders are completely back ordered due to insufficient stock | SRB Team | Pass |  |  | SO189
44 | Build and Release Ecomm/DS Singles Order | SRB Team | Pass |  |  | Single-Ecomm/DS-MY1995BL24-240819-14:48:35-1
45 | Build and Release Ecomm/DS Multis Order | SRB Team | Pass |  |  | Multi-Ecomm/DS-240819-15:05:55-1
46 | Build and Release Ecomm/DS Priority | SRB Team | Ready to Test |  |  | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
47 | Build and Release Wholesale Batch Order | SRB Team | Pass |  |  | SO191
48 | Build and Release Prepick Order | SRB Team | Pass
49 | Build and Release Sample Order | SRB Team | Pass |  |  | SO197
| Single Scan Picking |  |  | 2024-07-07
50 | Pick Ecomm/DS singles wave of single unit orders onto one cart | SRB Team | Pass |  |  | Picked wave Single-Ecomm/DS-MY1995BL24-240819-14:48:35-1.
51 | Pick wave of one Wholesale Order onto one pallet | SRB Team | Pass |  |  | DEP191
52 | Pick wave of one Sample Order onto one pallet | SRB Team | Pass |  |  | SO190
53 | Perform exception during picking when stock not found/damaged | SRB Team | Pass |  |  | SO197
54 | Attempt to scan invalid item during picking | SRB Team | Pass
55 | Attempt to scan invalid location during picking | SRB Team | Pass
56 | Attempt to pick quantity larger than allocated | SRB Team | Pass
| Batch Picking |  |  | 2024-05-07
57 | Pick wave of ecomm/ds priority unit orders into designated bins | SRB Team | Pass |  |  | Multi-Ecomm/DS-240819-15:05:55-1
58 | Perform exception during picking when stock not found/damaged | SRB Team | Pass
59 | Create Cycle Count task via picking exception | SRB Team | Pass
60 | Attempt to scan invalid item during picking | SRB Team | Pass
61 | Attempt to scan invalid location during picking | SRB Team | Pass
62 | Attempt to scan invalid container/bin during picking | SRB Team | Pass
63 | Attempt to pick quantity larger than allocated | SRB Team | Ready to Test |  |  | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
| Singles Packing |  |  | 2024-03-09
64 | Pack order from cart picked via Single Scan Picking | SRB Team | Pass
65 | Capture box dimensions during packing for Pack Order by Item (Preferred Pack if it is assigned) | SRB Team | Pass
66 | Print shipping label at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
67 | Attempt to pack a multi unit order via Pack Order by Item (should not allow) | SRB Team | Ready to Test |  |  | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
68 | Back out of container during packing and re-scan container to continue | SRB Team | Pass
69 | Scan invalid items during Pack Order by Item | SRB Team | Pass
70 | Third Party Shipping | SRB Team | Ready to Test |  |  | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
71 | Print packing list at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
72 | Print SSCC labels at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
| Multis Packing |  |  | 2024-02-06
73 | Pack order from cart picked via Batch Picking | SRB Team | Pass
74 | Pack Order into multiple containers | SRB Team | Pass
75 | Scan invalid items during Multis Packing | SRB Team | Pass
76 | Print shipping label at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
77 | Print packing list at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
78 | Print SSCC labels at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
| Wholesale Packing |  |  | 2024-04-07
79 | Pack an order picked into a bin via Wholesale Packing | SRB Team | Pass
80 | Pack a large order picked alone to a cart via Wholesale Packing | SRB Team | Pass
81 | Capture box dimensions during Wholesale Packing | SRB Team | Pass
82 | Use New Bin functionality to create multiple shipping containers for one order | SRB Team | Pass
83 | Print shipping label(s) at conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
84 | Print SSCC labels at the conclusion of packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
85 | Scan invalid items during Single Scan Packing | SRB Team | Ready to Test |  | Will need to be tested on Tues. | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
| Assign Trip to Container |  |  | 2024-01-01
86 | Close trip for wholesale order by scanning containers to dock door | SRB Team | Pass
Void and Reprocess Shipment
87 | Void and Reprocess one Shipment | SRB Team | Ready to Test |  |  | We will be finalizing today/tomorrow with new orders Marlon is pushing for each Trading Partner.
SSCC Labels (UCC-128)
88 | Zappos | SRB Team | Open |  |  | *Only checked format, not data.
89 | VonMaur | SRB Team | Open |  |  | *Only checked format, not data.
90 | Saks | SRB Team | Open |  |  | *Only checked format, not data.
91 | Nordstrom | SRB Team | Open |  |  | *Only checked format, not data. 3rd Address line missing on the FROM section
92 | Neiman Marcus | SRB Team | Open |  |  | *Only checked format, not data. Zip code line missing on the FROM section (3rd line)
93 | Macys/Bloom | SRB Team | Open |  |  | *Only checked format, not data.
94 | Garnet Hill | SRB Team | Open |  |  | *Only checked format, not data.
95 | Dillards | SRB Team | Open |  |  | *Only checked format, not data.
96 | Beals FL | SRB Team | Open |  |  | *Only checked format, not data.
97 | Beals Outlet | SRB Team | Needs Info |  |  | Awaiting specs, AS: I see the Sample in the SSCC Folder, do you need a different label?
98 | Amazon | SRB Team | Open |  |  | *Only checked format, not data.
Packing Slips
99 | Bloomingdales ds | SRB Team | Open |  |  | *Only checked format, not data. 1: Pick Tick* (to be corrected to *ticket*) Barcode is missing, 2: returns barcode with reserv# and desc. 3: Description on the item line is missing. 4: Order Number should be CONTRACT NUMBER (CPO) | SN - Changes made as requested
100 | ECOM | SRB Team | Open |  |  | *Only checked format, not data. | SN - Changes made as requested
101 | Macys DS | SRB Team | Open |  |  | *Only checked format, not data. 1: PT Barcode is missing, 2: Customer Order#/Reserv# should come from cmmnts- SRB TEAM?
102 | Nordstrom DS | SRB Team | Open |  |  | *Only checked format, not data.
103 | Generic DS | SRB Team | Open |  |  | *Only checked format, not data. 1: Qty Column, remove decimals.3: Please remove time stamp on Pick Date | SN - Changes made as requested
104 | Generic Reg | SRB Team | Open
105 | Dillards DS | SRB Team | Open |  |  | *Only checked format, not data. 1: Customer Order# should come from cmmnts- SRB TEAM?, 2: Qty Column, remove decimals.3: Style column, should be the complete Style Number/Color
106 | Nordstrom Rack DS | SRB Team | Open |  |  | RM
107 | Neiman Marcus DS | SRB Team | Open |  |  | *Only checked format, not data. 1: Missing Style Desciption and UPC#, 2: Pick Ticket Barcode. missing
108 | Antrho DS | SRB Team | Open |  |  | *Only checked format, not data. TEAM: Are we not having the bill to acct # added ANTHDS?
109 | GovX DS | SRB Team | Open |  |  | *Only checked format, not data.
110 | Nexdr DS | SRB Team | Open |  |  | *Only checked format, not data. 1: Customer Order# should come from cmmnts- SRB TEAM?, 2: Qty Column, remove decimals.
Reports
111 | Storage min/max view (show stock qty) - look at replenishment report view on Location | SRB Team | Open |  |  | On location view, replenishment report

## On Site UAT Training
Client: |  | Sunrise Brands
Client Code: |  | SRB
Test Cases Required: |  | 91
Test Cases Executed: |  | 8
Test Cases Passed: |  | 8
Test Cases Failed: |  | 0
% Complete: |  | 8.791%
Test Number | Scenario | Assignee | Status | Test Data | Date Complete | SRB Comments | Deposco Comments | In SOP Document?
Inbound
1 | ASN receive an inbound shipment. | SRB Team | Pass | RF00016163 |  |  |  | Yes
2 | ASN receive an inbound shipment. | SRB Team | Pass | RF00016163 |  |  |  | Yes
3 | ASN receive an inbound shipment. | SRB Team | Pass | RF00016166 |  |  |  | Yes
4 | Close ASN process (bulk edit receipt lines) | SRB Team | Pass | RF00016163
Move Stock
5 | Putaway - move stock | SRB Team | Pass | isaac1
Move Container
6 | Putaway - move full pallet | SRB Team | Pass | edwin001
7 | Putaway - move full pallet | SRB Team | Pass | ophelia1
Cycle Count
8 |  | SRB Team | Open
9 |  | SRB Team | Open
Adjust Inventory
30 |  | SRB Team | Open
31 |  | SRB Team | Open
32 |  | SRB Team | Open
33 |  | SRB Team | Open
34 |  | SRB Team | Open
Replenishment
35 |  | SRB Team | Open
36 |  | SRB Team | Open
37 |  | SRB Team | Open
38 |  | SRB Team | Open
39 |  | SRB Team | Open
40 |  | SRB Team | Open
Build and Release Wave
41 | Manual BnR on Ecomm/DS | SRB Team | Pass | SO595
42 | Scheduled BnR | SRB Team | Ready to Test
43 | Assign Users via WorkGroup view | SRB Team | Open
44 |  | SRB Team | Open
45 |  | SRB Team | Open
46 |  | SRB Team | Open
47 |  | SRB Team | Open
48 |  | SRB Team | Open
49 |  | SRB Team | Open
Single Scan Picking
50 | Singles Ecomm/DS Wave | SRB Team | Open
51 |  | SRB Team | Open
52 |  | SRB Team | Open
53 |  | SRB Team | Open
54 |  | SRB Team | Open
55 |  | SRB Team | Open
56 |  | SRB Team | Open
| Batch Picking |  |  | 2024-05-07
57 | Multis Ecomm/DS Wave | SRB Team | Open | Multi-Ecomm/DS-240904-14:28:11-1
58 |  | SRB Team | Open
59 |  | SRB Team | Open
60 |  | SRB Team | Open
61 |  | SRB Team | Open
62 |  | SRB Team | Open
63 |  | SRB Team | Open
Singles Packing
64 |  | SRB Team | Open
65 |  | SRB Team | Open
66 |  | SRB Team | Open
67 |  | SRB Team | Open
68 |  | SRB Team | Open
69 |  | SRB Team | Open
70 |  | SRB Team | Open
71 |  | SRB Team | Open
72 |  | SRB Team | Open
Multis Packing
73 |  | SRB Team | Open
74 |  | SRB Team | Open
75 |  | SRB Team | Open
76 |  | SRB Team | Open
77 |  | SRB Team | Open
78 |  | SRB Team | Open
Wholesale Packing
79 |  | SRB Team | Open
80 |  | SRB Team | Open
81 |  | SRB Team | Open
82 |  | SRB Team | Open
83 |  | SRB Team | Open
84 |  | SRB Team | Open
85 |  | SRB Team | Open
Assign Trip to Container
86 |  | SRB Team | Open
Void and Reprocess Shipment
87 |  | SRB Team | Open
SSCC Labels (UCC-128)
88 | Zappos | SRB Team | Open
89 | VonMaur | SRB Team | Open
90 | Saks | SRB Team | Open
91 | Nordstrom | SRB Team | Open
92 | Neiman Marcus | SRB Team | Open
93 | Macys/Bloom | SRB Team | Open
94 | Garnet Hill | SRB Team | Open
95 | Dillards | SRB Team | Open
96 | Beals FL | SRB Team | Open
97 | Beals Outlet | DEP Team | Needs Info
98 | Amazon | SRB Team | Open
Packing Slips
99 | Bloomingdales ds | SRB Team | Open
100 | ECOM | SRB Team | Open
101 | Macys DS | SRB Team | Open
102 | Nordstrom DS | SRB Team | Open
103 | Generic DS | SRB Team | Open
104 | Generic Reg | DEP Team | Open |  |  |  | Need to update this packing slip to show style name, size, and qty per size on the order. Do not want to show line by line.
105 | Dillards DS | SRB Team | Open
106 | Nordstrom Rack DS | DEP Team | Open
107 | Neiman Marcus DS | SRB Team | Open
108 | Antrho DS | SRB Team | Open
109 | GovX DS | SRB Team | Open
110 | Nexdr DS | SRB Team | Open
Reports
111 | Storage min/max view (show stock qty) - look at replenishment report view on Location | SRB Team | Open
Other

## Packing Slip Mapping
Report | Packing Slip Fields | Deposco Fields
Bloomingdales DS | Reservation number | orderheader.notes.body where title= Reservation Number
ECOM | "1405144 SPLIT" in the example *** | orderheader.notes.body
Generic Reg (Need to print this during ATTC) | Sales Rep name | remove
| Terms and Freight Terms | remove
| Other charges | remove
| B.O.L number | shipment.trackingNumber
| Invoice number | remove
Nordstrom Rack DS | Barcode with "002" in the middle
| Other charges | remove
B.O.L number
| Invoice number | remove
| Freight | remove
| Other charges | remove
Neiman Marcus DS | Number next to description. Assumption made that this is UPC.
Anthropologie DS | 'ANTHDS" below Ship Via | remove
*** | Please note that the majority of ATS, Boutiques, Major accounts have notes and we need to print that information in the packing slip
at the bottom of the form. We are sending the Notes in a field called "Body" in the sales order
Nordstrom | PO Number | OH.ContractNumber
| Return Address | Facility Address
| Sold To | OH.ShipToAddress
| Returns Validator Barcode on the top right for ALL packing slips | OH.importType
| Nordstrom Customer Order Number | Body of Noted Attached to order. (title of note will be 'Comment 3')
| Sku, Style, Description Row needs to be stretched to the right so everything is on one line | UPC, Style Number, and Description
Macys/Bloomingdales/Bloomingdale's Outlet | UPC | Item.UPC,
Style Name, Style Number, Color, Size
| Order Number | Notes.body comment 3
| Reservation Number | Notes.body comment 4
| Barcode near bottom left under UPC column | Remove, not needed
| Barcode at the very bottom | Barcode of the reservation number (notes.title= comment 4)
| Billing Address | OH.shipToAddress
Neiman Marcus | Ensure this is formatted as Landscape
| Item Id | Item.Style,Color,Size
| Description | Item.StyleName,UPC
| Order Date | Shipment.createdDate
Dillards | Customer Order Number | one of the comments TBD
Generic/Ecomm DropShip (ECOMM-GENERIC-SAMPLE) | ECOMMRM | OH.accountNumber
| value on bottom left | Any notes on the order
Generic for all shipments besides Ecomm/DS (REGULARS-GENERIC-SAMPLES) | Style | Item.styleNumber
Sizes
Report | UCC Label Fields | Deposco Fields
Macy's Label | PO Number | OH.contractNumber
| Department | OH.CA7
| Store | OH.shipToAttention
| Store City | Trading Partner Site Address.city?
| Store Address | concat Trading Partner Site Address.line1, city, state, zip
| SSCC Display | Container/ContainerHist.lpnNumber Extend barcode for container number
| MTYP | Body of Noted Attached to order. (title of note will be 'comment 9')
| store number | OH.shipToAttention
| Address in the top right | OH.shipToAddress
Bloomingdales | same as Macy's
Neiman Marcus | Division | Body of Noted Attached to order. (title of note will be 'comment 9')
| store number | OH.shipToAttention
Nordstrom | Vendor # | TP.contactName
| DC # | OH.shipToContactName
| BOL | will be left blank that's fine
| Pro | will be left blank that's fine
Generic | used for boutiques/mom and pop B2B, can re-use the label used for Von Maur
Dillards | Pack for store # | OH.shipToAttention
Von Maur | same as other label mappings
Amazon | Ship To Address | OH.shipTo Address
| To: | Amazon.com
| Item Description | if single SKU carton, use item description. if mixed SKU carton, just say "Mixed SKU"
| Carton Logistic Barcode | Expand barcode
| Pro# | trip.bolNumber, not required
| B/L | trip.bolNumber, not required
| ARN | Trip.licenseNumber (labeled as "Load ID")
| expiration date | not needed
| Single Asin Number | item UPC number
Belk
Saks | GRP Number | Body of Noted Attached to order. (title of note will be 'comment 9')
| top barcode | OH.shipToPostalCode
| middle barcode | OH.shipToAttention
| lower barcode | SSCC Number (lpn number)
Garnett Hill | top barcode | OH.shipToPostalCode
| middle barcode | OH.contractNumber
| lower barcode | SSCC Number (lpn number)
Zappos | top barcode | OH.shipToPostalCode
| middle barcode | OH.contractNumber
| lower barcode | SSCC Number (lpn number)
| Product Type | Body of Noted Attached to order. (title of note will be 'comment 9')
| Ship Date | Shipment.createdDate

## QuestionsDeposco
Questions: | Answers: | amber.santiago@sunrisebrands.com FYI I unhighlighted the ones I answered on 8/21.
How to find a master pallet by LPN# or Purchase Order#? | The MP# will disappear once its been putaway.
When we create a Master Pallet and select the type as PALLET instead of CART, does it switch it to CART after we've used it for receiving? | All MP# need to be CART not Pallet.
On the ReceiptLines, why doesn't the Container update the MP or container # for all lines. | The MP# will disappear once its been putaway.
On the StockUnitsList, why doesn't the PO#/Location column populate for all lines? | Owen checking for a different column that can display on all lines.
Under 'Bulk Edit for Receipt Lines', we need the date to default during receiving and want a calendar pop-up for user to select the date when updating/editing. | Owen made modification to fix.
When using 'Move Stock' option, after we scan the Cart/MasterPallet, the Move Source Screen seems irrelevant if we only need to click MOVE to proceed, why do we need it? We have tried scanning the LPN in this screen, and it skips to Select Item, but no quantities are shown. | Can't change program, just click MOVE
^^After selecting the MOVE option in MoveSourceScreen, it takes you to MoveItemScreen where it asks you to select an LPN, but there's also a QTY field, what's the purpose for it when we will always have only a 1 to 1. | this will be irrelevant, deposco to change the cursor to LPN field.
^^when in SelectItemFromLPN screen, we need to be able to scan UPC's 1 by 1, and for the qty to decrease after each scan when we are splitting an LPN to different locations. | Need to keep, WHS will need to enter qty
^^On MoveDestinationScreen, can you confirm the 'Suggested Locations' only gives us locations that have the same SKU's we've selected? If so, can we exclude Receiving from this list? | Can't exclude 'receiving' only from the suggested locations.
^^After selecting the location, we must enter the LPN again, wha'ts the purpose of that? Can we skip it? Additionally when we are splitting the LPN by size we need to enter a UPC on the LPN/Container field to proceed, what's the purpose of that, and won't it affect something else down the line? | We don't need to enter a UPC, it can be the cart#?
Reports Builder - Inventory | There is a scheduled demo on 8/27.
split carton put away: enter UPC requires quantity to be typed in | Need to keep, WHS will need to enter qty
We will SCAN we do not want anyone entering quantities. | resolved, need to keep
Shippable Flag? Should all styles/tems have this checkbox marked? Any item that will be on an order and will be able to be shipped for order fulfillment should have this flag set | yes
The Reprint LPN label is only printing the pack style, but not it's contents, please advise. | This should be good to test. Please send an email with your feedback. | AS: Provided Sample to Deposco. Do you need anything else from our end?
Inbound Questions:
- General Receiving, how to identify; When we do general receiving and go to purchasing receipt lines we need to see shipment # the way we see our others, which is PO#+. Right now we do not see the PO number | Deposco can add an API SQL on receipt line to show PO# | completed
- Over Receiving status update, we are still able to over receive when we shouldn't. | Ready for retest, check on status with Martha.
- Pending Outbound Orders to receive customer return for testing | Ready to test. Switched mapping to oh.importType. | AS: Can we use orders, completed from 8/20?
WHSE Received Date Error keeps coming out when trying to adjust. | OZ to look at why WHSE received date not populating (GR rules) | AQ: Will be using BornOnDate going forward
**How do we Reverse a receiving? | Added Unreceiving button, just follow steps during process and reach out with questions. We will not hold a separate demo on this since this was requested after design doc signature. | AQ: Will need demo after we explore.
Field Questions:
- Order Type | customerOrder.customAttribute1/orderHeader.customAttribute1 | settled.
- Department | customerOrder.customAttribute7/orderHeader.customAttribute7 | settled.
- Merchandise Type | This is on the custom field mapping document. | AS: Still pending on our end??
Move Stock:
- Adding mult units/items, to putaway in mult locations. Still pending in our test cases.
When moving a Master Pallet to a location, the stock isn't available if we want to move as an item to a diff location | This is because stock unit is on hold. | Martha has printouts.
Adjust Inventory:
Can you add the MOVE ITEM option to the INVENTORY Menu | 8.16: Deposco added.
- Consume All Location, not an option in the HH Menu. | This has been updated, validation added. | AQ: Visible AFTER we click on any option under Adjust Inventory and clicking Back. Can you please advise?
- Returns Interim Solution, can they please elaborate? | Returns > Adjust Inventory | AQ: temp solution since orders not in Dep. still need to test, can we review?
Replenishment:
Replace pulled stock to source loc, not in the demo. | Use Exception - Destination Full button
Perform exception during Replenishment Putaway | Yes | AS: Is this the same as what we did in the Picking process? NO
ORDERS: What field are we using to see the ShipTo/Store # |  | AS: resolved... under account
API:
Posting dates on coheader: which specific date fields are needed? Ex.) To post Planned Released Date, CoDate with a qualifier of PRD is needed <coDate> <qualifier>PRD</qualifier> <value>07/18/2024</value> </coDate> | This was closed on 8/20 | AS: Still pending? NO
CSD = Cancel by Ship Date
PRD = Planned Release Date
SRB will be sending orders on 9/18 to validate.

## End to End Testing (hidden)
Test Scenario (Print validation) | Status | Team | Owner | Notes
Receiving
Receive full PO | Ready to Test | SRB
Receive Partial PO | Ready to Test | SRB
Receive damaged products | Ready to Test | SRB
Receive Blind RMA order | Ready to Test | SRB
Receive Blind Order | Ready to Test | SRB
Receive Customer Return | Ready to Test | SRB
Create RMA | Ready to Test | SRB
Order Structure Scenarios
Ship Single Unit Order | Ready to Test | SRB
Ship Multi Unit Order | Ready to Test | SRB
Ship multi order in two boxes | Ready to Test | SRB
Ship Express Singles | Ready to Test | SRB
Ship Express Multis | Ready to Test | SRB
Ship Wholesale Order | Ready to Test | SRB
Ship Bulk Orders | Ready to Test | SRB
| Ready to Test | SRB
| Ready to Test | SRB
| Ready to Test | SRB
Order Hold Scenarios
Address Validation Hold | Ready to Test | SRB
Exception Scenarios
Select exception during SSPicking | Ready to Test | SRB
Select exception during Batch Picking | Ready to Test | SRB
Cancelation Scenarios
Fully cancel an order | Ready to Test | SRB
Partially cancel an order | Ready to Test | SRB
Partially cancel an order line | Ready to Test | SRB

## CutoverGo Live Activities
SRB Cutover
SRB Cutover
Cutover Day - 10/16
Ref | Area Owner | Assigned Resource | Status | Task Description | Date | Actual Finish | Dependencies | Comments
Number | Task Owner | Task Owner |  | Cutover Day
Cutover Activities
1 | DEP | Kyle | Complete | Update Prod with latest UA Backup
2 | SRB | SRB team | Complete | Validate each pack station is setup to coresponding printers
3 | SRB | Maria | Complete | Upload Locations into Prod
4 | SRB | Maria | Complete | Upload Location Zones Template
5 | SRB | Marlon | Complete | Post Item Payload to Prod
6 | SRB | Maria | Complete | Upload RM inventory in Deposco (final location counts)
7 | DEP | JM | Open | Enable Schedulers (NS, Build and Release, etc.)
8 | DEP | Nidhi | Open | Validate API endpoints in each direction are flowing
9 | SRB | Marlon | Complete | Push open Sales Orders into Deposco
10 | SRB | Marlon | Open | Push open Purchase Orders into Deposco
11 | SRB | Maria | Open | Do and end to end smoke test with a PO and SO
12 | SRB | Liza | Complete | Create All Shipping Accounts in Production for RebMink |  |  |  | UPS (2) "northstar" Fedex (1) "northstar"
13 | SRB | Liza | Open | Confirm all Trading Partner info is correct for "RM"
14 | DEP | Nidhi | Open | Confirm SFTP connector is communicating in prod and turn off in UA
15 | DEP | Kyle/Nidhi | Open | Any SSCC label changes

## GoNo-Go Decision
Factors | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Due Date | Comment | SRB Team Tested | DEP Team Tested
| Deposco Setup | 80 |  |  |  | 60.5
Deposco Setup | Printer Details | 10 |  | SRB | 100% | 10 | Are all printers configured? |  |  | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | SRB | 100% | 10 | Are all print stations setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | SRB | 100% | 10 | All reports assigned to printers and resources? |  |  | FALSE | FALSE
Deposco Setup | RF Scanners/Handheld Devices | 10 |  | SRB | 100% | 10 | Are all handheld units configured? Are all of the handhelds working correctly? |  |  | FALSE | FALSE
Deposco Setup | Label Printers | 10 |  | SRB | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 | Y | SRB | 0% | 0 | Are the report documents configured to print on the proper printers? Are some reports configured with device overrides (e.g. processing area printers). |  | Check latency with printers-PDF,UPS,ZPL 10/7: Still seeing slowness in general. No known issues on the Deposco side. Deposco can try and pull in someone from dev ops team | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | Deposco | 100% | 10 | Have all High and Critical issues from the issues list been resolved? |  | 10/7: Everything from UAT is completed and flipped to validation | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release- Sample BnR, Ecomm/DS BnR, Confirm if Prepick and Wholesale will be manual or scheduled | 10 | Y | Deposco | 5% | 0.5 | Backups, day, month end jobs. |  | 10/7: not finished but started | FALSE | FALSE
| Warehouse Prep | 40 |  |  |  | 38
Warehouse Prep | Location Labels | 10 |  | SRB | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 10 |  | SRB | 90% | 9 | Procure Carts for moving of inventory and label them |  | 10/7: Have carts & bins, labels created | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 10 |  | SRB | 100% | 10 | Item inventory barcoded and labeled to scan |  |  | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 |  | SRB | 90% | 9 | Is the connectivity strong and cover all necessary scan areas? |  | 10/7: Going to run some network tests in the Rebecca Minkoff area this week to ensure there are no dead zones | FALSE | FALSE
| Standard Operating Procedure Documentation | 90 |  |  |  | 80
Standard Operating Procedures | Receiving | 10 |  | SRB | 100% | 10 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Putaway | 10 |  | SRB | 100% | 10 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 10 |  | SRB | 100% | 10 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Single Scan Picking- Ecomm/DS Singles, Wholesale Ship Via Picking, Wholesale SRG Picking,Samples Picking | 10 |  | SRB | 90% | 9 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  | Finished Ecomm/DS, Wholesale and Prepick in progress | FALSE | FALSE
Standard Operating Procedures | Batch Picking- Prepick Picking,Multi Ecomm/DS Picking | 10 | Y | SRB | 85% | 8.5 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Single Scan Packing | 10 |  | SRB | 100% | 10 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Pack Order by Item | 10 |  | SRB | 100% | 10 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | LTL Shipping (Wholesale)- LTL Hard Close | 10 | Y | SRB | 50% | 5 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Customer Order- Waving | 10 | Y | SRB | 75% | 7.5 | SOP's been written? Online Help, plus SRB-specific. Start with SRB template. |  |  | FALSE | FALSE
| Training & Testing | 50 |  |  |  | 41
Training & Testing | Business Scenarios Definition | 10 |  | SRB | 100% | 10 | Define all Business scenario including exception processes Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Process Training and Testing - Receiving - Putaway - Cycle Counting - Single Scan/Batch Picking - Single Scan Packing/ Pack Order by Item - LTL Shipping - Parcel Shipping | 10 | Y | SRB | 60% | 6 | Unit and End to End Test Case Execution |  |  | FALSE | FALSE
Training & Testing | User Acceptance Testing | 10 |  | SRB | 100% | 10 | Execute all defined business scenarios within Deposco |  |  | FALSE | FALSE
Training & Testing | Supervisor/Administrator | 10 |  | SRB | 100% | 10 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | End-user | 10 | Y | SRB | 50% | 5 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  | Training has started as of 10/7 | FALSE | FALSE
| Configurations/Master Data (Production) | 70 |  |  |  | 66
Configurations | Inventory Validation | 10 |  | SRB | 100% | 10 | Putaway Audits |  |  | FALSE | FALSE
Configurations | Items | 10 |  | SRB | 100% | 10 | Are all items setup? Are all of the units of measure defined for each item? |  | Items will not be copied over to production. Items will be uploaded to production separately 10/7: completed & sent to production | FALSE | FALSE
Configurations | Zones | 10 |  | SRB | 100% | 10 | Have all of the Zone and Zone Location records been set up? Has the pick flow been tested? |  |  | FALSE | FALSE
Configurations | Locations | 10 |  | SRB | 100% | 10 | Are the location types, zones, and location masters configured accurately. |  |  | FALSE | FALSE
Configurations | Handheld Menu Structures | 10 | Y | SRB | 60% | 6 | Have the appropriate menu levels been created for the different departments? |  |  | FALSE | FALSE
Configurations | Packs (UOMs) / Pack UPCs | 10 |  | SRB | 100% | 10 | Have all valid pack types been entered into the system? |  |  | FALSE | FALSE
Configurations | Containers | 10 |  | SRB | 100% | 10 | Pallets, bins, carts |  |  | FALSE | FALSE
| Cutover and Conversion Plans | 10 |  |  |  | 10
Cutover and Conversion Plans | Cutover plan developed | 10 |  | Deposco | 100% | 10 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  |  | FALSE | FALSE
| Data Exchange Interfaces - Imports/Exports with Deposco (in Production) | 15 |  |  |  | 15
Interfaces - Imports to Deposco | Carton Types from SRB to Deposco | 0 |  | SRB | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Locations/Zones from SRB to Deposco | 10 |  | SRB | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Items/Packs from SRB to Deposco | 0 |  | SRB | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Inventory from SRB to Deposco | 5 |  | SRB | 100% | 5 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Purchase Orders from SRB to Deposco | 0 |  | SRB | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Integrations | 80 |  |  |  | 60
Integrations with Deposco | Items | 10 |  | SRB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Purchase Order | 10 | Y | SRB | 25% | 2.5 |  |  |  | FALSE | FALSE
Integrations with Deposco | Ship Notice | 10 | Y | SRB | 25% | 2.5 |  |  |  | FALSE | FALSE
Integrations with Deposco | Customer Order | 10 | Y | SRB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Inventory | 10 | Y | SRB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Field Mappings | 10 |  | SRB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Data Exchange Configs | 10 |  | SRB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Carrier SRB Socket Setup and Validated - UPS - Fedex | 10 | Y | SRB | 50% | 5 |  |  |  | FALSE | FALSE
| Interfaces - Exports From Deposco | 0 |  |  |  | 0
Interfaces - Exports From Deposco | Shipment Confirmation from Deposco to Email* | 0 |  | Deposco | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Reports and Labeling | 70 |  |  |  | 30
Reports and Labeling | Shipping Label | 10 | Y | SRB | 0% | 0 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Location Label | 10 |  | SRB | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Item Label | 10 |  | SRB | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | LPN Label | 10 |  | SRB | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Packing Slips (12) | 10 | Y | SRB | 10% | 0 | Does the report print from the application accurately and timely? |  | Rebecca Minkoff needs: Macy's/Bloomingdales, Neiman Marcus, Nordstrom, Generic, Dillards (5 total) | FALSE | FALSE
Reports and Labeling | SSCC Lables (11) | 10 | Y | SRB | 0% | 0 | Does the report print from the application accurately and timely? |  | Rebecca Minkoff needs: Macy's/Bloomingdales, Neiman Marcus, Nordstrom, Generic, Dillards, Von Maur, Amazon, Belk, Saks (9 total) | FALSE | FALSE
Reports and Labeling | Manifest | 10 | Y | SRB | 0% | 0 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | Deposco SRB | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? |  |  | FALSE | FALSE
| Total Weighted Score: | 410.5
| Total Possible Score: | 515
| Total Percentage: | 79.71%
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Brand Rollout Plan
Go Live Rollout Plan
Brand | Go Live Date | Master Data Uploaded? | Workflow Testing Complete? | Integration Testing Complete? | Notes
Rebecca Minkoff | 2024-10-14 | FALSE | FALSE | FALSE
Merchantly (handles ecomm for 2 other brands) |  | FALSE | FALSE | FALSE
Donald Pliner |  | FALSE | FALSE | FALSE
Seven Licensing |  | FALSE | FALSE | FALSE
NYDJ (3pl) |  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
^whole list as of 10/25/24, will confirm with Maria |  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE

## Precutover Activities
SRB Cutover
SRB Pre-Cutover Steps
Purpose: Organize all tasks that are to be executed in preparation for deployment.
Ref | Area Owner | Assigned Resource | % | Task Description | Comments | Target Date | Comp Date | Required Comp Date | Dependencies | Comments
| Task Owner |  |  | Pre Deployment Steps
SRB
1 | SRB |  | 0% | Upload/Create all Locations to Deposco
2 | SRB |  | 0% | Scanners at each workstation
3 | SRB |  | 0% | Validate Pack Station laptops
4 | SRB |  | 0% | Validate Scales
5 | SRB |  | 0% | Set up pack stations
6 | SRB |  | 0% | Set up printers (Print Client is setup, printers are on same device)
7 | SRB |  | 0% | Set up wifi
8 | SRB |  | 0% | Configure packstations as a resource and assign printers
9 | SRB |  | 0% | Shipping Label - print out and validate
10 | SRB |  | 0% | Packing Slip - print out and validate
11 | SRB |  | 0% | End User Configuration
12 | SRB |  | 0% | Continued Super User Training
13 | SRB |  | 0% | User Training (Happy Path and Exception Scenarios)
14 | SRB |  | 0% | Validate/Test integration schedulers for Deposco are working
15 | SRB |  | 0% | Review Scheduler Frequencies
16 | SRB |  | 0% | Review Waving Logic
17 | SRB |  | 0% | Build SOP document for entire solution. Leave a relevant copy at each given area (packing sections for pack stations)
18 | SRB |  | 0% | Validate all Locations in proper zones
19 | SRB |  | 0% | Test with all set-up Printers
20 | SRB |  | 0% | Repull product data into production
Deposco
1 | DEP |  | 0% | Build system monitoring queries |  |  | - | - | -
2 | DEP |  | 0% | Wipe out test orders |  |  |  |  | 9
3 | DEP |  | 0% | Review each packstation is configured as a resource |  |  |  |  | -
4 | DEP |  | 0% | Validate all master data has been configured |  |  |  |  | 9
5 | DEP |  | 0% | Review Waving Logic |  |  |  |  | -
6 | DEP |  | 0% | Purge Transactional Data |  |  | - | - | -
7 | DEP |  | 0% | Validate all schedulers are enabled for production environment
8 | DEP |  | 0% | Validate all Integration changes needed are in production environment |  |  |  |  | 9
9 | DevOps |  | 0% | Build Production environment |  |  |  |  | -
10 | DevOps |  | 0% | Add socket credientals to Production environment |  |  |  |  | 9
11 | DEP |  | 0% | Wipe product data |  |  |  |  | 9

## Go Live Critical Tasks
Go Live Critical Tasks
1-Blocker (Blocking progress on the project within next week)
Task No. | TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | STATUS | TEAM | Go Live Critical | OWNER | Date Opened | Due Date | DEP Comments | SRB Comments
1 | SSCC Label Rules | Validate base printing logic to print SSCC label reports stored on the trading partner in Single Scan Packing ("wholesale soft close") |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | Still pending validation. Seeing some slowness
2 | Packing Slip Updates - Macy's/Bloomingdales | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | Matthew- updated and tested label fields. Ready for SRB validation. - update made by Nidhi 10/14 10/15: not printing at POBI | Tested and few changes needed, Readable Return Barcode
3 | Packing Slip Updates - Neiman Marcus | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Matthew | 2024-10-07 |  | Matthew- updated and tested label fields. Ready for SRB validation. - update made by Nidhi 10/14 | 1.Readable Return Barcode 2. Order Number: Oh.noted (comment3) 3. PO Number needs to be co.ContractNumber 4. needs city and state and zip in right square box
4 | Packing Slip Updates - Nordstrom | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Matthew | 2024-10-07 |  | Matthew- updated and tested label fields. Ready for SRB validation. Nordstrom Packing Slip - update made by Nidhi 10/14 | 1. Readable Return Barcode 2. remove created date and packing slip just left of barcode 3. customer order #, needs to be "notes comment 3' 4. PO NUMBER needs to be co.ContractNumber
5 | Packing Slip Updates - Generic Regular/Non-Dropship Major Accounts | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Matthew | 2024-10-07 |  | 2024-10-15 | Would like to a see a single row per style number and then columns of shipped qty per size (Small, Medium, Large, XL, etc), Readable Return Barcode
6 | Packing Slip Updates - Generic Dropship | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Matthew | 2024-10-07 |  | Matthew- updated and tested label fields. Ready for SRB validation. - update made by Nidhi 10/14 | 1. Readable Return Barcode 2. generic dropship does NOT require logo 10/15: SRB confirmed as validated
7 | Packing Slip Updates - Ecommerce | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Matthew | 2024-10-07 |  | 10/15- validated by Liza | 1. Readable Return Barcode 2. when ecomm, need logo which is stored on trading partner (test SO6484)
8 | Packing Slip Updates - Dillards | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Matthew | 2024-10-07 |  | Matthew- updated and tested label fields. Ready for SRB validation. - update made by Nidhi 10/14 | 1. Readable Return Barcode 2. customer order needs "notes comment 3" 3. PO needs to be contractNumber 4. confirm 'order date' is dep createdDate 5.
9 | SSCC Label Updates - Saks | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate 10/15: need lenghten of small barcodes, and qty to show (count of eaches in box), then trim front 2 so it shows 20 | example: 0009145742
10 | SSCC Label Updates - Macy's/Bloomingdales | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate | Liza - was able to print this. top right corner has too many lines, cosmetic issue.3604276 | moved to prod
11 | SSCC Label Updates - Zappos | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Nidhi | 2024-10-07 |  | Need to review, needs additional cartonm 1 of 1 details 10/22: Nidhi deployed to production
11 | SSCC Label Updates - Neiman Marcus | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate | Good example: 10101067998 | moved to prod
12 | SSCC Label Updates - Nordstrom | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Nidhi | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate 10/15: need to see if we can add "carton x of x" "Some trading partners (e.g. Zappos's, Nordstrom) require a carton counter ("1 of 3", "2 of 3", 3 of 3") on the SSCC labels. Deposco is not currently setting this on any labels. " 10/22: Nidhi deployed to production
13 | SSCC label Updates - Generic | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate 10/15: remove SRG, and show proper qty
14 | SSCC Label Updates - Dillards | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate | 10/15: liza to validate 3119132205 | moved to prod
15 | SSCC Label Updates - Von Maur | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate 10/15: need to show "# of units" to label 10/22: Nidhi deployed to production | 1.Move (00) barcode down nand SSCC-18 2. bigger font for Sotre # data, po, dep data 3. stretch out ship to postal code barcode 4. carrier gone if SRG 5. example: 368107
16 | SSCC Label Updates - Amazon | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate 10/15: need to show "# of units" to label 10:16: remove SRG if showing, when nmore than one, print just "mixed skus", quantity needs to show 10/21: 'Mixed SKU' is validated, 'Single SKU' is still pending validation 10/22: Nidhi deployed to production | need to show "# of units" to label
17 | SSCC Label Updates - Beall's | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/10: Lanie - updated and printed labels in Deposco office printers. Flipped to SRB to test/validate 10/22: Nidhi deployed to production
18 | SSCC Label Updates - Belk | Update based on SRB feedback |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | copy the saks, BUT GRP needs to be DIV, need example and look a little deeper as it is currentl very off from the saks 10/21: similar to SAKs which was validated, but still pending validation 10/22: Nidhi deployed to production
19 | SSCC Label Updates - Sam's Club | Update based on SRB feedback |  |  |  | Hold | SRB | FALSE |  | 2024-10-07
20 | Zone-Based Waving Validation | Configure/validate zone-based waving |  |  |  | Completed | SRB | FALSE | Maria/Amber | 2024-10-07 |  | 10/8: Ready for SRB team to validate in UA 10/10: JM - updated Wholesale and Prepick waving rules to group by brand, also updated wholesale waving rules to only allocate to TEJ1 or TEJ2 zones
21 | Pre-Manifest Report | Configure new Pre-Manifest report that prints/generates via a Trip PAL before hard close (no shipment/container hists) |  |  |  | Completed | SRB | FALSE | Liza | 2024-10-07 |  | 10/9: Nidhi has setup and flipped to SRB team to validate in UA 10/15: need to upodate it to count total # of cases
22 | Manifest Report Updates | Update existing Manifest (the one that generates after hard close) |  |  |  | Completed | SRB | FALSE | Nidhi | 2024-10-07
23 | Multi Order Trip Hard Closing Issue | Investigate multi order trip hard closing & generating shipment lines for all orders, but only updating one of the order headers to shipped. Example shipment 417 with orders SO4052 (shipment lines but not marked as shipped at OH) and SO4053 (marked as shipped) |  |  |  | Validation | DEP | FALSE | JM | 2024-10-07 |  | possibly just retest here
24 | Configure OMS changes | Configure to avoid base duplicate order validation which is blocking the processing of legitimate orders (Haley mentioned CAP used a preprocessing rule) |  |  |  | Completed | SRB | FALSE | Maria/Marlon | 2024-10-07 |  | 10/10: JM - added a rule which should prevent this for new orders posted to Deposco. Flipped to SRB team to validate in UA. 10/15: JM - made update to rule, SRB to test again | SRB - found CoHeaders which got flagged as duplicate even with this setup. Examples- CO6258,CO6257.
25 | Review / end to end to test prepick wholesale flow | Review / end to end to test prepick wholesale flow |  |  |  | Completed | DEP/SRB | FALSE | JM |  |  | 10/14: JM - adding lines to review/test this process per Maria's request
26 | Review and test cycle counting scenarios (exceptions, approval process, etc) | Review and test cycle counting scenarios (exceptions, approval process, etc) |  |  |  | Completed | DEP/SRB | FALSE | JM |  | 2024-10-21 | 10/14: JM - adding lines to review/test this process per Maria's request
27 | Picking wave entry lists | Remove rules in batch picking and single scan picking wave entry which are requiring manual workgroup assignment to users. SRB to migrate to normal wave assignment with group level permissions and views (e.g. 'Prepick' waves only in 'Prepick Picking' button that only certain users have access to) |  |  |  | Completed | SRB | FALSE | JM |  |  | 10/15: JM updated batch picking and sspicking wave entry rules. SRB to validate and create additional groups as necessary.
28 | Assign trip ship via validations | Update rule 'Error if Ship Via is SRG/Truck' to check the ship via of the shipment record rather than the order header in AssignTripToContainers_TripCustomDetailsScreen-post |  |  |  | Completed | DEP | FALSE | JM |  |  | 10/16: JM configured and validated in UA. Flipping to SRB to validate before we deploy to production.
29 | Whole Packing Slip Printing in ATTC | Add rules to print Generic REGS Packing Slip in assign trip hard close, 1 packing slip per order/store/shipment, with multiple stores/orders/shipments per trip |  |  |  | Completed | SRB | FALSE | JM |  |  | 10/15: JM configured and validated on Deposco side, flipping to SRB to validate
30 | Updates to single scan packing printing rules | Update single scan packing packing slip printing rules to only print for Ecomm/Dropship. Orders where CA1 is Prepick or orders where ship via is SRG will not need a packing slip in sspacking, they will print later in assign trip hard close |  |  |  | Completed | SRB | FALSE | JM |  |  | 10/15: JM made update to sspacking rule to NOT print for processes which soft close (prepick and Wholesale SRG)
31 | add reprint option for SSCC labels when they are still containers/ soft closed. Currently can only reprint for hard closed / shipped containers | add reprint option for SSCC labels when they are still containers/ soft closed. Currently can only reprint for hard closed / shipped containers |  |  |  | Completed | SRB | FALSE | Nidhi
32 | Seperate Multis waving rules for ecomm vs dropship | Configure post order import rule to tag orders as dropship or ecomm based on the trading partner (if trading code contains 'ecom' or if partnership type is 'Drop Ship Vendor'). Configured 4 new waving rules: Priority Drop Ship Multis, Regular Drop Ship Multis, Priority Ecomm Multis, Regular Ecomm Multis which restrict eligbile zones to TEC1/TEC2 for Ecomm and TDV1/TDV2 for Dropship |  |  |  | Completed | SRB | FALSE | JM |  |  | 10/15: JM configured new API SQL, POI rule, and 4 new waving rules. Tested on Deposco side. SRB team to validate.
33 | Exception pick | When a pick is exceptioned the eligible location is not honored |  |  |  | Closed | DEP |  |  |  |  | example S06538, this is a base Deposco issue which will require development. Moved to Go Live Issues tracker
34 | Inbound shipment FTP import | Investigate Inbound shipment ftp import behavior |  |  |  | Completed | DEP |  | Nidhi
35 | Inbound Shipment separate UA/Prod Folders | SRB to create separate UA/Prod Folders |  |  |  | Open | SRB |  | Marlon
36 | Pack Order By Item close shipment script/packing slip printing rules not running when ship via is UPS, | Pack Order By Item close shipment script/packing slip printing rules not running when ship via is UPS. It DOES run during ship outside sstem. |  |  |  | Completed | SRB |  | JM |  |  | 10/17: JM - logs for UPS POBI show up under Workflow: SocketTask-SRB-North Star Opco Wholesaleshippinglabel.
37 | Configure fix parcel carrier account lookup logic for orders which come in as SRG which are switched to UPS/FedEx before hard closing | Currently, orders which come in as SRG are NOT setting the UPS/Fedex account name on the OH. So later, if they decide to update a pending shipmwent's ship via to a ups/fedex servcoe and they go to ship, we are looking up oh.ca6 and it is empty so it's throwing an error because it doesnt know which account to use. Suggestion is to update the findbytype query to reference the shipment's ship via and TP on the OH instead of the OH level field which is stamped in POI |  |  |  | Completed | SRB |  | JM |  |  | 10/17: JM configured ATTC rules in UA and validated with changing SRG ship via on Shipments to both FedEx and UPS. Flipping to SRB to validate.
38 | Add "CTN" requirement on bin scan |  |  |  |  | Closed | SRB |  | JM |  |  | Moved to Go Live Issues page
39 | ATTC update for it to show Carton not pallet |  |  |  |  | Closed | SRB |  | JM |  |  | 10/17: JM updated the screen to say Carton instead of Pallet, flipping to SRB to validate. 10/21: Moving to Go Live Issues page for ongoing tracking
40 | PO Purchase Order Updates | PO needs updates when it is still in New |  |  |  | Completed | SRB |  | Marlon |  |  | Asked marlon for the original Payload and the update payload

## Go Live Issue Tracker
Date Reported | Issue Log | Status | Owner | Comment | Solution
2024-10-14 | Add validation in Prepick picking to only allow picking into containers that start with CTN | Moved to Ticket Portal | Nidhi
2024-10-14 | Add validation in SS Picking and Batch Picking to only allow picking into containers that start with BIN | Moved to Ticket Portal | Nidhi | Nidhi set up validation for SS Picking
2024-10-14 | Do not autopopulate dims for singles, dropship, and ecomm orders | Moved to Ticket Portal | Nidhi
2024-10-14 | Need to test SOS Order SO6507 | Closed | Nidhi | originally thought this Trading Partner not stamping CA6 was an issue
2024-10-16 | Move CA6 POI rule to Automation Rules | Moved to Ticket Portal | Nidhi
2024-10-16 | SSCC labels are printing at hard close and ss packing to the shipping label printer most likely because of the shippinglabel printer assignment when they should not | Closed
2024-10-17 | Packing Slip Updates - Generic Regular/Non-Dropship Major Accounts | Moved to Ticket Portal | Sahil | Would like to a see a single row per style number and then columns of shipped qty per size (Small, Medium, Large, XL, etc), Readable Return Barcode | need to revise and get these to show the sizes better
2024-10-17 | Non grocery packing packing should have pack remiander button, grocery scan should not | Moved to Ticket Portal | Sahil | Grocery Scan Packing will not have the pack remainder button
2024-10-17 | Waves are being marked as Released even though there are no work groups on there or pick tasks and the order is back ordered | Moved to Ticket Portal | JM
2024-10-17 | API Sql to pull oh.contracNumber on shipment | Completed | Nidhi
2024-10-17 | Boutiquw wholesale orders should be getting freight terms type as Prepaid not Collect | Open | Confirm with SRB team | Is this still happening? Have the necessary changes been made to sent Freight Terms Type= Prepaid when posting orders
2024-10-17 | Exception Pick - When a pick is exceptioned the eligible location is not honored. example S06538 | Moved to Ticket Portal | JM | this is a base Deposco issue which will require development. Deposco team will create workaround options and present to SRB team, ticket: https://deposco.atlassian.net/browse/DEPWMS-4477
2024-10-17 | ATTC update for it to show Carton not pallet | Validation | SRB | 10/17: JM updated the screen to say Carton instead of Pallet, flipping to SRB to validate.
2024-10-21 | Resolve Unreceiving error with container 000001284950 Seeing "Item [RM-HH24HGQXBO-001-O/S] current location is not in [Receiving]. Please move the stock before unreceiving." when unreceiving | Completed | JM | 10/22: There is a business rule in the Receiving process which stamps the receipt date on the 'Born On Date' field of the Receipt Line. When you later go to un-receive, the base process compares the receipt line fields with the stock unit fields. Since the 'Born On Date' field is set on the Receipt Line, but not on the Stock Unit, the system detects a mismatch and throws the error. If we remove the born on date from the receipt line, the unreceiving process works as intended.
2024-10-21 | Update Zones API on Location to be on stock unit instead | Completed | Nidhi | 10/23: Nidhi configured and deployed to production
2024-10-21 | Investigate if the time on the wave can be updated to PST | Completed | Nidhi | 10/22 Scheduler appears to be creating waves with timestamp in PST.
2024-10-21 | In ASN Receiving, remove Type and BU columns, and add # of Cartons per shipment next to the Inbound Shipment Number. Refer to the picture->> | Moved to Ticket Portal | Nidhi
2024-10-22 | Investigate why Inbound Shipments are being linked to Order Header over and over (example RM000162740823 is linked to its PO 95 times. it only has 20 containers. it should only be linked 1 time). This issue is causing the Shipment to duplicate on the Purchasing UI view which shows the total carton count per shipment | Moved to Ticket Portal | Sahil | 10/22: Sahil investigating 10/23: Internal ticket created
2024-10-22 | Investigate wave entry listbox rules for when wave linked on order header is not the one with pick tasks for the order | Completed | JM | 10/22: JM added
2024-10-22 | Review and resolve location update import error when trying to update pick sequence | Completed | Maria | 10/22: Nidhi investigating 10/22: Nidhi resolved issue, Maria to update the file with 80 rows and finish upload
2024-10-22 | add orderHeader.pickWaveNumber == null for prepick, wholesale SRG and Wholesale Ship Via PWBP:14,15,16 | Completed | JM | 10/22: JM added
2024-10-22 | Investigate why containers are getting moved to system generated containers that start with Stage-- ""no picked orders in staging container" | Moved to Ticket Portal | JM | Happens when a container with stock also has multiple inner containers. Not sure yet why that occurs sometimes.
2024-10-23 | Deposco to test Fill or Kill. Example production line SO955--3 was not canceled when the other part of the order was shipped. | Completed | Nidhi | 10/24: Nidhi to demo using order 7702 https://sandboxapi.deposco.com/ua/integration/SRB/search/shipment?orderHeaders.number=7701
2024-10-23 | Configure new Order Release Profile to be used for Ecomm wave types to use a different order close policy. Ecomm orders should use 'Don't close if backordered'. All other wave types should stay as is (Fill or Kill) | Completed | JM | 10/23: JM - created new order release profile called "Ecomm Profile" which uses 'don't close if backordered' policy. Update Ecomm Singles and Multis wave rules to use this ORP
2024-10-23 | Deposco to investigate if API Shipment Response for partially shipped orders return the Killed / canceled lines for orders using Fill or Kill | Completed | Nidhi | https://sandboxapi.deposco.com/ua/integration/SRB/search/shipment?orderHeaders.number=7701
2024-10-24 | Check API URL to send Inventory Adjustments to return location or set up a Data Exchange | Moved to Ticket Portal | DEP
2024-10-24 | Prevent auto enter of the weight after it popualtes during packing | Validation | SRB | 10/24: Nidhi updated screen tabbing in UA, and it is ready for SRB to test
2024-10-24 | Pre Manifest and Manifest is printing blank | Completed | Nidhi/Liza | AUTO-UPS2-241024
2024-10-24 | Turn off fill or kill in Production | Completed | Nidhi | 10/25: Nidhi updated ORP and PWBP in UA and Prod
| Update Zappos Label to add Prefix in front of MTYP based on criteria in screenshot on the right->>> | Moved to Ticket Portal | Nidhi