## Schedule
WFL Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal | Metric | Status
Client Goal #1 | Atomation to drive efficiency (cutting down order processing time) | Open
Client Goal #2 | Enhanced compliance and client trust (SKU tracking, inventory visibility, and accurate billing) | Open
Client Goal #3 | TBD | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions | 2025-05-07
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports
Deposco University | Customer completes Deposco University training courses for relevant subjects. | 2025-05-07
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | https://drive.google.com/drive/folders/1pDpHW6ynOVQNvdB0b_M0swJNXGKB-Ls- | 2025-06-04
Master Design Document | LINK | TBD
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | ERP/WebStore/ShippingCarrier/ChannelAggregator/EDI - data requirements, troubleshooting, mapping updates, steps etc. |  | 0%
Order Orchestration | Sourcing, Routing, Exception and Backorder Management |  | 0%
Inbound | General Receiving(PO, Blind Receipt, Customer Returns), Move Item, Move Stock, Move Container |  | 10.71%
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock |  | 0%
Outbound | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking, Packing, Shipping |  | 0%
Other - WMS | Transfer orders, 3PL Billing, etc. |  | 0%
Reporting | Report Builder, Dashboard Widgets |  | 0%
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Completion Date
End to End Testing | Testing all process flows with live data end to end | 0%
UAT Onsite Agenda | LINK | 0%
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0%
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0%
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned.
Deposco Onsite Support | Travel booked for cutover and go-live week.
Project Closeout | Agreement of final deliverables provided.

## Timeline (hidden)
Milestone | Start Date | End Date
Project Management | 2025-05-01 | 2025-10-01
Orientation | 2025-05-15 | 2025-05-25
Design | 2025-05-20 | 2025-06-27
Configuration | 2025-06-27 | 2025-07-30
Validation | 2025-08-01 | 2025-08-30
Deployment | 2025-09-01 | 2025-09-30

## Task Tracker
WFL Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | DEP Comments | XXX Comments
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  | FALSE | FALSE | Completed | DEP | Priyesh P
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  | FALSE | FALSE | Completed | DEP | Priyesh P
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task |  | FALSE | FALSE | Completed | DEP | Priyesh P
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Begin development for new socket APIs | Deposco Socket team begins development for new socket APIs as per initial project SOW | Task |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network 2) Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task |  | FALSE | FALSE | In Progress | DEP | Business Consultant / Technical Lead |  | 2025-08-06 | 7/1: DEP to confirm if this was sent out from BC team 7/15: Aleyda shared the list of devices, DEP to provide feedback on recommended devices 8/5: Devices have been ordered, ETA 8/11
Orientation | Setup Parcel Carrier Accounts | UPS: Client utilizes Deposco UPS Registration Wizard to setup UPS account FedEx: Clients configures FedEx account and Meter # within Deposco CompanyConfig UI screen | Task |  | FALSE | FALSE | Closed | DEP/WFL | Technical Lead
Orientation | Setup Exisiting Sockets | Client utilizes Deposco help site guides to setup existing socket connections | Task |  | FALSE | FALSE | Closed | DEP/WFL | Technical Lead
Orientation | General Application and UI Overview | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Message Center Overview - Handheld Menu Access | Task |  | FALSE | FALSE | Completed | DEP/WFL | Full team
Orientation | Begin Master Data Gathering | Sample Master Data templates for items, packs, locations, zones, storages, etc. to be provided by Deposco to be used by client | Task |  | FALSE | FALSE | Completed | WFL | Aleyda |  | 2025-07-11
Orientation | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task |  | FALSE | FALSE | Closed | WFL | Warehouse Leads
Orientation | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task |  | FALSE | FALSE | Closed | WFL | Inbound Lead
Orientation | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task |  | FALSE | FALSE | Closed | WFL | Outbound Lead / Customer Service Lead
Orientation | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task |  | FALSE | FALSE | Closed | WFL | Outbound Lead
Orientation | Schedule recurring project calls | Weekly status call Bi-weekly executive steering call | Task |  | FALSE | FALSE | Completed | DEP | Priyesh P |  | 2025-06-06
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | FALSE | Completed | DEP | Zach B |  | 2025-05-28
Design | 3PL Client Matrix | WFL team to fillout 3PL client Matrix | Task |  | FALSE | FALSE | Completed | WFL | Aleyda
Design | Billing | WFL team to provide current billing rates / invoicing details | Task |  | FALSE | FALSE | In Progress | DEP | Lanie W |  | 2025-07-18 | 7/10: Need to confirm with Zach 7/15: Zach in progress of review
Design | Master Design Document Delivery | Deliver master design document for client team to review | Task |  | FALSE | FALSE | Completed | DEP | Zach B |  | 2025-07-03
Design | Review and Sign Master Design Document | Client to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  | FALSE | FALSE | In Progress | DEP/WFL | Full Team |  | 2025-07-23
Design | Complete 3PL Matrix for new clients | Complete 3PL Matrix for new clients | Task |  | FALSE | FALSE | In Progress | WFL | Aleyda |  | 2025-07-11 | 7/15: Lanie to review the document to confirm, still need to add the code
Configuration | Deliver Inbound Configuration | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Lanie W |  | 2025-07-23
Configuration | Deliver Inventory Management Configuration | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Lanie W |  | 2025-07-23
Configuration | Deliver Outbound Configuration Pt 1 | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Implementation Lead |  | 2025-07-31
Configuration | Deliver Outbound Configuration Pt 2 | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Completed | DEP | Implementation Lead |  | 2025-07-31
Configuration | Deliver Integration Configuration Training | Via demo sessions or loom videos | Task |  | FALSE | FALSE | Open | DEP | Implementation Lead |  | 2025-08-07
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task |  | FALSE | FALSE | Open | DEP | Implementation Lead |  | 2025-07-28
Configuration | Label Physical Locations within Warehouse | Label Physical Locations within Warehouse | Task |  | FALSE | FALSE | Open | WFL | Operations Lead
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | In Progress | WFL | Inbound Lead |  | 2025-07-31
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Open | WFL | Inventory Lead |  | 2025-07-31
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Open | WFL | Outbound Lead |  | 2025-08-14
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  | FALSE | FALSE | Open | WFL | Outbound Lead |  | 2025-08-14
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task |  | FALSE | FALSE | Open | WFL | Technical Lead
Validation | End to End Test Case Execution | Complete end to end test cases | Task |  | FALSE | FALSE | Open | WFL | Warehouse Leads + Technical Lead
Validation | Deliver Onsite UAT Agenda |  | Task |  | FALSE | FALSE | Open | DEP | Implementation Lead
Validation | Train End Users | During UAT and any additional training as needed | Task |  | FALSE | FALSE | Open | WFL | Warehouse Leads
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task |  | FALSE | FALSE | Open | DEP/WFL | Full Team
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task |  | FALSE | FALSE | Open | DEP | Priyesh P
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task |  | FALSE | FALSE | Open | DEP | Implementation Lead
Deployment | Execute Cutover Plan Steps |  | Task |  | FALSE | FALSE | Open | DEP/WFL | Full Team
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task |  | FALSE | FALSE | Open | DEP | Priyesh P
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Recordings
WFL Demo Videos
Date | Category | Config Code | DESCRIPTION | LINK
Baseline Education
Deposco User Exerience
Master Data / Data Exchange
Process Demos
Integrations
Inbound
Inventory Management
Outbound
Reporting
Miscellaneous Demos
Testing/Training Support

## DEP Config Tasks
TASK TRACKER
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
| Category | Title | Priority | Status | Team | Owner | Notes | Due Date | % Complete
Data | Pre-Design | Data Exchange Template for Items |  | Complete | Deposco | Lanie | Support item creation with components for Kit to Order Items
Data | Pre-Design | Data Exchange Template for LOcations/Zones |  | Complete | Deposco | Lanie
Data | Pre-Design | Create example DTC Client and example Items |  | Complete | Deposco | Lanie | Create example items. Create some Items with Kit to Order Assemblies. Follow Glossier as example items
Data | Pre-Design | Create example Pallet Based Client and example Items |  | Complete | Deposco | Lanie
Inbound | Pre-Design | Receiving v2 Initial Setup |  | Complete | Deposco | Lanie | Receiving v2 where we receive items onto LPN (similiar to DIVB)
Data | Pre-Design | Send Client API Documentation and API Next steps for client |  | Complete | Deposco | Brandon
Inbound | Pre-Design | Setup basic Diected Putaway |  | Open | Deposco | Zach
Outbound | Pre-Design | Setup basic Singles and Batch Flow under DTC Client for Design Demos |  | Complete | Deposco | Lanie
Outbound | Pre-Desgn | Get familiar with OFP and OFP based replens. Are Storage Details required for OFP Replens? |  | Open | Deposco | Zach
Inventory | Pre-Desgn | Set up initial replen flow |  | Hold | Deposco | Zach
Data | Pre-Design | Billing Doc/3PL Matrix from Client |  | Complete | Deposco | Brandon | Sent over 3PL matrix but will hold off on the Billing Documentation and review during design.
Outbound | Design | Configure Pallet Based Outbound Flows for Design Demos based on Day 1 walkthrough |  | Hold | Deposco
Outbound | Design | Create Jira Ticket for Trip Creation and Planning PAL |  | Complete | Deposco | Zach
Outbound | Design | Create Jira Ticket for non-rules based image captue - Images to be captured within Receiving and Picking Processes |  | Open | Deposco | Zach
Outbound | Design | Create Jira Ticket for CoHeader Entry - CoLine/Orderline Attribute Capture - Lot Number, Serial Number, LPN Number (CoLine does not have inbound LPN or serial Number, orderLine has all of the above) |  | Complete | Deposco | Zach
Inbound | Design | Create Jira Ticket for PO Entry - Orderline Attribute Capture - Lot Number, Serial Number, LPN Number |  | Complete | Deposco | Zach
Inbound | Design | Create Jira Ticket for PO Entry - Ability to allow User to create PO with custom Order Header Number - The PO Number would ideally be able to created as a BOL Number, Container Number (Inbound Steel Container), or Trailer Number |  | Complete | Deposco | Zach
Inbound | Configuration | Receiving V2 |  | Complete | Deposco | Lanie
Inbound | Configuration | Add weight to receiving screen and transfer to stock unit |  | Complete | Deposco | Lanie
Inbound | Configuration | Transfer PO Number to stock unit |  | Complete | Deposco | Lanie
Inbound | Configuration | Blind Receiving for Copper |  | Complete | Deposco | Lanie
Inbound | Configuration | Add unload type for billing purposes |  | Complete | Deposco | Lanie
Inbound | Configuration | Adjust putaway query |  | Complete | Deposco | Lanie
Inbound | Configuration | Create Data exchange for POs |  | Complete | Deposco | Lanie
Outbound | Configuration | Create data exchange for COs |  | Complete | Deposco | Lanie
Outbound | Configuration | Transfer invenotry tracking to SO correctly when released |  | Complete | Deposco | Lanie
Outbound | Configuration | Add order to stock unit if orderLine has inventory tracking |  | In-Progress | Deposco | Lanie
Outbound | Configuration | Test Break Bulk OFP to verify correct stock unit is being waved |  | In-Progress | Deposco | Lanie
Outbound | Configuration | Test picking process |  | In-Progress | Deposco | Lanie
Outbound | Configuration | Adjust picking screen to show relevant information |  | Open | Deposco | Lanie
Outbound | Configuration | Test assign trips to open trip |  | In-Progress | Deposco | Lanie
Outbound | Configuration | Test close trip process |  | In-Progress | Deposco | Lanie
Reporting | Configuration | create PACSUN BOL |  | Complete | Deposco | Lanie
Reporting | Configuration | create generic BOL |  | Complete | Deposco | Lanie
Outbound | Configuration | Print BOL when trip is closed |  | Open | Deposco | Lanie
Outbound | Configuration | Add release number to the trip entity |  | Open | Deposco | Lanie
Reporting | Configuration | Create PO crossdock receiving report |  | Open | Deposco | Lanie
Outbound | Configuration | Test Crossdock configuration |  | Open | Deposco | Lanie
Outbound | Configuration | Configure print button for receiving report |  | Open | Deposco | Lanie
Outbound | Configuration | Print PACSUN BOL when order is closed |  | Open | Deposco | Lanie
Reporting | Reporting | Create inventory report |  | Open | Deposco | Lanie
Reporting | Reporting | Create receiving report |  | Open | Deposco | Lanie
Reporting | Reporting | Create outbound report |  | Open | Deposco | Lanie
Reporting | Reporting | Create manifest report |  | Open | Deposco | Lanie
Reporting | Reporting | Create PACSUN Report that has vendor name, weight, PO number, CBMs |  | Open | Deposco | Lanie
Pacsun FTP and INtegration Review
Cross Dock Flow - Picking - Stage to Parent Container
Cross Dock Flow - Inbound - remove inner lpns?
Trip Management Pal and Config
BU Level Allocation Determination
Inventory Expiration scheduler
Inbound | August On-site testing | See if possible to delete New LPN Button in Pacsun receiving |  | WFL Validation | Deposco | Zach
Inbound | August On-site testing | See if possible to automatically Create Stock Unit with Lot Number for Pacsun receiving |  | Open | Deposco | Zach
Inbound | August On-site testing | POI not automatically being run for Purchase Order uploads Pacsun |  | Open | Deposco | Zach
Inbound | August On-site testing | See if possible to Auto-Populate or Set LPN Number field on Identifier Input Screen with entered PO Number |  | Open | Deposco | Zach
Inbound | August On-site testing | See if possible to remove Weight Input Fields on Pacsun Receiving Process Pack Input Screen and Print Labels Selection |  | WFL Validation | Deposco | Zach
Inbound | August On-site testing | See if Possible to rename Serial Number during Pacsun Receiving Label to say carton identifier |  | Open | Deposco | Zach
Outbound | August On-site testing | How to Catch PO Number Typos or CoLines where stock with matching Lot Number is not found - Catch it in Pre-Processing? |  | Open | Deposco | Zach
Outbound | August On-site testing | Look into CoHeader Duplicate check Fields |  | Open | Deposco | Zach
Outbound | August On-site testing | Remove Location Scan from Pacsun Picking Screen |  | Open | Deposco | Zach
Outbound | August On-site testing | Remove Stage Button in Pacsun Picking Screen , Also maybe |  | Open | Deposco | Zach
|  | Add Validations in Receiving to ensure that LPN entered = PO Number |  | Open
|  | Add Rules in ATTC to Move trip to "Loaded" Status when soft close occurs |  | Open

## Test Cases - Unit
WFL Unit Test Cases |  |  | Category |  | % Complete
|  |  | Integrations |  | 0%
|  |  | Order Orchestration |  | 0%
|  |  | Inbound |  | 10.71%
|  |  | Inventory Management |  | 0%
|  |  | Outbound |  | 0%
|  |  | Other WMS |  | 0%
|  |  | Reporting |  | 0%
|  |  | PacSun/Cross Dock |  | 76.47%
|  |  | TOTAL |  | 7.456%
Category | Subcategory | Config Code | Scenario | Steps for Testing | Expected Outcome | Owner | Status | Test Data | Comments
Integrations
Integrations | Shopify - Item Pull |  | Execute: scheduled run at 00:00:00 nightly |  | Doc Store created at time of scheduled run. Doc Store status is Success, Failed, or INFO based on results of api search. Only items created or updated since last runtime of the scheduler are returned. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with no entries into pop-ups |  | Doc Store created at time of manual run. Doc Store status is Success, Failed, or INFO based on results of api search. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with one valid product ID |  | Doc Store created at time of manual run. Doc Store status is Success. Item is created if not already in Deposco and updated if already in Deposco. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with multiple valid product IDs |  | Doc Store created at time of manual run. Doc Store status is Success. Items are created if not already in Deposco and updated if already in Deposco. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with one invalid product ID |  | Doc Store created at time of manual run. Doc Store status is Failed. Item is not found by Shopify and nothing is created/updated in Deposco. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with "Shopify Product ID(s) To Pull (CSV)" populated with mix of valid/invalid product IDs |  | Doc Store created at time of manual run. Doc Store status is Failed. Items that are found by Shopify are created or updated in Deposco and items that are not found by Shopify are not. Failures/successes per item are visible in Doc Store Details |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with "Number of Days To Go Back (Number)" populated to valid number greater than 0 |  | Doc Store created at time of manual run. Doc Store status is Success, Failed, or INFO based on results of api search. Only items created or updated in number of days entered are returned. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Execute: manual run with "Number of Days To Go Back (Number)" populated to invalid number (non-numeric or <=0) |  | Doc Store created at time of manual run. Doc Store status is |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: "How Do You Want to Handle Items?" set to "Create Item and Channel Listing If Not Found and Only Allow Channel Listing Updates" - Pull item that does NOT yet exist in Deposco |  | Doc Store status is Success, Failed, or INFO based on results of api search. Item and channel listing are created if returned by Shopify. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: "How Do You Want to Handle Items?" set to "Create Item and Channel Listing If Not Found and Only Allow Channel Listing Updates" - Pull item that DOES already exist in Deposco |  | Doc Store status is Success, Failed, or INFO based on results of api search. Only channel listing is updated if Item is returned by Shopify. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: "Update Pack Weight" set to true |  |  |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: "Map Inventory Item Fields" set to true |  |  |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: Throttle Group Configured |  |  |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: Page Size set to 250 when more than 250 products are returned in the search |  |  |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: Page Size set to 250 when less than or equal to 250 products are returned in the search |  |  |  | Ready to Test
Integrations | Shopify - Item Pull |  | Criteria: "Shopify Product Status" set to "Active" only |  | Only "Active" products in Shopify returned and created/updated as necessary. |  | Ready to Test
Integrations | Shopify - Item Pull |  | Data: Pull product with a UPC that is already tied to another item in Deposco. |  | Doc Store status is Failed. |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: scheduled run every 15 minutes |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one valid order ID |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with multiple valid order IDs |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one invalid order ID |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with mix of valid and invalid order IDs |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: manual run with "Number of Days To Go Back (Number)" populated to valid number greater than 0 |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Execute: manual run with "Number of Days To Go Back (Number)" populated to invalid number (non-numeric or <=0) |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Shopify Status" set to Any |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Financial Status" have Paid, Partially Refunded, and Refunded checked |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Fulfillment Status" set to Unfulfilled |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Order Number Convention" set to order_number--id |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Since ID" left blank |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Intangible Line Item Status" set to Complete |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Tag Filter" set to ______ |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Enable OMS" set to true |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Ignore Existing" set to true where order already exists |  |  |  | Ready to Test
Integrations | Shopify - Order Pull |  | Criteria: "Ignore Existing" set to true where order does not already exist |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship full order at one time - single tracking number |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship full order at one time - multiple tracking numbers |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship partial order - single tracking number |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship partial order - multipile tracking numbers |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship kit to order products on full order at one time - single tracking number |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship kit to order products on full order at one time - multiple tracking numbers |  | Fail |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship order that was manually marked as fulfilled in Shopify |  | Fail |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Data: Ship quantity greater than quantity order line in Shopify |  | Fail |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Criteria: Notify Customer set to false |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Execute: Re-generate ship notice for failed transaction |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Execute: Re-process ship notice event for failed transaction |  |  |  | Ready to Test
Integrations | Shopify - Ship Notice |  | Execute: Scheduled re-process of ship notice event for failed transactions that have been retied less than 3 times |  |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync |  | Execute: Scheduled inventory sync nightly |  |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync |  | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to true |  |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync |  | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to false |  |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync |  | Criteria: "Measure Name" set to Total ATP Qty API |  |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync |  | Criteria: "Page Size" set to 200 with more than 200 items to sync |  |  |  | Ready to Test
Integrations | Shopify - Outbound Inventory Sync |  | Criteria: "Page Size" set to 200 with less than or equal to 200 items to sync |  |  |  | Ready to Test
Integrations | Quickbooks Online | [5 empty] | Ready to Test
Integrations | Quickbooks Online | [5 empty] | Ready to Test
Integrations | Netsuite - Item Pull |  | Execute: scheduled run at 00:00:00 nightly |  |  |  | Ready to Test
Integrations | Netsuite - Item Pull |  | Execute: manual run with no entries into pop-ups |  |  |  | Ready to Test
Integrations | Netsuite - Item Pull |  | Execute: manual run with "refNumberToPull " populated with one valid product ID
Integrations | Netsuite - Item Pull |  | Execute: manual run with "refNumberToPull" populated with multiple valid product IDs
Integrations | Netsuite - Item Pull |  | Execute: manual run with "refNumberToPull" populated with one invalid product ID
Integrations | Netsuite - Item Pull |  | Execute: manual run with "refNumberToPull" populated with mix of valid/invalid product IDs
Integrations | Netsuite - Item Pull |  | Data: Pull valid item with defined subsidiary
Integrations | Netsuite - Item Pull |  | Data: Pull valid item outside of defined subsidiary
Integrations | Netsuite - Item Pull |  | Data: Pull valid item of specified item type
Integrations | Netsuite - Item Pull |  | Data: Pull valid item of non-specified item type
Integrations | Netsuite - Item Pull |  | Data: Pull valid item where "Sent to Deposco" is true in Netsuite
Integrations | Netsuite - Item Pull |  | Data: Pull manual run for validi item where "Sent to Deposco" is false in Netsuite
Integrations | Netsuite - Item Pull |  | Data: "How do you want to handle missing items?" set to "Create or Update Item, Update Links If Found" - Pull item that DOES already exist in Deposco
Integrations | Netsuite - Item Pull |  | Data: "How do you want to handle missing items?" set to "Create or Update Item, Update Links If Found" - Pull item that DOES NOT already exist in Deposco
Integrations | Netsuite - Customer Pull |  | Execute: scheduled run at 01:00:00 nightly
Integrations | Netsuite - Customer Pull |  | Execute: manual run with no entries into pop-ups
Integrations | Netsuite - Customer Pull |  | Execute: manual run with "refNumberToPull " populated with one valid customer ID
Integrations | Netsuite - Customer Pull |  | Execute: manual run with "refNumberToPull" populated with multiple valid customer IDs
Integrations | Netsuite - Customer Pull |  | Execute: manual run with "refNumberToPull" populated with one invalid customer ID
Integrations | Netsuite - Customer Pull |  | Execute: manual run with "refNumberToPull" populated with mix of valid/invalid customer IDs
Integrations | Netsuite - Customer Pull |  | Data: Pull valid Customer with defined subsidiary
Integrations | Netsuite - Customer Pull |  | Data: Pull valid Customer outside of defined subsidiary
Integrations | Netsuite - Customer Pull |  | Data: Pull valid Customer of specified Category Id
Integrations | Netsuite - Customer Pull |  | Data: Pull valid Customer of non-specified Category Id
Integrations | Netsuite - Customer Pull |  | Data: Pull valid Customer where "Sent to Deposco" is true in Netsuite
Integrations | Netsuite - Customer Pull |  | Data: Pull valid Customer where "Sent to Deposco" is false in Netsuite
Integrations | Netsuite - Customer Pull |  | Criteria: Use Internal Id = True -- Create Customer
Integrations | Netsuite - Customer Pull |  | Criteria: Use Internal Id = True -- Update Customer
Integrations | Netsuite - Customer Pull |  | Criteria: Use Internal Id = False -- Create Customer
Integrations | Netsuite - Customer Pull |  | Criteria: Use Internal Id = False -- Update Customer
Integrations | Netsuite - Sales Order Pull |  | Execute: scheduled run every 15 minutes
Integrations | Netsuite - Sales Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with one valid order ID
Integrations | Netsuite - Sales Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with multiple valid order IDs
Integrations | Netsuite - Sales Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with one invalid order ID
Integrations | Netsuite - Sales Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with mix of valid and invalid order IDs
Integrations | Netsuite - Sales Order Pull |  | Data: Pull SO in status Pending Fulfillment
Integrations | Netsuite - Sales Order Pull |  | Data: Pull SO NOT status Pending Fulfillment
Integrations | Netsuite - Sales Order Pull |  | Data: Pull order with matching subsidiary id
Integrations | Netsuite - Sales Order Pull |  | Data: Pull order without matching subsidiary id
Integrations | Netsuite - Sales Order Pull |  | Data: Pull order with matching location id
Integrations | Netsuite - Sales Order Pull |  | Data: Pull order without matching location id
Integrations | Netsuite - Sales Order Pull |  | Data: Pull order with "Sent to Deposco" = true in Netsuite
Integrations | Netsuite - Sales Order Pull |  | Data: Pull order with "Sent to Deposco" = false in Netsuite
Integrations | Netsuite - Purchase Order Pull |  | Execute: scheduled run every 15 minutes
Integrations | Netsuite - Purchase Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with one valid order ID
Integrations | Netsuite - Purchase Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with multiple valid order IDs
Integrations | Netsuite - Purchase Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with one invalid order ID
Integrations | Netsuite - Purchase Order Pull |  | Execute: manual run with "NetSuite Order Number" populated with mix of valid and invalid order IDs
Integrations | Netsuite - Purchase Order Pull |  | Data: Pull PO in status Pending Receipt
Integrations | Netsuite - Purchase Order Pull |  | Data: Pull PO NOT status Pending Receipt
Integrations | Netsuite - Purchase Order Pull |  | Data: Pull order with matching subsidiary id
Integrations | Netsuite - Purchase Order Pull |  | Data: Pull order without matching subsidiary id
Integrations | Netsuite - Purchase Order Pull |  | Data: Pull order with "Sent to Deposco" = true in Netsuite
Integrations | Netsuite - Purchase Order Pull |  | Data: Pull order with "Sent to Deposco" = false in Netsuite
Integrations | Netsuite - RMA Pull |  | Execute: scheduled run every 15 minutes
Integrations | Netsuite - RMA Pull |  | Execute: manual run with "refNumberToPull" populated with one valid order ID
Integrations | Netsuite - RMA Pull |  | Execute: manual run with "refNumberToPull" populated with multiple valid order IDs
Integrations | Netsuite - RMA Pull |  | Execute: manual run with "refNumberToPull" populated with one invalid order ID
Integrations | Netsuite - RMA Pull |  | Execute: manual run with "refNumberToPull" populated with mix of valid and invalid order IDs
Integrations | Netsuite - RMA Pull |  | Data: Pull RMA in status Pending Receipt
Integrations | Netsuite - RMA Pull |  | Data: Pull RMA NOT status Pending Receipt
Integrations | Netsuite - RMA Pull |  | Data: Pull order with matching subsidiary id
Integrations | Netsuite - RMA Pull |  | Data: Pull order without matching subsidiary id
Integrations | Netsuite - RMA Pull |  | Data: Pull order with "Sent to Deposco" = true in Netsuite
Integrations | Netsuite - RMA Pull |  | Data: Pull order with "Sent to Deposco" = false in Netsuite
Integrations | Netsuite - Inbound Transfer Order Pull |  | Execute: scheduled run every 15 minutes
Integrations | Netsuite - Inbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with one valid order ID
Integrations | Netsuite - Inbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with multiple valid order IDs
Integrations | Netsuite - Inbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with one invalid order ID
Integrations | Netsuite - Inbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with mix of valid and invalid order IDs
Integrations | Netsuite - Inbound Transfer Order Pull |  | Data: Pull ITO in status Pending Receipt
Integrations | Netsuite - Inbound Transfer Order Pull |  | Data: Pull ITO NOT status Pending Receipt
Integrations | Netsuite - Inbound Transfer Order Pull |  | Data: Pull order with matching subsidiary id
Integrations | Netsuite - Inbound Transfer Order Pull |  | Data: Pull order without matching subsidiary id
Integrations | Netsuite - Inbound Transfer Order Pull |  | Data: Pull order with "Sent to Deposco" = true in Netsuite
Integrations | Netsuite - Inbound Transfer Order Pull |  | Data: Pull order with "Sent to Deposco" = false in Netsuite
Integrations | Netsuite - Outbound Transfer Order Pull |  | Execute: scheduled run every 15 minutes
Integrations | Netsuite - Outbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with one valid order ID
Integrations | Netsuite - Outbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with multiple valid order IDs
Integrations | Netsuite - Outbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with one invalid order ID
Integrations | Netsuite - Outbound Transfer Order Pull |  | Execute: manual run with "refNumberToPull" populated with mix of valid and invalid order IDs
Integrations | Netsuite - Outbound Transfer Order Pull |  | Data: Pull OTO in status Pending Fulfillment
Integrations | Netsuite - Outbound Transfer Order Pull |  | Data: Pull ITO NOT status Pending Fulfillment
Integrations | Netsuite - Outbound Transfer Order Pull |  | Data: Pull order with matching subsidiary id
Integrations | Netsuite - Outbound Transfer Order Pull |  | Data: Pull order without matching subsidiary id
Integrations | Netsuite - Outbound Transfer Order Pull |  | Data: Pull order with "Sent to Deposco" = true in Netsuite
Integrations | Netsuite - Outbound Transfer Order Pull |  | Data: Pull order with "Sent to Deposco" = false in Netsuite
Integrations | Netsuite - Ship Notice |  | Data: Ship full order at one time - single tracking number
Integrations | Netsuite - Ship Notice |  | Data: Ship full order at one time - multiple tracking numbers
Integrations | Netsuite - Ship Notice |  | Data: Ship partial order - single tracking number
Integrations | Netsuite - Ship Notice |  | Data: Ship partial order - multipile tracking numbers
Integrations | Netsuite - Ship Notice |  | Data: Ship kit to order products on full order at one time - single tracking number
Integrations | Netsuite - Ship Notice |  | Data: Ship kit to order products on full order at one time - multiple tracking numbers
Integrations | Netsuite - Ship Notice |  | Data: Ship order that was manually marked as fulfilled in Netsuite
Integrations | Netsuite - Ship Notice |  | Data: Ship quantity greater than quantity order line in Netsuite
Integrations | Netsuite - Ship Notice |  | Execute: Re-generate ship notice for failed transaction
Integrations | Netsuite - Ship Notice |  | Execute: Re-process ship notice event for failed transaction
Integrations | Netsuite - Ship Notice |  | Execute: Scheduled re-process of ship notice event for failed transactions that have been retied less than 3 times
Integrations | Netsuite - Inventory Adjustment |  | Execute: scheduled run Friday at 23:00:00
Integrations | Netsuite - Inventory Adjustment |  | Execute: manual run of scheduler
Integrations | Netsuite - Inventory Adjustment |  | Data: Summarize quantities = true -- Multiple adjustment records created for same item/location
Integrations | Netsuite - Inventory Adjustment |  | Data: Summarize quantities = true -- Single adjustment records created for each item/location
Integrations | Netsuite - Inventory Adjustment |  | Data: No adjustments found
Integrations | Netsuite - Inventory Adjustment |  | Data: Adjustments found
Integrations | Netsuite - Inventory Transfer |  | Execute: scheduled run Daily at 22:00:00
Integrations | Netsuite - Inventory Transfer |  | Execute: manual run of scheduler
Integrations | Netsuite - Inventory Transfer |  | Data: No transfers found
Integrations | Netsuite - Inventory Transfer |  | Data: Transfer found
Integrations | Netsuite - PO Receipt |  | Execute: Scheduled run every x minutes
Integrations | Netsuite - PO Receipt |  | Execute: Manual run
Integrations | Netsuite - PO Receipt |  | Data: No receipts found
Integrations | Netsuite - PO Receipt |  | Data: Receipts found
Integrations | Netsuite - PO Receipt |  | Data: Receipts found for PO manually received in Netsuite
Integrations | Netsuite - PO Receipt |  | Data: Order partilly received when job runs
Integrations | Netsuite - PO Receipt |  | Data: Order fully received when job runs
Integrations | Netsuite - RMA Receipt |  | Execute: Scheduled run every x minutes
Integrations | Netsuite - RMA Receipt |  | Execute: Manual run
Integrations | Netsuite - RMA Receipt |  | Data: No receipts found
Integrations | Netsuite - RMA Receipt |  | Data: Receipts found
Integrations | Netsuite - RMA Receipt |  | Data: Receipts found for PO manually received in Netsuite
Integrations | Netsuite - RMA Receipt |  | Data: Order partilly received when job runs
Integrations | Netsuite - RMA Receipt |  | Data: Order fully received when job runs
Integrations | UPS - Rate Shop |  | Retrieve rates for domestic shipment |  |  |  | Ready to Test
Integrations | UPS - Rate Shop |  | Retrieve rates for international shipment |  |  |  | Ready to Test
Integrations | UPS - Rate Shop |  | Retrieve rates for Saturday Delivery shipment |  |  |  | Ready to Test
Integrations | UPS - Rate Shop |  | Retrieve rates for all relevant Ship Vias: UPS Ground, UPS 2Day etc. |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label for all relevant Ship Vias: UPS Ground, UPS 2Day etc. |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve domestic shipping label |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve international shipping label |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label using Prepaid Freight Terms Type |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label using Collect Freight Terms Type |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label using Third Party Freight Terms Type |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label for Saturday Delivery shipment |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label for Residential shipment |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label for shipment where Insurance is required |  |  |  | Ready to Test
Integrations | UPS - Shipping Label |  | Retrieve shipping label for shipment where Delivery Signature is required |  |  |  | Ready to Test
Integrations | UPS - Shipping Documents |  | Retrieve Commercial Invoice for international shipment |  |  |  | Ready to Test
Integrations | FedEx - Rate Shop |  | Retrieve rates for domestic shipment |  |  |  | Ready to Test
Integrations | FedEx - Rate Shop |  | Retrieve rates for international shipment |  |  |  | Ready to Test
Integrations | FedEx - Rate Shop |  | Retrieve rates for Saturday Delivery shipment |  |  |  | Ready to Test
Integrations | FedEx - Rate Shop |  | Retrieve rates for all relevant Ship Vias: |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label for all relevant Ship Vias: FedEx Ground, FedEx Home Delivery etc. |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve domestic shipping label |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve international shipping label |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label using Prepaid Freight Terms Type |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label using Collect Freight Terms Type |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label using Third Party Freight Terms Type |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label for Saturday Delivery shipment |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label for Residential shipment |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label for shipment where Insurance is required |  |  |  | Ready to Test
Integrations | FedEx - Shipping Label |  | Retrieve shipping label for shipment where Delivery Signature is required |  |  |  | Ready to Test
Integrations | FedEx - Shipping Documents |  | Retrieve Commercial Invoice for international shipment |  |  |  | Ready to Test
Order Orchestration
Order Orchestration | Preprocessing - Data Validations |  | Ship Via missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations |  | Ship To Address info missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations |  | Trading Partner missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations |  | Line Item info missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations |  | Multiple data validations are triggered on CO |  | Order goes to Review status until all data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations |  | Duplicate order warning is triggered |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations |  | No data validation is triggered |  | Order is either Back Ordered or Released automatically upon creation |  | Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection |  | Order/order line meets ____ criteria |  | Order sources to Sourcing Group A based on sourcing profile. |  | Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection |  | Order/order line meets no matching Sourcing Selection Criteria |  | Order goes to Review with CoNotice message that sourcing could not be completed |  | Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile |  | Order meets ____ criteria |  | Order uses Routing Profile A based on routing selection profile. |  | Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile |  | Order meets no matching Routing Selection Criteria |  | Order goes to Back Order |  | Ready to Test
Order Orchestration | Order Release - Available Inventory |  | Inventory not available to fulfill entire CO in facility A |  | CO Back Orders |  | Ready to Test
Order Orchestration | Order Release - Available Inventory |  | Inventory is available to fulfill entire CO in facility A |  | CO Releases to facility A and creates an SO |  | Ready to Test
Order Orchestration | Order Management - Scheduled Routing |  | Scheduled re-route attempt on orders in Back Order status |  | Orders in Back Order automatically re-routed ever x hours. Order either stays in Back Order or moves to Released if inventory now available. |  | Ready to Test
Order Orchestration | Order Exception Management - Reprocess |  | Manual Reprocess CO in Review status |  | Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | Ready to Test
Order Orchestration | Order Exception Management - Reprocess |  | Scheduled Reprocess CO in Review status |  | Orders in Review automatically reprocessed every x hours. Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | Ready to Test
Order Orchestration | Enterprise Inventory Management |  | Inventory by Facility |  | Reports execute timely and accurately for all skus |  | Ready to Test
Order Orchestration | Inventory Segmentation - Manage Segments | [5 empty] | Ready to Test
Inbound
Inbound | Pre Receiving - Inbound Cancelation |  | Cancel entire PO before receiving has started |  | 1. PO status will be updated to "Canceled" 2. OrderLine status is moved to "Canceled" and canceled pack quantity reflects total order pack quantity |  | Needs Info | 2025-08-04 | PO_demo01 - Actions > Cancel Entire Order. Current status said receiving but Order status said new. "Action of cancel order cannot be completed" because the current status was in receiving. >> Changed Current Status to match the Order status of New. Then Actions > Cancel Entire Order. "The order has already been cancelled". How is that possible if before system error said "Action of cancel order cannot be completed." ???
Inbound | Pre Receiving - Inbound Cancelation |  | Cancel some PO lines before receiving has started |  | 1. Canceled pack quantity should be updated with entire order pack quantity 2. OrderLine status is moved to "Canceled" 3. When receiving, those items should not appear |  | Needs Info | 2025-08-06 | PACPO-ZB-1 - #1 requires clarification. Total line count is showing as 3 under Orders List > Total Line Count (API). #2 and 3 passed.
Inbound | Pre Receiving - Inbound Cancelation |  | Cancel part of PO line before receiving has started |  | 1. Canceled pack quantity should be updated with canceled quantity 2. When receiving, updated amount will is listed in receiving screen |  | Needs Info | 2025-08-06 | What is the difference between this test case and the one prior?
Inbound | Pre Receiving - Adjust Inventory |  | Adjust incorrect inventory out of the system |  | Stock Unit should be removed from the system |  | Needs Info | 2025-08-04 | 38001 > QTY 2 > "Please select the inventory you want to consume". Attempted Ctrl + Select to select multiple inventory but did not work. How do we change a QTY higher than 1? | you can find this process under handheld > invnetory > adjust inventory
| Pre Receiving - Adjust Inventory |  | Create correct inventory in the system |  | Stock Unit should be created with correct inventory tracking |  | Pass | 2025-08-05
Inbound | Receiving |  | Scan item not on PO |  | Should receive an error that the orderLine for that item does not exist |  | Pass | 2025-07-25
Inbound | Receiving |  | Scan item on PO |  | Should be prompted for quantity and weight of item received to that LPN |  | Failed | 2025-07-25 | For Pacsun 38001-LPN screen marks the LPN as received. No prompt for QTY and weight. 7/29 From Lanie, need to retest with a different PO because the cross dock process needed for Pacsun has not been demoed yet.
Inbound | Receiving |  | Scan item that doesn't exist |  | should receive an error to scan a valid item |  | Pass | 2025-07-25 | System output is the same as 'Scan item not on PO'. Unsure if verbiage needs to be changed.
Inbound | Receiving |  | Enter quantity less than quantity on PO |  | Item should still be available on item scanning screen with amount remaining to be received as the quantity |  | Pass | 2025-07-26 | Verbiage is unclear. Test completed under the assumption 'Enter' means 'receive'.
Inbound | Receiving |  | Enter quantity equal to quantity on PO |  | Item should disappear from item selection screen |  | Ready to Test
Inbound | Receiving |  | Enter quantity greater than quantity on PO |  | should be allowed to over-receive up to 20% more inventory. If you enter a quantity larger, should receive an error |  | Ready to Test
Inbound | Receiving |  | Click finish before scanning all units on PO |  | 1. PO should move into "Partial Received" Status 2. PO lines that have been received will be in "received status", otherwise they should be in "partial receipt" or "new" status 3. Stock Units are created with correct inventory tracking information and orderHeader is updated with unload type |  | In Progress | 2025-07-25 | #1 complete. Require clarity for expected outcomes #2 and #3.
Inbound | Receiving |  | Click next without scanning LPN |  | Output response is "Please scan LPN to receive." |  | Needs Info | 2025-07-26 | Test case scenario added - Please capitalize LPN in the system output
Inbound | Blind Receiving |  | Scan PO Number that does not exist |  | Should be prompted to continue and create the order as a blind receipt |  | Pass | 2025-07-25 | System output needs to be updated from 'continue as blind order' to continue as blind receipt.'
Inbound | Blind Receiving |  | Scan the item number that is being received |  | Should be prompted for item tracking information and amount of items on LPN |  | Failed | 2025-08-04 | Inbound > Blind Receiving > 12001 - Item Number for MTO Copper "No records found matching that identifier, click Next to continue as Blind Order". The sysem should already know this is a Blind Order. Prompt for TRK + QTY not reached.
Inbound | Blind Receiving |  | Attempt to add items to LPN that has stock |  | Should receive an error that the container already has stock |  | Ready to Test
Inbound | Blind Receiving |  | Click finish after scanning all items in the container |  | 1. Order should be created with scanned PO number as "Blind Receipt" 2. OrderLines are created with correct quantity 3. Stock Units are created with inventory tracking information and orderHeader is updated with unload type |  | Ready to Test
Inbound | Blind Receiving |  | Enter PO Number for non-Copper customer |  | Output response is "Please enter a PO for Copper Receiving." |  | Failed | 2025-07-26 | Tested for PO 744981. Not Copper, but allowed by system.
Inbound | Receiving - Misc Receiving Scenarios |  | Receive damaged products |  | LPN should be moved to damaged area |  | Invalid | 2025-07-26 | From Design Doc - " After receipt, the operations team will update the inventory status to "hold, damaged" directly in the system's user interface to prevent the inventory from being allocated to orders, rather than transferring these items to a specific damaged area within the warehouse.. Users can utilize Handhelds to capture images of the damaged goods and store them to the Purchase Order in Deposco."
Inbound | Receiving - Misc Receiving Scenarios |  | Receive Lot Tracked products |  | User will be prompted for lot information after receiving the product |  | Ready to Test
Inbound | Receiving - Misc Receiving Scenarios |  | Receive Expiration Date tracked products |  | User will be prompted for expiration date information after receiving the product |  | Ready to Test
Inbound | Receiving - Misc Receiving Scenarios |  | Receive Serial Tracked Products - unique serial |  | User will be prompted for serial number information after receiving the product |  | Ready to Test
Inbound | Receiving - Misc Receiving Scenarios |  | Receive Serial Tracked Products - duplicate serial number |  | User should receive an error that the serial number already exists |  | Ready to Test
Inbound | Receiving - Misc Receiving Scenarios |  | Receive each pack |  | When finished receiving, stock units should be created with "Each" as the pack type |  | Ready to Test
Inbound | Directed Putaway |  | Putaway single sku from receiving to suggested putaway location |  | 1. User should be directed to put the item away in locations that have the same item and if none, empty locations 2. When user selects a location, LPN is moved to that location |  | Ready to Test
Inbound | Directed Putaway |  | Putaway single sku from receiving to non-suggested putaway location |  | User should be able to scan any location and move LPN to that location |  | Ready to Test
Inbound | Putaway - Move Container |  | Putaway single sku from receiving to suggested putaway location |  | 1. User should be directed to put the item away in locations in empty locations 2. When user selects a location, LPN is moved to that location |  | Ready to Test
Inbound | Putaway - Move Container |  | Putaway single sku from receiving to non-suggested putaway location |  | User should be able to scan any location and move LPN to that location |  | Ready to Test
Inventory Management
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a single reserve location (enough to refill storage to maximum capacity) |  | Scheduler runs successfully. Replenishment task created to pull enough stock from reserve location to refill storage location to maximum capacity. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a single reserve location (but NOT enough to refill storage to maximum capacity) |  | Scheduler runs successfully. Replenishment task created to pull all stock from reserve location to refill storage location with remaining units. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a multiple reserve locations (each with enough stock to refill storage to maximum capacity) |  | Scheduler runs successfully. Replenishment task created to pull enough stock from the reserve location with the lowest pick sequence to refill storage location to maximum capacity. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a multiple reserve locations (only one with enough stock to refill storage to maximum capacity) |  | Scheduler runs successfully. Replenishment task created to pull enough stock from the reserve location full quantity to refill storage location to maximum capacity. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a multiple reserve locations (neither with enough stock to refill storage to maximum capacity alone) |  | Scheduler runs successfully. Multiple replenishment tasks created to pull enough stock from the each reserve location to sum up to the amount that will refill storage location to maximum capacity. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is below the storage minimum but NO additional stock exists in a reserve location |  | Scheduler runs successfully. No replenishment tasks created. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Execute replenishment scheduler when stock for a storage location is greater than or equal to the storage minimum |  | Scheduler runs successfully. No replenishment tasks created. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Generate Replenishment Task for serialized product |  | Replenishment tasks generated per serial number to be replenished - each task with quantity of 1 and serial number to pull associated. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Generate Replenishment Task for lot tracked product |  | Replenishment tasks generated per lot number to be replenished - each task with corresponding lot and quantity associated. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Generate Replenishment Task for expiration date tracked product |  | Replenishment tasks generated per expiration date to be replenished - each task with corresponding expiration date and quantity associated. |  | Ready to Test
Inventory Management | Replenishment Creation |  | Generate Replenishment Task for products with no lot, serial, or expiration date tracking. |  | Replenishment tasks generated per pull location and item. |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull requested quantity on replenishment task |  | Quantity entered is moved to replenishment cart for putaway |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull more than requested quantity on replenishment task |  | Quantity entered is moved to replenishment cart for putaway |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Perform exception for full quantity to pull |  | Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Perform exception for partial quantity to pull |  | Quantity entered is moved to repelnishment cart for putaway. Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull from LPN Controlled Location |  | User is prompted to enter LPN from which they pull inventory |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull from Non-LPN Controlled Location |  | User is prompted to enter only the sku and quantity to pull |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull serialized products |  | User is prompted first to enter the sku and quantity, then to confirm the serial number to pull |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull lot tracked products |  | User is prompted first to enter the sku and quantity, then to confirm the lot number to pull |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Pull expirationd date tracked products |  | User is prompted first to enter the sku and quantity, then to confirm the expiration date to pull |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Complete all pull tasks before moving to put tasks |  | User is automatically prompted to begin putaway |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Pull - Select Cart Full to put away already pulled products before pulling more |  | Direct user to complete the replenishments that have already been picked, once completed, direct user back to replenishment task screen to continue with replenishment process |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Put - Replenish to an LPN Controlled Location |  | User is prompted to enter putaway location, sku, LPN, and quantity |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Put - Replenish to a Non-LPN Controlled Location |  | User is prompted to enter putaway location, sku, and quantity |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Put - Replenish serialized products |  | User is prompted first to enter the location, sku and quantity, then to confirm the serial number to put away |  | Ready to Test
Inventory Management | Replenishment |  | Replenishment Put - Replenish lot tracked products |  | User is prompted first to enter the location, sku and quantity, then to confirm the lot number to put away
Inventory Management | Replenishment |  | Replenishment Put - Replenish expiration date tracked products |  | User is prompted first to enter the location, sku and quantity, then to confirm the expiration date to put away
Inventory Management | Replenishment |  | Replenishment Put - Perform exception for full quantity to put |  | Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process. Task is created to put stock back to source reserve location.
Inventory Management | Replenishment |  | Replenishment Put - Perform exception for partial quantity to put |  | Quantity entered is put away. Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process. Task is created to put remaining stock back in source reserve location.
Inventory Management | Kitting |  | Create Workorder Manually |  | Workorder with correct kit and quantity is created for kitting location
Inventory Management | Kitting |  | Attempt to complete workorder when insufficient inventory exists in kitting workcell to create any quantity of output sku |  | Error message: Workcell doesn't have enough inventory to build.
Inventory Management | Kitting |  | Attempt to complete a workorder when insufficient inventory exists in kitting workcell to complete entire workorder, however enough exists to build some quantity of output skus. |  | User is allowed to build as many outputs as the input quantities allow. Workorder remains in "Active" status and partial quantity of kit is successfully created, item components quantity is decremented properly
Inventory Management | Kitting |  | Attempt to build quantity greater than workorder quantity with sufficient inventory available of input skus in kitting workcell. |  | Receive an error for attempting to build quantity over workorder quantity
Inventory Management | Kitting |  | Attempt to build quantity equal to the workorder quantity with sufficient inventory available of input skus in kitting workcell. |  | Receive message that workorder has been completed. Output item quantity in Kit location increases by correct amount and item componenet is decremented
Inventory Management | Cycle Count Creation |  | Cycle Count LPN-Controlled Location |  | Will be prompted to count in LPNs
Inventory Management | Cycle Count Creation |  | Create Cycle Count via A,B, C Mover Scheduler |  | Cycle Count tasks generated for locations
Inventory Management | Cycle Count Creation |  | Create Full Physical Cycle Count Via Full Physical Scheduler |  | Cycle Count tasks generated for locations
Inventory Management | Cycle Count Creation |  | Bulk Count via Handheld |  | Quantity will be displayed on item pack screen when cycle counting
Inventory Management | Cycle Count Creation |  | Blind Count via Handheld |  | Quantity will not be displayed on item pack in handheld
Inventory Management | Cycle Count Creation |  | Create Location Cycle Count via Location PAL |  | A screen message will show saying "The Location [location] is scheduled for Cycle Count". A cycle count task with status NEW should be generated for the specified location with the specified priority.
Inventory Management | Cycle Count Creation |  | Approve Variances |  | Quantity in Variance Stock Unit will not reflect UNTIL manager approves variance via approve variances screen
Inventory Management | Cycle Count Creation |  | Create Location Cycle Count via Item PAL |  | A screen message will show saying "A cycle count has been scheduled" A cycle count task with status NEW should be generated for the specified item with the specified priority. CC type will be 'By item'
Inventory Management | Cycle Count Creation |  | Execute cycle count task scheduler for A movers when there are A classified items that have have not been counted in 90 days. |  | Cycle count tasks generated for A classified items that have not been counted in 90 days
Inventory Management | Cycle Count Creation |  | Execute cycle count task scheduler for B movers when there are B classified items that have have not been counted in 180 days. |  | Cycle count tasks generated for B classfieid items that have not been counted in 180 days
Inventory Management | Cycle Count Creation |  | Execute cycle count task scheduler for C movers when there are C classified items that have have not been counted in 365 days. |  | Cycle count tasks generated for C classified items that have not been counted in 365 days
Inventory Management | Cycle Count Creation |  | Execute cycle count task scheduler for A movers when there are NO A classified items that have have not been counted in 90 days. |  | No cycle count tasks created
Inventory Management | Cycle Count Creation |  | Execute cycle count task scheduler for B movers when there are NO B classified items that have have not been counted in 180 days. |  | No cycle count tasks created
Inventory Management | Cycle Count Creation |  | Execute cycle count task scheduler for C movers when there are NO C classified items that have have not been counted in 365 days. |  | No cycle count tasks created
Inventory Management | Cycle Count Creation |  | Execute cycle count scheduler for full physical count |  | Count task created for all items/locations
Inventory Management | Cycle Count Creation |  | Use Process Action Link to create count by location for location where Cycle Count = true |  | Count task created for location
Inventory Management | Cycle Count Creation |  | Use Process Action Link to create count by location for location where Cycle Count = false |  | No cycle count tasks created
Inventory Management | Cycle Count Creation |  | Use Process Action Link to create count by item for item where Cycle Count = true |  | Count task created for every location in which the item exists
Inventory Management | Cycle Count Creation |  | Use Process Action Link to create count by item for item where Cycle Count = false |  | No cycle count tasks created
Inventory Management | Cycle Count |  | Count location with one item |  | 1 item will display in CC item listbox when user scans location in Handheld
|  |  | Count location with multiple items |  | Multiple items will display in CC item listbox when user scans location from CC task
|  |  | Count exact quantity that actually exists in the location systematically |  | No variance is recorded in 'Approve Variances' and cycle count task status goes to COMPLETE
|  |  | Count different quantity than what actually exists in the location systematicall |  | Variance recorded in 'Approve Variances' - must be approved my admin user. SU wil reflect original QTY until this variance is approved
|  |  | Skip counting an item in a location by hitting "Next Location" before all items are counted |  | CC task for location will be complete status
|  |  | Scan an item that does not systematically exist in a location when counting |  | Item does not exist in this location - Error Message
|  |  | Count items in an LPN controlled location |  | Will be prompted to scan for LPNS
|  |  | Count items in a Non-LPN controlled location |  | Will not be prompted to scan in LPNS
|  |  | Count serial tracked items |  | Will have to enter serial/sku via grocery scanning process instead of QTY entry
|  |  | Count lot tracked items |  | Lot required
|  |  | Count expiration date tracked items |  | Expiration date required
Outbound
Outbound | Outbound Order Management - Address Validation |  | Process order that fails address validation with suggested change |  | Sales Order goes to status "Hold - AV" and Order Header Note created with suggested address changes - POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - Address Validation |  | Process order that fails address validation with NO suggested change |  | Sales Order goes to status "Hold - AV" and Order Header Note created indicating no suggestions could be found - POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - Address Validation |  | Process order that passes address validation |  | Sales Order stays in New status - POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - POI Done |  | POI runs successfully |  | POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - POI Done |  | POI fails |  | POI Done flag stays false. Waving does not run on the order. |  | Ready to Test
Outbound | Outbound Order Management - Re-run POI |  | Scheduler re-runs POI on orders where POI Done is not true |  |  |  | Ready to Test
Outbound | Pickwave Management - Waving Execution |  | Manually wave one order |  | Order selected remains in New, moves to Back Ordered, or moves to Released based on profile match and inventory evaluation |  | Ready to Test
Outbound | Pickwave Management - Waving Execution |  | Manually wave multiple orders |  | All orders selected remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation |  | Ready to Test
Outbound | Pickwave Management - Waving Execution |  | Scheduled wave multiple orders |  | All orders in New or Back Ordered status are waved in order of created date ascending. All orders remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation. |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  | Order matches large order profile conditions |  | Order waved on Large Order Wave - can only be picked in Single Scan Picking |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  | Order matches singles order profile conditions |  | Order waved on Singles Wave - can only be picked in Single Scan Picking |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  | Order matches multis order profile conditions |  | Order waved on Multis Wave - can only be picked in Batch Picking |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  | Order matches no waving criteria |  | Order stays in New or Back Ordered status |  | Ready to Test
Outbound | Pickwave Management - Back Order Management |  | Order waved has sufficient inventory available to release |  | Order moves to Released and is assigned a Pickwave with work group and pick tasks |  | Ready to Test
Outbound | Pickwave Management - Back Order Management |  | Order waved as no sufficient inventory available to release |  | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
Outbound | Pickwave Management - Back Order Management |  | Order waved as partially sufficient inventory available to release |  | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
Outbound | Picking - Singles Picking |  | Select the top pickwave from the list when multiple waves are available and scan a valid LPN |  |  |  | Ready to Test
Outbound | Picking - Singles Picking |  | Select a pickwave from the list that is not at the top of the list when multiple waves are available and scan a valid LPN
Outbound | Picking - Singles Picking |  | Select a pickwave from the list and scan a pre-existing, empty LPN to start picking
Outbound | Picking - Singles Picking |  | Select a pickwave from the list and scan a pre-existing, non-empty LPN to start picking
Outbound | Picking - Singles Picking |  | Select a pickwave from the list and scan a value in the LPN field that is not already tied to any LPN in the system
Outbound | Picking - Singles Picking |  | Scan a valid LPN whithout selecting a pickwave from the list of multiple pickwaves
Outbound | Picking - Singles Picking |  | Scan a valid LPN whithout selecting a pickwave from the list when only one pickwave exists in list.
Outbound | Picking - Singles Picking |  | Scan a location other than the one prompted on location pick screen. |  | Error message: "The location [x] does not match the required location." |  | Ready to Test
Outbound | Picking - Singles Picking |  | Scan a location that matches the one prompted on location pick screen. |  | Takes user to the item selection picking screen to enter in the SKU |  | Ready to Test
Outbound | Picking - Singles Picking |  | Scan a barcode value that does not match the Item Number or Item UPC prompted on the item pick screen |  | Error message: "The SKU [x] could not be found. Please enter a valid SKU." |  | Ready to Test
Outbound | Picking - Singles Picking |  | Scan a barcode value that matches the item number prompted on the item pick screen |  | Takes user to the quantity picking sreen |  | Ready to Test
Outbound | Picking - Singles Picking |  | Scan a barcode value that matches the item upc that matches the item prompted on the item pick screen |  | Takes user to the quantity picking sreen
Outbound | Picking - Singles Picking |  | Enter in a quantity greater than quantity prompted on quantity input screen. |  | Error Message: "The quantity that you entered [x] is more than the quantity that is required [x]. |  | Ready to Test
Outbound | Picking - Singles Picking |  | Enter in a quantity less than quantity prompted on quantity input screen.
Outbound | Picking - Singles Picking |  | Enter in quantity that matches the quantity prompted on quantity input screen |  | If there are more pick tasks on the wave, it will take the user to the next location to complete the next task. If the task is the last one on the wave, it willt take the user back to the picking menu screen with a message"Picking LPN [x] staged to [Shipping]." |  | Ready to Test
Outbound | Picking - Singles Picking |  | Select "stage" on location input screen after picking one item on a wave. |  | Picking cart will be staged to shipping and user will be prompted to scan new picking cart to finish the pick wave |  | Ready to Test
Outbound | Picking - Singles Picking |  | Select "stage" on location input screen before picking any items on the wave. |  | ?
Outbound | Picking - Singles Picking |  | Select Exception and choose "No Stock" |  | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item
Outbound | Picking - Singles Picking |  | Suspend a pick Task |  | The task is now moved to the end of the queue, it is picked last
Outbound | Picking - Singles Picking |  | Suspend a Work Group |  | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated
Outbound | Picking - Singles Picking |  | End a Work Group |  | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore
Outbound | Picking - Singles Picking |  | Select "Back" on picking exception screen
Outbound | Picking - Singles Picking |  | Pick one unit of an item that is serial tracked |  | User is prompted for Serial Number after selecting the quantity
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is serial tracked from the same location |  | User is prompted for a Serial Number for each unit picked after selecting the quantity
Outbound | Picking - Singles Picking |  | Pick one unit of an item that is lot tracked |  | User is prompted for Lot Number after selecting the quantity
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is lot tracked from the same location - only one lot in location
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  | Pick one unit of an item that is expiration date tracked |  | User is prompted for Exp Date after selecting the quantity
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is expiration date tracked from the same location - only one lot in location
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  | Pick multiple units of an item that is expiration date tracked from the same location - multiple expiration dates in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  | Pick order with Order Header Note with Title = Picking Note
Outbound | Picking - Singles Picking |  | Pick order without Order Header Note with Title = Picking Note
Outbound | Picking - Singles Picking |  | Pick order with Order Line Note with Title = Picking Note
Outbound | Picking - Singles Picking |  | Pick order with Order Line Note without Title = Picking Note
Outbound | Picking - Multis Picking |  | Select pick wave and click "Summary" for an Exception Re-pick Wave |  | User is given the bin associated with the stock previously picked
Outbound | Picking - Multis Picking |  | Select pick wave and click "Summary" for a non-exception re-pick wave
Outbound | Picking - Multis Picking |  | Select the top pickwave from the list when multiple waves are available and submit
Outbound | Picking - Multis Picking |  | Select a pickwave from the list that is not at the top of the list when multiple waves are available and submit
Outbound | Picking - Multis Picking |  | Select the pickwave from the list when only one wave is available and submit
Outbound | Picking - Multis Picking |  | Select no pickwave from the list when only one wave is available and submit
Outbound | Picking - Multis Picking |  | Select no pickwave from the list when multiple waves are available and submit
Outbound | Picking - Multis Picking |  | Scan a location other than the one prompted on location pick screen. |  | Error message: "Please scan a valid location" |  | Ready to Test
Outbound | Picking - Multis Picking |  | Scan a location that matches the one prompted on location pick screen. |  | Takes user to the item selection picking screen to enter in the SKU |  | Ready to Test
Outbound | Picking - Multis Picking |  | Scan a barcode value that does not match the Item Number or Item UPC prompted on the item pick screen |  | Error message: "Please scan a valid item."
Outbound | Picking - Multis Picking |  | Scan a barcode value that matches the item number prompted on the item pick screen |  | Takes user to the quantity picking sreen
Outbound | Picking - Multis Picking |  | Scan a barcode value that matches the item upc that matches the item prompted on the item pick screen |  | Takes user to the quantity picking sreen
Outbound | Picking - Multis Picking |  | Enter in a quantity greater than quantity prompted on quantity input screen. |  | Error Message: "Quantity entered is greater than required."
Outbound | Picking - Multis Picking |  | Enter in a quantity less than quantity prompted on quantity input screen. |  | user is asked to put the initial quantity into a bin and then brought back to scan the location, quantity, and bin for the reamaining quanitites on the wave
Outbound | Picking - Multis Picking |  | Enter in quantity that matches the quantity prompted on quantity input screen |  | User is brought to the bin selection picking screen
Outbound | Picking - Multis Picking |  | Scan LPN for first pick of an order (no suggested LPN) that has stock units in it already |  | Error Message: "Scanned bin [x] contains other orders
Outbound | Picking - Multis Picking |  | Scan LPN for first pick of an order (no suggested LPN) that does not have stock units in it |  | User is brought to the next pick task and is asked to scan the next location if there are available pick tasks.
Outbound | Picking - Multis Picking |  | Scan LPN for a unit that is not the first pick of an order that does not match the suggested LPN displayed |  | Error Message: The suggested bin is [x].
Outbound | Picking - Multis Picking |  | Scan LPN for a unit that is not the first pick of an order that matches the suggested LPN displayed |  | Item & stock units are moved to the bin. User is brought to the next task if available, else it will bring the user to the Picking Menu screen to select another wave to complete if available
Outbound | Picking - Multis Picking |  | Select "New Bin" when prompted to scan into a suggested LPN that is full |  | Message: "New bin created for Order [x]. and user is able to select another bin to put item into if there is not existing stock in the new bin
Outbound | Picking - Multis Picking |  | Select "New Bin" when no suggested LPN is prompted |  | ?
Outbound | Picking - Multis Picking |  | Select Exception and choose "No Stock" |  | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item
Outbound | Picking - Multis Picking |  | Suspend Task |  | The task is now moved to the end of the queue, it is picked last
Outbound | Picking - Multis Picking |  | Suspend Work Group |  | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated
Outbound | Picking - Multis Picking |  | End Work Group |  | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore
Outbound | Picking - Multis Picking |  | Select "Back" on picking exception screen
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is serial tracked from the same location |  | User is prompted for a Serial Number for each unit picked after selecting the quantity |  | Ready to Test
Outbound | Picking - Multis Picking |  | Pick one unit of an item that is lot tracked |  | User is prompted for Lot Number after selecting the quantity |  | Ready to Test
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is lot tracked from the same location - only one lot in location |  |  |  | Ready to Test
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  | Pick one unit of an item that is expiration date tracked |  | User is prompted for Exp Date after selecting the quantity
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is expiration date tracked from the same location - only one lot in location
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  | Pick multiple units of an item that is expiration date tracked from the same location - multiple expiration dates in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  | Pick order with Order Header Note with Title = Picking Note
Outbound | Picking - Multis Picking |  | Pick order without Order Header Note with Title = Picking Note
Outbound | Picking - Multis Picking |  | Pick order with Order Line Note with Title = Picking Note
Outbound | Picking - Multis Picking |  | Pick order with Order Line Note without Title = Picking Note
Outbound | Packing - Singles Packing |  | Scan an invalid or non-existent identifier as the tote lpn |  | User gets an error and is prompted to scan an existing container
Outbound | Packing - Singles Packing |  | Scan a valid tote LPN which is NOT eligible for pack order by item due to the following reasons 1. Multi item orders (Non Ready to Ship packs) 2. Multi quantity order (Non Ready to Ship packs) |  | User gets an error and is prompted to scan a valid tote lpn with single unit orders
Outbound | Packing - Singles Packing |  | Scan a valid tote LPN which is eligible (stock quantities are for singles eligible orders on the pallet). 1. Single item/quantity/order 2. Order with multiple Ready to Ship Items |  | User is taken to the next screen to see the item selection screen
Outbound | Packing - Singles Packing |  | Scan a valid item barcode of an item displayed on the packing screen in the handheld |  | Scan is accepted and user is taken to the next screen scan the package weight and dims
Outbound | Packing - Singles Packing |  | Scan a valid UPC barcode of an item displayed on the packing screen in the handheld |  | Scan is accepted and user is taken to the next screen to scan the package weight and dims
Outbound | Packing - Singles Packing |  | Scan an invalid or non-existent identifier as the Item scan Invalid = not an item displayed on the screen. Non-existent = barcode not in system. |  | User gets an error and is prompted to scan the item again
Outbound | Packing - Singles Packing |  | Click back during packing. Container contains contents for multiple single unit orders |  | Order is rolled back into shipping container.
Outbound | Packing - Singles Packing |  | Pack serial tracked item, scan a serial number that does not exist for an item in the picking container or is tied to stock in a different location/lpn |  | User gets an error and is forced to scan a valid serial number for the item
Outbound | Packing - Singles Packing |  | Pack serial tracked item, scan a serial number that does exist for an item in the picking container or is tied to stock in a different location/lpn |  | User is able to continue through the process and the system accepts the serial number entry
Outbound | Packing - Singles Packing |  | Pack lot tracked item, select a lot number that matches the item being packed when multiple lots exist in picking container for the item |  | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Singles Packing |  | Pack lot tracked item, select a lot number that matches the item being packed when one lot exists in picking container for the item |  | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Singles Packing |  | Pack expiration tracked item, select an expiration date that matches the item being packed when one expiration date exists in picking container for the item |  | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Singles Packing |  | Pack expiration tracked item, select an expiration date that matches the item being packed when multiple expiration dates exists in picking container for the item |  | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Singles Packing |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do not match any stock units in the picking container |  | Error message - stock unit not found
Outbound | Packing - Singles Packing |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do match a stock unit in the picking container |  | User is able to continue through the process and the system takes the displayed lot and expiration from the drop down list
Outbound | Packing - Singles Packing |  | Manually select a carton type on the container weight and dimension screen |  | User is allowed to proceed and the selected carton type will be used for declaring dimensions in the shipping request
Outbound | Packing - Singles Packing |  | Scan an invalid or non-existent identifier as the carton type on the container weight and dimension screen |  | User gets an error and is prompted to scan an existing carton type
Outbound | Packing - Singles Packing |  | Scan a carton type identifier in the carton type input on the container weight and dimension screen |  | System accepts the selected carton type and will be used for declaring dimensions in the shipping request
Outbound | Packing - Singles Packing |  | User manually enters the weight of the shipping container after packing is complete |  | The package is packed, and takes the weight that the user manually entered
Outbound | Packing - Singles Packing |  | User validates the autocalulated weight (weight is auto calculated on the basis of the quantity picked and the pack weight in the master data set up) |  | System displays the sum of the weight using the pack weight for the items for each order
Outbound | Packing - Singles Packing |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non integer value in the package weight entry box |  | User gets an error due to an invalid entry
Outbound | Packing - Singles Packing |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non numeric value in the package weight entry box |  | User gets an error due to an invalid entry
Outbound | Packing - Singles Packing |  | User hits submit, and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). |  | User gets a packing slip for the orders
Outbound | Packing - Singles Packing |  | User hits submit, and shipping labels print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). |  | User gets a shipping label for the order
Outbound | Packing - Singles Packing |  | User hits submit, and shipping label and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). |  | User gets a shipping label and packing slip for the orders
Outbound | Packing - Multis Packing |  | Scan an invalid or non-existent identifier as the tote lpn |  | User gets an error and is prompted to scan an existing container
Outbound | Packing - Multis Packing |  | Scan a valid tote lpn which contains the picks for one order in it. However, the order is in an invalid status and is not eligible for packing (back ordered, released, etc) |  | User gets an error and is prompted to scan an existing container
Outbound | Packing - Multis Packing |  | Scan a valid tote lpn which contains the picks for one order in it, and the order is eligible for packing |  | User is taken to the next screen to see the item selection screen
Outbound | Packing - Multis Packing |  | Scan a valid item barcode of an item displayed on the packing screen in the handheld |  | Scan is accepted and user is taken to the next screen to scan the package weight and dims, or to continue scanning additional items if additional items remain to be packed
Outbound | Packing - Multis Packing |  | Scan a valid UPC barcode of an item displayed on the packing screen in the handheld |  | Scan is accepted and user is taken to the next screen to scan the package weight and dims, or to continue scanning additional items if additional items remain to be packed
Outbound | Packing - Multis Packing |  | Scan an invalid or non-existent identifier as the Item scan Invalid = not an item displayed on the screen. Non-existent = barcode not in system. |  | User gets an error and is prompted to scan the item again
Outbound | Packing - Multis Packing |  | Click back during packing. Container contains contents for multiple single unit orders |  | Packer exits from the container screen. Can rescan container and pack what is remaining
Outbound | Packing - Multis Packing |  | Pack in grocery scan mode (single unit pack per scan) by scanning the item barcode or item UPC barcode |  | 1. Scan registers 1 qty everytime the item identifier is scanned in the process. 2. If item attributes are required for the item, the user is taken to the item tracking capture screen 3. If more units are required to be packed for the same lpn, the user stays on the item screen to scan the item again 4.If there are no more units left in the picking lpn (tote), the user is directed to the container weight and dims screen to continue packing after any required item tracking attributes have been captured
Outbound | Packing - Multis Packing |  | Enter a non numeric value in the quantity input section of the screen (Non Grocery Mode) |  | User gets an error and is prompted to enter the quantity again
Outbound | Packing - Multis Packing |  | Enter a quantity that is higher than the required quantity in the quantity input section of the screen (Non Grocery Mode) |  | User gets an error suggesting entered qty is greater than required.
Outbound | Packing - Multis Packing |  | Enter a negative quantity in the quantity input section of the screen (Non Grocery Mode) |  | User gets an error and is prompted to enter the quantiy again
Outbound | Packing - Multis Packing |  | Enter a quantity that is lesser than the required quantity in the quantity input section of the screen (Non Grocery Mode) |  | Quantity is registered and the system suggests to pack the remainder quantity to the user
Outbound | Packing - Multis Packing |  | Enter a quantity that is exactly the required quantity in the quantity input section of the screen (Non Grocery Mode) |  | Quantity is registered and the user continues to pick the rest of the picks or is prompted to stage the LPN.
Outbound | Packing - Multis Packing |  | Enter a non integer (decimal value) in the quantity input section of the screen (Non Grocery Mode) |  | User gets an error and is prompted to enter the quantity again
Outbound | Packing - Multis Packing |  | Pack serial tracked item, scan a serial number that does not exist for an item in the picking container or is tied to stock in a different location/lpn |  | User gets an error and is forced to scan a valid serial number for the item
Outbound | Packing - Multis Packing |  | Pack serial tracked item, scan a serial number that does exist for an item in the picking container or is tied to stock in a different location/lpn |  | User is able to continue through the process and the system accepts the serial number entry
Outbound | Packing - Multis Packing |  | Pack lot tracked item, select a lot number that matches the item being packed when multiple lots exist in picking container for the item |  | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Multis Packing |  | Pack lot tracked item, select a lot number that matches the item being packed when one lot exists in picking container for the item |  | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Multis Packing |  | Pack expiration tracked item, select an expiration date that matches the item being packed when one expiration date exists in picking container for the item |  | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Multis Packing |  | Pack expiration tracked item, select an expiration date that matches the item being packed when multiple expiration dates exists in picking container for the item |  | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Multis Packing |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do not match any stock units in the picking container |  | Error message - stock unit not found
Outbound | Packing - Multis Packing |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do match a stock unit in the picking container |  | User is able to continue through the process and the system takes the displayed lot and expiration from the drop down list
Outbound | Packing - Multis Packing |  | Hit 'New Bin' to continue packing into a new shipping box since the existing box is too full and cannot accept any more items |  | System registers the new bin scan and user is taken to confirm the weight and dims screen to confirm the dimensions and weight of the previous (full) box before continuing with packing into a new shipping box
Outbound | Packing - Multis Packing |  | Manually select a carton type on the container weight and dimension screen |  | User is allowed to proceed and the selected carton type will be used for declaring dimensions in the shipping request
Outbound | Packing - Multis Packing |  | Scan an invalid or non-existent identifier as the carton type on the container weight and dimension screen |  | User gets an error and is prompted to scan an existing carton type
Outbound | Packing - Multis Packing |  | Scan a carton type identifier in the carton type input on the container weight and dimension screen |  | System accepts the selected carton type and will be used for declaring dimensions in the shipping request
Outbound | Packing - Multis Packing |  | User manually enters the weight of the shipping container after packing is complete |  | The package is packed, and takes the weight that the user manually entered
Outbound | Packing - Multis Packing |  | User validates the autocalulated weight (weight is auto calculated on the basis of the quantity picked and the pack weight in the master data set up) |  | System displays the sum of the weight using the pack weight for the items for each order
Outbound | Packing - Multis Packing |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non integer value in the package weight entry box |  | User gets an error due to an invalid entry
Outbound | Packing - Multis Packing |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non numeric value in the package weight entry box |  | User gets an error due to an invalid entry
Outbound | Packing - Multis Packing |  | User hits submit, and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). |  | User gets a packing slip for the orders
Outbound | Packing - Multis Packing |  | User hits submit, and shipping labels print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). |  | User gets a shipping label for the order
Outbound | Packing - Multis Packing |  | User hits submit, and shipping label and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). |  | User gets a shipping label and packing slip for the orders
Outbound | Outbound - Cartonization | [5 empty] | Ready to Test
Outbound | Outbound - Rate Shopping | [5 empty] | Ready to Test
Outbound | Outbound - EDI Fulfillment | [5 empty] | Ready to Test
Other WMS
Other WMS | Other WMS - Transfer Orders |  | -- |  | Report returns timely and accurately for customer needs |  | Ready to Test
Other WMS | Other WMS - Shipping Documents/Labels |  | -- |  | Report returns timely and accurately for customer needs |  | Ready to Test
Other WMS | Other WMS - 3PL Billing |  | -- |  | Report returns timely and accurately for customer needs |  | Ready to Test
Other WMS |  |  | -- |  | Report returns timely and accurately for customer needs |  | Ready to Test
Other WMS |  |  | -- |  | Report returns timely and accurately for customer needs |  | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Reporting
Reporting | Dashboard - Inbound
Reporting | Dashboard - Inventory Management Dashboard
Reporting | Dashboard - Outbound
Reporting | Dashboard - User Performance
Reporting | Report Builder -
PacSun/Cross Dock
Cross Dock | PacSun - Pre Receiving |  | Upload PacSun spreadsheets to FTP server |  | 1. PO should be created with PacSun PO number 2. Sould have one orderLine per carton with serial number as SSCC number 3. POI Check field should be "true" 4. Order line quantity should be 1 for all lines and lot number should be PO number |  | Needs Info |  | 8/4/25 FTP Server needs to be moved to WF.
Cross Dock | PacSun - Receiving |  | Scan Container and PO on receiving screen |  | 1. LPN should be the PO number (Is the container number=PO?) 2. If there are additional items to be received it will take you to the PO Details screen to show the outstanding items and qty on the Purchase Order. If the entire PO has been received, the receiving process will complete and provide a message indicating the PO is received. |  | Pass | 2025-08-05 | We always have the container and we always have the PO#. The customer sends us this info to POLA DL. We're having challenges creating purchase orders. Why can't we search by supplier or bill to? Container is mandatory. At what point do we get that info put in to Deposco?
Cross Dock | PacSun - Receiving |  | Receive all cartons onto LPN |  | 1. Should be prompted to enter in then inventory tracking information (For Pacsun, Serial number). 2. Serial number should be UCC (Carton identifier) number on carton. |  | Pass | 2025-08-05 | All PO are in received state. Need to unreceive PO, move container from cross-dock-receiving to default unreceiving location (receiving). Error "Item [38001] has no stock with attributes at default unreceiving location [receiving]."
Cross Dock | PacSun - Receiving |  | Fully receive LPN |  | 1. PO status should be "Received" 2. Stock units should be created for each carton with SSCC/UCC number as serial number and PO number as lot number 3. Stock units should all be associated with one LPN that is named for the PO they are on |  | Pass | 2025-08-05 | 744982 - "Please run Post Order Import Logic Before Receiving." What does this mean?
Cross Dock | PacSun - Receiving |  | Partially Receive PO |  | 1. PO should be in "Partial Receipt" Status 2. The order lines that were received should be in "received" status 3. Should be able to identify which boxes were not received |  | Pass | 2025-08-05 | 744982 - Based on TY of units ordered, we can identify which item # (not boxes) has status of new vs received.
Cross Dock | PacSun - Receiving |  | Auto Receive Entire PO - Used for "Blue Tape" POs and PO's where cartons barcodes are not provided |  |  |  | Needs Info | 2025-08-06 | We discovered a portion of the POs are not scanned. WFL will speak to Pacsun. Options #1 Input "fake" UCC per carton. #2 Assign POs different item not serialized (allows for inpout of # of cartons received; would require way to identify the POs upfront). #3 create an autoreceive button for PO (would require Ops update order QTY prior to auto receiving. Receives full PO QTY without actual receiving process.) #2 is best. | On-site Notes - Identify PO's which are not scanned - WHLS/Chino Orders Assign Different Item which is not UCC Scanned to PO so that UCC Scans not required for PO
Cross Dock | PacSun - Receiving |  | Review Report Builder |  | PO should show up on "PacSun ATP POs" report - Report should include PO's which have been received or Partially Received and have not been assigned to a Sales Order |  | Pass | 2025-08-05 | Which POs do we expect to show up on "PacSun Available POs" report? All Partial Received? All Received? Other category? |  | Under Report Builder -> Look for Report callled Pacsun available PO's
Cross Dock | PacSun - Outbound Order Management |  | Create Customer Order | 1. Go to Data Exchange -> PAC Customer Order Upload 2. Download Template File by clicking three dots next to PAC Customer Order Upload 3. Fill out Template file with Order Information 4. External Order Number should be filled out as Date + Container Number 5. Upload File by by clicking three dots next to PAC Customer Order Upload -> Run -> Select File | 1. Each PO should have one order line with quantity of cartons on PO 2. Customer Order should go into released status with a fulfillment order in "New" status |  | Pass | 2025-08-04 | What is the purpose of the cross dock button? It seems redundant to the root menu buttons.
Cross Dock | PacSun - Outbound Order Management |  | Create Customer Order - Customer Order Line is created and Stock is not found with matching Lot Number | 1. Customer order is created 2. Customer Order Put into On Hold Status 3. CoNotice Error displays message for Mismatching Lot Number | 1. Customer order is created 2. Customer Order Put into On Hold Status 3. CoNotice Error displays message for Mismatching Lot Number |  | Needs Info | 2025-08-06 | 9876-Error when trying to create new order line. "Item and pack doesnt match." Both = 38001. 8/7 Zach-Deposco to add order ON HOLD and incorporate error message for order to make sure the provided number matches the PO.
Cross Dock | PacSun - Outbound Order Management |  | Sales Order is Created |  | 1. Sales order is created with "SO" followed by numbers 2. POI Check field should be "True" 3. Waving Type field should be "CrossDock" 4. The stock units should have the sales order number on the allocated order field |  | Pass | 2025-08-04 | What is the difference between a sales order and a PO? PO is incoming. Sales order is outgoing. POI=Post Order Input. #1, 2pass. Revisit tmrw. Need to add test case for SO ON HOLD.
Cross Dock | PacSun - Outbound Order Management |  | Create Associated Trip |  | 1. Associated trip will show up on "Associated Trip" field 2. New trip should appear under trip entity 3. shipments are associated with the trip -> one for each LPN and they should be in "Shipping" status 4. Change trip to "Open" status |  | Pass | 2025-08-07 | No Outbound button under Cross Dock. Cross Dock > Assign Trip? How would we know what to use for Source Location? Will this be a scan into barcode? We need to ask Ops if test case is applicable. Manuela + Karly.
Cross Dock | PacSun - Outbound Order Management |  | Update Trip Information |  | 1. Update trip fields (pro number, BOL number, Seal number, etc) 2. Assign dock door for the trip |  | Pass | 2025-08-07 | Where do we test this in UI? Menu only has Assign Trip and Close Trip. We need to ask Ops if trip is applicable. Manuela + karly.
Cross Dock | PacSun - Picking |  | Wave the Order | 1. Go to Distribution -> Order Processing - > Orders 2. Select the Check box by the order(s) that want to be waved 3. Select Actions - > Process Orders 4. This will began the process of waving and releasing the Order and it should be placed on to a Wave | 1. Wave should be created with "CrossDock" as the start 2. Pick wave should have one work group and one pick task per carton 3. The pick tasks should be associated with the stock received on the PO desired |  | Pass | 2025-08-05 | "No pick waves are available for picking."
Cross Dock | PacSun - Picking |  | Picking the Order | 1. Go to Handheld menu (Or open from a handheld Scanner device) 2. Go to Pacsun -> Picking 3. Find and select the wave/order you are looking to pick and click submit 4. This will open up the Picking Screen where you will be shown the physical Warehouse Locations to pick the needed inventory for the order 5. Operator will be prompted to scan/input the LPN that is being picked (In pacsun's case, the LPN to be picked will be the PO Number) 5. Physically, at this time the operator should pick the LPN (In pacsun's case, the operator should pick all cartons for the PO) 6. Repeat Steps 4-5 until the entire order is picked (In Pacsun's case, the operator should be led to perform a pick for each PO that is on the Sales Order) 7. Once entire Order is picked, operator will be shown a successful message saying that the picked LPNs have been staged to CrossDockStaging | 1. Wave should appear on wave selection list 2. User will be prompted for location and pallet (the pallet should be the PO number) 3. User should only have to scan the pallet once to pick all the stock units on that pallet 4. After picking all the pallets, user should receive message that the order is staged to "crossDockStaging" |  | Pass | 2025-08-04 | "No pick waves are available for picking." #1,2,3,4 passed.
Cross Dock | PacSun - Assign Trips |  | Open trip for order |  | 1. User should be see the trip for this order after selecting the door 2. User should be able to add pallets and weight to trip 3. Trip details should be auto-populated with the information entered in 4. If no information auto-populated, user should be able to enter in that information |  | Pass | 2025-08-05 | Could we have a drop down menu here with Options? or is it intended to be a scan location? What do we mean by pallet? What is the identifier? The table presented needs headers, please.
Cross Dock | PacSun - Assign Trips |  | Close trip (From Handheld or UI) |  | 1. Trip status should change to closed 2. Shipments associated with the trip should be in "Shipped" status 3. Order should be in "Ship Complete" status |  | Pass | 2025-08-05
Cross Dock | PacSun - Assign Trips |  | Print PacSun BOL |  | 1. BOL should print on printer that is associated with the printer resource of the user 2. BOL should have trip information and all cartons that were sent |  | Needs Info | 2025-08-06 | We need to determine which printers at POLA will be used for PO and manifest printing. Need to download a print server onto one of our machines. Shaun-We can spin up a print server. 8/7 Print server is now set up. 'Deposco Test Print' was successful out of the black multifunction printer across conf room.

## Test Cases - End to End - PacSu
WFL End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 0%
Category | Scenario | Status | Team | Owner | Expected Result | Test Data | Notes
Inbound
Inbound | Receiving: Receive Break Bulk PO full | Ready to Test | WFL |  | 1. PO should change to "Received" 2.receipt lines should be created successfully
| Receiving: Confirm that information is transfered to stock unit correctly | Ready to Test | WFL |  | Stock unit should have weight, inbound container/PO number, serial number or lot number if applicable
Inbound | Receiving: Receive Partial PO | Ready to Test | WFL |  | 1. PO Status should change to "Partial Receipt" 2. receipt lines should be created for received items, 3. orderLines should have number in "Received Pack Quantity" field
Inbound | Receivng: Define Floor Loaded vs Pallet Loaded Container within Receiving Process | Ready to Test | WFL |  | The order field for "Unload Type" should be updated with the selection chosen during receiving process
| Copper Receiving: Receive a Copper PO with multiple items/Brands | Ready to Test | WFL |  | 1. PO should be created with number given at receiving, 2. orderLines should be created for each item, 3. status should be "received", 4. receipt lines should be created
| Copper Receiving: Confirm inventory tracking is transfered to stock unit | Ready to Test | WFL |  | Stock unit should have weight, inbound container/PO number, serial number or lot number if applicable
| Copper Receiving: Confirm unload type is transfered to order properly | Ready to Test | WFL |  | The order field for "Unload Type" should be updated with the selection chosen during receiving process
Inbound | Unreceive full PO | Ready to Test | WFL |  | 1. Stock Unit(s) is removed from environment 2. PO Should go back to "New" Status 3. Receipt Lines are created with negative quantity 4. OrderLine received quantity is reset to 0
Inbound | Unrecieve partial PO | Ready to Test | WFL |  | 1. Stock Unit(s) is removed from environment 2. PO Should go back to "Partial Receipt" Status 3. Receipt Lines are created with negative quantity 4. OrderLine received quantity is set to correct new quantity
Inbound | Blind receive additional units found after receiving | Ready to Test | WFL |  | Create new order and orderlines for newly found inventory
Inbound | Over receive PO | Ready to Test | WFL |  | 1. Stock Units are created for correct quantity 2. Order Status is changed to "Received" 3. Orderline "Received Pack Quantity" should have larger quantity than "Order Pack Quantity" field
Inbound | Putaway single item containers | Ready to Test | WFL |  | 1. Putaway process should direct you to like item locations or empty locations 2. verify container and items are moved to proper location
Inbound | Putaway containers to reserve locations | Ready to Test | WFL |  | 1. Putaway process should direct you to like item locations or empty locations 2. verify container and items are moved to proper location
Inbound | Putaway containers to pickable locations | Ready to Test | WFL |  | 1. Putaway process should direct you to like item locations or empty locations 2. verify container and items are moved to proper location
Outbound
Outbound | Fulfill Break Bulk order where Container Number is defined for Allocation | Ready to Test | XXX
Outbound | Fulfill single unit orders | Ready to Test | XXX
Outbound | Fulfill multi unit orders | Ready to Test | XXX
Outbound | Fulfill international orders | Ready to Test | XXX
Outbound | Fulfill domestic orders | Ready to Test | XXX
Outbound | Exception a pick task for "large" order | Ready to Test | XXX
Outbound | Exception a pick task for a single unit order | Ready to Test | XXX
Outbound | Exception a pick task for a multi unit order | Ready to Test | XXX
Outbound | Cancel an order that has not yet been released | Ready to Test | XXX
Outbound | Cancel an order that has been released but not picked | Ready to Test | XXX
Outbound | Cancel an order that has been picked but not packed or shipped | Ready to Test | XXX
Outbound | Cancel an order that has been packed but not shipped | Ready to Test | XXX
Outbound | Roll back an order that has been shipped and cancel it | Ready to Test | XXX
Outbound | Roll back an order that has not been shipped and re-ship | Ready to Test | XXX
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Ready to Test | XXX
Inventory Management | Perform scheduled cycle counts by item | Ready to Test | XXX
Inventory Management | Perform on demand cycle counts by location | Ready to Test | XXX
Inventory Management | Perform scheduled replenishment tasks | Ready to Test | XXX
Inventory Management | Perform on demand replenishment tasks | Ready to Test | XXX
Inventory Management | Over-replenish | Ready to Test | XXX
Inventory Management | Perform exception during replenishment | Ready to Test | XXX

## Billing
Transload Service | RATE | DESCRIPTION | Bill Method | Open Questions | Deposco Comments |  |  | Deposco Owner | Status
20' Container Handlin in and Handlin out | 400 | Pallets to Pallets | Scheduled | 1. Are Pallets billed for during inbound or Outbound? 2. Is the rate per receiving the entire container or per pallet? | 1. CSR Responsible for creating PO with accurate container size/type 2. Operator will be prompted to input whether Container is floor vs Pallet Loaded | Reference fields on purchase order for container size and container number, group by container number on purchase orders Project level billing not in scope | Billed on Inbound. Rate per Container | Lanie | Ready for WFL Testing | - Configured per inbound container when the status is received and the container size is 20' standard and pallet loaded and lastest receiptLine date is in billing period - Currently configured to group by orderHeader.otherReferenceNumber if not null or orderHeader.number if other reference number is null. hoping this accounts for containers with more than one PO being sent on it as they bill by container, not individual PO
20' Container Handlin in and Handlin out | 450 | Floor loaded in/out | Scheduled | 1. Are Pallets billed for during inbound or Outbound? 2. Is the rate per receiving the entire container or per carton? | 1. CSR Responsible for creating PO with accurate container size/type 2. Operator will be prompted to input whether Container is floor vs Pallet Loaded | Reference fields on purchase order for container size and container number, group by container number on purchase orders |  | Lanie | Validation | - Configured per inbound container when the status is received and the container size is 20' standard and floor loaded and lastest receiptLine date is in billing period - Currently configured to group by orderHeader.otherReferenceNumber if not null or orderHeader.number if other reference number is null. hoping this accounts for containers with more than one PO being sent on it as they bill by container, not individual PO
40'/40HC/45' Container Handlin in and Handlin out | 475 | Pallets to Pallets | Scheduled | 1. Are Pallets billed for during inbound or Outbound? 2. Is the rate per receiving the entire container or per pallet? | 1. CSR Responsible for creating PO with accurate container size/type 2. Operator will be prompted to input whether Container is floor vs Pallet Loaded | Reference fields on purchase order for container size and container number, group by container number on purchase orders |  | Lanie | In Progress | NEED TO SEPARATE - Configured per inbound container when the status is received and the container size is 40' standard, 45' standard or 40' HC and pallet loaded and lastest receiptLine date is in billing period - Currently configured to group by orderHeader.otherReferenceNumber if not null or orderHeader.number if other reference number is null. hoping this accounts for containers with more than one PO being sent on it as they bill by container, not individual PO
40'/40HC/45' Container Handlin in and Handlin out | 595 | Floor loaded in/out | Scheduled | 1. Are Pallets billed for during inbound or Outbound? 2. Is the rate per receiving the entire container or per carton? | 1. CSR Responsible for creating PO with accurate container size/type 2. Operator will be prompted to input whether Container is floor vs Pallet Loaded | Reference fields on purchase order for container size and container number, group by container number on purchase orders |  | Lanie | In progress | NEED TO SEPARATE - Configured per inbound container when the status is received and the container size is 40' standard, 45' standard or 40' HC and floor loaded and lastest receiptLine date is in billing period - Currently configured to group by orderHeader.otherReferenceNumber if not null or orderHeader.number if other reference number is null. hoping this accounts for containers with more than one PO being sent on it as they bill by container, not individual PO
Overweight transload rate | 450 |  | Scheduled | 1. What exactly is this charge? 2. When is this billed or based off of? |  | When it is loaded - Depends on 20 ft vs 40 ft - Client will indicate that it is overweight when container is inbounded. Billed in addition to above standa container receiving fees |  | lanie | validation | configured per trip when the trip is closed and load type is "Overweight" and shipment lines were created during the billing period (shipment lines are not created until trip is closed)
Gate Transaction | 25 | Per Transaction | TBD | 1. What exactly is this charge? 2. When is this billed or based off of? 3. Is a gate transaction fee charged each time the truck passes the gate or just once per truck? |  | Applied only for outside carriers. Per time passing the gate - So would essentially be billed twice for every truck. CSR would know whether carrier is outside carrier or not. Need to imput on trip creation |  |  |  | Need to determine what shipping carriers are used and how to determine if gate charges are needed
Pallet Storage | 3 | Per pallet per day ( cannot stack over 12ft) | Scheduled | 1. Is this billed daily or only after the pallet has been shipped? | Billed per day | Only charged when pallet shipped. |  | lanie | validation | configured per pick detail hist (assumption is one pallet per pick detail therefore one pallet per pick detail hist) by taking the PO number stored on inventoryAttribute1 and finding the date the receipt line was created for that PO line number assoicated with the same item on the pick detail hist, days is calculated by subtracting the difference between pickDetailHist.createdDate and receiptLine.receiptDateTime
Dedicated long term storage | 1.85 | Per sqft | Scheduled | 1. Is this billed daily or only after the pallet has been shipped? 2. Is this billed in addition to the Pallet Storage Fee? Or is one or the other billed? 3. Is the Sq Ft rate per day? | 1. Need to determine how sq ft is calculated 2. Are Item Dimensions/sq ft captured on inbound? | What is considered long term? - Depending on contract of client - Different day threshold per client. Inventory only begans to incur Long term storage Fee once it is past the day threshold. Typicaly for steel clients - Billed metric ton - Not sq ft - Weight need to be captured on inbound |  | lanie | validation | Configured two separate configs for sqft and weight - Each is configured by summing the total sqft or weight of current stock units that meet the date threshold field on the company entity and multiplying by rate - Note: the total sqft is taken by counting number of stock that qualifies and multilplying by standard sqft of pallet (13.333), can use pack dimensions in future state if those are updated
Bundle Over Size Outdoor Storage | 27.5 | Per Bundle per day | Scheduled | 1. Is this billed daily or only after the pallet has been shipped? 2. Is this billed in addition to the Pallet Storage Fee? |  | Clients receive free days similar to above Long Term Storage. Either this is billed or Long Term Storage Not both. Dependent on Location. Need to create an outdoor storage fee that Calculates by Bundle and one that calculates by metric ton. |  | lanie | validation | Will most likely have a yard storage location and will bill for stock in the location
Split Palletized freight | 125 | split palletized freight (2-3 splits) | adhoc | 1. What does it mean by Split Palletized Freight? 2. What is the "trigger" for splitting freight? |  | Container comes in with certain number of Pallets - If different number of pallets is shipped than number of pallets received. Number of Splits is calculated based on Inbound Container divided by number of shipments for that container - Would be on fee of 125$ (or whatever client rate is) Some clients are billed one time split fee, other accounts are billed for each split. |  | lanie | validation
Hazmat | 75 | per HAZ Container | Scheduled | 1. Is this billed upon inbound or outbound? 2. Is the rate per receiving the entire container or per pallet? |  | Client knows if container is hazmat - lets CSR know if it is Hazmat container Outbound container - Billed upon outbound |  | lanie | validation | configured to charge for each trip that is closed and contains a item is considered hazmat on an associated shipment line during the billing period
Pallets | cost+15% | Pallets (Grade A Pallets $10.25 +15%, Grade B pallets $9.75+ 15%) | adhoc |  | 1. Deposco cannot determine the pallet grade within the system |  |  | lanie | validation | Need to enable business unit selection screen
Shrink Wrap/ Slip Sheets | 2.75 | per pallet ( Steel/ Vinyl bands) | adhoc | 1. Is this billed upon inbound or outbound? 2. Is every pallet wrapped or is this in certain cases? Certain BU's? |  | Outbound fee If needs to be shrink wrapped upon shipping Per pallet determination - Adhoc charge |  | lanie | validation | Need to enable business unit selection screen
Dunnage/ Wood/ Straps/ Air Bags | 125 | per Container/ Trailer/ Flat Bed | adhoc | 1. Is this billed upon inbound or outbound? 2. Is every pallet require dunnage/Wood/Airbags or is this in certain cases? Certain BU's? |  | Outbound Fee Per container basis - Decision made by Customer/Operations Team Likely adhoc |  | lanie | validation | Need to enable business unit selection screen
Labels | 0.55 | for label and apply | adhoc | 1. Is this billed upon inbound or outbound? 2. Does every pallet require labels or is this in certain cases? Certain BU's? 3. Is there a certain trigger to the label printing? |  | Per Label Outbound Fee Requested by Client Client may request to put container number/item number/etc onto pallet |  | lanie | validation | Adhoc for labels applied
BOL Charge | 8.2 | per outbound | Scheduled | 1. Is it 1 BOL per truck? 2. Is the client charged if they provide their own BOL? |  | 1 BOL Per Truck Not charged if client provides BOL. Decision made by CSR - Can input on trip whether BOL provided by WFL or by client |  | lanie | validation | configured to charge if trip.accountNumber is "WFL Provided BOL" and the trip is closed
LTL Delivery | 1.75 | per carton | Scheduled |  |  | Minimum is $75 per delivery
Freight Sortation | 0.5 | per CBM | adhoc
Supplies | Cost + 15% | per container/ Trailer/ Flat Bed |  | 1. How is the cost determined?
Bonded Moves | 100 | per filling |  | 1. When is this billed?
Excess Carton Fee | 0.15 | per carton |  |  |  | billed for containers will more than 1200 cartons
Container Storage | 45 | per day |  |  |  | have threshold for free days similar to pallet storage
Trio Global
Transload Service | RATE |  | Bill Method | Open Questions | Deposco Comments
Transload Service | 400 | If K&P Trucking was carrier (theirs) we do not bill drayage only Transload. | TBD | 1. How do we know if an order is transload? All Orders for this BU? 2. Is this billed upon inbound or outbound? |  | K&P is Trio's carrier - Drayage portion would not be charged if K&P is the carrier This is the rate for shipping an order - Will apply to any order shipped unless otherwise specified by Sales Rep for clietn
Storage |  |  |  | 1. Is storage billed for this customer? If so, how? |  | Trio does not typically incur storage If storage is billed it will be based upon previosuly defined storage rates above
Daryage Service to POLA | RATE | DESCRIPTION
Voss
Service | RATE | DESCRIPTION | Bill Method | Open Questions | Deposco Comments
Handling In/Out |  | Per Pallet Shipped (Outbound) | Scheduled |  |  | Rate per Pallet Shipped
Pallet Storage |  | Per Pallet Per Month | Scheduled | 1. Is this only for pallets within the building on the 15th? 2. What if a Pallet was received on 1st and shipped on the 5th? Would this pallet ever be billed? A pallet would not be billed in this scenario |  | Snapshot of however many Pallets are within the facility on the 15th day of the month.
Unload and Stage in WH by PO (Drayage) |  | Per 40 ft Standard Container | Scheduled |  |  | Does not apply
Unload and Stage in WH by PO (Drayage) |  | Per 40 ft HC Container | Scheduled |  |  | Does not apply
Unload and Stage in WH by PO (Drayage) |  | Per 45 ft Standard Container | Scheduled |  |  | Does not apply
Clerical/Data Entry/Admin |  | Per Hour | Adhoc
Palletize Shrink Wrap | 16 | Per Pallet (Cost + 15%) | Adhoc
Shuttle Service |  | Per Round trip to Montebello | TBD | 1. Not sure what this means? Is this tracked in system? |  | Does not apply
Bob Tail |  |  | TBD | 1. Is this determined when CSR Routes the order with Freight company? Can this be inputted by CSR upon routing? |  | Does not apply
Supplies | at cost + 10% | Dunnage Bags, Pallets, Hard Seals | Adhoc
BOL |  |  | TBD | 1. Is it 1 BOL per truck? 2. Is the client charged if they provide their own BOL? |  | 1 BOL Per Truck Not charged if client provides BOL. Decision made by CSR - Can input on trip whether BOL provided by WFL or by client
Tri Axle Chasis |  | On Containers over 44,500 Lbs | TBD | 1. Is this determined when CSR Routes the order with Freight company? Can this be inputted by CSR upon routing? |  | Outbound CSR would know upon routing of truck - CSR can input on Trip - When container is overweight
Chassis |  |  | TBD | 1. Is this determined when CSR Routes the order with Freight company? Can this be inputted by CSR upon routing? |  | Outbound CSR would know upon routing of truck - "Normal" container shipping fee. Either one or the other is applied for a truck
Inbound Handling
Container Unloading thru Put-away | 5.25 | Per Pallet Received | Scheduled |  |  | Inbound Based on how many pallets are received
Drayage
Cutomer Name | Drage Fee | Chassis |  | Carrier Fee | Drayage | Chassis/per day |  |  | Bill Method | Open Questions | Deposco Comments
AMCARCA | 375 | 40 |  |  | 375 | 40 |  |  | TBD | 1. Need to dive into deeper into Logic Around Drayage and how this is tracked. 2. Need to determine if possible to bill in Deposco or adhoc |  | Inbound Fee Customer will assign Container to WFL Fee for inbounding container from Port Chasis Fee is per day Game Change has different Chassis Fee - Not billed per day Game Change Chassis Fee is one time Fee
CAMPBELL | 375 | 100 |  |  | 325 | 100
CAMPBELL- TRANFER |  |  |  |  | 500
CEC | N/A | NA |  |  |  |  | We did not bill customer
CH ROBINSON | 750
ENCOMPASS
GOLDENBRIDGE_EXPORT
GOLDENBRIDGE_IMPORTS
GAMECHANGE |  |  |  |  | 375 | 50
HARTREE PARTNERS
KUEHNE_NAGEL
KN_AOB
KN_BLACK_DECKER
KN_SAFRAN
KN_SKM
MC_TANK
MEDLOG
METOX - FLATRACK |  |  |  |  | 350
METOX - CONTAINER |  |  |  |  | 475 | 75
MSC
NZS_WORLDWIDE
RDONE
POLA_WAREHOUSE
RISE
RMC
ROME
ROYALENFIELD
SAIN
SCM
SILICA
TILEBAR
USA_LOGISTICS
VOSS_TRANSFER
Pacsun
Transload
Service | RATE | DESCRIPTION | Bill Method | Open Questions | Deposco Comments
Container Size - 20' |  |  |  |  | Handled in Previous Billing
Container Size - 40' |  |  |  |  | Handled in Previous Billing
Container Size - 40'HC |  |  |  |  | Handled in Previous Billing
Container Size - 45' |  |  |  |  | Handled in Previous Billing
CBM Sort Fee | 0.5 | $.50 per CBM * (From Rate Sheet) - If Freight Sortation/Segregation is required add $.50 per CBM per Sort Does every inound require sortation/Segregation? If not, how is this determined? |  | If Freiight
LTL
LTL Delivery - Per Carton
Minimum Delivery
Storage
Yard Storage - Per Pallet Per Day | 1.25 | Per Pallet Per Day Yard Storage - 1st Day Free
Container Storage | 45 | $45 Per Day
Other Fees
Supplies
BOLs | 6.5 | Per BOL
Bonded Moves - In Transit or Permit to Transfer | 100 | Per Filing |  | What is this Fee? How is it determined if it is a Bonded Move? What Indeicates a Filing?
Shrink Wrap Fee | 4 | Per Pallet
Excess Carton Fee | 0.15 | Per Carton Over 1,200 Cartons on Container Invoiced on all Cartons
VAS
Order Processing Fee | 2 | Per Order |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders?
Small Parcel Processing | 0.75 | Per Carton |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders? How do we determine if it is a small parcel order?
De-Seeding of Inner Cartons, Units, or Polybags |  | Per Touch |  | Is this charged to client?
Bonded WH Fee (In/Out) |  | Per FEU |  | What is this Fee? How is it determined if it is a Bonded Move? What is an FEU?
Bonded Storage |  | Per Pallet Per Week |  | What is this Fee? How is it determined if it is a Bonded Move? What is an FEU?
Sort and Segregation (Transload) |  | Per CBM |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders?
Sort and Segregation per unique inbound sort |  | Per Sort |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders? What is considered a Sort?
Facility Weekend/Holiday Opening and Closing Fee |  | Per Day
Yard Management Non-Taylored Container delivery |  | Per Container |  | Applies to all Containers? Or only specific Containers? Outbound or Inbound Containers? Is Taylor the carrier?
Gift Wrap (White Glove Service) |  | Per Carton |  | Applies to all Containers/Orders? Or only specific Containers/Orders? Outbound or Inbound? What is criteria for Gift Wrap?
Price Hang Tags/Tickets |  | Per Unit |  | Applies to all Containers/Orders? Or only specific Containers/Orders? Outbound or Inbound? What is criteria for this?
Price Hang Tags/Tickets - Inside Placement |  | Per Unit |  | Applies to all Containers/Orders? Or only specific Containers/Orders? Outbound or Inbound? What is criteria for this?
Hangers |  | Per Unit
Polybags |  | Per Bag
Plastic Straps |  | Per Carton
Wire Straps |  | Per Carton
Plastic Wrap |  | Per Carton
Ticketing - No Size/Color
Ticketing - By Size/Color
Ticketing Polybags - No Size/Color
Ticketing Polybags - By Size/Color
Hang Tag
Expedited orders - Same Day | 75 | Per Order |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders? What determines Expedited?
Carrier No Show | 200 | Per No Show? |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders? What determines No Show? How is this determined?
Containers/Trailers Left on Propert after 3 Days | 45 | Per Day |  | Per Day after 3 Days
Minimum Charge Per Project | 150 | Per Order |  | Applies to all Orders? Or only specific Orders? Outbound or Inbound Orders? What is criteria for this?

## GoNo-Go Decision - PacSun
WFL Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 3100
Deposco Setup | Label Printers | 10 |  | WFL | 100 | 1000 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 |  | WFL | 100 | 1000 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 |  | WFL | 10 | 100 | Are all scanners procured? Deposco app installed? Auto-send features enabled? Zebra TC58 auto enter instructions needed | Recommend 50%+ by UAT Recommend 100% by Go Live |  | Lanie to find handheld scanner instructions
Deposco Setup | End users | 10 | Y | WFL | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | Lanie to follow up on SSO login WFL to follow up on need for associate users
Deposco Setup | Printer Details | 10 |  | WFL | 100 | 1000 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | #REF! | WFL | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | WFL | 0% | 0 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 0% | 0 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 0% | 0 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 30 |  |  |  | 1000
Warehouse Prep | Location Labels | 10 | Y | XXX | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Container Labels | 10 | Y | XXX | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 |  | XXX | 100 | 1000 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 30 |  |  |  | 0
SOP Documents | Receiving | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cross Dock Picking | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Trip Loading and Shipping | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | CSR Roles and Responsibilities | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Billing Setup and Responsibilties | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Entry and Waving | 5 |  | WFL | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 60 |  |  |  | 1520
Training & Testing | Test Case Scenarios Definition | 10 |  | DEP / WFL | 76 | 760 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and XXX to add/remove test cases as needed for their business.
Training & Testing | Billing Testing and Completion | 10 | Y | DEP / WFL | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature
Training & Testing | Unit Test Case Completion - Inbound - Outbound Order Management - Picking - Trip loading and shipping - FTP server upload | 10 |  | WFL | 76 | 760 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Outbound Order Management - Picking - Trip loading and shipping - FTP server upload All test cases performed with full integration involvement as will be in production. | 10 | Y | WFL | 0% | 0 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | WFL | 0% | 0 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | WFL | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 50 |  |  |  | 750
Master Data | Cutover Inventory Validation | 10 | Y | WFL | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 | Y | WFL | 0% | 0 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Lanie to send item upload templates
Master Data | Locations and Zones | 10 |  | WFL | 75 | 750 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | WFL | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Menu Structures | 10 | Y | WFL | 0% | 0 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / WFL | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 0
Interfaces - Imports to Deposco | Carton Types Upload | 10 | Y | WFL | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 | Y | WFL | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 | Y | WFL | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | WFL | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 | Y | WFL | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
| Reports and Labeling | 40 |  |  |  | 0
Reports and Labeling | Location Label | 10 | Y | WFL | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Bill of Lading | 10 | Y | WFL | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | LPN Label | 10 | Y | WFL | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Receiving Worksheet | 10 | Y | WFL | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 0
Contingency Plans | Contingency Plans | 10 | Y | DEP / WFL | 0% | 0 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 6370
| Total Possible Score: | 365
| Total Percentage: | 1745%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## GoNo-Go Decision - Break Bulk
WFL Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 0
Deposco Setup | Label Printers | 10 | Y | WFL | 0% | 0 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 | Y | WFL | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | WFL | 0% | 0 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 | Y | WFL | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | WFL | 0% | 0 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | WFL | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | WFL | 0% | 0 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 0% | 0 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 0% | 0 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 30 |  |  |  | 0
Warehouse Prep | Location Labels | 10 | Y | XXX | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Container Labels | 10 | Y | XXX | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 | Y | XXX | 0% | 0 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 40 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Break Bulk Picking | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cross Dock Flow | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Trip Loading and Shipping | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | CSR Roles and Responsibilities | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Billing Setup and Responsibilties | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Entry and Waving | 5 |  | XXX | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 60 |  |  |  | 0
Training & Testing | Test Case Scenarios Definition | 10 | Y | DEP / XXX | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and XXX to add/remove test cases as needed for their business.
Training & Testing | Billing Testing and Completion | 10 | Y | DEP / XXX | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | XXX | 0% | 0 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | XXX | 0% | 0 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | XXX | 0% | 0 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | XXX | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 60 |  |  |  | 0
Master Data | Cutover Inventory Validation | 10 | Y | XXX | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Kit/Component Relationships | 10 | Y | XXX | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | XXX | 0% | 0 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / XXX | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 55 |  |  |  | 0
Interfaces - Imports to Deposco | Carton Types Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Trading Partner Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 | Y | XXX | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 0 |  |  |  | 0
Integrations with Deposco | Netsuite - Item - Pull | 0 |  | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Trading Partner - Pull | 0 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Sales Order - Pull | 0 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order - Pull | 0 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Customer Return - Pull | 0 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Ship Notice - Push | 0 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order Receipt - Push | 0 | Y | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 0 |  | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 0 |  | XXX | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 0 |  | XXX | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Rate Shop Request | 0 |  | XXX | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 40 |  |  |  | 0
Reports and Labeling | Location Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Bill of Lading | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | LPN Label | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Receiving Worksheet | 10 | Y | XXX | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 0
Contingency Plans | Contingency Plans | 10 | Y | DEP / XXX | 0% | 0 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 0
| Total Possible Score: | 395
| Total Percentage: | 0%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan (hidden)
WFL Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE
3 | Set up Shopify | Set up Shopify Instances in Production environment | FALSE
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE
5 | Test Order Pull | Create a test order in Shopify and bring order into Deposco | FALSE
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify | FALSE
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify | FALSE
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE
10 | Master Data Check - Items | Look through items in production environment | FALSE
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE
18 | Inventory Push to Shopify | Inventory is pushed to shopify | FALSE
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Shopify Instances to bring in orders | FALSE
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE

## Future ItemsParking Lot (hidden)
WFL Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | WFL Comments