## Schedule
BBB Project Tracker - Key Dates and Documents
Demos/Training Schedule
Demo Topic | Description | Demo/Training Date | Goal Action Item Completion Date | Training Recording Link | Password
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions
Data Exchange Introduction | Data Exchange/Field Mapping/Transmission training + troubleshooting
Inbound/Putaway | General Receiving(PO, Blind Receipt, Customer Returns, Create RMA), Move Item, Move Stock, Move Container |  |  |  | Passcode: 4^0xZ3R*
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Product Conversion |  |  |  | Passcode: E+gcu2v*
Outbound I | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking
Outbound II | Packing and Shipping (Singles,Multis,Bulk) Repalletize, Assign trip ,Rollback After Picking, Void and Reprocess Shipment
Reporting | Report Builder, Dashboard Widgets
Billing | 3PL Billing and Invoice
Integrations | Imtegrations
Other Key Activities
Task/Activity | Description | Status | Start Date | Completion Date
Unit Testing | Testing specific processes in the Test Script | Open
End to End Testing | Testing all processes with live data end to end | Open
Pre-Cutover Activities | Completion of all Pre-Cutover Steps | Open
UAT - User Acceptance Training | Training of all superusers and end users - Dep onsite support 3 days | Open
Go/No-Go Decision Tracker | Complete evaluation of Go/No-Go Decision Plan | Open
Cutover | Operational Go-Live - Dep onsite support full week | Open
Important Document Links
Document Name | Description | Link
SOP Document | Owned by BBB team to document standard operating proceedures for all major Deposco functions. To be printed and stationed at various places thorughout the warehouse during Go-Live and for onboarding new associates.
Master Design Document | In-depth outline of solution design agreed upon by BBB and Deposco during the Design phase of the implementation
Capability Map | Document outlining configuration decisions made by BBB and Deposco during the Design Phase

## Parking Lot (hidden)
Process | Item | Covered
FALSE
FALSE
FALSE
FALSE
FALSE

## Task Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Due Date | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | BBB Comments | ETA | LINK TASK
Kits | Multi Box Items |  | NTH |  | FALSE | FALSE
Return | "unlink" return orders from Shopify |  | NTH |  | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## DeposcoUnit Test Cases
Test Number | Scenario | Assignee | Status | Test Data | Date Complete | BBB Comments | Deposco Comments | In SOP Document?
General Receiving
| Receive full PO | DEP Team
| Receive PO with Putaway = "No" | DEP Team
| Receive PO with Putaway = "Yes" - Putaway to suggested location | DEP Team
| Receive PO with Putaway = "Yes" - Putaway to non-suggested location | DEP Team
| Receive partial PO and leave open - receive more product later | DEP Team
| Receive Blind Order | DEP Team
| Capture Exp Date | DEP Team
| Capture Lot Number | DEP Team
| Capture Country of Origin | DEP Team
| Receive an received email confirmation | DEP Team
| Receive an order into an LPN (Pallet) | DEP Team
| Receive a Customer Return/ Blind RMA (Returns Button) | DEP Team
| Create RMA | DEP Team
| Receive product to a container (LPN) receive the other items into a different container | DEP Team
Move Item
| Move one item from staging location to picking location | DEP Team
| Move qty > 1 for an item | DEP Team
| Move product from receiving location into Damaged | DEP Team
| Move product from return location to picking location | DEP Team
Move Stock
| Move stock - add multiple units of different products to cart and put away to the same location | DEP Team
| Move stock - add multiple units of different products to cart and put away to two different locations | DEP Team
Move Container
| Move container - use move only stock to move contents of the pallet into to a new location | DEP Team
Cycle Count
| Create Cycle Count task via scheduler - Count by Item | DEP Team
| Create Cycle Count task via scheduler - Count by Location | DEP Team
| Create Cycle Count task via picking exception | DEP Team
| Create Cycle Count task manually via Handheld to be performed later - Count by Item | DEP Team
| Create Cycle Count task manually via Handheld to be performed later - Count by Location | DEP Team
| Create Cycle Count task manually via Handheld and perform immediately (on demand) | DEP Team
| Perform a cycle count and capture same value found in location | DEP Team
| Perform a cycle count and capture value different from quantity found in location (double confirm) | DEP Team
| Perform a cycle count and skip a location that you are prompted to count | DEP Team
| Accept cycle count variances | DEP Team
| Reject cycle count variances | DEP Team
| Trigger a recount of a completed cycle count task via Manage Cycle Count Variances | DEP Team
Adjust Inventory
| Consume all in location | DEP Team
| Consume some quantity of a particular item in a location | DEP Team
| Consume all inventory in a specific container (LPN) | DEP Team
| Create inventory in a specific location | DEP Team
Replenishment
| Create a Replenishment via Scheduler | DEP Team
| Scan the wrong item | DEP Team
| Scan the wrong COO | DEP Team
| Select Cart if full and proceed to put it away | DEP Team
| Select Exception when putting away the stock | DEP Team
| Complete a Replenishment Taks | DEP Team
Repalletize
| Repalletize stock from one picked container to another | BBB Team | Open
|  | BBB Team | Open
Cancel Order/Cancel Order Line
| Cancel entire order | BBB Team | Open
| Cancel entire order line | BBB Team | Open
| Cancel part of one order line | BBB Team | Open
|  | BBB Team | Open
Rollback After Picking
| Perform rollback after picking for an entire order | BBB Team | Open
| Perform rollback after picking for part of an order | BBB Team | Open
| Perform rollback after picking and put stock away to shelf location | BBB Team | Open
| Perform rollback after picking and put stock away to staging location to be moved at a later time | BBB Team | Open
|  | BBB Team | Open
Build and Release Wave
| Build and Release wave manually by selecting orders | DEP Team
| Build and Release wave automatically via scheduler | DEP Team
| Build and Release wave where some orders are completely back ordered due to insufficient stock | DEP Team
| Build and Release Singles Order | DEP Team
| Build and Release Priority Singles Order | DEP Team
| Build and Release Batch Order | DEP Team
| Build and Release Priority Batch Order | DEP Team
| Build and Release Large Singles Order | DEP Team
| Build and Release Exception Re-Pick | DEP Team
Single Scan Picking
| Pick wave of single unit orders onto one cart | BBB Team
| Pick wave of one Wholesale Order onto one pallet | BBB Team
| Stage picking cart when full and continue picking | BBB Team
| Attempt to scan invalid item during picking | BBB Team
| Attempt to scan invalid location during picking | BBB Team
| Attempt to pick quantity larger than allocated | BBB Team
BBB Team
Batch Picking
| Pick wave of multi unit orders into designated bins | BBB Team
| Perform exception during picking when stock not found/damaged | BBB Team
| Use New Bin functionality to pick an order into multiple bins | BBB Team
| Attempt to scan invalid item during picking | BBB Team
| Attempt to scan invalid location during picking | BBB Team
| Attempt to scan invalid container/bin during picking | BBB Team
| Attempt to pick quantity larger than allocated | BBB Team
Bulk Picking
| Bulk Pick orders with same items | BBB Team
BBB Team
BBB Team
Singles Packing
| Pack order from cart picked via Single Scan Picking | BBB Team
| Capture box dimensions during packing for Pack Order by Item | BBB Team
| Print shipping label at the conclusion of packing | BBB Team
| Attempt to pack a multi unit order via Pack Order by Item (should not allow) | BBB Team
| Back out of container during packing and re-scan container to continue | BBB Team
| Scan invalid items during Pack Order by Item | BBB Team
| Pack an item with "Preferred Carton Type" set on pack entity (should autopopulate carton type to use) | BBB Team
| Change carton type from suggested | BBB Team
| Perform Rate shopping | BBB Team
Wholesale Packing
| Pack an order picked into a bin via Wholesale Packing | BBB Team
| Pack a large order picked alone to a cart via Wholesale Packing | BBB Team
| Capture box dimensions during Wholesale Packing | BBB Team
| Use New Bin functionality to create multiple shipping containers for one order | BBB Team
| Print container label(s) at conclusion of packing | BBB Team
| Scan invalid items during Single Scan Packing | BBB Team
BBB Team
Bulk Packing
| Pack an bulk packing order | BBB Team
| Select the dimensions | BBB Team
| Make sure all items are split into different container | BBB Team
| Print shipping label(s) at the end of packing | BBB Team
| Attempt to pack an invalid item | BBB Team
BBB Team
Assign Trip to Container
| Close trip for wholesale order by scanning containers to dock door | BBB Team
Void and Reprocess Shipment
| Void and Reprocess one Shipment | BBB Team

## BBB Unit Test Cases
Test Number | Scenario | Assignee | Status | Test Data | Date Complete | BBB Comments | Deposco Comments | In SOP Document?
General Receiving
| Receive full PO | BBB Team
| Receive PO with Putaway = "No" | BBB Team
| Receive PO with Putaway = "Yes" - Putaway to suggested location | BBB Team
| Receive PO with Putaway = "Yes" - Putaway to non-suggested location | BBB Team
| Receive partial PO and leave open - receive more product later | BBB Team
| Receive Blind Order | BBB Team
| Capture Exp Date | BBB Team
| Capture Lot Number | BBB Team
| Capture Country of Origin | BBB Team
| Receive an received email confirmation | BBB Team
| Receive an order into an LPN (Pallet) | BBB Team
| Receive a Customer Return/ Blind RMA (Returns Button) | BBB Team
| Create RMA | BBB Team
| Receive product to a container (LPN) receive the other items into a different container | BBB Team
Move Item
| Move one item from staging location to picking location | BBB Team
| Move qty > 1 for an item | BBB Team
| Move product from receiving location into Damaged | BBB Team
| Move product from return location to picking location | BBB Team
Move Stock
| Move stock - add multiple units of different products to cart and put away to the same location | BBB Team
| Move stock - add multiple units of different products to cart and put away to two different locations | BBB Team
Move Container
| Move container - use move only stock to move contents of the pallet into to a new location | BBB Team
Cycle Count
| Create Cycle Count task via scheduler - Count by Item | BBB Team
| Create Cycle Count task via scheduler - Count by Location | BBB Team
| Create Cycle Count task via picking exception | BBB Team
| Create Cycle Count task manually via Handheld to be performed later - Count by Item | BBB Team
| Create Cycle Count task manually via Handheld to be performed later - Count by Location | BBB Team
| Create Cycle Count task manually via Handheld and perform immediately (on demand) | BBB Team
| Perform a cycle count and capture same value found in location | BBB Team
| Perform a cycle count and capture value different from quantity found in location (double confirm) | BBB Team
| Perform a cycle count and skip a location that you are prompted to count | BBB Team
| Accept cycle count variances | BBB Team
| Reject cycle count variances | BBB Team
| Trigger a recount of a completed cycle count task via Manage Cycle Count Variances | BBB Team
Adjust Inventory
| Consume all in location | BBB Team | Closed
| Consume some quantity of a particular item in a location | BBB Team | Closed
| Consume all inventory in a specific container (LPN) | BBB Team | Closed
| Create inventory in a specific location | BBB Team | Closed
Replenishment
| Create a Replenishment via Scheduler | DEP Team
| Scan the wrong item | DEP Team
| Scan the wrong COO | DEP Team
| Select Cart if full and proceed to put it away | DEP Team
| Select Exception when putting away the stock | DEP Team
| Complete a Replenishment Taks | DEP Team
Cancel Order/Cancel Order Line
| Cancel entire order | BBB Team
| Cancel entire order line | BBB Team
| Cancel part of one order line | BBB Team
Rollback After Picking
| Perform rollback after picking for an entire order | BBB Team
| Perform rollback after picking for part of an order | BBB Team
| Perform rollback after picking and put stock away to shelf location | BBB Team
| Perform rollback after picking and put stock away to staging location to be moved at a later time | BBB Team
Build and Release Wave
| Build and Release wave manually by selecting orders | BBB Team
| Build and Release wave automatically via scheduler | BBB Team
| Build and Release wave where some orders are completely back ordered due to insufficient stock | BBB Team
| Build and Release Singles Order | BBB Team
| Build and Release Priority Singles Order | BBB Team
| Build and Release Batch Order | BBB Team
| Build and Release Priority Batch Order | BBB Team
| Build and Release Large Singles Order | BBB Team
| Build and Release Exception Re-Pick | BBB Team
Single Scan Picking
| Pick wave of single unit orders onto one cart | BBB Team
| Pick wave of one Wholesale Order onto one pallet | BBB Team
| Stage picking cart when full and continue picking | BBB Team
| Attempt to scan invalid item during picking | BBB Team
| Attempt to scan invalid location during picking | BBB Team
| Attempt to pick quantity larger than allocated | BBB Team
Batch Picking
| Pick wave of multi unit orders into designated bins | BBB Team
| Perform exception during picking when stock not found/damaged | BBB Team
| Use New Bin functionality to pick an order into multiple bins | BBB Team
| Attempt to scan invalid item during picking | BBB Team
| Attempt to scan invalid location during picking | BBB Team
| Attempt to scan invalid container/bin during picking | BBB Team
| Attempt to pick quantity larger than allocated | BBB Team
Singles Packing
| Pack order from cart picked via Single Scan Picking | BBB Team
| Capture box dimensions during packing for Pack Order by Item | BBB Team
| Print shipping label at the conclusion of packing | BBB Team
| Attempt to pack a multi unit order via Pack Order by Item (should not allow) | BBB Team
| Back out of container during packing and re-scan container to continue | BBB Team
| Scan invalid items during Pack Order by Item | BBB Team
| Pack an item with "Preferred Carton Type" set on pack entity (should autopopulate carton type to use) | BBB Team
| Change carton type from suggested | BBB Team
| Perform Rate shopping | BBB Team
Multis Packing
| Pack an order that is cartonized into one container | BBB Team
| Pack an order that is cartonized into multiple containers | BBB Team
| Change the suggested carton type from what was suggested by cartonization | BBB Team
| Print Container Labels | BBB Team
| Print shipping label(s) at the end of packing | BBB Team
| Attempt to pack an invalid item | BBB Team
Build Pallet
| Scan a gaylord | BBB Team
| Scan shipping container into gaylord | BBB Team
| Attempt to scan a shipping container with different ship via than previously scanned | BBB Team
Assign Trip to Container
| Close trip for wholesale order by scanning containers to dock door | BBB Team
Void and Reprocess Shipment
| Void and Reprocess one Shipment | BBB Team

## Inbound Test Cases
Client: |  | BBB
Client Code: |  | BBB
Process: |  | Receiving
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 16
Test Cases Executed: |  | 16
Test Cases Passed: |  | 16
Test Cases Failed: |  | 0
% Complete: |  | 100%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receiving Purchase Order Test Cases
1 | PO Receiving | 1.01 | ALL | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen | yes | 04323 | Pass | Action buttons are cutoff on certain screens Adding Items to Order Lines: cannot search Item or Pack using UPC
|  | 1.02 | ALL | Select Purchase Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Check Yes for Summary if you want to display additional PO Details for receipt and check Yes for Putaway if you want to direct stock to a location other than the default Receiving location. | moves to next screen | yes | 04323
|  | 1.03 | ALL | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen | yes
|  | 1.04 | ALL | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 1.05 | ALL | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 1.06 | ALL | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 1.07 | ALL | Keep repeating step 1.03 - 1.05 if there are multiple items in the order that you are receiving until all items have been received | PO is fully received
2 | Blind Order Receiving | 2.01 |  | Select Blind Receiving from Admin menu on Handheld | moves to general receiving screen |  |  | Pass
|  | 2.02 |  | Select Blind Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Confirm user receives an error if they attempt to continue receiving without inputting or scanning an identifier. Check Yes for Putaway if you want to direct stock to a location other than the default Receiving location. | moves to next screen
|  | 2.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 2.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 2.05 |  | Hit Enter | If Print Label was checked yes, user is prompted print item label screen
|  | 2.06 |  | Keep repeating step 3.03 - 3.05 if there are multiple items in the order that you are receiving until all items have been received
|  | 2.07 |  | Hit Finish
3 | Hot Pick Putaway "Receiving-LPN" -> Reserve (Move Stock) | 3.01 |  | Select Move Stock from the Inbound menu |  | fail on 3.05 |  | Pass |  | Simon Siewior
|  | 3.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 3.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 3.04 |  | Scan/Enter the Item you are moving | item is entered
|  | 3.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 3.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 3.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 3.08 |  | Enter the Item and the Quantity that will be moved
|  | 3.09 |  | User will then see a listbox of eligible Hot Pick locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 3.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
4 | Receiving to Picking Putaway "Receiving" -> Picking (Move Item) | 4.01 |  | Select Move Item from the Inbound menu |  | works | REC-STG-1 | Pass | moved 50 sku 69974654 | Simon Siewior
|  | 4.02 |  | Enter/Scan the source location of the stock you will be moving your items from
|  | 4.03 |  | Scan/Enter the Items you are moving to a Picking location | item is entered
|  | 4.04 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 4.05 |  | User will then see a listbox of eligible locations to move the items to. Scan/Enter a location | Enter/Scan the locator of the location
|  | 4.06 |  | Once user hits enter, they will be directed back to the Item selelction screen where they can scan more items to move if they choose to do so.
|  | 4.07 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
6 | PO Receiving (with Item Image Display in Handheld) | 6.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen | failed | PO 1222, Item 301003115 | Pass | fixed by installing google play version of app. the link from support page provides an apk with non working image | Simon Siewior
|  | 6.02 |  | Select Purchase Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Check Yes for Summary if you want to additional PO Details and check Yes for Putaway if you want to direct stock to a location other than the default Receiving location. | moves to next screen
|  | 6.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 6.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 6.05 |  | On the bottom right of your screen, you will see "View Item" button. If you want to display the item image, click "View Item" | "View Item" screen will pop up. You will be able to see item image
|  | 6.06 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 6.07 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 6.08 |  | Keep repeating step 1.03 - 1.05 if there are multiple items in the order that you are receiving until all items have been received | PO is fully received
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Print Item label
7 | Print Item Label Through Process Action Link | 7.01 |  | Go to Master Data-> Items-> Select an item | Message: Succesfully printed 1 of report [Item Label] for each Item | yes | 301000649 | Pass |  | Simon Siewior
|  | 7.02 |  | Select the Actions drop down menu-> Print Item Label
|  | 7.03 |  | Select your printer-> Print
8 | Print Item Label Through Handheld in General Receiving | 8.01 |  | Handheld-> Inbound-> General Receiving | Message: Report [Item Label] succesfully printed. | yes | 69742453 | Pass |  | Simon Siewior
|  | 8.02 |  | Scan/Enter PO Identifier
|  | 8.03 |  | Scan/ Enter the Item Number
|  | 8.04 |  | Print Item Label By Choosing Yes on This Screen
|  | 8.05 |  | Choose Quantity of Item Labels to Print and Confirm Physical Printing of Item Label
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receiving Edge Cases
9 | Incorrect PO# Entry | 1.01 |  | Navigate to the General Receiving button found in the Inbound Menu | A message should dispay reading, "Purchase Order _____ does not exist" | works |  | Pass |  | Simon Siewior
|  | 1.02 |  | Enter a PO Number that does not exist
10 | Scanning Already Received PO | 2.01 |  | User enters Receiving Process | Error message appears reading, "There are no lines eligible to receive for this order". | works | 69696969 | Pass |  | Simon Siewior
|  | 2.02 |  | User scans a Purchase Order that has already been received instead of a new Purchase Order
|  | 2.03 |  | User will be prevented from continuing with the process
11 | Attempt to Finish without Receiving Item | 3.01 |  | User will enter General Receiving button | Message will populate indicating nothing has been received from the associated PO | works | PO90 | Pass |  | Simon Siewior
|  | 3.02 |  | User hits "Finish/Exit"
|  | 3.03 |  | If nothing has been received, user will receive message "You have not received any item for order [_____]"
12 | Receiving an existing Item not on a PO | 4.01 |  | User will enter receiving transaction | Error message appears reading, "Please enter a valid SKU for [PO Number]." | works |  | Pass |  | Simon Siewior
|  | 4.02 |  | User scans/Keys an Item not on PO for receiving
|  | 4.03 |  | User will be prevented from receiving the item in the process
13 | Negative Item Qty Entry | 6.01 |  | During General Receiving, user keys in a negative quantity to be received | Error message appears reading, "Please enter a valid quantity." | works | 0 | Pass |  | Simon Siewior
|  | 6.02 |  | User will be prompted to re-enter quantity
14 | Invalid Item Qty Entry | 7.01 |  | During General Receiving, user keys in an invalid number like "2YN" | Error message appears reading, "Please enter a valid quantity." | nothing | ABC | Pass | app does not allow alpha numeric input so only digits work | Simon Siewior
|  | 7.02 |  | User will be prompted to re-enter quantity
15 | Over-Receive a PO | 15.01 |  | During General Receiving, user keys in quantity that is 10% greater than the order pack quantity | Message should appear reading "You can only receive up to the max amount (QTY) of Each." | works | 99999 | Pass |  | Simon Siewior
9 | Attempt to Over-Receive over 25% | 9.01 |  | During General Receiving, user keys in quantity that is greater than the order pack quantity (over 25%) | Error message appears reading "You can only receive up to a maximum of [10%] of Each" | same message as above |  | Pass |  | Simon Siewior
|  | 9.02 |  | User will be prevented from receiving the item in the process as it exceeds the over-receipt threshold of 25%
16 | Unreceiving | 16.01 |  | Navigate to the 'Unreceiving' button in the Inbound menu on the handheld |  | fail | 04323 | Pass | Multiple orders with number [04323] in business unit [BBB]. Please assign unique order numbers ---passed once duplicate [04323] order header was edited | Robert Moreira
|  | 16.02 |  | Enter the order header number of the order needed to be unreceivied
|  | 16.03 |  | Scan the item to be unreceived and enter the quantity to be decremented from the current received quantity. Container is not required but can be scanned to put the item into when unreceiving
|  | 16.04 |  | Press enter or select submit

## Follow-up Inbound Test Cases
Client: |  | BBB
Client Code: |  | BBB
Process: |  | Inbound
Date Updated:
Test Cases Required: |  | 8
Test Cases Executed: |  | 4
Test Cases Passed: |  | 4
Test Cases Failed: |  | 0
% Complete: |  | 50%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Inbound
1 | General Receiving - Scan with SKU | [6 empty] | Pass
2 | General Receiving - Scan with UPC | [6 empty] | Pass
3 | General Receiving - Accept the Randomly Generated LPN Number in LPN Putaway Screen | [6 empty] | Ready for Testing
4 | General Receiving - Remove the Randomly Generated LPN Number in LPN Putaway Screen and Input your own | [6 empty] | Ready for Testing
5 | General Receiving - Choose Yes to Print the LPN Label in LPN Putaway Screen | [6 empty] | Ready for Testing
6 | General Receiving - Choose No to Print the LPN Label in LPN Putaway Screen | [6 empty] | Ready for Testing
7 | Move Item - Scan SKU | [6 empty] | Pass
8 | Move Item - Scan UPC | [6 empty] | Pass

## Inventory Test Cases
Client: |  | BBB
Client Code: |  | BBB
Process: |  | Inventory Management |  | Replenishment Tasks show SKU number need to switch to UPC
Date Updated:
Test Cases Required: |  | 24
Test Cases Executed: |  | 24
Test Cases Passed: |  | 24
Test Cases Failed: |  | 0
% Complete: |  | 100%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Cycle Count
1 | Create Cycle Count Task by Location | 1.01 | Kenny | Make sure Cycle Count checkbox is checked for both Item and the Location that contains its stock units (Inventory). | Using the location cycle count creation handheld process will create cycle count tasks for a specific location Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING. When cycle counting via handheld "Perform Cycle Count" process, user will be prompted to count all specified items in the location. | pass |  | Pass |  | Kenny Titus
|  | 1.02 | Kenny | Navigate to "Create Cycle Count By Location" under Inventory in handheld menu |  | pass
|  | 1.03 | Kenny | Scan or enter the location to count |  | pass
|  | 1.04 | Kenny | Optionally enter a priority for the cycle count. If no priority is entered, then the priority will default to five (Medium). |  | pass
|  | 1.05 | Kenny | Cycle count tasks for the location will appear in the Cycle Count Queue table. (located in Inventory Admin menu option on the desktop UI) |  | pass
2 | Manage Cycle Count Variances | 2.01 | Kenny | User (typically a supervisor or manager) will enter the "Approve Variances" UI through a laptop or desktop | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances". | pass |  | Pass |  | Kenny Titus
|  | 2.02 | Kenny | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system. |  | pass
|  | 2.03 | Kenny | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted. |  | pass
|  | 2.04 | Kenny | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted). |  | pass
3 | On Demand Cycle Count | 3.01 | Joanne | User will select "On Demand Location Cycle Count" from Inventory menu | If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. (ref seq. 7) Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING. | pass |  | Pass |  | Joanne Rodriguez
|  | 3.02 | Joanne | User will be prompted to enter a location and priority (1-10 w/1 being highest priority). Priority defaults to 5 if left empty. |  | pass
|  | 3.03 | Joanne | User creates cycle count task and will immediately begin task (reference seq. 3, steps 3.04-3.10) and will be assigned to the user to complete. |  | pass
4 | Physical Count | 4.01 | Jamie | Select "Physical Count" from Inventory Menu | 1) When Physical Count Activity is started from Physical Count Admin button, message will appear saying "[controlled/non-controlled] Physical Count Activity [process name] is started on [date time] and is active". 2) Non-controlled Physical Count Activity will be able to create and delete inventory. Stock units will be updated with whatever is counted for that location. 3) If controlled, discrepancies will be recorded in "Manage Cycle Count Variances" . 4) Once physical count activity is complete, screen will return to MainMenu and will display a message saying "[controlled/non-controlled] Physical Count Activity [process name] is finished at [date time]". 5) Adjustments to item's SU will show up in Inventory General Ledger Table |  |  | Pass |  | Jamie A
|  | 6.02 | Jamie | Scan/Enter a location
|  | 6.03 | Jamie | User counts items in location
|  | 6.04 | Jamie | To go onto the next location, User can select "Next Location"
|  | 6.05 | Jamie | If phys count activity is non-controlled, user is taken to phys count summary screen and can click "Recount" or "Apply" before finally confirming.
|  | 6.06 | Jamie | When done with physical count activity, navigate to "Physical Count Admin" button and click "Finish Physical Count Activity" |  | Admin->Physical Count Admin
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Putaway
1 | Move Item | 1.01 | Joanne | Navigate to "Move Item" under Inbound on handheld MainMenu | This process allows a user to move unique items individually out of a location and into a different location Stock units that were moved are decremented from their source location, and are created in the destination location | item moved |  | Pass |  | Joanne Rodriguez
|  | 1.02 | Joanne | Enter the location that contains the stock you want to move |  | item moved
|  | 1.03 | Joanne | A listbox of available SKUs to move display. User must scan or select item to move |  | item moved
|  | 1.04 | Joanne | User selects pack type, pack UOM, and enters quantity of how much stock to move |  | item moved
|  | 1.05 | Joanne | User is prompted to putaway screen. User must scan or select a location in which to put the stock away. |  | item moved
|  | 1.06 | Joanne | If user wants to continue moving items from this location, user can repeat steps 1.03-1.05 |  | item moved
|  | 1.07 | Joanne | Otherwise, user can exit the process |  | item moved
2 | Move Stock | 2.01 | Robert M | Navigate to "Move Stock" under Inbound on handheld MainMenu | This process allows a user to move multiple items instead of one unique SKU 1) When all stock has been moved successfully, a message displays on menu saying "All Items Moved." 2) Picking Cart is now empty and remains in its original location 3) Stock units that were moved are decremented from their source location, and are created in the destination location |  |  | Pass |  | Robert Moreira
|  | 2.02 | Robert M | Enter/scan the container in which you want to put the stock you are wanting to move
|  | 2.03 | Robert M | Enter or scan location with the stock you want to move
|  | 2.04 | Robert M | A listbox of available SKUs to move display. User must scan or select item to move
|  | 2.05 | Robert M | Select Pack UOM and enter in quantity to move and select Submit
|  | 2.06 | Robert M | Repeat steps 2.04-2.05 to move more items in the location
|  | 2.07 | Robert M | When finished, select Move Source Screen
|  | 2.08 | Robert M | User is given a summary of the number of unique Skus and quantity in cart. If user wants to move stock in a different location, User can scan another location.
|  | 2.09 | Robert M | Otherwise, User can select "Move" or "Move Full" to move the stock to a directed location
|  | 2.10 | Robert M | User enters quantity and selects/scans item
|  | 2.11 | Robert M | A listbox of suggested putaway locations is displayed. User must select or scan a location to move the stock
|  | 2.12 | Robert M | User repeats 2.10-2.11 to move the rest of the stock, if any
|  | 2.13 | Robert M | Otherwise, User can select All to move all of the stock in the cart and then scan the destination location of where the stock should be moved
2 | Move Container | 2.01 | Joanne | Navigate to "Move Container" under Inventory on handheld MainMenu | This process allows a user to move an entire container (LPN) out of a location and into a different location The container (LPN) that container the stock (inventory) is decremented from the source location, and created in the destination location |  |  | Pass |  | Joanne Rodriguez
|  | 2.02 | Joanne | Enter/Scan the container (LPN) that contains the stock (inventory) you want to move. Container type must be Pallet or Transient
|  | 2.03 | Joanne | A listbox of suggested locations should populate. The user should now navigate to one of the suggested locations, scanning that location they wish to put the container away to
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Adjust Inventory
1 | Adjust Inventory: Decrement Inventory out of a Location | 1.01 | Joanne | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 4) Updates made to Item's SU in location |  |  | Pass | Did not prompt for Reason Code | Joanne Rodriguez
|  | 1.02 | Joanne | Scan/key in Location
|  | 1.03 | Joanne | Select "Consume by Item"
|  | 1.04 | Joanne | Scan Item SKU
|  | 1.05 | Joanne | Enter quantity of item's SU you want to consume
|  | 1.06 | Joanne | If you have more than one item's SU you want to consume in the location, click next and repeat steps 2.04 and 2.05
|  | 1.07 | Joanne | Once finished, click Confirm
|  | 1.08 | Joanne | Once final reviewing all items, select Reason Code and click Commit
2 | Adjust Inventory: Add Inventory to a Location | 2.01 | Joanne | Select "Adjust Inventory" from the Inventory menu | 1) After items have been confirmed and the user clicks commit, user is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" 2) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 3) Updates made to Item's SU in location |  |  | Pass | Did not prompt for Reason Code | Joanne Rodriguez
|  | 2.02 | Joanne | Scan/key in Location
|  | 2.03 | Joanne | Select "Create Inventory"
|  | 2.04 | Joanne | Scan Item SKU
|  | 2.05 | Joanne | Enter quantity of item's SU you want to create. User can optionally enter serial, lot, and LPN #.
|  | 2.06 | Joanne | If you have more than one item's SU you want to create, click next and repeat steps 3.04 and 3.05
|  | 2.07 | Joanne | Once finished, click Confirm
|  | 2.08 | Joanne | Once final reviewing all items, select Reason Code and click Commit
3 | Adjust Inventory: Consume All Inventory in Location | 3.01 | Joanne | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location |  |  | Pass | Did not prompt for Reason Code
|  | 3.02 | Joanne | Scan/key in Location
|  | 3.03 | Joanne | Select "Consume All in Location"
|  | 3.04 | Joanne | Select Reason Code and Click Commit
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Adjust Inventory
1 | Replenishment Based on Storage and Inventory Quantities | 1.01 | Rob M | Replenishments are generated on a scheduled basis for every location-item combination where current inventory levels for an item in a picking location is LESS than the Item's Storage's Maximum Value and if there is any inventory in a Reserve Location. All replenishments can be viewed in the "ReplenishmentTaskNew" entity |  |  |  | Pass |  | Joanne Rodriguez
|  | 1.02 | Rob M | Run the Create Replenishment Tasks Scheduler
|  | 1.03 | Joanner | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 1.04 | Joanner | Scan a container that is Type=Cart or create a new container from this process
|  | 1.05 | Joanner | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 1.06 | Joanner | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 1.07 | Joanner | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 1.08 | Joanner | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 1.09 | Joanner | User will scan the destination location, the SKU, and the replen quantity
|  | 1.1 | Joanner | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Inventory Edge Cases
1 | Ad-Hoc Cycle Count - Counting Less than the Item's Qty | 1.01 | Maria S | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances" UI for a manager or supervisor to review 2) If qty count entered is less than the system's qty, a negative variance qty will be displayed for that item in "Approve Variances" |  |  | Pass |  | Maria Storts
|  | 1.02 | Maria S | User will enter quantity less than the item's SU quantity currently in Deposco's system
|  | 1.03 | Maria S | User will be asked to recount and will proceed to re-enter the quantity.
2 | Ad-Hoc Cycle Count - Counting More than the Item's Qty | 2.01 | Maria S | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances UI for a manager or supervisor to review 2) If qty count entered is more than the system's qty, a positive variance qty will be displayed for that item in "Approve Variances" |  |  | Pass |  | Maria Storts
|  | 2.02 | Maria S | User will enter quantity more than the item's SU quantity currently in Deposco's system
|  | 2.03 | Maria S | User will be asked to recount and will proceed to re-enter the quantity.
3 | Perform Cycle Count - Scanning incorrect Location | 3.01 | Maria S | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) Error message saying "You must cycle count the given location [required location]". 2) User will be prevented from ever counting in an incorrect location. |  |  | Pass |  | Maria Storts
|  | 3.02 | Maria S | Scan or enter starting location and hit enter
|  | 3.03 | Maria S | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 3.04 | Maria S | User scans an incorrect location
|  |  | Maria S | User is prompted to re-enter correct location. Proceed as normal.
4 | Perform Cycle Count - Scanning Item that does not exist in Location | 4.01 | Maria S | Select Perform Cycle Count button in handheld menu from Inventory | 1) Variance be generated in the "Approve Variances" UI for a manager or supervisor to review |  |  | Pass |  | Maria Storts
|  | 4.02 | Maria S | Scan or enter starting location and hit enter
|  | 4.03 | Maria S | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 4.04 | Maria S | User will incorrectly scan an item not listed nor existing in the location
|  | 4.05 | Maria S | On the next screen they'll select the pack type and enter the quantity they counted
|  | 4.06 | Maria S | User will be brought back to the screen displaying the list box of items and can proceed as normal
5 | Physical Count- Physical Count Activity not Started | 5.01 | Maria S | User makes sure there is no physical count activity started by navigating to Physical Count Admin button. If there is one existing, user should select "Finish Physical Count Activity". | 1) User will get an error on MainMenu saying "PHYSICAL_COUNT Activity has not started." 2) User will not be able to start physical count process unless the activity has been started in Physical Count Admin. |  |  | Pass |  | Maria Storts
|  | 5.02 | Maria S | Select "Physical Count" button in Admin Folder
|  | 5.03 | Maria S | User will not be able to start physical count
7 | Move Item / Move Stock - Incorrect Source Location Scan | 7.01 | Maria S | During Move Item/Move Stock, user scans a source location that does not exist | User should see an error on MainMenu saying "[....] is not a valid location" or "No such location or LPN in the current facility." depending on process |  |  | Pass |  | Maria Storts
|  | 7.02 | Maria S | The user should be prevented from moving forward with the process
8 | Move Item / Move Stock - Putaway to non Suggested Location | 8.01 | Robert M | During Move Item/Move Stock user wants to put away to a location other than the suggested location | 1) Stock unit will be created in the putaway location the user entered 2) Message will appear reading, "All items Moved." if using Move Item |  |  | Pass |  | Robert Moreira
|  | 8.02 | Robert M | User will leave the suggested location list box alone and scan the desired putaway location
9 | Move Item / Move Stock - Incorrect Item Qty Entry | 9.01 | Joanne R | During Move Item/Move Stock, user enters in more than the item's current SU quantity to move | 1) Message will appear reading, "The entered quantity exceeds the total movable Each quantity of [...]." and "Quantity to move [..] larger than quantity in found stocks [...]." depending on process. 2) User should not be allowed to enter more than the item's current SU quantity. |  |  | Pass |  | Joanne Rodriguez
|  | 9.02 | Joanne R | User will be prompted to re-enter quantity and scan putaway location
10 | Move Item / Move Stock - Negative Item Qty Entry | 10.01 | Maria S | During Move Item/Move Stock, user enters in a negative value for the item's current SU quantity to move | 1) Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process. 2) User should not be allowed to enter or move a negative quantity in this process. |  |  | Pass |  | Maria Storts
|  | 10.02 | Maria S | User will be prompted to re-enter quantity and scan putaway location
11 | Move Item / Move Stock - Invalid Item Qty Entry | 11.01 | Maria S | During Move Item/Move Stock, user enters in for the item's current SU quantity to move an invalid number like "2YN". | 1) Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process. 2) User should not be allowed to enter an invalid item's SU quantity. |  |  | Pass |  | Maria Storts
|  | 11.02 | Maria S | User will be prompted to re-enter quantity and scan putaway location
12 | Replen edge cases | 12.01 | Joanne R | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen |  |  |  | Pass |  | Joanne Rodriguez
|  | 12.02 | Joanne R | In the Picking screen, select "Exception"
|  | 12.03 | Joanne R | The user is directed to "Replenishment Picking Exception" screen
|  | 12.04 | Joanne R | Hit Complete
|  | 12.05 | Joanne R | The replenishment task is marked with a status of "Full", this replenishment task is skipped and the user is taken to the next replenishment task
13 | Replen edge cases | 13.01 | Joanne R | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen | The location that the Exception occured at will then have a status of "On Hold" |  |  | Pass |  | Joanne Rodriguez
|  | 13.02 | Joanne R | In the Picking screen, select "Exception"
|  | 12.03 | Joanne R | The user is directed to "Replenishment Picking Exception" screen
|  | 13.04 | Joanne R | Select No Stock and hit Exception
|  | 13.05 | Joanne R | The replenishment task is marked with a status of "Exception", this replenishment task is skipped and the user is taken to the next replenishment task
14 | Replen edge cases | 14.01 | Joanne R | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen |  |  |  | Pass |  | Joanne Rodriguez
|  | 14.02 | Joanne R | Scan a container that is Type=Cart
|  | 14.03 | Joanne R | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 14.04 | Joanne R | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 14.05 | Joanne R | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 14.05 | Joanne R | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 14.05 | Joanne R | User will scan the destination location, the SKU, and the replen quantity
|  | 14.05 | Joanne R | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
|  | 14.05 | Joanne R | Select Suspend Task and hit Exception
|  | 14.05 | Joanne R | The replenishment task is skipped and the user is taken to the next replenishment task
|  | 14.06 | Joanne R | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 14.07 | Joanne R | Select Exception, and user will be directed to the Replenishment putaway exception screen. Select Location Full and then click "Exception" again
|  | 14.08 | Joanne R | User will then be directed to put the stock back to where they pick it from
|  | 14.09 | Joanne R | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."

## Outbound Test Cases
|  | BBB | Additional Note: Before starting to Test Packing out Singles Ecom orders, remember to check that your test order has a valid shipVia (ex. FedEx Ground) before packing out. Otherwise, your user will experience an error when attempting to pack out. With Multis, you'll be able to rate-shop in the Packing Processes, so this will not pose as much of an issue once rate-shop license is active
Client Code: |  | BBB | Order Flows Cheatsheet:
Process: |  | Outbound | Multis Ecom Flow: BatchPicking --> SingleScanPacking/CubedPacking
Date Updated: |  | 2025-08-12 | Singles Ecom Flow: SingleScanPicking --> PackOrderByItem
Test Cases Required: |  | 27 | Large Ecom Flow: SingleScanPicking --> SingleScanPacking
Test Cases Executed: |  | 11 | B2B/LTL Orders Flow: SingleScanPicking --> SingleScanPacking --> AssignTripToContainer
Test Cases Passed: |  | 10
Test Cases Failed: |  | 1
% Complete: |  | 37.04%
Picking Test Cases
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking
1 | Batch Picking - Ecom Small Order Volume Multis Picking | 1.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecomm Small Order Volume Multis Pickwave (<= 10 totalUnits per order) | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest2 | Pass |  | Maria Storts
|  | 1.02 | Maria S | User will select Batch Picking button from Outbound menu --> User will see a list of multis Ecom waves and can select or enter the wave of their choosing
|  | 1.03 | Maria S | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 1.04 | Maria S | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 1.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 1.06 | Maria S | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
2 | Batch Picking - Ecom Medium Order Volume Multis Picking | 2.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecom Medium Order Volume Multis Pickwave (> 10, <= 20 total units per order) | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest3 | Pass |  | Robert Moreira
|  | 2.02 | Rob M | User will select Batch Picking button from Outbound menu --> User will see a list of Ecom multis waves and can select or enter the wave of their choosing
|  | 2.03 | Rob M | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 2.04 | Rob M | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 2.05 | Rob M | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 2.06 | Rob M | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
3 | Single Scan Picking - Ecom RTS High Picking Zone Singles Picking | 3.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecom RTS High Picking Zone Singles Pickwave | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest4 bbbtest1 | Pass |  | Robert Moreira
|  | 3.02 | Rob M | User will select Singles Scan Picking in corresponding Outbound menu --> User will see a list of SinglesBulkPick waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 3.03 | Rob M | User will scan location, SKU, bin and enter in quantity to complete pick task(s).
|  | 3.04 | Rob M | Once all pick tasks have been completed, user is returned to the wave selection screen
4 | Single Scan Picking - Ecom RTS Low Picking Zone Singles Picking | 4.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecom RTS Low Picking Zone Singles Pickwave | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest5 | Pass |  | Jamie A
|  | 4.02 | JamieA | User will select Singles Scan Picking in corresponding Outbound menu --> User will see a list of SinglesBulkPick waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 4.03 | JamieA | User will scan location, SKU, bin, and enter in quantity to complete pick task(s)
|  | 4.04 | JamieA | Once all pick tasks have been completed, user is returned to the wave selection screen
5 | Single Scan Picking - Ecom Non-RTS High Picking Zone Singles Picking | 5.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecom Non-RTS High Picking Zone Singles Pickwave | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest_5_1 bbbtest_5_2 | Pass |  | Jamie A
|  | 5.02 | JamieA | User will select Singles Scan Picking in corresponding Outbound menu --> User will see a list of SinglesBulkPick waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 5.03 | JamieA | User will scan location, SKU, bin, and enter in quantity to complete pick task(s)
|  | 5.04 | JamieA | Once all pick tasks have been completed, user is returned to the wave selection screen
6 | Single Scan Picking - Ecom Non-RTS Low Picking Zone Singles Picking | 6.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecom Non-RTS Low Picking Zone Singles Pickwave | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest6_1 bbbtest6_2 | Pass |  | Robert Moreira
|  | 6.02 | Rob M | User will select Singles Scan Picking in corresponding Outbound menu --> User will see a list of SinglesBulkPick waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 6.03 | Rob M | User will scan location, SKU, bin, and enter in quantity to complete pick task(s)
|  | 6.04 | Rob M | Once all pick tasks have been completed, user is returned to the wave selection screen
7 | Single Scan Picking - Ecom Large B2C Order Volume Picking | 7.01 | Rob M | User will identify order(s) that accomplish the requirement of an Ecom Large B2C Order Volume PickWave (>20 totalUnits per order, each order will likely be on their own wave depending on sizing determined by BBB team) | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest7_1 bbbtest7_2 | Pass |  | Simon Siewior
|  | 7.02 | Simon Maria | User will select Single Scan Picking in corresponding Outbound menu --> User will see a list of SInglesBulkPick waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 7.03 | Simon Maria | User will scan location, item SKU, and quantity
|  | 7.04 | Simon Maria | Once all pick tasks have been completed, user is returned to the wave selection screen
8 | Single Scan Picking - B2B Orders Picking | 8.01 | Rob M | User will identify order(s) that accomplish the requiremenr of a B2B Orders PickWave | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location |  | bbbtest8 | Pass |  | Robert Moreira
|  | 8.02 | Rob M | User will select Singles Scan Picking in corresponding Outbound menu --> User will see a list of SinglesBulkPick waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 8.03 | Rob M | User will scan location, item SKU, and quantity
|  | 8.04 | Rob M | Once all pick tasks have been completed, user is returned to the wave selection screen
Packing Test Cases
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
1 | Single Scan Packing - Multis Ecom Packing | 1.01 | Joanner | Can Be Tested with Any Multis Ecom, Large B2C, and B2B Orders | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container. |  |  | Fail | bin1 used for multiple orders error generated
|  | 1.02 | Joanner | Select Single Scan Packing from Outbound menu --> Scan the LPN label of the picking container, and select Next.
|  | 1.03 | Joanner | The Item Screen appears with a list of items in the container. Scan an item in container, then enter the quantity that will be packed on the next screen
|  | 1.04 |  | Select the CartonType from the Box list on the ContainerAndDimension Screen and confirm the pre-populated weight or input weight as needed
|  | 1.05 |  | Shipping label and packing list will print after previous screen is executed - if applicable
|  | 1.06 |  | If there are more items in the picking bin, then you are returned to the Item Screen to scan/select another item to repeat the process for each picking bin
2 | Pack Order By Item - Singles Ecom Packing | 2.01 |  | Can Be Tested with Any Singles Pickwave (RTS, Non-RTS, Low Picking Zone, High Picking Zone) | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container. |  |  | Pass
|  | 2.02 |  | Select Pack Order By Item from Outbound menu --> Scan the LPN label of the picking container, and select Next.
|  | 2.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container, then Scan or enter the order the item corresponds to.
|  | 2.04 |  | Select the CartonType from the Box list on the ContainerAnDimension Screen and confirm the pre-populated weight or input weight as needed
|  | 2.05 |  | Shipping label and packing list will print after previous screen is executed - if applicable
|  | 2.06 |  | If there are more items in the picking bin, then you are returned to the Item Screen to scan/select another item to repeat the process for each picking bin
3 | Cubed Packing - Multis Ecom Packing | 3.01 |  | Can Be Tested with Any Multis Ecom and Large B2C Order(s) - Difference with SingleScanPacking is Cubed Packing can perform Cartonization and RateShopping within process | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container. |  |  | Ready for Testing
|  | 3.02 |  | Select Cubed Packing from Outbound menu --> Scan the LPN label of the picking container, and select Next.
|  | 3.03 |  | The Item Screen appears with a list of items with a selected container CartonType Based on the Dimensions of the Items/Packs within an order
|  | 2.04 |  | Select the CartonType from the Box list on the ContainerAndDimension Screen and confirm the pre-populated weight or input weight as needed
|  | 2.05 |  | Shipping label and packing list will print after previous screen is executed - if applicable
|  | 2.06 |  | If there are more items in the picking bin, then you are returned to the Item Screen to scan/select another item to repeat the process for each picking bin
4 | Assign Trip To Container - B2B Orders Closing | 4.01 |  | Can Be Tested with Any B2B Order Not Closed through Other Packing Methods | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container. |  |  | Pass | Needed to change container type to ship out
|  | 4.02 |  | Select Shipping Door to Proceed
|  | 4.03 |  | Input the weight of container content and the tare weight of your pallet (if applicable) --> Scan container below weight values
|  | 2.04 |  | Input Trip Details if available or leave screen fields empty
|  | 2.05 |  | Close Trip and Verify That Order is Fully Shipped and Closed Now
Exceptional Picking Test Cases
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking Edge Cases
1 | Batch Picking - Entering Less Quantity | 1.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed |  |  | Ready for Testing
|  | 1.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
2 | Singles Picking - Entering Less Quantity | 2.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed |  |  | Ready for Testing
|  | 2.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
3 | Batch Picking - User Scans Incorrect Location | 3.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen |  |  | Ready for Testing
|  | 3.02 |  | User scans a location other than the one listed on the screen during picking
|  | 3.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 3.04 |  | User should proceed to correct location and continue as normal
4 | Batch Picking - User Scans Incorrect Item | 4.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. |  |  | Ready for Testing
|  | 4.02 |  | User scans the wrong item
|  | 4.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
5 | Batch Picking - User Enters too Much Quantity | 5.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Ready for Testing
|  | 5.02 |  | User accidentally enters more than the pick quantity
|  | 5.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 5.04 |  | User will again be prompted to enter location, SKU, and quantity.
6 | Batch Picking - Scanning Incorrect Container/Bin | 6.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Ready for Testing
|  | 6.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
7 | Batch Picking - Exceptions (no stock, damaged, etc.) | 7.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Ready for Testing
|  | 7.02 |  | User can select "exception" button
|  | 7.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 7.04 |  | Select "exception" again from that screen after selecting a reason
|  | 7.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 7.06 |  | If no other stock exists for that item, it will go to back ordered status.
8 | Batch Picking - Suspend Task | 8.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Ready for Testing
|  | 8.02 |  | User can select "exception" button
|  | 8.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 8.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
9 | Batch Picking - Suspend Workgroup | 9.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Ready for Testing
|  | 9.02 |  | User can select "exception" button
|  | 9.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 9.04 |  | User is taken back to MainMenu screen
|  | 9.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
10 | Batch PIcking - Suspend Workgroup and Keep Assigned User | 10.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Ready for Testing
|  | 10.02 |  | User can select "exception" button
|  | 10.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 10.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 10.05 |  | Assigned user can select wave again to continue picking
11 | Singles Picking - User Scans Incorrect Location | 11.01 |  | During picking, the user will see the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen |  |  | Ready for Testing
|  | 11.02 |  | User scans a location other than the one listed on the screen during picking
|  | 11.03 |  | Error message will appear "Please scan a valid location."
|  | 11.04 |  | User should proceed to correct location and continue as normal
12 | Singles Picking - User Scans Incorrect Item | 12.01 |  | During picking, the user scans the wrong item | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. |  |  | Ready for Testing
|  | 12.02 |  | Screen message will appear stating "Please scan a valid item"
13 | Singles Picking - User Enters Too Much Quantity | 13.01 |  | User enters locatiton and SKU | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Ready for Testing
|  | 13.02 |  | User accidentally enters more than what is called for to pick
|  | 13.03 |  | Screen message will appear as follows: "Quantity entered is greater than required."
|  | 13.04 |  | User will again be prompted to enter location, SKU, and quantity.
14 | Singles Picking - Exceptions (no stock, damaged, etc.) | 14.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order will go to back ordered status. Also, the stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Ready for Testing
|  | 14.02 |  | User can select "exception" button
|  | 14.03 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 14.04 |  | If no other stock exists for that item, it will go to back ordered status.
15 | Singles Suspend WorkGroup | 15.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Ready for Testing
|  | 15.02 |  | User can select "exception" button
|  | 15.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 15.04 |  | User is taken back to MainMenu screen
|  | 15.05 |  | User or another user can select the pick wave and complete the remaining picking tasks

## Follow-up Outbound Test Cases
Client: |  | BBB
Client Code: |  | BBB
Process: |  | Outbound
Date Updated: |  | 2024-08-01
Test Cases Required: |  | 9
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | 0%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Inbound
1 | Single Scan Picking - Scan with SKU | [6 empty] | Ready for Testing
2 | Single Scan Picking - Scan with UPC | [6 empty] | Ready for Testing
3 | BatchPicking - Scan with SKU | [6 empty] | Ready for Testing
4 | BatchPicking - Scan with UPC | [6 empty] | Ready for Testing
5 | Pack Order By Item - Scan with SKU | [6 empty] | Ready for Testing
6 | Pack Order By Item - Scan with UPC | [6 empty] | Ready for Testing
7 | Single Scan Packing - Scan with SKU | [6 empty] | Ready for Testing
8 | Single Scan Packing - Scan with UPC | [6 empty] | Ready for Testing
9 | Singles Packing - Item Dims |  |  |  | Confirm the ShippingLabel Request to Fedex Displays the Dimensions for the Item on the Order Successfully |  |  | Ready for Testing

## Integration Test Cases
BBB
Client Code: |  | BBB
Process: |  | Integration
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 12
Test Cases Executed: |  | 12
Test Cases Passed: |  | 12
Test Cases Failed: |  | 0
% Complete: |  | 100%
Shopify and Zoho Integration Test Cases
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Integration
1 | Shopify Ecom Item Pull | 1.01 |  | Singlular Item Pull with ChannelListing Association |  |  |  | Pass
|  | 1.02 |  | Multiple Item Pulls with ChannelListing Associations in one transaction
|  | 1.03 |  | Intangible Item Pull with ChannelListing Association
|  | 1.04 |  | RTS vs. Non-RTS Item Test Cases
2 | Shopify Ecom Sales Order Pull | 2.01 |  | Single Sales Order Pull - 1 line, totalQty of 1 |  |  |  | Pass
|  | 2.02 |  | Multi-Line Sales Order Pull
|  | 2.03 |  | Any Type of Sales Order Including Intangible Line Item
|  | 2.04 |  | Singles vs. Multis OrderPull
3 | Shopify Ecom Outbound Inventory Sync | 3.01 |  | To confirm current inventory sending to Shopify, identify any items with a Shopify Ecom integration link |  |  |  | Pass
|  | 3.02 |  | Navigate to the Item's ChannelListing tab
3.03
|  | 3.04 |  | Verify that the Total ATP Qty API field column is present on the ChannelListing
3.05
|  | 3.06 |  | If zero value, repeat first three steps until able to find a non-zero value and verify quantity based on the Item's stockUnit records
4 | Shopify Ecom Ship Notice | 4.01 |  | Ship Notice for Single Line Sales Order |  |  |  | Pass
|  | 4.02 |  | Ship Notice for a multi-Line Sales Order
|  | 4.03 |  | Ship Notice for Any Type of Order Containing an Intangible Line Item
6 | Zoho/Data Exchange B2B Sales Order Pull | 6.01 |  | Single Sales Order Pull - 1 line, totalQty of 1 |  |  |  | Pass
|  | 6.02 |  | Multi-Line Sales Order Pull
|  | 6.03 |  | Any Type of Sales Order Including Intangible Line Item
7 | Zoho/Data Exchange Purchase Order Pull | 7.01 |  | Single-Line Purchase Order Pull - 1 line, totalQty of 1 |  |  |  | Pass
|  | 7.02 |  | Multi-Line Purchase Order Pull
|  | 6.03 |  | Any Type of Purchase Order Including Intangible Line Item
Shipping FedEx Test Cases
1 | Generate Fedex ShippingLabel with FedEx Ground shipVia | 1.01 |  | Test with any kind of order from Outbound Test Cases |  |  |  | Pass
2 | Generate Fedex ShippingLabel with FedEx 2Day shipVia | 2.01 |  | Test with any kind of order from Outbound Test Cases |  |  |  | Pass
3 | Generate Fedex ShippingLabel with FedEx Priority Overnight shipVia | 3.01 |  | Test with any kind of order from Outbound Test Cases |  |  |  | Pass
4 | Generate Fedex ShippingLabel with FedEx First Overnight shipVia | 4.01 |  | Test with any kind of order from Outbound Test Cases |  |  |  | Pass
5 | Generate Fedex ShippingLabel with FedEx SmartPost shipVia | 5.01 |  | Test with any kind of order from Outbound Test Cases |  |  |  | Pass
6 | Generate Fedex ShippingLabel with any Fedex service not listed above | 6.01 |  | Test with any kind of order from Outbound Test Cases |  |  |  | Pass

## UAT Prep Action Items
Item | Details | Owned By | Status | Notes
Item SKU Label | Request for New Label containing - Sku Number, Item Description, and Item UPC from Item Entity in order to assist with Testing | Deposco | Complete
Dummy Label | BBB has requested Deposco to create and print a dummy label to print after packing when the order in question has a Ship Outside System shipVia - Containing Order Number and Ship To Attention | Deposco/BBB | Complete
Inbound Testing | Testing of Inbound Transfer Order Receipt with BBB team | BBB | Complete
Outbound Testing | Testing of Outbound Transfer Order Fulfillment with BBB team | BBB | Complete
Continued Outbound Testing
Tuesday Working Session | Schedule Tuesday working session with Deposco & BBB teams | Deposco | Complete
Deposco Tasks | Deposco to figure out: rate shopping, address validation for residential, oubound inventory sync | Deposco | Complete
Fedex 3rd Party Shipping |  | Deposco/BBB | Complete
Receiving | Include Ship To Attention line after PO scanned in GenReceiving |  | Complete
Staging | Allow Staging Process to Occur in SingleScanPicking Process Between Pallet Picking anf Display order's Ship To Attention as the Staging Location as a screen message to the picking user | Deposco/BBB | Complete | For visibility on Validation Testing in my Comment: Please test the SingleScanPicking Process for Outbound Transfer Order Fulfillment Staging Capabilities by Navigating to Inbound --> B2B Picking; Following completion of Picking since Staging Locations will be separate from Shipping, use Move Container process to move Picking LPNs/Pallets to the Shipping Location Before Going Through AssignTripToContainer Process | Move Container to Store Staging Location after TO pick Move Container to "Shipping" prior to Assign Trip to Container to close out the TO

## End to End Testing
Test Scenario (Print validation) | Status | Team | Owner | Notes
Receiving
Receive full PO | Hold | BBB
Receive Partial PO | Hold | BBB
Receive damaged products | Hold | BBB
Receive Blind RMA order | Hold | BBB
Receive Blind Order | Hold | BBB
Receive Customer Return | Hold | BBB
Create RMA | Hold | BBB
Order Structure Scenarios
Ship Single Unit Order | Hold | BBB
Ship Multi Unit Order | Hold | BBB
Ship multi order in two boxes | Hold | BBB
Ship Express Singles | Hold | BBB
Ship Express Multis | Hold | BBB
Ship Wholesale Order | Hold | BBB
Ship Bulk Order | Hold | BBB
| Hold | BBB
| Hold | BBB
| Hold | BBB
Order Hold Scenarios
Address Validation Hold | Hold | BBB
Exception Scenarios
Select exception during SSPicking | Hold | BBB
Select exception during Batch Picking | Hold | BBB
Cancelation Scenarios
Fully cancel an order | Hold | BBB
Partially cancel an order | Hold | BBB
Partially cancel an order line | Hold | BBB

## Cutover Activities
BBB Cutover
BBB Cutover
Go Live Day - 09/09
Ref | Area Owner | Assigned Resource | Status | Task Description | Date | Time | Dependencies | Comments
Number | Task Owner | Task Owner |  | Cutover Week
Cutover Activities
1 | DEP | All | Complete | Code Freeze - no more changes in production | 2024-09-03
2 | BBB | Kenny | Complete | Warehouse prep - Location sequences,power, TVs, Guns | 2024-09-03
3 | DEP | Erica | Complete | Stand up production environment | 2024-09-04
4 | BBB | Rob | Complete | Set up integration and shipping account in Production | 2024-09-05
5 | BBB | Rob | Complete | Prepare DEP Production - Item Pull, Update weights, upload carts | 2024-09-05
6 | BBB | Kenny | Complete | Switch off fulfilling from previous system | 2024-09-06 | 10:00 |  | Fri (10 am - EOD), Sat (3 pm - Late)
7 | BBB | Kenny | In Progress | Cycle Count all Pick Face Locations | 2024-09-06 | 10:00 |  | Fri (10 am - EOD), Sat (3 pm - Late)
8 | BBB | Kenny | Open | Cycle Count all Reserve Locations | 2024-09-06
9 | DEP | Erica | Complete | Enable Daily Item History Scheduler | 2024-09-06
10 | BBB | Simon | Open | Flip API endpoints from staging to production | 2024-09-07 |  |  | Do we need what exactly needs to be flipped here? What statuses to be pushed to DEP?
11 | BBB | Kenny | Open | Validate each packstation is set-up to corresponding printers | 2024-09-07
12 | DEP | Isaac | Open | Enable Sockets and and Schedulers | 2024-09-08 | 12:00
13 | BBB | Rob/Simon | Open | Pull open Sales Orders into Deposco from Shopify | 2024-09-08 | 13:00
14 | DEP | Isaac | Open | Enable all DEP socket endpoints in each direction | 2024-09-09 | 8:00
15 | DEP | Erica | Open | Clean up production environment of all test data (if any) | 2024-09-09 | 8:30
16 | DEP | Erica | Open | Stock unit export from DEP, to be emailed to Steve/Rob | 2024-09-09 | 9:00
17 | DEP | Erica | Open | Update and Turn on Socket Alerts | 2024-09-09 | 9:15
18 | BBB | Rob | Open | Confirm all orders are in DEP | 2024-09-09 | 9:15
19 | DEP | Isaac | Open | Push Inventory to Shopify | 2024-09-09 | 9:30
20 | BBB | Kenny | Open | Run Wave schedulers to release orders | 2024-09-09 | 9:45
21 | BBB | Kenny | Open | Review all waves are created as expected | 2024-09-09 | 10:00
22 | BBB | Kenny | Open | Begin Fulfilling orders | 2024-09-09 | 10:30

## GoNo-Go Decision
Factors | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Due Date | Comment | BBB Team Tested | DEP Team Tested
| Deposco Setup | 80 |  |  |  | 70
Deposco Setup | Printer Details | 10 |  | BBB | 100% | 10 | Are all printers configured? |  |  | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | BBB | 100% | 10 | Are all print stations setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | BBB | 100% | 10 | All reports assigned to printers and resources? |  |  | FALSE | FALSE
Deposco Setup | RF Scanners/Handheld Devices | 10 |  | BBB | 100% | 10 |  |  |  | FALSE | FALSE
Deposco Setup | Label Printers | 10 |  | BBB | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 |  | BBB | 100% | 10 | Are the report documents configured to print on the proper printers? Are some reports configured with device overrides (e.g. processing area printers). |  |  | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | Deposco | 0% | 0 | Have all High and Critical issues from the issues list been resolved? |  |  | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release - Cycle Counts | 10 |  | Deposco | 100% | 10 | Backups, day, month end jobs. |  | Base schedulers are set up, will start them closer to go live | FALSE | FALSE
| Warehouse Prep | 40 |  |  |  | 0
Warehouse Prep | Location Labels | 10 |  | BBB | 100% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 10 | Y | BBB | 80% | 0 | Procure Carts for moving of inventory and label them |  |  | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 10 |  | BBB | 100% | 0 | Item inventory barcoded and labeled to scan |  |  | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 |  | BBB | 100% | 0 | Is the connectivity strong and cover all necessary scan areas? |  |  | FALSE | FALSE
| Standard Operating Procedure Documentation | 90 |  |  |  | 14
Standard Operating Procedures | Receiving | 10 | Y | BBB | 20% | 0 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Putaway | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Picking | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Picking | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Packing | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Packing | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | LTL Shipping (Wholesale) | 10 | Y | BBB | 20% | 2 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
Standard Operating Procedures | Customer Order Creation/Updates/Waving | 10 | Y | BBB | 0% | 0 | SOP's been written? Online Help, plus BBB-specific. Start with BBB template. |  |  | FALSE | FALSE
| Training & Testing | 50 |  |  |  | 39.5
Training & Testing | Business Scenarios Definition | 10 | Y | BBB | 75% | 7.5 | Define all Business scenario including exception processes Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Process Training and Testing - Receiving - Putaway - Cycle Counting - Parcel Picking - Parcel Packing - LTL Shipping - Shipping | 10 | Y | BBB | 85% | 8.5 | Unit and End to End Test Case Execution |  |  | FALSE | FALSE
Training & Testing | User Acceptance Testing | 10 |  | BBB | 90% | 9 | Execute all defined business scenarios within Deposco |  |  | FALSE | FALSE
Training & Testing | Supervisor/Administrator | 10 |  | BBB | 95% | 9.5 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | End-user | 10 | Y | BBB | 50% | 5 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
| Configurations/Master Data | 80 |  |  |  | 66.5
Configurations | Inventory Validation | 10 | Y | BBB | 20% | 2 | Putaway Audits |  |  | FALSE | FALSE
Configurations | Items | 10 | Y | BBB | 85% | 8.5 | Are all items setup? Are all of the units of measure defined for each item? |  |  | FALSE | FALSE
Configurations | Zones | 10 |  | BBB | 100% | 10 | Have all of the Zone and Zone Location records been set up? Has the pick flow been tested? |  |  | FALSE | FALSE
Configurations | Locations | 10 |  | BBB | 100% | 10 | Are the location types, zones, and location masters configured accurately. |  |  | FALSE | FALSE
Configurations | Menu Structures | 10 |  | BBB | 90% | 9 | Have the appropriate menu levels been created for the different departments? |  |  | FALSE | FALSE
Configurations | Packs (UOMs) / Pack UPCs | 10 |  | BBB | 100% | 10 | Have all valid pack types been entered into the system? |  |  | FALSE | FALSE
Configurations | Containers | 10 | Y | BBB | 70% | 7 | Pallets, bins, carts |  |  | FALSE | FALSE
Configurations | Kit/Component Relationships | 10 | Y | BBB | 100% | 10 | KitHeaders/KitDetails for Kit to Stock Item/Component for Kit to Order |  |  | FALSE | FALSE
| Cutover and Conversion Plans | 10 |  |  |  | 9
Cutover and Conversion Plans | Cutover plan developed | 10 |  | Deposco | 90% | 9 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  |  | FALSE | FALSE
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 45
Interfaces - Imports to Deposco | Carton Types from BBB to Deposco | 10 |  | BBB | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Locations/Zones from BBB to Deposco | 10 |  | BBB | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Items/Packs from BBB to Deposco | 10 |  | BBB | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Inventory from BBB to Deposco | 5 |  | BBB | 100% | 5 | Is the interface accurate and does it meet the customer's production needs? |  | tested | FALSE | FALSE
Interfaces - Imports to Deposco | Purchase Orders from BBB to Deposco | 10 |  | BBB | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Integrations | 80 |  |  |  | 74
Integrations with Deposco | Items | 10 |  | BBB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Trading Partner | 10 | Y | BBB | 100% | 10 |  |  | Have one | FALSE | FALSE
Integrations with Deposco | Purchase Order | 10 | Y | BBB | 90% | 9 |  |  |  | FALSE | FALSE
Integrations with Deposco | Inv Adjustments & Inv Transfer | 10 | Y | BBB | 50% | 5 |  |  |  | FALSE | FALSE
Integrations with Deposco | Ship Notice | 10 | Y | BBB | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Purchase Order | 0 | Y | BBB | 0% | 0 |  |  |  | FALSE | FALSE
Integrations with Deposco | Field Mappings | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Data Exchange Configs - v1 vs v2 | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Carrier BBB Socket Setup and Validated | 10 |  | BBB | 100% | 10 |  |  |  | FALSE | FALSE
| Interfaces - Exports From Deposco | 0 |  |  |  | 0
Interfaces - Exports From Deposco | Shipment Confirmation from Deposco to Email* | 0 |  | Deposco | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Reports and Labeling | 60 |  |  |  | 60
Reports and Labeling | Shipping Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  | FedEx label is printing appropriately | FALSE | FALSE
Reports and Labeling | Location Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Item Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | LPN Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Carton Type Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Packing Slip | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | Deposco BBB | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? |  |  | FALSE | FALSE
| Total Weighted Score: | 388
| Total Possible Score: | 545
| Total Percentage: | 71.19%
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Go-Live Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | STATUS | TEAM | OWNER | Date Opened | Due Date | Date Completed | Next Steps
Inventory Discrepancy | CycleCounted Inventory in Deposco is different between what's reocrded in Shopify | Issue | 3-High(Impacting our path during go-live but able to work around or deal) | 3 (High) | Completed | BBB Team | Warehouse team | 2024-09-09 | 2024-09-11 |  | BBB Team currently going through recounting the inventory shown to be different
Socket Alerts | Set-up Socket Alerts in production | Go-Live Cutover Task | 4-Low (No impact to path to completion) | 4 (Low) | Completed | DEP Team |  |  |  | 2024-09-09
Printing Orientation | Fixed printing orientation of shippingLabel to print shippingLabel with bottom of label text to print first | Request | 5- NTH (Nice to Have) | 5 (NTH) | Completed | DEP Team |  | 2024-09-09 |  | 2024-09-09
Invalid Shipping Service | When BBB pulls in Ecom Sales Orders from Shopify, update POI to update the current status with the following conditions: - Empty Order shipVia - "Hold - Empty Shipping Service" - Invalid Order shipVia - "Hold - Invalid Shipping Service" | Request | 3-High(Impacting our path during go-live but able to work around or deal) | 3 (High) | Completed | DEP Team |  | 2024-09-09 |  | 2024-09-10
AutoPick Functionality | Allow for 500 Outbound Transfer Orders to utilize AutoPick Workflow Process for Picking in order to Bypass Validating Order contents Typical for Picking | Request | 5- NTH (Nice to Have) | 5 (NTH) | Completed | DEP Team |  | 2024-09-09 |  | 2024-09-09
AutoPick Capabilities | Accessories Needed in AutoPick Workflow Process Necessary for BBB warehouse functions: - Print "LTL and B2B Label" at end of AutoPicking process - Allow for pickwave to contain multiple Outbound Transfer Orders to print "LTL and B2B Label" for multiple orders | Request | 4-Low (No impact to path to completion) | 4 (Low) | Completed | DEP Team |  | 2024-09-09 |  | 2024-09-10
Receipt Push to Zoho | Identify best path forward to pull receipts into Zoho | Issue | 2-Critical (Critical to go-live) | 2 (Critical) | Completed | BBB Team | Simon | 2024-09-10 |  | 2024-09-11
Shopify Location Switching | Shopify payload not updated when location ID for order line is updated. Solution - add tag | Issue | 2-Critical (Critical to go-live) | 2 (Critical) | Completed | BBB Team | Simon (tags to Shopify orders) | 2024-09-10 |  |  | OM team may need to be involved with process change if Simon's flag solution doesn't work
Faulty Ecom Sales Order Pulls | We've identified faulty Sales Order Pulls from Shopify in the Following Scenarios, orders are set to Voided status in all scenarios: - Order was partially Fulfilled in Shopify, the rest of the Sales Order pulled in Deposco - Order was Fulfilled in Shopify, Order pulled in with no orderLines to fulfill in Deposco, meaning the only orderLines available are already in "Complete" status (Cutover Behavior) - Order was Fulfilled in Shopify, Order pulled in with no orderLines at all | Issue | 3-High(Impacting our path during go-live but able to work around or deal) | 3 (High) | Completed | DEP Team |  | 2024-09-09 |  | 2024-09-10
Opportunistic Cycle Counting | Trigger Cycle Count when PIcking Item picks last item at a location? | Request | 4-Low (No impact to path to completion) | 4 (Low) | Open | DEP Team
Platform Error | When clicking into outbound transfer order TO-T9-091124-504-009 in the Orders table, BBB user is receiving the following error pop-up: "could not extract result set..." | Issue | 3-High(Impacting our path during go-live but able to work around or deal) |  | Completed | DEP Team |  | 2024-09-18 |  |  | Attempts to replicate same error with Dep user, but was unsuccessful in attempt; requesting BBB user to confirm steps to replicate and possibly provide screen recording of error if possible
Compiling Script Error | Error appearing due to requested rules to not allow users to scan a Transient container if it is already tied to a different order/pickwave; rules were originally input week of go-live but it was noticed on 9/18 that further tweaks on the rules were needed in order to avoid the Compiling Script Error from appearing | Issue | 3-High(Impacting our path during go-live but able to work around or deal) | 3 (High) | Validation | BBB Team | Still recieving Type error...we imported LPNPallet containers to bridge this gap in the mean time | 2024-09-18 |  |  | Update 9/20 - DEP noticed that a null check in Business Rules that were originally written contained a typo as the logic was transferrred over from UA environment; BBB team should no longer be receiving the Compiling Script Error anymore, but currently in Validation phase for their team to verify
B2B and LTL Label Update | Request to only print the B2B and LTL Label for the Pallet # that is scanned from the ATTC process, currently gathering more details from email to confirm this is what they're wanting even when an order can be tied to multiple pallets that aren't the ones necessarily getting scanned | Request | 5- NTH (Nice to Have) | 5 (NTH) | Validation | BBB Team |  |  |  |  | Update 9/20 - DEP suggested creating two different versions of the same Label, one with Order.number as the parameter and another with lpnNumber as the parameter; BBB contact agreed to have this set-up and are currently testing each process in UA Environment with this change Update 9/30 - BBB's Feedback from previous Set-up presented use-case of the need to reprint the Label with different parameters. Config on Admin --> Print LTL and B2B Label - OrderHeader and Print LTL and B2B Label - Container Options are available in UA and currently in testing on BBB team
Generating FedEx labels outside of Deposco | Need to understand all steps that need to happen if we needed to generate FedEx shipping labels outside of Deposco, but still use Deposco to pick and pack | Issue | 2-Critical (Critical to go-live) | 2 (Critical) | Open | DEP Team