## On-site Design AI (hidden)
| On-site Design Action Items |  |  | 1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
ITEM # | DESCRIPTION | CREATE DATE | DUE DATE | OWNER | PRIORITY | STATUS | TEAM | OWNER | CREATED | ETA | NOTES

## Task Tracker
BL101 Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
CATEGORY | DESCRIPTION | TYPE | STATUS | OWNER | SEVERITY | PRIORITY | UAT Critical? | Go Live Critical? | Due Date | DEP Comments | BL101 Comments
Design | Provide sample of shipping labels | Task | Closed | BL101 |  |  | FALSE | FALSE |  | Parker requested via email 11/19
Design | Setup Carrier Shipping Accounts (stamps.com & UPS) | Task | Closed | BL101 |  |  | FALSE | FALSE |  | Parker requested via email 11/19
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE

## Design Parking Lot
Design Parking Lot
ITEM # | DETAILS | PRIORITY | ADDITIONAL DETAILS
1 | Shipment consolidation | Phase 2 | Currently using Shipstation

## Reporting Requirements
Reports
BL101 REQUESTED REPORTS | TYPE | STATUS | ADDITIONAL DETAILS

## Demo Schedule + Recordings (hidden)
Recordings
DATE | TOPIC | PROPOSED TIME | LINK | PASSWORD | COMMENTS

## On-site UAT Issue Log
On-site UAT Issue Log
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
DATE REPORTED | ISSUE DESCRIPTION | TYPE | STATUS | TEAM | OWNER | SEVERITY | PRIORITY | GO LIVE CRITICAL? | DUE DATE | DEP COMMENTS | BL101 COMMENTS
2025-03-26 | Wifi Spotty in the WH | Facility Setup | In Progress | BL101 | Wasif |  |  | TRUE | 2025-04-04 |  | Handheld load testing hasn't been completed. Routers do not seem to be the issue.
2025-03-26 | Warehouse Location Labeling not complete | Facility Setup | In Progress | BL101 | David |  |  | TRUE | 2025-04-11 |  | Most are labeled, list of 700 ish locations bc import didn't show in Deposco. Ls do not show up - error message about duplicate records
2025-03-26 | Secondary building(Wholesale) Location not finalized | System Setup | In Progress | BL101 | David |  |  | TRUE
2025-03-26 | End Users still not in the system only super users | Process SOP | In Progress | BL101 | David |  |  | TRUE | 2025-04-11
2025-03-26 | Location not finalized and No Racking in Denver | Facility Setup | In Progress | BL101 | Dennis |  |  | TRUE |  |  | Discussing today to finalize plans for layout
2025-03-26 | SPS testing/validation pending | Integration | In Progress | BL101 | Wasif |  |  | FALSE | 2025-04-11 |  | Waiting on more orders from SPS
2025-03-26 | Saved Searches pending to be created in NS | Integration | Open | BL101 | Wasif |  |  | FALSE |  |  | Working with CCC to determine workflow
2025-03-26 | Testing fulfllment with good sales order in NS pending | Integration | Open | BL101/ DEP |  |  |  | FALSE |  | Good refers to data accuracy
2025-03-26 | NS team finalizing supply chain allocation/commitments | Integration | Open | BL101 |  |  |  | FALSE
2025-03-26 | B2B flow testing pending with Dep | Process SOP | Open | BL101/ DEP |  |  |  | TRUE |  | Once SPS integration is finalized, we will start on this
2025-03-26 | B2B data setup pending in Dep | System Setup | Open | BL101/ DEP |  |  |  | TRUE
2025-03-26 | Container Labeling not complete | Facility Setup | Open | BL101 | David |  |  | FALSE |  |  | Same with Locations, would want to import those
2025-03-26 | Additional Printer Setup and testing | System Setup | In Progress | BL101 | Wasif |  |  | FALSE |  |  | 1 is on Deposco, 2 are setup but not on Deposco, ordering 4 more
FALSE
FALSE
FALSE
FALSE

## Go Live Items
Go - Live Issue Log
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
DATE REPORTED | ISSUE DESCRIPTION | TYPE | STATUS | TEAM | OWNER | SEVERITY | PRIORITY | EXPECTED DELIVERY DATE | DEP COMMENTS | BL101 COMMENTS
2025-06-02 | Inventory Adjustments Failing | Issue | Resolved | BL101 / DEP | Parker | Critical | 2 | 2025-06-06 | Not sending adjustments and transfers to NS causing inventory discrepancies. Sean M able to assist to resolve
2025-06-02 | Item not existing in Deposco from NS | Issue | Resolved | BL101 | Wasif | High | 3 | 2025-06-06 | Prevents orders from correctly creating in Deposco
2025-06-02 | No inventory for Items | Issue | In Progress | BL101 | Dave | High | 3 | 2025-06-06 | Order routing backordering orders preventing them to be fulfilled (POs waiting to be received)
2025-06-02 | Locating inventory in Pick Face locations | Task | In Progress | BL101 | Warehouse Team | High | 4 | 2025-06-06 | Order not getting waved preventing running through the backlog
2025-06-04 | Third Party Shipping for B2B Partners | Request | Open | BL101 / DEP | Nick Bland | Medium | 5 |  | Is only impacting one partner. Current method to ship outside system and generate the tracking label using Ship Station
2025-06-04 | Transfer Order Picking - change from grocery scan to qty entry | Request | Needs Info | DEP | Parker | Medium | 4 | 2025-06-04 | Changed qty prompt threshold in transfer order picking from 0 to 5. All transfer orders are now qty entry picking
2025-06-05 | Multis group picking - carts would not fit down the aisles | Issue | Resolved | BL101 / DEP | Parker | High | 1 | 2025-06-05 | originally grouping 12 orders but changed to 1 for multis, couldn’t get carts down the aisles, this means more waves, david was happy with this & it’s going well.

## Pre-Cutover Activities
PRE-CUTOVER ACTIVITIES
BL101 PRE-CUTOVER STEPS
Purpose: Organize all tasks that are to be executed in preparation for deployment.
ITEM # | TEAM OWNER | ASSIGNED RESOURCE | % COMPLETE | TASK DESCRIPTION | INITIAL ETA | TARGET DATE | COMPLETION DATE | REQUIRED COMPLETION DATE | DEPENDENCIES | COMMENTS
BL101
1 | BL101 |  | 0% | Upload/Create all Locations to Deposco
2 | BL101 |  | 0% | Scanners at each workstation
3 | BL101 |  | 0% | Validate Pack Station laptops
4 | BL101 |  | 0% | Validate Scales
5 | BL101 |  | 0% | Set up pack stations
6 | BL101 |  | 0% | Set up printers (Print BL101 is setup, printers are on same device)
7 | BL101 |  | 0% | Set up wifi
8 | BL101 |  | 0% | Configure packstations as a resource and assign printers
9 | BL101 |  | 0% | Shipping Label - print out and validate
10 | BL101 |  | 0% | Packing Slip - print out and validate
11 | BL101 |  | 0% | End User Configuration
12 | BL101 |  | 0% | Continued Super User Training
13 | BL101 |  | 0% | User Training (Happy Path and Exception Scenarios)
14 | BL101 |  | 0% | Validate/Test integration schedulers for Deposco are working
15 | BL101 |  | 0% | Review Scheduler Frequencies
16 | BL101 |  | 0% | Review Waving Logic
17 | BL101 |  | 0% | Build SOP document for entire solution. Leave a relevant copy at each given area (packing sections for pack stations)
18 | BL101 |  | 0% | Validate all Locations in proper zones
19 | BL101 |  | 0% | Test with all set-up Printers
20 | BL101 |  | 0% | Repull product data into production
DEPOSCO
1 | DEP |  | 0% | Build system monitoring queries
2 | DEP |  | 0% | Wipe out test orders
3 | DEP |  | 0% | Review each packstation is configured as a resource
4 | DEP |  | 0% | Validate all master data has been configured
5 | DEP |  | 0% | Review Waving Logic
6 | DEP |  | 0% | Purge Transactional Data
7 | DEP |  | 0% | Validate all schedulers are enabled for production environment
8 | DEP |  | 0% | Validate all Integration changes needed are in production environment
9 | DevOps |  | 0% | Build Production environment
10 | DevOps |  | 0% | Add socket credientals to Production environment
11 | DEP |  | 0% | Wipe product data

## Cutover Activities
CUTOVER ACTIVITIES
BL101 CUTOVER TASKS
CUTOVER DAY
ITEM # | TASK OWNER | ASSIGNED RESOURCE | STATUS | TASK DESCRIPTION | PLANNED COMPLETION DATE | ACTUAL FINISH DATE | DEPENDENCIES | COMMENTS
1 | BL101 |  | Open | Validate each pack station is setup to coresponding printers
2 | BL101 |  | Open | Upload inventory into Deposco
3 | BL101 |  | Open | Enable Sockets and Schedulers
4 | DEP |  | Open | Enable all socket endpoints in each direction
5 | DEP |  | Open | Enable BL101 endpoints
6 | BL101 |  | Open | Pull open Sales Orders into Deposco
7 | BL101 |  | Open | Create open Purchase Orders into Deposco
8 | BL101 |  | Open | Do and end to end smoke tests with some POs and SOs
9 | DEP |  | Open | Wipe out end to end test orders
10 | DEP |  | Open | Remove non-admin users from UA Environment

## GoNo-Go Decision
Go/No-Go Decision
FACTORS | DETAILS | WEIGHT | CRITICAL? | OWNER | % COMPLETE | SCORE | ANALYSIS | DUE DATE | COMMENT | BL101 TEAM TESTED | DEP TEAM TESTED
| Deposco Setup | 80 |  |  |  | 71.5
Deposco Setup | Printer Details | 10 |  | BL101 | 95% | 9.5 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  | 3 of 13 printers setup in NY 2 need in CO 4/28 - ordered printers, arriving today | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | BL101 | 95% | 9.5 | Are all printers stations/resources set up with the appropriate printers? |  | Will need DEP assistance during testing/training sessions | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | BL101 | 95% | 9.5 | Are all printer assignments set up on the appropriate printers (shipping label, packing slip, customs docs, item label, LPN label)? |  | Will need DEP assistance during testing/training sessions | FALSE | FALSE
Deposco Setup | RF Scanners/Handheld Devices | 10 |  | BL101 | 95% | 9.5 | Are all handheld units configured? Are all of the handhelds working correctly? |  | Complete for NY (25) TBD for CO (5 ready, may need more). Wasif making changes to them | FALSE | FALSE
Deposco Setup | Label Printers | 10 |  | BL101 | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 |  | BL101 | 100% | 10 | Are the report documents configured to print on the proper printers? Are some reports configured with device overrides (e.g. processing area printers). |  |  | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | Deposco | 40% | 4 | Have all High and Critical issues from the issues list been resolved? |  | Waiting on SPS mapping info | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release - Order - Item - Incremental Inv Sync - POI for PO's - Cycle Counts | 10 |  | Deposco | 95% | 9.5 | Backups, day, month end jobs. All jobs have been scheduled. Order Pull, Item Pull, Inventory Sync, Cycle Counts, Replenishments, Waving |  |  | FALSE | TRUE
| Warehouse Prep | 40 |  |  |  | 36
Warehouse Prep | Location Labels | 10 |  | BL101 | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 10 |  | BL101 | 100% | 10 | Procure Carts for moving of inventory |  |  | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 10 | Y | BL101 | 80% | 8 | Item inventory barcoded and labeled to scan |  |  | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 | Y | BL101 | 80% | 8 | Is the connectivity strong and cover all necessary scan areas? |  | Need to test wholesale side & test w/ multiple users - testing this week 5/23 | FALSE | FALSE
| Standard Operating Procedure Documentation | 80 |  |  |  | 75
Standard Operating Procedures | Receiving | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Putaway | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Picking | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Picking | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Packing | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Packing | 10 |  | BL101 | 100% | 10 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  |  | FALSE | FALSE
Standard Operating Procedures | Customer Order Creation/Updates/Waving | 10 | Y | BL101 | 50% | 5 | SOP's been written? Online Help, plus BL101-specific. Start with BL101 template. |  | David & Wasif setting up time to complete | FALSE | FALSE
| Training & Testing | 50 |  |  |  | 46
Training & Testing | Business Scenarios Definition | 10 | Y | BL101 | 85% | 8.5 | Define all Business scenario including exception processes Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Process Training and Testing - Receiving - Putaway - Cycle Counting - Parcel Picking - Parcel Packing - Transfer Orders - Shipping | 10 |  | BL101 | 90% | 9 | Unit and End to End Test Case Definition |  | Need guidance on Cycle Counting process & staging - will discuss in a training session next week | FALSE | FALSE
Training & Testing | User Acceptance Testing | 10 |  | BL101 | 95% | 9.5 | Execute all defined business scenarios within Deposco |  |  | FALSE | FALSE
Training & Testing | Supervisor/Administrator | 10 |  | BL101 | 95% | 9.5 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | End-user | 10 |  | BL101 | 95% | 9.5 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
| Configurations/Master Data | 70 |  |  |  | 69
Configurations | Inventory Validation | 10 |  | BL101 | 100% | 10 | Putaway Audits |  |  | FALSE | FALSE
Configurations | Items | 10 |  | BL101 | 100% | 10 | Are all items setup? Are all of the units of measure defined for each item? |  |  | FALSE | FALSE
Configurations | Zones | 10 |  | BL101 | 100% | 10 | Have all of the Zone and Zone Location records been set up? Has the pick flow been tested? |  | All zones have been uploaded, may need cleanup | FALSE | FALSE
Configurations | Locations | 10 |  | BL101 | 90% | 9 | Are the location types, zones, and location masters configured accurately. |  | All locations have been uploaded, may need cleanup | FALSE | FALSE
Configurations | Menu Structures | 10 |  | BL101 | 100% | 10 | Have the appropriate menu levels been created for the different departments? |  |  | FALSE | FALSE
Configurations | Packs (UOMs) | 10 |  | BL101 | 100% | 10 | Have all valid pack types been entered into the system? |  |  | FALSE | FALSE
Configurations | Containers | 10 |  | BL101 | 100% | 10 | Pallets, bins, carts |  |  | FALSE | FALSE
| Cutover and Conversion Plans | 10 |  |  |  | 4
Cutover and Conversion Plans | Cutover plan developed | 10 | Y | Deposco | 40% | 4 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  |  | FALSE | FALSE
| Interfaces - Imports/Exports with Deposco | 40 |  |  |  | 37
Interfaces - Imports to Deposco | Items from BL101 to Deposco | 10 |  | BL101 | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Customer Orders from BL101 to Deposco | 10 | Y | BL101 | 70% | 7 | Is the interface accurate and does it meet the customer's production needs? |  | ecomm tested correctly, edi orders came in but waiting on package contents to send data back, manual orders created in NS - got stuck on those - releated to sps mapping ticket | FALSE | FALSE
Interfaces - Imports to Deposco | Locations/Zones from BL101 to Deposco | 10 |  | BL101 | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Items/Packs from BL101 to Deposco | 10 |  | BL101 | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Integrations | 40 |  |  |  | 38
Integrations with Deposco | Netsuite Socket - Item/Channel Listing - Customer Order | 10 | Y | BL101 | 80% | 8 |  |  |  | FALSE | FALSE
Integrations with Deposco | Field Mappings | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Data Exchange templates - UPCs - Pack BL101 Dimensions/Weights - Locations/Zones | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Carrier BL101 Socket Setup and Validated - UPS (Online Tools) - USPS (Stamps) | 10 |  | BL101 | 100% | 10 |  |  |  | FALSE | FALSE
| Interfaces - Exports From Deposco | 10 |  |  |  | 8
Interfaces - Exports From Deposco | Shipment Notice from Deposco to Netsuite | 10 | Y | Deposco | 80% | 8 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Reports and Labeling | 40 |  |  |  | 40
Reports and Labeling | Shipping Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Location Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Item Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | LPN Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | Deposco BL101 | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? |  |  | FALSE | FALSE
| Total Weighted Score: | 434.5
| Total Possible Score: | 470
| Total Percentage: | 92.45%
| Go Live Recommendation: | Yes | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Future (hidden)
Potential Future Cases
ITEM # | DETAILS | NOTES | TIMELINE

## Test Case Summary
BL101 Testing Summary
BL101: |  | BL101
BL101 Code: |  | BL101
Buiness Unit: |  | Multiple
Test Cases Required: |  | #REF!
Test Cases Executed: |  | #REF!
Test Cases Remaining: |  | #REF!
Test Cases Passed: |  | #REF!
Test Cases Failed: |  | #REF!
% Complete: |  | #REF!
Process | Test Cases Required | Test Cases Complete | Test Cases Failed | % Complete
Receiving | 0 | 0 | 0 | #DIV/0!
Inventory Management | 0 | 0 | 0 | #DIV/0!
Picking | 0 | 0 | 0 | #DIV/0!
Packing | 0 | 0 | 0 | #DIV/0!
Waves (Build and Release Logic) | #REF! | #REF! | #REF! | #REF!
Data Imports | 5 | 0 | 0 | 0%
Integration | 0 | 0 | 0 | #DIV/0!
Order Management | #REF! | #REF! | #REF! | #REF!
UAT/Go-Live Checklist | Status
Test Cases | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Inbound (hidden)
BL101: |  | BL101
BL101 Code: |  | BL101
Process: |  | Receiving
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receiving Purchase Order Test Cases
1 | PO Receiving | 1.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen
|  | 1.02 |  | Select Purchase Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 1.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 1.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 1.05 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 1.06 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 1.07 |  | Keep repeating step 1.03 - 1.05 if there are multiple items in the order that you are receiving until all items have been received | PO is fully received
2 | ITO Receiving | 2.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen
|  | 2.02 |  | Select Inbound Transfer Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 2.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 2.04 |  | Scan/Key Item you are receiving (list of items on the ITO will be provided in the list box) | item is entered
|  | 2.05 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 2.06 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 2.07 |  | Keep repeating step 2.03 - 2.05 if there are multiple items in the order that you are receiving until all items have been received | ITO is fully received
3 | Blind Order Receiving | 3.01 |  | Select Blind Receiving from Admin menu on Handheld | moves to general receiving screen
|  | 3.02 |  | Select Blind Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 3.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 3.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 3.05 |  | Hit Enter | If Print Label was checked yes, user is prompted print item label screen
|  | 3.06 |  | Keep repeating step 3.03 - 3.05 if there are multiple items in the order that you are receiving until all items have been received
|  | 3.07 |  | Hit Finish
4 | Hot Pick Putaway | 4.01 |  | Select Move Stock from the Inbound menu
|  | 4.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 4.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 4.04 |  | Scan/Enter the Hot Pick Item you are moving | item is entered
|  | 4.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 4.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 4.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 4.08 |  | Enter the Item and the Quantity that will be moved
|  | 4.09 |  | User will then see a listbox of eligible Hot Pick locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 4.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
5 | Reserve Putaway | 5.01 |  | Select Move Stock from the Inbound menu
|  | 5.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 5.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 5.04 |  | Scan/Enter the Items you are moving to a Reserve location | item is entered
|  | 5.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 5.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 5.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 5.08 |  | Enter the Item and the Quantity that will be moved
|  | 5.09 |  | User will then see a listbox of eligible Reserve locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 5.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
6 | Speed Cell Putaway | 6.01 |  | Select Move Stock from the Inbound menu |  | All results as expected
|  | 6.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 6.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 6.04 |  | Scan/Enter the Hot Pick Item you are moving | item is entered
|  | 6.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 6.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 6.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 6.08 |  | Enter the Item and the Quantity that will be moved
|  | 6.09 |  | User will then see a listbox of eligible Hot Pick locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 6.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
7 | Miniatures Putaway | 7.01 |  | Select Move Stock from the Inbound menu
|  | 7.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 7.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 7.04 |  | Scan/Enter the Items you are moving to a Miniatures location | item is entered
|  | 7.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 7.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 7.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 7.08 |  | Enter the Item and the Quantity that will be moved
|  | 7.09 |  | User will then see a listbox of eligible Miniatures locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 7.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
8 | Product Category Putaway | 8.01 |  | Select Move Stock from the Inbound menu
|  | 8.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 8.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 8.04 |  | Scan/Enter the Item you are moving | item is entered
|  | 8.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 8.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 8.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 8.08 |  | Enter the Item and the Quantity that will be moved
|  | 8.09 |  | User will then see a listbox of eligible Category Zone locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 8.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
9 | PO Receiving (with Item Image Display) | 9.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen
|  | 9.02 |  | Select Purchase Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 9.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 9.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 9.05 |  | On the bottom right of your screen, you will see "View Item" button. If you want to display the item image, click "View Item" | "View Item" screen will pop up. You will be able to see item image
|  | 9.06 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 9.07 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 9.08 |  | Keep repeating step 1.03 - 1.05 if there are multiple items in the order that you are receiving until all items have been received | PO is fully received
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receive by item
1 | Receive By Item | 1.01 |  | Select Receive By item from Inbound menu on Handheld
|  | 1.02 |  | Scan/Key Item you are receiving | User is Prompted to Receiveing order screen to select order
|  | 1.03 |  | Select Order from order list | User is Prompted to Receive Item screen to receive item
|  | 1.04 |  | Select Pack type and enter quantity | selected item is received and move back to Receiving Item Screen
|  | 1.05 |  | Keep repeating step 1.03 - 1.04 if there are multiple items in the order that you are receiving until all items have been received
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Print Item label
1 | Print Item Label Through Process Action Link | 1.01 |  | Go to Master Data-> Items-> Select an item | Message: Succesfully printed 1 of report [Item Label] for each Item
|  | 1.02 |  | Select the Actions drop down menu-> Print Item Label
|  | 1.03 |  | Select your printer-> Print
2 | Print Item Label Through Handheld | 2.01 |  | Handheld-> Admin-> Print Item Label | Message: Report [Item Label] succesfully printed. | All Results as Expected
|  | 2.02 |  | Scan/ Enter the Item Number
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receiving Edge Cases
1 | Incorrect PO# Entry | 1.01 |  | Navigate to the General Receiving button found in the Inbound Menu | A message should dispay reading, "Purchase Order _____ does not exist" | Result as Expected
|  | 1.02 |  | Enter a PO Number that does not exist
2 | Scanning Already Received PO | 2.01 |  | User enters Receiving Process | Error message appears reading, "There are no lines eligible to receive for this order". | Result as Expected
|  | 2.02 |  | User scans a Purchase Order that has already been received instead of a new Purchase Order
|  | 2.03 |  | User will be prevented from continuing with the process
3 | Attempt to Finish without Receiving Item | 3.01 |  | User will enter General Receiving button | Message will populate indicating nothing has been received from the associated PO | Result as Expected
|  | 3.02 |  | User hits "Finish/Exit"
|  | 3.03 |  | If nothing has been received, user will receive message "You have not received any item for order [_____]"
4 | Receiving an existing Item not on a PO | 4.01 |  | User will enter receiving transaction | Error message appears reading, "Please enter a valid SKU for [PO Number]." | Result as Expected
|  | 4.02 |  | User scans/Keys an Item not on PO for receiving
|  | 4.03 |  | User will be prevented from receiving the item in the process
5 | Negative Item Qty Entry | 6.01 |  | During General Receiving, user keys in a negative quantity to be received | Error message appears reading, "Please enter a valid quantity." | Result as Expected
|  | 6.02 |  | User will be prompted to re-enter quantity
6 | Invalid Item Qty Entry | 7.01 |  | During General Receiving, user keys in an invalid number like "2YN" | Error message appears reading, "Please enter a valid quantity." | Result as Expected
|  | 7.02 |  | User will be prompted to re-enter quantity
7 | Over-Receive a PO | 7.01 |  | During General Receiving, user keys in quantity that is greater than the order pack quantity | Message should appear reading "You can only receive up to the max amount (QTY) of Each."
9 | Attempt to Over-Receive over 25% | 9.01 |  | During General Receiving, user keys in quantity that is greater than the order pack quantity (over 25%) | Error message appears reading "You can only receive up to a maximum of [125%] of Each" | Message stated "You can only receive up to the max amount of 6 of each" when attempting to receive 20
|  | 9.02 |  | User will be prevented from receiving the item in the process as it exceeds the over-receipt threshold of 25%
8 | Undo Receipt | 8.01 |  | Navigate to the 'Undo Receipt' button in the Inbound menu on the handheld
|  | 8.02 |  | Enter the order header number of the order needed to be unreceivied
|  | 8.03 |  | Scan the item to be unreceived and enter the quantity to be decremented from the current received quantity. Container is not required but can be scanned to put the item into when unreceiving
|  | 8.04 |  | Press enter or select submit

## Data Exchange (hidden)
BL101: |  | BL101
BL101 Code: |  | BL101
Process: |  | Imports
Date Updated:
Test Cases Required: |  | 5
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | 0%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Test Notes | Pass/Fail | Tester
1 | Container Import | 1.01 |  | In the application menu, navigate to the Field Mapping tab under Data Exchange | 1) Containers/LPN's should be created in 'Ready' status in the location specified (if applicable) | CSV Imported as Expected
|  | 1.02 |  | Select the "Container Import" field mapping and select 'Download Sample CSV'
|  | 1.03 |  | Complete the template. Required fields: Container Number, LPN Number, Location, Type
|  | 1.04 |  | Save the template to your local device
|  | 1.05 |  | In the application menu, navigate to the Data Exchange tab under Data Exchange
|  | 1.06 |  | Select the "3 dots" at the end of the row for 'Picking Container/LPN Import' and select 'Run'
|  | 1.07 |  | Select the saved template from the local device and select 'Upload'
|  | 1.08 |  | In the application menu, navgate to the Transmission tab under Data Exchange
|  | 1.09 |  | Verify the import's status by checking the 'Status' column
2 | Zone Import | 2.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Zones should be created | CSV Imported as Expected
|  | 2.02 |  | Select the Zone Import field mapping and select 'Download Sample CSV'
|  | 2.03 |  | Complete the template. Required fields: Code
|  | 2.04 |  | Save the template to your local device
|  | 2.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 2.06 |  | Select the "3 dots" at the end of the row for 'Product Category Import' and select 'Run'
|  | 2.07 |  | Select the saved template from the local device and select 'Upload'
|  | 2.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 2.09 |  | Verify the import's status by checking the 'Status' column
3 | Location Import | 3.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Locations should be created as 'Ready' type with corresponding Zones (if applicable) | CSV Imported as Expected
|  | 3.02 |  | Select the Location Import field mapping and select 'Download Sample CSV'
|  | 3.03 |  | Complete the template. Required fields: Location(l) Number, l.Facility, l.Locator, l.storageType, l.Type, l.multiItemThreshold, l.Pickable Optional: Zone(z) Facility, z.Name, Storage(s)
|  | 3.04 |  | Save the template to your local device
|  | 3.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 3.06 |  | Select the "3 dots" at the end of the row for 'Location Import' and select 'Run'
|  | 3.07 |  | Select the saved template from the local device and select 'Upload'
|  | 3.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 3.09 |  | Verify the import's status by checking the 'Status' column. Reference the 'Errors' column if status is 'Failed'
4 | Pack Import | 4.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Packs should be created with corresponding Items | CSV Imported as Expected
|  | 4.02 |  | Select the Pack Import field mapping and select 'Download Sample CSV'
|  | 4.03 |  | Complete the template. Required fields: Item Number, Pack Quantity
|  | 4.04 |  | Save the template to your local device
|  | 4.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 4.06 |  | Select the "3 dots" at the end of the row for 'Item/Pack Import' and select 'Run'
|  | 4.07 |  | Select the saved template from the local device and select 'Upload'
|  | 4.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 4.09 |  | Verify the import's status by checking the 'Status' column
5 | Purchase Order Import | 5.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) OrderHeaders should be created as 'Purchase Order' type with corresponding OrderLines | Initial upload attempts were failures due to an incorrect Business Unit.
|  | 5.02 |  | Select the Purchase Order Import field mapping and select 'Download Sample CSV'
|  | 5.03 |  | Complete the template. Required fields: OrderHeader(oh) Number, oh.currentStatus, OrderLine (ol) Number, ol.customerLineNumber, ol.orderLineStatus
|  | 5.04 |  | Save the template to your local device |  | Single line PO uploaded successfully
|  | 5.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export |  | Multi-line PO failure due to Customer Line Number being set as a Business Key
|  | 5.06 |  | Select the "3 dots" at the end of the row for 'Purchase Order Import' and select 'Run' |  | Multi-line PO uploaded successfully
|  | 5.07 |  | Select the saved template from the local device and select 'Upload'
|  | 5.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 5.09 |  | Verify the import's status by checking the 'Status' column. Reference the 'Errors' column if status is 'Failed'

## Inventory Management (hidden)
BL101: |  | BL101
BL101 Code: |  | BL101
Process: |  | Inventory Management
Date Updated:
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Cycle Count
2 | Create Cycle Count Task by Location | 1.01 |  | Make sure Cycle Count checkbox is checked for both Item and the Location that contains its stock units (Inventory). | Using the location cycle count creation handheld process will create cycle count tasks for a specific location Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING. When cycle counting via handheld "Perform Cycle Count" process, user will be prompted to count all specified items in the location.
|  | 1.02 |  | Navigate to "Create Cycle Count By Location" under Inventory in handheld menu
|  | 1.03 |  | Scan or enter the location to count
|  | 1.04 |  | Optionally enter a priority for the cycle count. If no priority is entered, then the priority will default to five (Medium).
|  | 1.05 |  | Cycle count tasks for the location will appear in the Cycle Count Queue table. (located in Inventory Admin menu option on the desktop UI)
3 | Perform Cycle Count (with Item Image Display) | 3.01 |  | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. More info on this in the next test script.
|  | 3.02 |  | Scan or enter starting location (any location in the warehouse) and hit enter
|  | 3.03 |  | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 3.04 |  | User will scan the location they're directed to
|  | 3.05 |  | User will be shown a list box with items in location needing to be cycle counted.
|  | 3.06 |  | User will scan SKU and hit enter
|  | 3.07 |  | On the next screen, user will select the pack type and enter the quantity they counted. **User will see item image on this screen
|  | 3.08 |  | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  | 3.09 |  | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  | 3.1 |  | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
4 | Manage Cycle Count Variances | 4.01 |  | User (typically a supervisor or manager) will enter the "Approve Variances" UI through a laptop or desktop | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances".
|  | 4.02 |  | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system.
|  | 4.03 |  | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted.
|  | 4.04 |  | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted).
5 | On Demand Cycle Count | 5.01 |  | User will select "On Demand Location Cycle Count" from Inventory menu | If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. (ref seq. 7) Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING.
|  | 5.02 |  | User will be prompted to enter a location and priority (1-10 w/1 being highest priority). Priority defaults to 5 if left empty.
|  | 5.03 |  | User creates cycle count task and will immediately begin task (reference seq. 3, steps 3.04-3.10) and will be assigned to the user to complete.
6 | Physical Count | 6.01 |  | Select "Physical Count" from Inventory Menu | 1) When Physical Count Activity is started from Physical Count Admin button, message will appear saying "[controlled/non-controlled] Physical Count Activity [process name] is started on [date time] and is active". 2) Non-controlled Physical Count Activity will be able to create and delete inventory. Stock units will be updated with whatever is counted for that location. 3) If controlled, discrepancies will be recorded in "Manage Cycle Count Variances" . 4) Once physical count activity is complete, screen will return to MainMenu and will display a message saying "[controlled/non-controlled] Physical Count Activity [process name] is finished at [date time]". 5) Adjustments to item's SU will show up in Inventory General Ledger Table
|  | 6.02 |  | Scan/Enter a location
|  | 6.03 |  | User counts items in location
|  | 6.04 |  | To go onto the next location, User can select "Next Location"
|  | 6.05 |  | If phys count activity is non-controlled, user is taken to phys count summary screen and can click "Recount" or "Apply" before finally confirming.
|  | 6.06 |  | When done with physical count activity, navigate to "Physical Count Admin" button and click "Finish Physical Count Activity"
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Putaway
1 | Move Item | 1.01 |  | Navigate to "Move Item" under Inbound on handheld MainMenu | This process allows a user to move unique items individually out of a location and into a different location Stock units that were moved are decremented from their source location, and are created in the destination location
|  | 1.02 |  | Enter the location that contains the stock you want to move
|  | 1.03 |  | A listbox of available SKUs to move display. User must scan or select item to move
|  | 1.04 |  | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  | 1.05 |  | User is prompted to putaway screen. User must scan or select a location in which to put the stock away.
|  | 1.06 |  | If user wants to continue moving items from this location, user can repeat steps 1.03-1.05
|  | 1.07 |  | Otherwise, user can exit the process
2 | Move Stock | 2.01 |  | Navigate to "Move Stock" under Inbound on handheld MainMenu | This process allows a user to move multiple items instead of one unique SKU 1) When all stock has been moved successfully, a message displays on menu saying "All Items Moved." 2) Picking Cart is now empty and remains in its original location 3) Stock units that were moved are decremented from their source location, and are created in the destination location |  |  | Not Ready for Testing
|  | 2.02 |  | Enter/scan the container in which you want to put the stock you are wanting to move
|  | 2.03 |  | Enter or scan location with the stock you want to move
|  | 2.04 |  | A listbox of available SKUs to move display. User must scan or select item to move
|  | 2.05 |  | Select Pack UOM and enter in quantity to move and select Submit
|  | 2.06 |  | Repeat steps 2.04-2.05 to move more items in the location
|  | 2.07 |  | When finished, select Move Source Screen
|  | 2.08 |  | User is given a summary of the number of unique Skus and quantity in cart. If user wants to move stock in a different location, User can scan another location.
|  | 2.09 |  | Otherwise, User can select "Move" or "Move Full" to move the stock to a directed location
|  | 2.10 |  | User enters quantity and selects/scans item
|  | 2.11 |  | A listbox of suggested putaway locations is displayed. User must select or scan a location to move the stock
|  | 2.12 |  | User repeats 2.10-2.11 to move the rest of the stock, if any
|  | 2.13 |  | Otherwise, User can select All to move all of the stock in the cart and then scan the destination location of where the stock should be moved
2 | Move Container | 2.01 |  | Navigate to "Move Container" under Inventory on handheld MainMenu | This process allows a user to move an entire container (LPN) out of a location and into a different location The container (LPN) that container the stock (inventory) is decremented from the source location, and created in the destination location
|  | 2.02 |  | Enter/Scan the container (LPN) that contains the stock (inventory) you want to move. Container type must be Pallet or Transient
|  | 2.03 |  | A listbox of suggested locations should populate. The user should now navigate to one of the suggested locations, scanning that location they wish to put the container away to
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Adjust Inventory
1 | Adjust Inventory: Decrement Inventory out of a Location | 1.01 |  | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 4) Updates made to Item's SU in location
|  | 1.02 |  | Scan/key in Location
|  | 1.03 |  | Select "Consume by Item"
|  | 1.04 |  | Scan Item SKU
|  | 1.05 |  | Enter quantity of item's SU you want to consume
|  | 1.06 |  | If you have more than one item's SU you want to consume in the location, click next and repeat steps 2.04 and 2.05
|  | 1.07 |  | Once finished, click Confirm
|  | 1.08 |  | Once final reviewing all items, select Reason Code and click Commit
2 | Adjust Inventory: Add Inventory to a Location | 2.01 |  | Select "Adjust Inventory" from the Inventory menu | 1) After items have been confirmed and the user clicks commit, user is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" 2) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 3) Updates made to Item's SU in location
|  | 2.02 |  | Scan/key in Location
|  | 2.03 |  | Select "Create Inventory"
|  | 2.04 |  | Scan Item SKU
|  | 2.05 |  | Enter quantity of item's SU you want to create. User can optionally enter serial, lot, and LPN #.
|  | 2.06 |  | If you have more than one item's SU you want to create, click next and repeat steps 3.04 and 3.05
|  | 2.07 |  | Once finished, click Confirm
|  | 2.08 |  | Once final reviewing all items, select Reason Code and click Commit
3 | Adjust Inventory: Consume All Inventory in Location | 3.01 |  | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location
|  | 3.02 |  | Scan/key in Location
|  | 3.03 |  | Select "Consume All in Location"
|  | 3.04 |  | Select Reason Code and Click Commit
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Adjust Inventory
1 | Replenishment Based on Open Orderline Quantity | 1.01 |  | Replenishments are generated on a scheduled basis for every location-item combination where current inventory levels for an item in a picking location is LESS than the the Open Orderlines for that item. The replenishment task will try to push the inventory level in the location to be enough to fulfill the open orders plus 20% more. All replenishments can be viewed in the "ReplenishmentTaskNew" entity
|  | 1.02 |  | Set up test data to where there is an open orderline qty for an item that is greater than the quantity of that item in a pickable location. Ensure that the item exists in a Reserve location
|  | 1.03 |  | Run the Open Orderline Replen Scheduler
|  | 1.02 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 1.03 |  | Scan a container that is Type=Cart
|  | 1.04 |  | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 1.05 |  | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 1.06 |  | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 1.07 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 1.08 |  | User will scan the destination location, the SKU, and the replen quantity
|  | 1.09 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
2 | Replenishment Based on Open Orderline Quantity | 2.01 |  | Replenishments are generated on a scheduled basis for every location-item combination where the stock unit quantity in a location is at 25% of the past two week volume in order to get the location back to maintaining a two week supply. All replenishments can be viewed in the "ReplenishmentTaskNew" entity
|  | 2.02 |  | Run the Two Week Demand Replen Scheduler
|  | 2.03 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 2.04 |  | Scan a container that is Type=Cart
|  | 2.05 |  | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 2.06 |  | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 2.07 |  | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 2.08 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 2.09 |  | User will scan the destination location, the SKU, and the replen quantity
|  | 2.1 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Inventory Edge Cases
1 | Ad-Hoc Cycle Count - Counting Less than the Item's Qty | 1.01 |  | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances" UI for a manager or supervisor to review 2) If qty count entered is less than the system's qty, a negative variance qty will be displayed for that item in "Approve Variances"
|  | 1.02 |  | User will enter quantity less than the item's SU quantity currently in Deposco's system
|  | 1.03 |  | User will be asked to recount and will proceed to re-enter the quantity.
2 | Ad-Hoc Cycle Count - Counting More than the Item's Qty | 2.01 |  | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances UI for a manager or supervisor to review 2) If qty count entered is more than the system's qty, a positive variance qty will be displayed for that item in "Approve Variances"
|  | 2.02 |  | User will enter quantity more than the item's SU quantity currently in Deposco's system
|  | 2.03 |  | User will be asked to recount and will proceed to re-enter the quantity.
3 | Perform Cycle Count - Scanning incorrect Location | 3.01 |  | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) Error message saying "You must cycle count the given location [required location]". 2) User will be prevented from ever counting in an incorrect location.
|  | 3.02 |  | Scan or enter starting location and hit enter
|  | 3.03 |  | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 3.04 |  | User scans an incorrect location
User is prompted to re-enter correct location. Proceed as normal.
4 | Perform Cycle Count - Scanning Item that does not exist in Location | 4.01 |  | Select Perform Cycle Count button in handheld menu from Inventory | 1) Variance be generated in the "Approve Variances" UI for a manager or supervisor to review
|  | 4.02 |  | Scan or enter starting location and hit enter
|  | 4.03 |  | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 4.04 |  | User will incorrectly scan an item not listed nor existing in the location
|  | 4.05 |  | On the next screen they'll select the pack type and enter the quantity they counted
|  | 4.06 |  | User will be brought back to the screen displaying the list box of items and can proceed as normal
5 | Physical Count- Physical Count Activity not Started | 5.01 |  | User makes sure there is no physical count activity started by navigating to Physical Count Admin button. If there is one existing, user should select "Finish Physical Count Activity". | 1) User will get an error on MainMenu saying "PHYSICAL_COUNT Activity has not started." 2) User will not be able to start physical count process unless the activity has been started in Physical Count Admin.
|  | 5.02 |  | Select "Physical Count" button in Admin Folder
|  | 5.03 |  | User will not be able to start physical count
7 | Move Item / Move Stock - Incorrect Source Location Scan | 7.01 |  | During Move Item/Move Stock, user scans a source location that does not exist | User should see an error on MainMenu saying "[....] is not a valid location" or "No such location or LPN in the current facility." depending on process
|  | 7.02 |  | The user should be prevented from moving forward with the process
8 | Move Item / Move Stock - Putaway to non Suggested Location | 8.01 |  | During Move Item/Move Stock user wants to put away to a location other than the suggested location | 1) Stock unit will be created in the putaway location the user entered 2) Message will appear reading, "All items Moved." if using Move Item
|  | 8.02 |  | User will leave the suggested location list box alone and scan the desired putaway location
9 | Move Item / Move Stock - Incorrect Item Qty Entry | 9.01 |  | During Move Item/Move Stock, user enters in more than the item's current SU quantity to move | 1) Message will appear reading, "The entered quantity exceeds the total movable Each quantity of [...]." and "Quantity to move [..] larger than quantity in found stocks [...]." depending on process. 2) User should not be allowed to enter more than the item's current SU quantity.
|  | 9.02 |  | User will be prompted to re-enter quantity and scan putaway location
10 | Move Item / Move Stock - Negative Item Qty Entry | 10.01 |  | During Move Item/Move Stock, user enters in a negative value for the item's current SU quantity to move | 1) Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process. 2) User should not be allowed to enter or move a negative quantity in this process.
|  | 10.02 |  | User will be prompted to re-enter quantity and scan putaway location
11 | Move Item / Move Stock - Invalid Item Qty Entry | 11.01 |  | During Move Item/Move Stock, user enters in for the item's current SU quantity to move an invalid number like "2YN". | 1) Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process. 2) User should not be allowed to enter an invalid item's SU quantity.
|  | 11.02 |  | User will be prompted to re-enter quantity and scan putaway location
12 | Replen edge cases | 12.01 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 12.02 |  | In the Picking screen, select "Exception"
|  | 12.03 |  | The user is directed to "Replenishment Picking Exception" screen
|  | 12.04 |  | Hit Complete
|  | 12.05 |  | The replenishment task is marked with a status of "Full", this replenishment task is skipped and the user is taken to the next replenishment task
13 | Replen edge cases | 13.01 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen | The location that the Exception occured at will then have a status of "On Hold"
|  | 13.02 |  | In the Picking screen, select "Exception"
|  | 12.03 |  | The user is directed to "Replenishment Picking Exception" screen
|  | 13.04 |  | Select No Stock and hit Exception
|  | 13.05 |  | The replenishment task is marked with a status of "Exception", this replenishment task is skipped and the user is taken to the next replenishment task
14 | Replen edge cases | 14.01 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 14.02 |  | Scan a container that is Type=Cart
|  | 14.03 |  | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 14.04 |  | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 14.05 |  | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 14.05 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 14.05 |  | User will scan the destination location, the SKU, and the replen quantity
|  | 14.05 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
|  | 14.05 |  | Select Suspend Task and hit Exception
|  | 14.05 |  | The replenishment task is skipped and the user is taken to the next replenishment task
|  | 14.06 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 14.07 |  | Select Exception, and user will be directed to the Replenishment putaway exception screen. Select Location Full and then click "Exception" again
|  | 14.08 |  | User will then be directed to put the stock back to where they pick it from
|  | 14.09 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."

## Picking (hidden)
BL101: |  | BL101
BL101 Code: |  | BL101
Process: |  | Picking
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking
1 | Batch Picking | 1.01 |  | User will select Batch Picking button from Outbound menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 1.02 |  | User will see a list of waves and can select or enter the wave
|  | 1.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 1.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 1.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 1.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
2 | High Value Orders | 2.01 |  | User will select High Value Orders button from Admin menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 2.02 |  | User will see a list of waves and can select or enter the wave
|  | 2.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 2.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 2.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 2.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
3 | Single Scan Picking | 3.01 |  | User will select Singles Picking in corresponding facility menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location | Good | selcted works bundle sku to test item componets imported
|  | 3.02 |  | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking cart to be used |  | Good
|  | 3.03 |  | User will scan location, SKU, bin and enter in quantity to complete pick task(s). |  | Good
|  | 3.04 |  | Once all pick tasks have been completed, user is returned to the wave selection screen |  | Good
4 | Outbound Transfer Picking | 4.01 |  | User will select Outbound Transfer Picking button from Outbound menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 4.02 |  | User will see a list of waves and can select or enter the wave
|  | 4.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 4.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 4.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 4.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
5 | Single Scan Picking (with Item Image Display) | 5.01 |  | User will select Singles Picking in corresponding facility menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 5.02 |  | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 5.03 |  | User will see picking screen and item image
|  | 5.04 |  | User will scan location, item SKU, and quantity
|  | 5.05 |  | Once all pick tasks have been completed, user is returned to the wave selection screen
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking Edge Cases
1 | Batch Picking - New Bin | 1.01 |  | During picking, if a picking container becomes too full to put any more items in, the user can select the New Bin button to continue the picking process | Current picking bin will unassign from the order to allow the user to pick into a new container. Picking will proceed as expected | Received an error stating, "Using multi-bins is not allowed." **Resolved** Tested on SO614 with no issues.
|  | 1.02 |  | Selecting New Bin will unassign the current picking bin from the order to allow the user to pick into a new container
|  | 1.03 |  | The picking screen should update to show no suggested bin to pick into
|  | 1.04 |  | User will proceed to complete the pick task in any empty container available
2 | Singles Picking - Stage | 2.01 |  | During picking, if the picking container becomes too full to put any more items in, the user can stage the bin to be packed. | Pick wave can be completed with multiple picking carts that are staged to the Shipping location upon completion | I initially picked x6 of x10 copies of AMGSWL89 from SO468 into BIN-022. I then selected "Stage", which took me to the screen to select a new container. I selected BIN-023, but the picking screen had me pick the original x10 copies into this bin. Looking at the data on SO468, there is only product located in BIN-023.
|  | 2.02 |  | Selecting Stage will prompt the user to select a new cart to continue picking
|  | 2.03 |  | User can proceed with picking as expected in new container
3 | Batch Picking - Entering Less Quantity | 3.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed
|  | 3.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
4 | Singles Picking - Entering Less Quantity | 4.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed
|  | 4.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
5 | Batch Picking - User Scans Incorrect Location | 5.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen | Message notes: please scan a valid location
|  | 5.02 |  | User scans a location other than the one listed on the screen during picking
|  | 5.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 5.04 |  | User should proceed to correct location and continue as normal
6 | Batch Picking - User Scans Incorrect Item | 6.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. | Message notes: please scan valid item
|  | 6.02 |  | User scans the wrong item
|  | 6.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
7 | Batch Picking - User Enters too Much Quantity | 7.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left.
|  | 7.02 |  | User accidentally enters more than the pick quantity
|  | 7.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 7.04 |  | User will again be prompted to enter location, SKU, and quantity.
8 | Batch Picking - Scanning Incorrect Container/Bin | 8.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin
|  | 8.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
9 | Batch Picking - Exceptions (no stock, damaged, etc.) | 9.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from.
|  | 9.02 |  | User can select "exception" button
|  | 9.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 9.04 |  | Select "exception" again from that screen after selecting a reason
|  | 9.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 9.06 |  | If no other stock exists for that item, it will go to back ordered status.
10 | Batch Picking - Suspend Task | 10.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped.
|  | 10.02 |  | User can select "exception" button
|  | 10.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 10.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
11 | Batch Picking - Suspend Workgroup | 11.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete"
|  | 11.02 |  | User can select "exception" button
|  | 11.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 11.04 |  | User is taken back to MainMenu screen
|  | 11.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
12 | Batch PIcking - Suspend Workgroup and Keep Assigned User | 12.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group.
|  | 12.02 |  | User can select "exception" button
|  | 12.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 12.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 12.05 |  | Assigned user can select wave again to continue picking
13 | Singles Picking - User Scans Incorrect Location | 13.01 |  | During picking, the user will see the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen
|  | 13.02 |  | User scans a location other than the one listed on the screen during picking
|  | 13.03 |  | Error message will appear "Please scan a valid location."
|  | 13.04 |  | User should proceed to correct location and continue as normal
14 | Singles Picking - User Scans Incorrect Item | 14.01 |  | During picking, the user scans the wrong item | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item.
|  | 14.02 |  | Screen message will appear stating "Please scan a valid item"
15 | Singles Picking - User Enters Too Much Quantity | 15.01 |  | User enters locatiton and SKU | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left.
|  | 15.02 |  | User accidentally enters more than what is called for to pick
|  | 15.03 |  | Screen message will appear as follows: "Quantity entered is greater than required."
|  | 15.04 |  | User will again be prompted to enter location, SKU, and quantity.
16 | Singles Picking - Exceptions (no stock, damaged, etc.) | 16.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order will go to back ordered status. Also, the stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from.
|  | 16.02 |  | User can select "exception" button
|  | 16.03 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 16.04 |  | If no other stock exists for that item, it will go to back ordered status.
17 | Singles Suspend WorkGroup | 17.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete"
|  | 17.02 |  | User can select "exception" button
|  | 17.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 17.04 |  | User is taken back to MainMenu screen
|  | 17.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
14 | RTV Picking - User Scans Incorrect Location | 14.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen |  |  | Not Tested
|  | 14.02 |  | User scans a location other than the one listed on the screen during picking
|  | 14.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 14.04 |  | User should proceed to correct location and continue as normal
15 | RTV Picking - User Scans Incorrect Item | 15.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. |  |  | Not Tested
|  | 15.02 |  | User scans the wrong item
|  | 15.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
16 | RTV Picking - User Enters too Much Quantity | 16.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Not Tested
|  | 16.02 |  | User accidentally enters more than the pick quantity
|  | 16.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 16.04 |  | User will again be prompted to enter location, SKU, and quantity.
17 | RTV Picking - Scanning Incorrect Container/Bin | 17.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Not Tested
|  | 17.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
18 | RTV Picking - Exceptions (no stock, damaged, etc.) | 18.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Not Tested
|  | 18.02 |  | User can select "exception" button
|  | 18.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 18.04 |  | Select "exception" again from that screen after selecting a reason
|  | 18.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 18.06 |  | If no other stock exists for that item, it will go to back ordered status.
19 | RTV Picking - Suspend Task | 19.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Not Tested
|  | 19.02 |  | User can select "exception" button
|  | 19.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 19.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
20 | RTV Picking - Suspend Workgroup | 20.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Not Tested
|  | 20.02 |  | User can select "exception" button
|  | 20.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 20.04 |  | User is taken back to MainMenu screen
|  | 20.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
21 | RTV PIcking - Suspend Workgroup and Keep Assigned User | 21.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Not Tested
|  | 21.02 |  | User can select "exception" button
|  | 21.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 21.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 21.05 |  | Assigned user can select wave again to continue picking

## Packing (hidden)
BL101: |  | BL101
BL101 Code: |  | BL101
Process: |  | Packing
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
1 | Build Transfer Order | 1.01 |  | Select Build Outbound Transfer Order from Store Operations menu | 1)Ensure your user's Facility is set to the DPR or STPR facility. Screen should read 'Ship-To Facility'
|  | 1.02 |  | Enter the Ship-To Facility Number
|  | 1.03 |  | Select a Transfer Purpose and scan the location with the stock to transfer
|  | 1.04 |  | Scan the container user will be picking into
|  | 1.05 |  | Scan the Items and on the next screen, enter the Quantity that user intends to transfer
|  | 1.06 |  | User will be brought to a sumamry screen showing all items added to the Transfer Order. Confirm order by selecting "Next."Stage your container to a location | User will see the following message: "Container (Container#) staged to (StagingLocation) for ship-to HZLHQ"
|  | 1.07 |  | Pack out the Transfer Order using the Transfer Order Packing button from the Store Operations menu
|  | 1.08 |  | Scan the LPN label of the picking container, and select Next.
|  | 1.09 |  | The Item Screen appears with a list of items in the container. Scan an item in container OR select the "Pack Remainder" button to pack out all items in the container
1.1
2 | Cubed Packing | 2.01 |  | Select Cubed Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container.
|  | 2.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 2.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container.
|  | 2.04 |  | Shipping label and packing list will print
|  | 2.05 |  | User will be returned to the Scan Container Screen and see the following message: "Order [ ] has been successfully packed."
3 | Single Scan Packing | 3.01 |  | Select Single Scan Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container.
|  | 3.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 3.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container, then enter the quantity that will be packed on the next screen
|  | 3.04 |  | Select the box from the Box list
|  | 3.05 |  | Shipping label and packing list will print
|  | 3.06 |  | If there are more items in the picking bin, then you are returned to the Item Screen to scan/select another item.
4 | Outbound Transfer Packing | 4.01 |  | Select Outbound Transfer Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order and an Inbound Transfer Order is created for the store to receive against
|  | 4.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 4.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container or use the pack remainder button to pack out all items in the container
|  | 4.04 |  | Packing list will print once all items are packed
|  | 4.06 |  | User will then be brought back to the Scan Container screen
5 | Bulk Packing | 5.01 |  | Select Bulk Packing from the Outbound Menu | User will see the following message at the end of packing: [The request has been placed to ship orders.] Please check the notification center for error messages. | Receiving an error on the Scan Container step stating, "For input string: "" ' Used BIN-060 for testing
|  | 5.02 |  | User will be prompted to scan/enter a container (a container that was just picked into)
|  | 5.03 |  | User will see an order summary screen showing all orders in the container, as well as the items that those orders have in common
|  | 5.04 |  | Select Enter BL101nsions
|  | 5.05 |  | Weight will autopopulate, but select the carton type to pack the order out into
|  | 5.06 |  | Select Ship All
|  | 5.07 |  | User will be returned to the container entry screen
6 | BOPIS Packing | 6.01 |  | Select BOPIS Packing from Outbound Menu | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's status shows status "Staged" and Order's shipping status shows "Not Shipped" | Re-tested with SO630
|  | 6.02 |  | User will be prompted to scan/enter a container (a container that was just picked into)
|  | 7.03 |  | User will then be prompted with a list of items that are in said container.
|  | 7.04 |  | Scan each item in container or use the Pack Remainder button to pack all items
|  | 7.05 |  | After all items have been scanned, Select a box from the Box list to pack your order into
|  | 7.06 |  | User will be returned to the container entry screen
| Move Container | 7.07 |  | Navigate to "Move Container" under Inventory on handheld MainMenu | Because BOPIS will be picked and packed through the main warehouse facility, and then moved to the store- this will be the next step. The order will be transported outside system. The "mover" will need to enter the device, and go to move container- where they will enter the container number and be given the option to change facility. Operator must change to destination facility, in order to receive product. From there, scan the location to drop off, and proceed to next step.
|  | 7.08 |  | Enter/Scan the container (LPN) that contains the stock (inventory) you want to move.
|  | 7.09 |  | User will change their facility to the facility the order is going to, then enter a store location (ex. Receiving)
| BOPIS Pickup | 7.1 |  | Select Close BOPIS Order from Store Operations Menu | 1) Screen message should appear saying "Packed [Order] containing x items.." 2) Order's status shows status "Complete" and Order's shipping status shows "Ship Complete"
|  | 7.11 |  | User will be prompted to scan/enter a container (the container that was packed)
|  | 7.12 |  | User will enter the BL101nsions of the box,
|  | 7.13 |  | User will be returned to the container entry screen
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Packing Edge Cases
1 | Single Scan Packing - Scanning a Non Existing Container | 1.01 |  | User enters Single Scan Packing process from facility menu | 1) Screen message should appear saying "Cannot find container [#]." 2) User will always be prevented from starting the packing process if they scan a non existent container
|  | 1.02 |  | User enters a container that does not exist in the system
|  | 1.03 |  | User is prevented from proceeding
2 | Single Scan Packing - New Bin | 2.01 |  | During packing, the user may select New Bin if items in picking container cannot be shipped in one shipping box | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created.
|  | 2.02 |  | On item screen, user will select New Bin
|  | 2.03 |  | User will be prompted to enter the BL101nsions of the first shipping box
|  | 2.04 |  | Process will return back to items screen to now pack remaining items in new shipping box
|  | 2.05 |  | This process can be repeated as many times as needed
3 | Single Scan Packing - Scanning an Empty Container | 2.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "There are no items to pack." 2) User will always be prevented from starting the packing process if they scan an empty container
|  | 2.02 |  | User is prevented from proceeding
4 | Single Scan Packing - Scanning Wrong Item | 3.01 |  | User scans item that is not on the listbox / not in the container that the user scanned | 1) Screen message should appear saying "Item scanned does not exist in this Order" 2) User should not be able to scan a non existing item for the order and container
|  | 3.02 |  | User is prevented from proceeding
|  | 3.03 |  | User scans the correct item and proceeds as normal
5 | Batch Packing - Scanning a Container with a Partially Picked Order (unfinished pick task) | 4.01 |  | User enters a container that does not have all items picked into it | 1) Screen message should appear saying "Order not fully picked." 2) User will always be prevented from starting the packing process if they scan an incomplete container
|  | 4.02 |  | User is prevented from proceeding
6 | Singles Packing - Scanning a Non Existing Container | 6.01 |  | User enters Singles Packing from facility menu | 1) Screen message should appear saying "Container does not exist or data issue." 2) User will always be prevented from starting the packing process if they scan a non existent container
|  | 6.02 |  | User enters a container that does not exist in the system
|  | 6.03 |  | User is prevented from proceeding
7 | Singles Packing - Scanning an Empty Container | 7.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "Scanned container contains no items" 2) User will always be prevented from starting the packing process if they scan an empty container
|  | 7.02 |  | User is prevented from proceeding
8 | Singles Packing - Scanning Wrong Item | 8.01 |  | User scans item that is not on the listbox / not in the container that the user scanned | 1) Screen message should appear saying "Invalid item number" 2) User should not be able to scan a non existing item for the order and container
|  | 8.02 |  | User is prevented from proceeding
|  | 8.03 |  | User scans the correct item and proceeds as normal
9 | Batch Packing - Scanning an Empty Container | 9.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "Container [#] does not have any stock units." 2) User will always be prevented from adding the empty container to the trip
|  | 9.02 |  | User is prevented from proceeding

## Integration (hidden)
BL101: |  | BL101
BL101 Code: |  | BL101
Process: |  | Integration
Date Updated: |  | 2025-08-12
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Integration
1 | - Item Pull | 1.01
1.02
1.03
1.04
1.05
1.06
2 | Sales Order Pull | 2.01
2.02
2.03
2.04
2.05
2.06
3 | Inventory Sync | 3.01
3.02
3.03
3.04
3.05
3.06
3.07
4 | Ship Notice | 4.01
4.02
4.03
5 | - Item Pull | 5.01
5.02
5.03
5.04
5.05
5.06
16 | RTV Picking - User Enters too Much Quantity | 16.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Not Tested
|  | 16.02 |  | User accidentally enters more than the pick quantity
|  | 16.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 16.04 |  | User will again be prompted to enter location, SKU, and quantity.
17 | RTV Picking - Scanning Incorrect Container/Bin | 17.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Not Tested
|  | 17.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
18 | RTV Picking - Exceptions (no stock, damaged, etc.) | 18.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Not Tested
|  | 18.02 |  | User can select "exception" button
|  | 18.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 18.04 |  | Select "exception" again from that screen after selecting a reason
|  | 18.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 18.06 |  | If no other stock exists for that item, it will go to back ordered status.
19 | RTV Picking - Suspend Task | 19.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Not Tested
|  | 19.02 |  | User can select "exception" button
|  | 19.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 19.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
20 | RTV Picking - Suspend Workgroup | 20.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Not Tested
|  | 20.02 |  | User can select "exception" button
|  | 20.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 20.04 |  | User is taken back to MainMenu screen
|  | 20.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
21 | RTV PIcking - Suspend Workgroup and Keep Assigned User | 21.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Not Tested
|  | 21.02 |  | User can select "exception" button
|  | 21.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 21.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 21.05 |  | Assigned user can select wave again to continue picking
6 | POS Order Pull | 6.01
6.02
6.03
6.04
6.05
6.06
7 | Inventory Sync | 7.01
7.02
7.03
7.04
7.05
7.06
7.07