## Schedule
EVE Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal | Metric | Status
Maintin Shipping Internal SLA - 48 hours | Hours between an order's "Placed Date" and the order's "Ship Date" Currently fulfill 50% of orders within 12 business hours, all within 48 hours | Open
Improve Inventory Accuracy | Minimize instances of negative inventory in stores Minimize quantity of CO Backorder/Re-route scenarios | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Status | Completion Date
Deposco University | EVE completes Deposco University training courses for relevant subjects. | In Progress
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | LINK | 2025-05-29 | 2025-05-29
Master Design Document | LINK | 2025-06-20 | 2025-06-27
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | Routing system/Shopify/ShopifyPOS/ShippingCarrier/- data requirements, troubleshooting, mapping updates, steps etc. | TBD | 0% | TBD
Order Orchestration | Sourcing, Exception and Backorder Management | 2025-08-14 | 0% | 2025-08-21
Inbound - Unit | Receiving(PO, Blind Receipt, EVE Returns), Putaway | 2025-07-31 | 0% | 2025-08-07
Inventory Management- Unit | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock | 2025-08-07 | 0% | 2025-08-14
Outbound 1 - Unit | Outbound Order Management, Waving | 2025-08-14 | 0% | 2025-08-21
Outbound 2- Unit | Picking, Packing, Shipping | 2025-08-21 | 0% | 2025-08-28
Inbound - E2E | Receiving(PO, Blind Receipt, EVE Returns), Putaway | 2025-07-31 | 0% | 2025-08-07
Inventory Management- E2E | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock | 2025-08-07 | 0% | 2025-08-14
Outbound - E2E | Outbound Order Management, Waving | 2025-08-21 | 0% | 2025-08-28
Store | Store fulfillment, receiving, returns & counting | TBD |  | TBD
Reporting | Report Builder, Dashboard Widgets | 2025-09-12 | 0% | 2025-09-19
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Due Date
Unit Test Cases WMS | Unit Test Cases for WMS processes | 0% | 2025-08-29
End to End Testing | Testing all process flows with live data end to end | 0% | 2025-09-05
UAT Onsite Agenda | LINK | 0% | 2025-08-28
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0% | 2025-09-19
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0% | 2025-09-12
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned. | 2025-09-12
Deposco Onsite Support | Travel booked for cutover and go-live week. | 2025-09-12
Project Closeout | Agreement of final deliverables provided. | 2025-10-10
Project PTO
Team | Team Member | Date(s)
EVE | Mary Pat | 7/24-7/30
DEP | Mitch | 7/28 - 8/5
EVE | Ryan | 7/28-8/1
EVE | Michon | 7/28 - 8/1
EVE | Tamer | 7/30-8/1
DEP | Rebecca | 8/11-8/14
DEP | Rebecca | 8/21-8/26
EVE | Erica | 9/15-9/16
EVE | Robby | 8/1 - 8/7

## Task Tracker
EVE Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | Comment Thread
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  | FALSE | Completed | DEP | Hannah
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  | FALSE | Completed | DEP | Hannah
Orientation | Setup Confluence and JIRA Project | Setup EVE confluence and JIRA Project | Task |  | FALSE | Completed | DEP | Hannah
Orientation | EVE UA Env. | Deposco to setup EVE UA environment with EVE code chosen by EVE during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  | FALSE | Completed | DEP | Kaleigh
Orientation | Company & Facility | Deposco to coordinate with EVE to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task | 4.Low | FALSE | Completed | DEP | Kaleigh
Orientation | User Creation Training | Deposco team to send training to show EVE team creation of super users in UA environment | Task | 2.High | FALSE | Completed | DEP | Mitch
Orientation | Setup Users | Deposco guides EVE super user through user setup with copying admin user from user UI. Password reset emails are sent to EVE users to complete final step for Deposco access | Task | 2.High | TRUE | Completed | EVE | Sherry
Orientation | Deposco University | Complete 101: Deposco Fundamentals course on Deposco University | Task | 2.High | FALSE | Completed | EVE | EVE team | 2025-05-28 | 2025-06-10
Orientation | Send EVE Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up EVE print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to EVE to complete setup on their server/network | Task | 2.High | TRUE | Completed | DEP | Daniel
Design | EVE Design Decision - Misc Orders | Internal Discussion reviewing how misc orders such as influencer or employee orders are desired to be created | Discussion | 2.High | TRUE | Completed | EVE | EVE team | 2025-06-16 | 2025-07-09 | 7/9: sherry to test shopify markets today 7/15: moving this to parking lot tab
Orientation | Send EVE Socket Setup Instructions | Deposco to send EVE team help site articles going over all in scope integration points | Task |  | FALSE | Completed | DEP | Daniel
Design | Review and Sign Master Design Document | EVE to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task | 1.Blocker | TRUE | In Progress | DEP/EVE | DEP/EVE | 2025-06-20 | 2025-07-25
Design | DEP Design Decision - Inventory Consolidation Flow | Deposco to meet to finalize design of stock consolidation | Discussion | 2.High | TRUE | Completed | DEP | Mitch | 2025-06-16 | 2025-06-20
Design | DEP Design Decision - Transfer Order Flow | Deposco to meet to finalize design of transfer order fulfillment | Discussion | 2.High | TRUE | Completed | DEP | Mitch | 2025-06-16 | 2025-06-20
Design | Shoe Product Types | EVE to provide the Deposco team with all product types for Footwear. | Task | 2.High | FALSE | Completed | EVE | EVE team | 2025-06-23 | 2025-07-03 | 7/2: Eve pref is use a metafield such as Category-Footwear not product type since product type changes. 7/1: MPS to provide to DEP.
Orientation | Send EVE Team Hardware Documentation | Deposco to send EVE team recommended hardware and hardware requirements | Task | 3.Medium | FALSE | Completed | DEP | Daniel | 2025-06-10 | 2025-06-20
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  | FALSE | Completed | DEP | Mitch
Design | EVE Design Decision - Shopify Fields | Provide shopify fields for the following attributes: - Brand - Style Number | Task | 3.Medium | TRUE | Completed | EVE | EVE team | 2025-06-16 | 2025-06-20 | See cell comment
Orientation | Setup Print Client | 2) EVE completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task | 4.Low | TRUE | Completed | EVE | EVE team | 2025-05-23 | 2025-06-13
Design | Inv Adjustment Pull cadence | EVE to decide how often are inv adjustments pulled | Discussion | 1.Blocker | TRUE | Completed | EVE | EVE team | 2025-06-20 | 2025-07-23 | 7/9 may consider on hold while we discuss inventory with product 7/15 - deposco solution proposed on 7/11, pending EVE final feedback
Design | Review and Order Hardware | Both teams to review and finalize hardware needs and order necessary hardware needed | Discussion | 1.Blocker | TRUE | Open | EVE | Sherry | 2025-06-10 | 2025-07-04 | 7/1 sherry to send email to deposco for their input. 7/9 Dep to provide feedback from Reformation on this. Daniel to send this week (daniel sent). EVE decide which server to store print client, ensure sufficient amount of handhelds in WH & Stores. 7/9 MPS working with Blake on store sccanners.
Design | Timeline | EVE team to discuss internally timeline for stores | Discussion | 2.High | TRUE | In Progress | EVE | EVE team | 2025-06-30 | 2025-07-18 | 7/9: EVE team meeting tomorrow Go Live with stores Q4-25 or Q1-26? 7/23: target late next week to meet with store teams
Design | DEP Design Decision - Shopify Inventory Sync | Deposco to meet with product internally to discuss Inventory sync Proposal discussed and sent to EVE - pending final feedback after remorse period demo | Discussion | 2.High | TRUE | In Progress | DEP | Mitch | 2025-06-16 | 2025-07-25
Design | Design Decision | Timeline/Decision on number of environments Hannah to draft SOW for licensing of third environment | Discussion | 2.High | FALSE | In Progress | DEP | Hannah | 2025-05-22 | 2025-06-27
Configuration | Set up receiving printers | Add receiving printers to the network, add to Deposco, get printer validation | Task | 2.High | TRUE | Open | EVE | Sherry | 2025-07-24
Configuration | Add printer assignments for receiving printers | Go in and add printer assignments for the following reports: - 1’ x .5’ Jewelry Item Label - 1.5’ x 1’ Jewelry Item Label - Clothing Item Label by PO - Clothing Item Label by Item | Task | 2.High | TRUE | Open | EVE | Sherry | 2025-07-24 |  | Demo under Recordings > Misc Demos
Configuration | Deliver Inbound Configuration | Via loom videos | Task | 2.High | TRUE | Open | DEP | Henry | 2025-07-28 | 2025-07-31
Configuration | Deliver Inventory Management Configuration | Via loom videos | Task | 2.High | TRUE | Open | DEP | Henry | 2025-07-28 | 2025-08-07
Configuration | Deliver Outbound: BO/Ord Mngt/Waving Configuration | Via loom videos | Task | 2.High | TRUE | Open | DEP | Henry | 2025-07-28 | 2025-08-14
Configuration | Deliver Outbound: Pick/Pack/Ship Configuration | Via loom videos | Task | 2.High | TRUE | Open | DEP | Henry | 2025-07-28 | 2025-08-21
Configuration | Deliver Integration Configuration Training | Via loom videos | Task | 2.High | TRUE | Hold | DEP | Mitch | 2025-07-28 | TBD | Pending Design Decision
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task | 2.High | TRUE | Open | DEP | Henry | 2025-07-28 | 2025-09-19
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-07-31 | 2025-08-07
Validation | Unit Test Cases- Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-08-07 | 2025-08-14
Validation | Unit Test Cases - Outbound: BO/Ord Mngt/Waving | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-08-14 | 2025-08-21
Validation | Unit Test Cases - Pick/Pack/Ship | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-08-21 | 2025-08-28
Validation | E2E Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-07-31 | 2025-08-07
Validation | E2E Test Cases- Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-08-07 | 2025-08-14
Validation | E2E Test Cases - Outbound | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | 2025-08-21 | 2025-08-28
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task | 2.High | TRUE | Hold | EVE | EVE team | TBD | TBD
Validation | Train End Users | During UAT and any additional training as needed | Task | 3.Medium | TRUE | Hold | EVE | EVE team |  | 2025-09-12
Validation | Deliver Onsite UAT Agenda |  | Task | 4.Low | TRUE | Hold | DEP | Mitch |  | 2025-08-28
Design | EVE Design Decision - Over receive threshold | Internal Discussion reviewing what percentage of the ordered quantity will end user be able to over receive | Discussion | 3.Medium | TRUE | Completed | EVE | EVE team | 2025-06-16 | 2025-06-20
Design | Item Labels | Send Deposco team pictures and sizes of 2 items labels for jewelry | Task | 3.Medium | TRUE | Completed | EVE | EVE team | 2025-06-16 | 2025-06-20 | MPS sent to Deposco 6.17.25
Design | EVE Design Decision - Reason Codes | Provide reason codes needed for Inventory Adjustment to Dep team | Discussion | 3.Medium | TRUE | Completed | EVE | EVE team | 2025-06-16 | 2025-06-20 | sent to Deposco 6/20. Eve has couple Qs, noted in the doc.
Orientation | Begin development for new socket APIs | Deposco Socket team begins development for new socket APIs as per initial project SOW | Task |  | TRUE | Closed | EVE | EVE team
Orientation | Set up Warehouse UPS Socket | EVE utilizes Deposco help site guides to setup UPS socket connections | Task | 2.High | TRUE | Completed | EVE | Erica | 2025-05-28 | 2025-06-27 | 7/8 Erica (not Sherry) to handle this task. MPS emailed Erica today. Erica has an email out to UPS to get an acct setup. 7/2 MPS following up with Sherry
Orientation | Set up Warehouse STAMPS Socket | EVE utilizes Deposco help site guides to setup STAMPS socket connections | Task | 4.Low | TRUE | Completed | EVE | EVE team | 2025-05-28 | 2025-06-27
Orientation | Set up Warehouse FedEx Socket | EVE utilizes Deposco help site guides to setup FedEx socket connections | Task | 4.Low | TRUE | Closed | EVE | EVE team | 2025-05-28 | 2025-06-27 | 7/2: closing as FedEx is not going to be used
Orientation | Set up Warehouse Shopify Socket | EVE utilizes Deposco help site guides to setup Shopify socket connections | Task | 4.Low | TRUE | Completed | EVE | EVE team | 2025-05-28 | 2025-06-27
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task | 4.Low | TRUE | Hold | DEP/EVE | DEP/EVE |  | 2025-09-12
Design | Accounting Codes for each Type | EVE to provide deposco team with all accounting codes needed to be placed in UPS ref label fields | Task | 2.High | TRUE | Closed | EVE | Erica | 2025-07-03 | 2025-07-11 | 7/11: mps sent to Dep.
Design | Buy in Store, Ship Online Example | EVE to send Deposco an example of a buy in store ship online order to help Deposco determine whether these types of orders come through the ecomm or POS sockets | Task | 2.High | TRUE | Completed | EVE | Sherry | 2025-07-08 | 2025-07-11
Design | Physical Count Adjustment Reason Code | If requested by EVE | Request | 4.Low | FALSE | Completed | DEP | Mitch
Orientation | Master Data - Location | Gather and Upload Initial Location Data | Task | 3.Medium | TRUE | Completed | EVE | Ryan | 2025-05-28 | 2025-07-18 | 7/9 Ryan emailed questions to Mitch, targeting 7/11 delivery 7/15 - initial upload completed, Ryan working on the rest
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task | 4.Low | TRUE | Hold | DEP | Hannah
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task | 4.Low | TRUE | Hold | DEP | Mitch |  | 2025-09-12
Deployment | Execute Cutover Plan Steps |  | Task | 4.Low | TRUE | Hold | DEP/EVE | DEP/EVE |  | 2025-09-19
Design | Master Design Document Delivery | Deliver master design document for EVE team to review | Task | 4.Low | TRUE | Completed | DEP | Mitch | 2025-06-16 | 2025-06-27
Orientation | Master Data - Carton Types | Gather and Upload Carton Types Data | Task | 4.Low | TRUE | Completed | EVE | Ryan | 2025-05-28 | 2025-06-27 | 7/2 Ryan checking with Sherry 7/15 - complete
Design | Store Zones | EVE to decide which zones will be utilized in stores | Discussion | 4.Low | FALSE | Completed | EVE | Sherry | 2025-06-20 | 2025-07-16
Design | EVE - Shipping Services | EVE to provide Deposco team with all shipping services used | Task | 2.High | TRUE | Completed | EVE | EVE team | 2025-06-26 | 2025-07-03 | 7/1: DD correctly reflects all shipping services. Deposco to inform if anything is outstanding for this item.
Design | Store Locations | EVE to decide which locations will be part of the stores | Discussion | 4.Low | FALSE | Completed | EVE | Sherry | 2025-06-20 | 2025-07-16
Design | Cycle Countable Location(s) - Stores | EVE to decide which locations in stores can be cycle count enabled | Discussion | 4.Low | FALSE | Completed | EVE | Sherry | 2025-06-20 | 2025-07-16 | 7/15 - store counts are by facility rather than by location
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task | 4.Low | TRUE | Hold | DEP | Hannah |  | TBD
Design | Department Values | EVE to send Deposco possible values under the Department meta field | Task | 3.Medium | FALSE | Completed | EVE | EVE team | 2025-07-09 | 2025-07-11
Configuration | Example Item for Custom Fields | EVE to provide Deposco an item in sandbox with all three custom fields needing to be mapped (custom.subcategory, custom.department, custom.style_number) to support with Developement. Developement is also asking if these fields are product level or variant level metafields? | Task | 1.Blocker | TRUE | Open | EVE | Sherry | 2025-08-07 | 2025-08-14
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## DEP Config Tasks
Currently in Config
Product / Task Group | Task | SOW Notes | SOW Hours | Pros Estimate | In Scope | Config Code | Configuration Notes | Owner | Status | % Complete
Total Project (Config) |  |  | 476 | 293.5 | [5 empty] | #REF!
Bright Warehouse Configuration (T&M) |  |  | 192 | 133.5 | [5 empty] | 26.87%
Setup | UI Configuration |  | 4 | 4 | TRUE |  |  |  |  | 0%
Setup | - Application Menu & Layout Setup |  |  | 2 | TRUE |  |  | Mitch | To-Do | 0%
Setup | - Initial User Stup |  |  | 2 | TRUE |  |  | Mitch | To-Do | 0%
Setup | Master Data Setup | Setup/Config of Data Exchange to support master data imports | 12 | 11 | TRUE |  |  |  |  | 3.333%
Setup | - Facility |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Henry | Complete - Ready for Client | 0%
Setup | - Location, Zone |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Henry | In Validation | 0%
Setup | - Container |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Henry | In Validation | 0%
Setup | - Carton Type |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Mitch | Complete - Ready for Client | 0%
Setup | - User |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Henry | In Validation | 0%
Setup | - Outbound Transfer Order |  |  | 1 | TRUE | DE Creation | Setup standard template | Henry | In Validation | 0%
Setup | Product Category |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Mitch | Complete - Ready for Client | 0%
Setup | LookUp Table |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Henry | To-Do | 0%
Setup | Marketing Orders |  |  | 1 | TRUE | DE Creation | Setup standard template | Henry | To-Do | 0%
Setup | Printer Resources |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Mitch | Complete - Ready for Client | 0%
Setup | Printer Assignments |  |  | 0.5 | TRUE | DE Creation | Setup standard template | Mitch | Complete - Ready for Client | 0%
Setup | Zones |  |  | 0.5 | TRUE | Zone | Set up all zones | Henry | To-Do | 0%
Setup | Staging Locations |  |  | 0.5 | TRUE | Locations | Set up all staging locations | Henry | To-Do | 0%
Setup | Shopify Mappings |  |  | 0.5 | TRUE | Data Needs | Map fields needed | Mitch | In Validation | 50%
Setup | - Q&A Support in Client Uploads |  |  | 3 | TRUE |  |  | Henry | To-Do | 0%
Inbound | Receiving |  | 12 | 9.75 | TRUE |  |  |  |  | 85.45%
Inbound | - Clothing Receiving |  |  | 3 | TRUE | Inb1.1 | Unit tests complete. All "Container" instances changed to "LPN". Ready for validation. | Henry | Complete - Ready for Client | 100%
Inbound | - Jewelry Receiving |  |  | 2 | TRUE | Inb1.2 | Unit tests complete. All "Container" instances changed to "LPN". Ready for validation. | Henry | Complete - Ready for Client | 100%
Inbound | - Returns Receiving |  |  | 2 | TRUE | Inb1.3 | Unit tests complete. All "Container" instances changed to "LPN". Ready for validation. | Henry | Complete - Ready for Client | 100%
Inbound | - Unreceiving |  |  | 0.5 | FALSE | Inb1.4 | Testing done. Ready for validation. | Henry | Complete - Ready for Client | 100%
Inbound | - Print 1.5’ x 1’ Jewelry Item Label |  |  | 0.25 | FALSE | Inb1.5 | Hours solely for process configuration | Henry | Ready for Internal Review | 90%
Inbound | - Print 1’ x 0.5’ Jewelry Item Label |  |  | 0.25 | FALSE | Inb1.6 | Hours solely for process configuration | Henry | Ready for Internal Review | 90%
Inbound | - Print Clothing Item Label by PO |  |  | 0.25 | FALSE | Inb1.7 | Hours solely for process configuration | Henry | Ready for Internal Review | 90%
Inbound | - Print Clothing Item Label by Item |  |  | 0.25 | FALSE | Inb1.8 | Hours solely for process configuration | Henry | Ready for Internal Review | 90%
Inbound | - Print LPN Label PAL |  |  | 0.25 | FALSE | Inb1.9 | Hours solely for process configuration | Henry | Ready for Internal Review | 90%
Inbound | - Test Cases & Loom Videos |  |  | 3 | FALSE | N/A |  | Henry | Ready for Internal Review | 90%
Inbound | - Testing Support |  |  | 1 | FALSE | N/A |  | Henry | To-Do | 0%
Inbound | Putaway |  | 20 | 20 | TRUE |  |  |  |  | 84.29%
Inbound | - Build Pallet |  |  | 1 | FALSE | Inb2.1 |  | Mitch | Complete - Ready for Client | 100%
Inbound | - Clothing Putaway |  |  | 5 | TRUE | Inb2.2 |  | Mitch | Complete - Ready for Client | 100%
Inbound | - Jewelry Putaway |  |  | 1 | TRUE | Inb2.3 |  | Mitch | Complete - Ready for Client | 100%
Inbound | - Footwear Putaway |  |  | 3 | TRUE | Inb2.4 |  | Mitch | Complete - Ready for Client | 100%
Inbound | - Returns Putaway |  |  | 5 | TRUE | Inb2.5 |  | Mitch | Complete - Ready for Client | 100%
Inbound | - Test Cases & Loom Videos |  |  | 3 | FALSE | N/A |  | Henry | Ready for Internal Review | 90%
Inbound | - Testing Support |  |  | 2 | FALSE | N/A |  | Henry | To-Do | 0%
Inventory Management | Cycle Counting |  | 12 | 10.5 | FALSE |  |  |  |  | 71.25%
Inventory Management | Scheduled Counts by Location - Pick Locations |  |  | 1 | TRUE | Inv1.1 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | Schedudled Counts by Location - Reserve Locations |  |  | 0.5 | TRUE | Inv1.2 | Config done - need to validate that tasks generate with correct master data | Henry | In Validation | 75%
Inventory Management | Create Cycle Count by Location - Handheld |  |  | 0.5 | TRUE | Inv1.3 |  | Henry | Ready for Internal Review | 90%
Inventory Management | Create Cycle Count by Location - Desktop |  |  | 0.5 | TRUE | Inv1.4 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | Create Cycle Count by Item - Handheld |  |  | 0.5 | TRUE | Inv1.5 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | On-Demand Cycle Count |  |  | 0.5 | TRUE | Inv1.6 | Config Done - Need to unit test and change all LPN screen labels to container. | Henry | In Progress | 75%
Inventory Management | Cycle Count |  |  | 2 | TRUE | Inv1.7 | Config Done - Need to unit test and change all LPN screen labels to container. | Henry | In Progress | 75%
Inventory Management | Start Physical Count Admin |  |  | 1 | TRUE | Inv1.8 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | Perform Physical Count |  |  | 1 | TRUE | Inv1.9 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | Variance Approval |  |  | 0 | TRUE | N/A | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | - Test Cases & Loom Videos |  |  | 2 | TRUE | N/A |  | Henry | To-Do | 0%
Inventory Management | - Testing Support |  |  | 1 | TRUE | N/A |  | Henry | To-Do | 0%
Inventory Management | Replenishment |  | 12 | 12.25 | FALSE |  | *Replace with Inventory Consolidation Processes* |  |  | 60%
Inventory Management | - Consolidate in 1D |  |  | 0.5 | TRUE | Inv2.1 |  | Mitch | In Validation | 75%
Inventory Management | - Move to Upper Zone |  |  | 4 | TRUE | Inv2.2 |  | Mitch | In Validation | 75%
Inventory Management | - Move to 1D |  |  | 1 | TRUE | Inv2.3 |  | Mitch | In Validation | 75%
Inventory Management | - Move to 2D |  |  | 1 | TRUE | Inv2.4 |  | Mitch | In Validation | 75%
Inventory Management | - Replenish to 4D and 2D |  |  | 1 | TRUE | Inv2.5 |  | Mitch | In Validation | 75%
Inventory Management | - Consolidation Report |  |  | 0.25 | TRUE | Inv2.6 | Solely for Print report process | Mitch | In Validation | 75%
Inventory Management | - Replenishment Report |  |  | 0.25 | TRUE | Inv2.7 | Solely for Print report process | Mitch | In Validation | 75%
Inventory Management | - Aged Pallet Report |  |  | 0.25 | TRUE | Inv2.8 | Solely for Print report process | Mitch | In Validation | 75%
Inventory Management | - Test Cases & Loom Videos |  |  | 3 | FALSE | N/A |  | Henry | To-Do | 0%
Inventory Management | - Testing Support |  |  | 1 | FALSE | N/A |  | Henry | To-Do | 0%
Inventory Management | Adjust Inventory |  | 0 | 2 | TRUE |  |  |  |  | 45%
Inventory Management | - User Adjust Inventory |  |  | 0.5 | TRUE | Inv3.1 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | - Admin Adjust Inventory |  |  | 0.5 | TRUE | Inv3.2 | Config done - Need to Unit Test | Henry | In Validation | 90%
Inventory Management | - Test Cases & Loom Videos |  |  | 0.5 | FALSE | N/A |  | Henry | To-Do | 0%
Inventory Management | - Testing Support |  |  | 0.5 | FALSE | N/A |  | Henry | To-Do | 0%
Outbound | Outbound Order Management |  | 12 | 6 | TRUE |  |  |  |  | 0%
Outbound | - Cross-Reference Translations |  |  | 2 | TRUE | OrdMgnt1.1 |  | Mitch | To-Do | 0%
Outbound | - Automations |  |  | 2 | TRUE | OrdMgnt1.2 |  | Mitch | To-Do | 0%
Outbound | - POI |  |  | 2 | TRUE | OrdMgnt1.3 |  | Mitch | To-Do | 0%
Outbound | Pickwave Management |  | 12 | 10.75 | TRUE |  |  |  |  | 0%
Outbound | - Profile Based Processing |  |  | 0 | TRUE | Wave1.1 | Train Only | Mitch | To-Do | 0%
Outbound | - Order Based Processing |  |  | 0 | TRUE | Wave1.2 | Train Only | Mitch | To-Do | 0%
Outbound | - Scheduled Processing |  |  | 0 | TRUE | Wave1.3 | Train Only | Mitch | To-Do | 0%
Outbound | - Undo Release |  |  | 0.25 | TRUE | Wave1.4 | Train Only | Mitch | To-Do | 0%
Outbound | - Clothing Singles Profile |  |  | 1 | TRUE | Outb1.1 |  | Mitch | To-Do | 0%
Outbound | - Shoe Singles Profile |  |  | 0.25 | TRUE | Outb1.2 |  | Mitch | To-Do | 0%
Outbound | - Gift Card Singles Profile |  |  | 0.25 | TRUE | Outb1.3 |  | Mitch | To-Do | 0%
Outbound | - Large Order Profile |  |  | 0.5 | TRUE | Outb1.4 |  | Mitch | To-Do | 0%
Outbound | - Small Multis Profile |  |  | 0.5 | TRUE | Outb1.5 |  | Mitch | To-Do | 0%
Outbound | - Large Multis Wave Profile |  |  | 0.5 | TRUE | Outb1.6 |  | Mitch | To-Do | 0%
Outbound | - Gift Card Multis Profile |  |  | 0.5 | TRUE | Outb1.7 |  | Mitch | To-Do | 0%
Outbound | - Trendsend Profile |  |  | 0.5 | TRUE | Outb1.8 |  | Mitch | To-Do | 0%
Outbound | - Exception Repick Profile |  |  | 0.5 | TRUE | Outb1.9.1 |  | Mitch | To-Do | 0%
Outbound | - Trendsend Exception Repick Profile |  |  | 0.5 | TRUE | Outb1.9.2 |  | Mitch | To-Do | 0%
Outbound | - RA Order Profile |  |  | 0.5 | TRUE | Outb1.11 |  | Mitch | To-Do | 0%
Outbound | - Donation Order Profile |  |  | 0.5 | TRUE | Outb1.12 |  | Mitch | To-Do | 0%
Outbound | - Employee POS Profile |  |  | 0.5 | TRUE | Outb1.13 |  | Mitch | To-Do | 0%
Outbound | - Test Cases & Loom Videos |  |  | 3 | TRUE | N/A |  | Mitch | To-Do | 0%
Outbound | - Testing Support |  |  | 1 | TRUE | N/A |  | Mitch | To-Do | 0%
Outbound | Picking |  | 24 | 21 | TRUE |  |  |  |  | 0%
Outbound | - Clothing/Footwear Singles Picking |  |  | 2 | TRUE | Outb2.1 |  | Henry | To-Do | 0%
Outbound | - Gift Card Singles Picking |  |  | 1 | TRUE | Outb2.2 |  | Henry | To-Do | 0%
Outbound | - Large Order Picking |  |  | 1 | TRUE | Outb2.3 |  | Henry | To-Do | 0%
Outbound | - Multis Picking |  |  | 2 | TRUE | Outb2.4 |  | Henry | To-Do | 0%
Outbound | - Gift Card Multis Picking |  |  | 1 | TRUE | Outb2.5 |  | Henry | To-Do | 0%
Outbound | - Trendsend Picking |  |  | 2 | TRUE | Outb2.6 |  | Henry | To-Do | 0%
Outbound | - Exception Repicks Picking |  |  | 2 | TRUE | Outb2.7.1 |  | Henry | To-Do | 0%
Outbound | - Trendsend Repicks Picking |  |  | 1 | TRUE | Outb2.7.2 |  | Henry | To-Do | 0%
Outbound | - RA/Donation Picking |  |  | 1 | TRUE | Outb2.9 |  | Henry | To-Do | 0%
Outbound | - Employee POS Picking |  |  | 1 | TRUE | Outb2.10 |  | Henry | To-Do | 0%
Outbound | - Test Cases & Loom Videos |  |  | 5 | TRUE | N/A |  | Henry | To-Do | 0%
Outbound | - Testing Support |  |  | 2 | TRUE | N/A |  | Henry | To-Do | 0%
Outbound | Packing and Shipping |  | 24 | 18.5 | TRUE |  |  |  |  | 0%
Outbound | - Pack From Container |  |  | 2 | TRUE | Outb3.1 |  | Henry | To-Do | 0%
Outbound | - Hard Close Packing |  |  | 2 | TRUE | Outb3.2 |  | Henry | To-Do | 0%
Outbound | - Soft Close Packing |  |  | 3 | TRUE | Outb3.3 |  | Henry | To-Do | 0%
Outbound | - Assign Trip Packing |  |  | 3 | TRUE | Outb3.4 |  | Henry | To-Do | 0%
Outbound | - Employee POS Ship PAL |  |  | 1 | TRUE | Outb3.5 |  | Henry | To-Do | 0%
Outbound | - Void Shipment |  |  | 0.25 | TRUE | Outb4.1 |  | Henry | To-Do | 0%
Outbound | - Rollback After Picking |  |  | 0.25 | TRUE | Outb4.2 |  | Henry | To-Do | 0%
Outbound | - Test Cases & Loom Videos |  |  | 5 | TRUE | N/A |  | Henry | To-Do | 0%
Outbound | - Testing Support |  |  | 2 | TRUE | N/A |  | Henry | To-Do | 0%
Outbound | Cartonization |  | 8 | 0 | TRUE |  |  |  |  | 0%
| *Descoped* ? |  |  | *Descoped* | FALSE
Outbound | Rate Shopping |  | 8 | 2 | TRUE |  |  |  |  | 0%
| - Generic Profile |  |  | 2 | FALSE | Outb5.1 |  | Henry | To-Do | 0%
Outbound | Transfer Order Support | Support for transfer orders across facilities to support DC to Store, Store to Store, Store to DC transfers. TOs to be sent to DEP via API | 12 | 5.75 | TRUE |  |  |  |  | 0%
Outbound | - Outbound Transfer Order Profile |  |  | 0.75 | TRUE | Outb1.10 |  | Henry | To-Do | 0%
Outbound | - Outbound Transfer Picking |  |  | 2 | TRUE | Outb2.8 |  | Henry | To-Do | 0%
Outbound | - Test Cases & Loom Videos |  |  | 2 | TRUE | N/A |  | Henry | To-Do | 0%
Outbound | - Testing Support |  |  | 1 | TRUE | N/A |  | Henry | To-Do | 0%
Bright Socket Configuration (T&M) |  |  | 136 | 98
Configure | Shopify | Setup/Configuration of Shopify socket for ecommerce -Item Pull -Customer Order Pull -Inventory Push -Ship Notice Push | 32 | 8 | TRUE
Shopify | - Item Pull |  |  | 1 | TRUE |  | - Channel Listings only |  | In Validation
Shopify | - Customer Order Pull |  |  | 4 | TRUE |  | - Paid status - Unfullfilled status |  | In Validation
Shopify | - Ship Notice Push |  |  | 3 | TRUE |  | - Normal (nothing to configure) |  | In Validation
Configure | Shopify POS | Shopify POS Socket configuration Testing & Training -POS Sale/ return -Inventory Sync | 40 | 40 | TRUE |  | (Touchpoints are easy. Assuming DEV hours + tetsing are high to validate how we send ATP) |  |  | 0%
Shopify POS | - Item Pull |  |  | 8 | TRUE |  | - Dev Needed to Pull Metadat field - inbiund mapping tool for vendor --> brandName -Webhooks instead of API calls - Only pull items in Active status |  | In Progress
Shopify POS | - Sales Retail Activity |  |  | 6 | TRUE |  | - CoHeader With type Retail Activity -Facility settings to decrement inventory from where sku exists |  | To-Do
Shopify POS | - Return Retail Activity |  |  | 6 | TRUE |  | -Facility Settings to decide which location to increment item quantity to - CoHeader With type Return |  | To-Do
Shopify POS | - Inventory Sync |  |  | 20 | TRUE |  | - Deposco To Remap where we send the ATP quantities (Pending esimation) - Send ATP Qty API - Only push changes for items where quantities have changed - Facility parameters will control which facilities we sync to |  | To-Do
Configure | API Support | Support for use of Deposco APIs for integration between Deposco & Celerant | 40 | 40 | TRUE |  |  |  |  | 0%
| - Testing & Dev Support |  |  | 40 | FALSE |  |  | Mitch | In Validation | 0%
Configure | UPS |  | 8 | 6 | TRUE |  |  |  |  | 0%
| - Shipping Options Setup |  |  | 2 | TRUE | Ship Ops |  | Henry | To-Do | 0%
| - Setup & Testing Support |  |  | 4 | FALSE | N/A |  | Henry | To-Do | 0%
Configure | USPS |  | 8 | 4 | TRUE |  |  |  |  | 0%
| - Shipping Options Setup |  |  | 0 | FALSE |  |  | Henry | To-Do | 0%
| - Setup & Testing Support |  |  | 4 | FALSE |  |  | Henry | To-Do | 0%
Configure | FedEx |  | 8 | 0 | TRUE |  |  |  |  | 73.5%
| *Descoped* |  |  | 0 | FALSE |  |  | Other
Bright Performance Configuration (T&M) |  |  | 50 | 40 | [5 empty] | 39%
Process Reports | Global Reports |  | 4 | 11 | TRUE |  |  |  |  | 75%
Inbound Labels | Clothing LPN Label |  |  | 2 | TRUE | Inb1.1 | Hours solely for label configuration | Henry | Ready for Internal Review | 90%
Inbound Labels | 1.5’ x 1’ Jewelry Item Label |  |  | 1 | TRUE | Inb1.5 | Hours solely for label configuration | Henry | Ready for Internal Review | 90%
Inbound Labels | 1’ x 0.5’ Jewelry Item Label |  |  | 1 | TRUE | Inb1.6 | Hours solely for label configuration | Henry | Ready for Internal Review | 90%
Inbound Labels | Print Clothing Item Label by PO |  |  | 1 | TRUE | Inb1.7 | Hours solely for label configuration | Henry | Ready for Internal Review | 90%
Inbound Labels | Print Clothing Item Label by Item |  |  | 1 | TRUE | Inb1.8 | Hours solely for label configuration | Henry | Ready for Internal Review | 90%
Outbound Reports | Packing Slip |  |  | 5 | TRUE | Pack Slip | Hours solely for report configuration | Henry | To-Do | 0%
Standard Dashboard and Reporting | Company Reports/Report Builder | Base report builder reports included If additional custom reports are required, CR/SOW may be needed | 12 | 12 | TRUE |  |  |  |  | 45%
Inbound Report | - Open Purchase Order Report Creation |  |  | 1 | FALSE | Inb1.10 | Hours solely for report configuration | Henry | In Validation | 90%
| - Adhoc time to revisit at UAT |  |  | 11 | FALSE |  |  |  |  | 0%
Standard Dashboard and Reporting | Report Scheduling |  | 2 | 2 | TRUE |  |  |  |  | 0%
| - Adhoc time to revisit at UAT |  |  | 2 | FALSE |  |  |  |  | 0%
Standard Dashboard and Reporting | Dashboards |  | 12 | 12 | TRUE |  |  |  |  | 0%
| - Adhoc time to revisit at UAT |  |  | 12 | FALSE |  |  |  |  | 0%
Dashboard and Reporting add-on | Inventory Consolidation Report | Configuration of report to guide inventory consolidation moves within warehouse | 4 | 3 | TRUE |  |  |  |  | 75%
Inventory Management | - Consolidation Report |  |  | 1 | FALSE | Inv2.6 | Hours solely for report config | Mitch | In Validation | 75%
Inventory Management | - Replenishment Report |  |  | 1 | FALSE | Inv2.7 | Hours solely for report config | Mitch | In Validation | 75%
Inventory Management | - Aged Pallet Report |  |  | 1 | FALSE | Inv2.8 | Hours solely for report config | Mitch | In Validation | 75%
Order Consolidation | *Descoped* |  |  | 0 | FALSE |  |  |  |  | 0%
Bright Store Configuration (T&M) |  |  | 62
Configure - Bright Store | Store Fulfillment | Support of fulfillment from retail stores Ship from Store - pick/pack process deployed at store locations. Pickup from Store - will call pickup | 30
- Store Waving
- Store Picking
- Store Packing/Shipping
Configure - Bright Store | Store Receiving | Support of transfer order/purchase order receiving at retail stores | 8
- Bulk Store Receiving
- Grocery Scan Store Receiving
Configure - Bright Store | Store Returns |  | 8 | 0
- Blind Receive Returns
Configure - Bright Store | Store Counting |  | 16
Bright Order Configuration (T&M) |  |  | 36 | 22 | [5 empty] | 18%
Configure - Bright Order | Enterprise Order Management | Setup/ Configuration of base Enterprise Order Management | 12 | 10 | [5 empty] | 54%
Bright Order | Sourcing Groups |  |  | 1 | TRUE | BO1.1 |  | Mitch | In Validation | 90%
Bright Order | Sourcing Profiles |  |  | 1 | TRUE | BO1.2 |  | Mitch | In Validation | 90%
Bright Order | Routing Profiles |  |  | 1 | TRUE | BO1.3 |  | Mitch | In Validation | 90%
Bright Order | - Test Cases & Loom Videos |  |  | 2 | TRUE | N/A |  | Mitch | To-Do | 0%
Bright Order | - Testing Support |  |  | 5 | TRUE | N/A |  | Mitch | To-Do | 0%
Configure - Bright Order | Order Consolidation | *Descoped* | 12 | 0 | [5 empty] | 0%
| *Descoped* |  |  | 0 | [5 empty] | 0%
Configure - Bright Order | Enterprise Inventory Management |  | 12 | 12 | [5 empty] | 0%
Bright Order | Initial Set Up |  |  | 2 |  |  |  | Mitch |  | 0%
Bright Order | Adhoc time to revisit at UAT |  |  | 10 |  |  |  | Mitch |  | 0%

## Recordings
EVE Demo Videos
Date | Category | Config Code | DESCRIPTION | LINK
Process Demos
Integrations
| Inbound | Inb1.1 | - Clothing Receiving | https://www.loom.com/share/d08e95eca2d34dcfa425a3f314fe702f?sid=72f2a374-cfca-49a4-9db8-f6fa65355bd8, https://www.loom.com/share/d58aeae08099463c869f0729a23b16cf?sid=4ee5aab3-cbb2-47fc-9443-0a43d79e2792
| Inbound | Inb1.2 | - Jewelry Receiving | https://www.loom.com/share/a0de2a55b2c24899bc6c3b8f61b5e7ad?sid=56e659f6-f7a6-4d65-b583-071dfaa2e72b
| Inbound | Inb1.3 | - Returns Receiving | https://www.loom.com/share/5365ed976ea94dde984a7c78ae13b36a?sid=074f0503-e970-49bb-8086-3c348275c2a5
| Inbound | Inb1.4 | - Unreceiving | https://www.loom.com/share/dfb085b296bb45de89cc5dd938b98ff7?sid=26dd908f-f4f2-44cd-b9c0-819c76ab9189
| Inbound | Inb1.5 | - Print 1.5’ x 1’ Jewelry Item Label | https://www.loom.com/share/1c092fc137964fa9b0abb9181b637768?sid=5482a094-cf7d-4d18-a958-45d0b2dbe9f4
| Inbound | Inb1.6 | - Print 1’ x 0.5’ Jewelry Item Label | https://www.loom.com/share/8bacd16c27dd45498c451e0d5b94eadf?sid=bd9e3876-6c88-4919-bde4-2cf3c72d7c43
| Inbound | Inb1.7 | - Print Clothing Item Label by PO | https://www.loom.com/share/fdcdcde59cc3428f93cc510858b1ad1b?sid=89f6d30e-ae5f-43bc-b0a7-279fedf4f38b
| Inbound | Inb1.8 | - Print Clothing Item Label by Item | https://www.loom.com/share/4809152cf86343feb3046eab99399691?sid=8db898bb-7ddd-4300-8e54-2b1b2d7fd55a
| Inbound | Inb1.9 | - Print LPN Label PAL | https://www.loom.com/share/383fda0568b8449d9dcc219a68d40db5?sid=5e8d1db4-87ef-46c0-a18b-c5c92eba3c7b
| Inbound | Inb2.1 | - Build Pallet | https://www.loom.com/share/1d1d106bcb964619844bfbbcac78e328?sid=f67e3a28-7edf-4c1a-b7e9-b70f06ebdcce
| Inbound | Inb2.2 | - Clothing Putaway | https://www.loom.com/share/efb2ea35b06d4ff6b9b080549e26df2c?sid=16b8e254-a713-465a-9a8b-33b37e58e7dc
| Inbound | Inb2.3 | - Jewelry Putaway | https://www.loom.com/share/408f9d33919f4691934c64f5d12bb98c?sid=a4e58e1d-7b6f-40b4-b285-f25c987f76d7
| Inbound | Inb2.4 | - Footwear Putaway | https://www.loom.com/share/0657ee3131434f79a7c6443b2d03873b?sid=d43c057f-d5dc-439a-8912-46841f97ba01
| Inbound | Inb2.5 | - Returns Putaway | Pending Updates
| Inventory Management | Inv1.1 | Scheduled Counts by Location - Pick Locations
| Inventory Management | Inv1.2 | Schedudled Counts by Location - Reserve Locations
| Inventory Management | Inv1.3 | Create Cycle Count by Location - Handheld
| Inventory Management | Inv1.4 | Create Cycle Count by Location - Desktop
| Inventory Management | Inv1.5 | Create Cycle Count by Item - Handheld
| Inventory Management | Inv1.6 | On-Demand Cycle Count
| Inventory Management | Inv1.7 | Cycle Count
| Inventory Management | Inv1.8 | Start Physical Count Admin
| Inventory Management | Inv1.9 | Perform Physical Count
| Inventory Management | Inv2.1 | - Consolidate in 1D
| Inventory Management | Inv2.2 | - Move to Upper Zone
| Inventory Management | Inv2.3 | - Move to 1D
| Inventory Management | Inv2.4 | - Move to 2D
| Inventory Management | Inv2.5 | - Replenish to 4D and 2D
| Inventory Management | Inv2.6 | - Consolidation Report
| Inventory Management | Inv2.7 | - Replenishment Report
| Inventory Management | Inv2.8 | - Aged Pallet Report
| Inventory Management | Inv3.1 | - User Adjust Inventory
| Inventory Management | Inv3.2 | - Admin Adjust Inventory
| Outbound | OrdMgnt1.1 | - Cross-Reference Translations
| Outbound | OrdMgnt1.2 | - Automations
| Outbound | OrdMgnt1.3 | - POI
| Outbound | Wave1.1 | - Profile Based Processing
| Outbound | Wave1.2 | - Order Based Processing
| Outbound | Wave1.3 | - Scheduled Processing
| Outbound | Wave1.4 | - Undo Release
| Outbound | Outb1.X | OFP Set Ups/Configuration Options
| Outbound | Outb2.1 | - Clothing/Footwear Singles Picking
| Outbound | Outb2.2 | - Gift Card Singles Picking
| Outbound | Outb2.3 | - Large Order Picking
| Outbound | Outb2.4 | - Multis Picking
| Outbound | Outb2.5 | - Gift Card Multis Picking
| Outbound | Outb2.6 | - Trendsend Picking
| Outbound | Outb2.7.1 | - Exception Repicks Picking
| Outbound | Outb2.7.2 | - Trendsend Repicks Picking
| Outbound | Outb2.8 | - Outbound Transfer Picking
| Outbound | Outb2.9 | - RA/Donation Picking
| Outbound | Outb2.10 | - Employee POS Picking
| Outbound | Outb3.1 | - Pack From Container
| Outbound | Outb3.2 | - Hard Close Packing
| Outbound | Outb3.3 | - Soft Close Packing
| Outbound | Outb3.4 | - Assign Trip Packing
| Outbound | Outb3.5 | - Employee POS Ship PAL
| Outbound | Outb4.1 | - Void Shipment
| Outbound | Outb4.2 | - Rollback After Picking
| Rate Shopping | Outb5.1 | - Generic Profile
Bright Order
Bright Order
Bright Order
Bright Order
Bright Order
Miscellaneous Demos
| Super User Creation |  | Creation of super users in Deposco | https://www.loom.com/share/bb09a5b3140e4e0ea87c2420f1474e05
| E2E Design Demo |  | Demo given last day on site | Recap: EVE - End to End Design Demos June 13
| Printing/Printing Master Data Setup |  | Demo going over printing and printing master data in Deposco | https://www.loom.com/share/56501ab6f7284f16a4dd4c64d3371b4b
| Remorse Period For Fraud Orders |  | Going over remorse period logic in Deposco | https://www.loom.com/share/5e7681cb686f45aa9db27cc4f1b800d6
Abbreviation Glossary
PO | Purchase Order
ITO | Inbound Transfer Order
Scan | Simulate by copy/pasting the barcode value and hitting "Enter" on your keyboard

## Test Cases - Unit
EVE Unit Test Cases |  |  |  | Category | % Complete
|  |  |  | Integrations | 0%
|  |  |  | Order Orchestration | 0%
|  |  |  | Inbound | 0%
|  |  |  | Inventory Management | 0%
|  |  |  | Outbound 1 | 0%
|  |  |  | Outbound 2 | 0%
|  |  |  | Reporting | 0%
|  |  |  | TOTAL | 0%
Category | Subcategory | Config Code | Screen | Scenario | Expected Outcome | Owner | Status | Test Data | Comments
Integrations
Integrations | Shopify - Item Pull | INT1.1
Integrations | Shopify - Item Pull | INT1.1 | Scheduler Criteria: - How Do You Want to Handle Items? = Skip Item Creation and Only Allow Channel Listing Updates/Creation - Shopify Product Status = Active - Select Webhook Events = Blank - Update All = True - Update Pack Weight = False - Map Inventory Item Fields = False | Execute: Run scheudler manually with no input parameters | Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Execute: Run scheudler manually with "Days to Go Back" input parameter set to a valid quantity | Doc Store Created / Search query looks for items created or updated in last X days where X is the valid nubmer entered. | DEP Team | NOT Ready to Test
|  |  |  | Execute: Run scheudler manually with "Days to Go Back" input parameter set to an invalid quantity | Input is ignored -- Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Execute: Run scheduler manually with "Shopify Item Id" input parameter set to a valid item id | Doc Store Created / Search query only looks for items with matchin Shopify Item Id regardless of last updated date | DEP Team | NOT Ready to Test
|  |  |  | Execute: Run scheduler manually with "Shopify Item Id" input parameter set to an invalid item id | Input is ignored -- Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Execute: Run scheduler manually with both valid "Days to Go Back" and "Shopify Item Id" input parameter set | Inputs are ignored -- Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Execute: Set schedule to run hourly and monitor over an hour when no items are created/updated in Shopify | Doc Store Created Hourly with results / Doc Store Status = INFO when no items found | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Execute: Set schedule to run hourly and monitor over an hour when new items are created/updated in Shopify | Doc Store Created Hourly with results / Doc Store Status = Success | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Data: Run scheduler when an item has been created in Shopify but is not yet in Deposco | Doc Store Created / No item created in Deposco | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Data: Run scheduler when an item has previously been created in Deposco but is not yet channel listed to scheduler's Integration Point | Doc Store Created / Channel Listing Created / No Item Updates Made | DEP Team | NOT Ready to Test
Integrations | Shopify - Item Pull | INT1.1 |  | Data: Run scheduler when an item has previously been created in Deposco and is already channel listed to scheduler's Integration Point | Doc Store Created / Channel Listing Updated / No Item Updates Made | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2
Integrations | Shopify - Order Pull | INT1.2 | Scheduler Criteria: - Shopify Status = Open - Financial Status = Any - Fulfillment Status = Unfulfilled - Order Number Convention = order_number--id - Since ID = Blank - Chose Item Number = ID - Source Name = Any - Intangible Line Item Status = Complete - Tag Filter = Blank - Select Webhook Events = Blank - Pull Order Risks = False - Pull Payments = False - Pull Gift Card Lines = True - Enable OMS Support = True - Ignore Existing = False - Ignore Intangible Line Items = False | Execute: scheduled run every 16 minutes |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one valid order ID |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with multiple valid order IDs |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one invalid order ID |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with mix of valid and invalid order IDs |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Number of Days To Go Back (Number)" input parameter set to a valid quantity |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Number of Days To Go Back (Number)" input parameter set to an invalid quantity |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" and with "Number of Days To Go Back (Number)" input parameter set |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: Enable schedule to run hourly and monitor over an hour when no orders are created/updated in Shopify |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Execute: Enable schedule to run hourly and monitor over an hour when new orders are created/updated in Shopify |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull orders not yet in Deposco |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull orders that already exist in Deposco in status "Open" |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull orders that already exist in Deposco in status "Released" |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull orders that already exist in Deposco in status "InFulfillment", "PartiallyInFulfillment", "Complete", "Partially Released" | Not allowed | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull update of address or shipping method change |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull update of partial cancellation |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull update of full order cancellation |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Order Pull | INT1.2 |  | Data: Pull update of items added to order |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3
Integrations | Shopify - Ship Notice | INT1.3 | Endpoint Criteria: - Notify Customer = False - Throttle Group = | Data: Ship full order at one time - single tracking number |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 |  | Data: Ship full order at one time - multiple tracking numbers |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 |  | Data: Ship partial order - single tracking number |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 |  | Data: Ship partial order - multipile tracking numbers |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 |  | Data: Ship order that was manually marked as fulfilled in Shopify | Fail | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 |  | Data: Ship quantity greater than quantity order line in Shopify | Fail | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 | Scheduler Task - Retry Failed Events | Execute: Manually run scheduler to re-generate ship notice for failed transactions |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 |  | Execute: Set scheduler to run automatically re-generate ship notice for failed transactions |  | DEP Team | NOT Ready to Test
Integrations | Shopify - Ship Notice | INT1.3 | Reprocess ESL - PAL | Execute: Re-generate ship notice for failed transaction |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1
Integrations | Shopify POS - Item Pull | INT2.1 | Scheduler Criteria: - How Do You Want to Handle Items? = Create and Update Item and Channel - Shopify Product Status = Active - Select Webhook Events = Products Create, Products Update - Update All = True - Update Pack Weight = True - Map Inventory Item Fields = False | Create a new item in Shopify | Webhooks should fire and pull the item into Deposco | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Update an existing item in Shopify that is already in Deposco | Webhooks should fire and pull the update into Deposco | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Execute: Run scheudler manually with no input parameters | Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Execute: Run scheudler manually with "Days to Go Back" input parameter set to a valid quantity | Doc Store Created / Search query looks for items created or updated in last X days where X is the valid nubmer entered. | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Execute: Run scheudler manually with "Days to Go Back" input parameter set to an invalid quantity | Input is ignored -- Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Execute: Run scheduler manually with "Shopify Item Id" input parameter set to a valid item id | Doc Store Created / Search query only looks for items with matchin Shopify Item Id regardless of last updated date | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Execute: Run scheduler manually with "Shopify Item Id" input parameter set to an invalid item id | Input is ignored -- Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Item Pull | INT2.1 |  | Execute: Run scheduler manually with both valid "Days to Go Back" and "Shopify Item Id" input parameter set | Inputs are ignored -- Doc Store Created / Search query looks for items created or updated in Shopify since last time the scheduler was run. | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Sales Retail Activity | INT2.2
Integrations | Shopify POS - Retail Activity | INT2.2 | Scheduler Criteria: - Pull Gift Card Lines = True | Execute: scheduled run every 16 minutes - no transactions to pull | Doc Store Created / Status INFO | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Retail Activity | INT2.2 |  | Execute: scheduled run every 16 minutes - new transactions to pull | Creates CoHeader of type Retail | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Retail Activity | INT2.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one valid order ID | Creates CoHeader of type Retail | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Retail Activity | INT2.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with multiple valid order IDs |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Retail Activity | INT2.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one invalid order ID |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Retail Activity | INT2.2 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with mix of valid and invalid order IDs |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Returns Retail Activity | INT2.3
Integrations | Shopify POS - Returns Retail Activity | INT2.3 | Scheduler Criteria: N/A | Execute: scheduled run every 25 minutes - no transactions to pull |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Returns Retail Activity | INT2.3 |  | Execute: scheduled run every 25 minutes - new transactions to pull |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Returns Retail Activity | INT2.3 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one valid order ID |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Returns Retail Activity | INT2.3 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with multiple valid order IDs |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Returns Retail Activity | INT2.3 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with one invalid order ID |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Returns Retail Activity | INT2.3 |  | Execute: manual run with "Shopify Order ID(s) To Pull (CSV)" populated with mix of valid and invalid order IDs |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Inventory Sync | INT2.4
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 | Scheduler Criteria: - Measure Name = Total ATP Qty API - Filter Query Name = Blank - Facilities Numbers = EVE099 | Execute: Scheduled inventory sync nightly |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to true |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS- Outbound Inventory Sync | INT2.4 |  | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to false |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Data: Run task when no items have changed ATP since last runtime |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Data: Run task when one or more items have changed ATP since last runtime |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 | Scheduler Criteria: - Measure Name = Total ATP Qty API - Filter Query Name = Blank - Facilities Numbers = EVE099, EVE001 | Execute: Scheduled inventory sync nightly |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to true |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS- Outbound Inventory Sync | INT2.4 |  | Execute: Manual inventory sync with "Exclude Items If Last Run Quantity Is Same" set to false |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Data: Run task when no items have changed ATP since last runtime |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Data: Run task when one or more items have changed ATP since last runtime |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 | Channel Listing PAL: Actions --> Sync Inventory | Execute: Sync inventory for one item manually via PAL |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Execute: Sync inventory for multiple items manually via PAL |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Data: Sync inventory manually via PAL when inventory level has not changed for an item since last sent |  | DEP Team | NOT Ready to Test
Integrations | Shopify POS - Outbound Inventory Sync | INT2.4 |  | Data: Sync inventory manually via PAL when inventory level has changed for an item since last sent |  | DEP Team | NOT Ready to Test
Integrations | API Support - PO Push | INT3.1
Integrations | PO Push | INT3.1 | Purchase Order API v1.0 | Create PO with one line |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Create PO with multiple lines |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Create PO for specific receiving facility |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Create PO in a "New" status |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Create PO with a specific Planned Arrival Date |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Update PO Header and Lines with Header in a "New" status |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Update PO Header and Lines with Header in a "Partial Receipt" status |  | DEP Team | NOT Ready to Test
Integrations | PO Push | INT3.1 |  | Update PO Header and Lines with Header in a "Received" status | Fail | DEP Team | NOT Ready to Test
Integrations | API Support - CO Push | INT3.2
Integrations | CO Push | INT3.2 | Customer Order API v1.0 | Create CO with one line |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Create CO with multiple lines |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Create CO for specific shipping facility |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Create CO in a "New" status |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Update CO Header and Lines with Header in "xxx" status |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Update CO Header and Lines with Header in "xxx" status |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Update CO Header and Lines with Header in "xxx" status |  | DEP Team | NOT Ready to Test
Integrations | CO Push | INT3.2 |  | Update CO Header and Lines with Header in "xxx" status |  | DEP Team | NOT Ready to Test
Integrations | API Support - Receipt Line Pull | INT3.3
Integrations | Receipt Line Pull | INT3.3 | Search API v1.0 - Receipt Lines Search Criteria: - Created Date >= Last Time Pulled | Search for receipt lines when none have been created since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when one has been created since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when multiple have been created since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when PO's have been received since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when ITO's have been received since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when blind receipts have been processed since last time pulled. |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when inbound order has been partially received since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Receipt Line Pull | INT3.3 |  | Search for receipt lines when inbound orders have been received in multiple facilities |  | DEP Team | NOT Ready to Test
Integrations | API Support - Shipment Pull | INT3.4
Integrations | Shipment Pull | INT3.4 | Search API v1.0 - Shipments Search Criteria: - Actual Ship Date >= Last Time Pulled - Type = Outbound Shipment - Status = Shipped, Partially Shipped | Search for shipments when none have been shipped since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments when one has been shipped since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments when multiple have been shipped since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments when SO's have been shipped since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments when OTO's have been shipped since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments when orders have shipped from multiple facilities |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments for parcel shipped orders |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4 |  | Search for shipments for freight/outside system shipped orders |  | DEP Team | NOT Ready to Test
Integrations | Shipment Pull | INT3.4
Integrations | Shipment Pull | INT3.4
Integrations | Shipment Pull | INT3.4
Integrations | Shipment Pull | INT3.4
Integrations | API Support - Inventory Adjustment Pull | INT3.5
Integrations | Inventory Adjustment Pull | INT3.5 | Search API v1.0 - Inventory Adjustments Search Criteria: - Created Date >= Last Time Pulled | Search for adjustments when none have occurred since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Inventory Adjustment Pull | INT3.5 |  | Search for adjustments when one had occurred since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Inventory Adjustment Pull | INT3.5 |  | Search for adjustments when multiple have occurred since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Inventory Adjustment Pull | INT3.5 |  | Search for adjustments when multiple have occurred from different facilities since the last time pulled |  | DEP Team | NOT Ready to Test
Integrations | API Support - Canceled CoLine Pull | INT3.6
Integrations | Canceled CoLine Pull | INT3.6 | Search API v1.0 - CoLines Search Criteria: - Updated Date >= Last Time Pulled - Canceled Quantity >= 1 | Search for cancellations when none have occurred since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Canceled CoLine Pull | INT3.6 |  | Search for cancellations when one has occurred since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Canceled CoLine Pull | INT3.6 |  | Search for cancellations when multiple have occurred since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | Canceled CoLine Pull | INT3.6 |  | Search for cancellations when multiple have occurred from different faciliteis since last time pulled |  | DEP Team | NOT Ready to Test
Integrations | UPS - Shipping | INT4.1
Integrations | Shipping Label | INT4.1 | Pack From Container Shipping Mechanism | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | Shipping Label | INT4.1 |  | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | Shipping Label | INT4.1 |  | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | Shipping Label | INT4.1 |  | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | USPS - Shipping | INT5.1
Integrations | Shipping Label | INT5.1 | Pack From Container Shipping Mechanism | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | Shipping Label | INT5.1 |  | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | Shipping Label | INT5.1 |  | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Integrations | Shipping Label | INT5.1 |  | Retrieve label for XXX Ship Via |  | DEP Team | NOT Ready to Test
Order Orchestration
Order Orchestration | Preprocessing - Data Validations |  | Data Scenarios | Ship Via missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) | DEP Team | NOT Ready to Test
Order Orchestration | Preprocessing - Data Validations |  |  | Ship To Address info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) | DEP Team | NOT Ready to Test
Order Orchestration | Preprocessing - Data Validations |  |  | Trading Partner missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) | DEP Team | NOT Ready to Test
Order Orchestration | Preprocessing - Data Validations |  |  | Line Item info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) | DEP Team | NOT Ready to Test
Order Orchestration | Preprocessing - Data Validations |  |  | Multiple data validations are triggered on CO | Order goes to Review status until all data is fixed and re-processing has been run (scheduled or manual) | DEP Team | NOT Ready to Test
Order Orchestration | Preprocessing - Data Validations |  |  | Duplicate order warning is triggered | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) | DEP Team | NOT Ready to Test
Order Orchestration | Preprocessing - Data Validations |  |  | No data validation is triggered | Order is either Back Ordered or Released automatically upon creation | DEP Team | NOT Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection |  |  | Order/order line meets ____ criteria | Order sources to Sourcing Group A based on sourcing profile. | DEP Team | NOT Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection |  |  | Order/order line meets no matching Sourcing Selection Criteria | Order goes to Review with CoNotice message that sourcing could not be completed | DEP Team | NOT Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile |  |  | Order meets ____ criteria | Order uses Routing Profile A based on routing selection profile. | DEP Team | NOT Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile |  |  | Order meets no matching Routing Selection Criteria | Order goes to Back Order | DEP Team | NOT Ready to Test
Order Orchestration | Order Release - Available Inventory |  |  | Inventory not available to fulfill entire CO in facility A | CO Back Orders | DEP Team | NOT Ready to Test
Order Orchestration | Order Release - Available Inventory |  |  | Inventory is available to fulfill entire CO in facility A | CO Releases to facility A and creates an SO | DEP Team | NOT Ready to Test
Order Orchestration | Order Management - Scheduled Routing |  | Processing Execution Scenarios | Scheduled re-route attempt on orders in Back Order status | Orders in Back Order automatically re-routed ever x hours. Order either stays in Back Order or moves to Released if inventory now available. | DEP Team | NOT Ready to Test
Order Orchestration | Order Management - Order Consolidation |  |  | Run scheduled routing when multiple orders meet consolidation condition | One SO created for multiple COs | DEP Team | NOT Ready to Test
Order Orchestration | Order Exception Management - Reprocess |  |  | Manual Reprocess CO in Review status | Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. | DEP Team | NOT Ready to Test
Order Orchestration | Order Exception Management - Reprocess |  |  | Scheduled Reprocess CO in Review status | Orders in Review automatically reprocessed every x hours. Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. | DEP Team | NOT Ready to Test
Order Orchestration | Enterprise Inventory Management |  | Reporting and Visibility | Inventory by Facility | Reports execute timely and accurately for all skus | DEP Team | NOT Ready to Test
Inbound
Receiving | Clothing Receiving | Inb1.1
Inbound | Receiving - Clothing | Inb1.1 | "Identifier Input" Screen | Scan a Clothing item that is on an open PO or ITO to begin receiving - where there is only one PO or ITO open for the item in the user's active facility | User is brought to "Receive Item" Screen | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan a Clothing item that is on an open PO or ITO to begin receiving - where there are mutliple PO's/ITO's open for the item in the user's active facility | User is brought to "Multiple Entries Found" Screen | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan a Non-Clothing item on PO or ITO to begin receiving | User is brought to "Receive Item" Screen or "Multiple Entries Found" Screen depending on how many PO's exist. No validation in place to ensure proper button is used for right products. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan a Clothing PO or ITO number to begin receiving | User is brought to "Receive Item" Screen | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan a Non-Clothing PO or ITO number to begin receiving | User is brought to "Receive Item" Screen or "Multiple Entries Found" Screen depending on how many PO's exist. No validation in place to ensure proper button is used for right products. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan item not on any PO or ITO to begin receiving | Error message: "Unable to find entity for identifier: [XXX] that is eligible to receive." | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan PO or ITO number that does not exist in user's active facility to begin receiving | Error message: "You can not receive this order as its ship to facility is: [XXX]." | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan PO or ITO with no valid order lines or quantities to receive | Error message: "Purchase Order [XXX] can not be received in because it is in status [XXX]." | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Select submit without entering an indetifier | Error message: "Please enter an identifier." | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 | "Multiple Entries Found" Screen | Click Back | User is brought back to "Identifier Input" Screen | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Click Submit without selecting an order from the listbox | User is brought back to "Identifier Input" Screen Error message "Please select a valid entry." is displayed. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Select an order from the listbox and click Submit | User is brought to "Receive Item" Screen. All eligible items/quantities to be received for the order are displayed. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 | "Receive Item" Screen | Click Back without scanning any items | User is brought back to "Identifier Input" Screen. PO/ITO status is unchanged, no new receipt lines created | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Click Finish without scanning any items | User stays on the "Receive Item" Screen | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Click Next without selecting an item in the listbox when multiple items are present in listbox | Error: Please scan an item. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Click New LPN without entering any values | User is brought to "Identifier Input" Screen and prompted for next LPN to receive into | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Click New LPN after entering item | User is brought to "Identifier Input" Screen and prompted for next LPN to receive into | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan any valid item and hit Next | Error message: "Please scan a container number." | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan any valid item and scan an invalid LPN that does not exist in the system | User is brought back to the "Receive Item" Screen for the next unit or LPN to be scanned. The invalid LPN is created in Deposco. The PO is now in a 'Receiving' status. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan any valid item and scan any valid LPN that exists in the system. Enter a receiving Note. | User is brought back to the "Receive Item" Screen for the next unit or LPN to be scanned. The PO is now in a 'Receiving' status. A note with title 'Receipt Note' is created on the PO | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan any valid item and scan any valid LPN that exists in the system. Do no enter a receiving Note. | User is brought back to the "Receive Item" Screen for the next unit or LPN to be scanned. The PO is now in a 'Receiving' status. No note is created | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Scan an item not on the PO and hit Next | Error: "Unable to find order line for item: XXX" | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | After receiving part of a PO select 'Finish'. | User is brought back to "Identifier Input" Screen. The PO is now in a 'Partial Reciept' Status | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | After receiving the full PO select 'Finish'. | User is brought back to "Identifier Input" Screen. The PO is now in a 'Received' Status | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 | "Identifier Input" Screen (LPN) | Back | User is brought back to the "Receive Item" Screen and can continue to receive into original LPN. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Next without LPN | User is brought back to the "Receive Item" Screen but is prompted to scan a new container. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Next with LPN that exists | User is brought back to the "Receive Item" Screen and can receive into the new LPN. | DEP Team | Ready to Test
Inbound | Receiving - Clothing | Inb1.1 |  | Next with LPN that does not exist | User is brought back to the "Receive Item" Screen and can receive into the new LPN. The new LPN is created in Deposco. | DEP Team | Ready to Test
Receiving | Jewelry/Footwear Receiving | Inb1.2
Inbound | Receiving - Jewelry/Footwear | Inb1.2 | "Identifier Input" Screen | All Scenarios Tested in Inb1.1 Clothing Receiving | All Scenarios Tested in Inb1.1 Clothing Receiving | DEP Team | Invalid
Inbound | Receiving - Jewelry/Footwear | Inb1.2 | "Multiple Entries Found" Screen | All Scenarios Tested in Inb1.1 Clothing Receiving | All Scenarios Tested in Inb1.1 Clothing Receiving | DEP Team | Invalid
Inbound | Receiving - Jewelry/Footwear | Inb1.2 | "Receive Item" Screen | All Scenarios Tested in Inb1.1 Clothing Receiving | All Scenarios Tested in Inb1.1 Clothing Receiving | DEP Team | Invalid
Inbound | Receiving - Jewelry/Footwear | Inb1.2 | "Pack Quantity" Screen | Click Back | User is brought back to "Receive Item" Screen PO/ITO status is unchanged, no new receipt lines created | DEP Team | Ready to Test
Inbound | Receiving - Jewelry/Footwear | Inb1.2 |  | Click Next or hit "Enter" on keyboard without entering a quantity to receive | Error: "Please enter a quantity to receive." | DEP Team | Ready to Test
Inbound | Receiving - Jewelry/Footwear | Inb1.2 |  | Click Next or hit "Enter" on keyboard after entering a quantity to receive that is less than the "Remaining Qty" displayed | User is brought back to the "Receive Item" Screen. The remaining quantity that can be received is displayed. The PO is in a 'Receiving' status. | DEP Team | Ready to Test
Inbound | Receiving - Jewelry/Footwear | Inb1.2 |  | Click Next or hit "Enter" on keyboard after entering a quantity to receive that is equal to the "Remaining Qty" displayed. Enter a note | If there is more to receive the user is brought back to the "Receive Item" Screen. The remaining quantity that can be received is displayed. The PO is in a 'Receiving' status. A order line note is created If that was the last item to receive the user is broguht tot the "Identifier Input" screen and the message "All lines have been received." appears. The PO is a 'Receipt' status and all received line quanties are as expected. A order line note is not created | DEP Team | Ready to Test
Inbound | Receiving - Jewelry/Footwear | Inb1.2 |  | Click Next or hit "Enter" on keyboard after entering a quantity to receive that is equal to the "Remaining Qty" displayed. Do not enter a note | If there is more to receive the user is brought back to the "Receive Item" Screen. The remaining quantity that can be received is displayed. The PO is in a 'Receiving' status. If that was the last item to receive the user is broguht tot the "Identifier Input" screen and the message "All lines have been received." appears. The PO is a 'Receipt' status and all received line quanties are as expected. | DEP Team | Ready to Test
Inbound | Receiving - Jewelry/Footwear | Inb1.2 |  | Click Next or hit "Enter" on keyboard without after entering a quantity to receive that is greater than the "Remaining Qty" displayed | If there is more to receive the user is brought back to the "Receive Item" Screen. The remaining quantity that can be received is displayed. The PO is in a 'Receiving' status. If that was the last item to receive the user is broguht tot the "Identifier Input" screen and the message "All lines have been received." appears. The PO is a 'Receipt' status and all received line quanties are as expected. | DEP Team | Ready to Test
Receiving | Returns Receiving | Inb1.3
Inbound | Receiving - Returns | Inb1.3 | "Identifier Input" Screen | Input any identifier | User is brought to "Confirm Blind Order" Screen | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.3 |  | Input no identifier and select 'Submit' | User is brought to "Confirm Blind Order" Screen | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.3 | "Confirm Blind Order" Screen | Click Back | User is brought back to "Identifier Input" Screen | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.3 |  | Click Next | User is brought to "Receive Item" Screen with no items in listbox to receive and auto-generated Blind Order Number | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 | "Receive Item" Screen | Click Back without scanning any items | User is brought back to "Identifier Input" Screen. The Blind receipt is created in Deposco with no Order Lines. | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Click Finish without scanning any items | A blind receipt is created with 0 lines and Includes Error Message: "Blind Receipt [XXX] can not be received in because it is in status [Received]." | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Click Next without selecting an item | Error: Please scan an item. | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Click New LPN without entering any values | User is brought to "Identifier Input" Screen and prompted for next LPN to receive into | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Click New LPN after entering item | User is brought to "Identifier Input" Screen and prompted for next LPN to receive into | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Scan any valid item and hit Next | Error message: "Please scan a container number." | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Scan any valid item and scan an invalid LPN that does not exist in the system | User is brought back to the "Receive Item" Screen for the next unit or LPN to be scanned. The invalid LPN is created in Deposco. The Blind Reciept is now in a 'Receiving' status. | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Scan any valid item and scan any valid LPN that exists in the system. Enter a receiving Note. | User is brought back to the "Receive Item" Screen for the next unit or LPN to be scanned. The Blind Reciept is now in a 'Receiving' status. A note with title 'Receipt Note' is created on the Blind Reciept | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | Scan any valid item and scan any valid LPN that exists in the system. Do not enter a receiving Note. | User is brought back to the "Receive Item" Screen for the next unit or LPN to be scanned. The Blind Reciept is now in a 'Receiving' status. No note is created | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.1 |  | After receiving enough products select 'Finish'. | User is brought back to "Identifier Input" Screen. The Blind Reciept is now in a 'Received' Status | DEP Team | NOT Ready to Test
Inbound | Receiving - Returns | Inb1.3 | "Identifier Input" Screen (LPN) | All Scenarios Tested in Inb1.1 Clothing Receiving | All Scenarios Tested in Inb1.1 Clothing Receiving | DEP Team | Invalid
Receiving | Unreceiving | Inb1.4
Inbound | Unreceive | Inb1.4 | "Select Order To UnReceive" Screen | Select "Back" | User is brought back to previous handheld menu screen. | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Select "Sumit" or hit "Enter" on your keyboard without entering anything in the "Order Number" prompt | Error Message: "Please enter a valid order number to un-receive." | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Submit/Enter with valid PO with stock in receiving location | User is brought to the "Select Item to UnReceive" Screen | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Submit/Enter with valid PO with stock NOT in receiving location | User is brought to the "Select Item to UnReceive" Screen | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Submit/Enter with invalid PO | Error Message: Order [XXX] not found. Please enter a valid order number to un-receive. | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 | "Select Item To UnReceive" Screen | Scan or select item, scan a container and click submit/enter without entering a quantity | Error Message: "Quantity is a required field." | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Scan item, enter a container, and enter a quantity greater than the quantity received into that container | Container [XXX] does not have enough quantity. Expected [XX] but only found [XX]. | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Scan item and enter a quantity less than or equal to the quantity shown in the listbox. Leave container entry blank. | Error Message: "Container is a required field." | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Scan the container and enter a quantity less than or equal to the quantity in the container. | Message "Item XXXX successfully unreceived." | DEP Team | Ready to Test
|  |  |  | Scan the container NO LONGER IN RECEIVING and enter a quantity less than or equal to the quantity in the container. | Error: "Container [XXX]'s current location [XXX] is not at default unreceiving location [Receiving]. Please move the container before unreceiving." | DEP Team | Ready to Test
Inbound | Unreceive | Inb1.4 |  | Click "Back" | User is brought back to the "Select Order To UnReceive" Screen | DEP Team | Ready to Test
Receiving | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 | "Print Report" Screen | Click "Back" | User is brought back to previous menu screen. | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 |  | Click "Submit" or hit "Enter" on your keyboard without entering item or quantity values. | Error Message: "Please enter a valid number of copies to print.'' | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 |  | Submit/Enter after inputting only item number | Error Message: "Please enter a valid number of copies to print.'' | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 |  | Submit/Enter after inputting only quantity to print | Error Message: "Item Number: is required. | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 |  | Submit/Enter after inputting invalid item | Nothing prints | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 |  | Submit/Enter after inputting valid item and quantity - user is NOT properly assigned to a receiving printer resource | Error Message: Cannot find printer for user 'XXX' and report 'XXX'. | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 |  | Submit/Enter after inputting valid item and quantity - user is properly assigned to a receiving printer resource | Quantity of labeles entered by user prints for item entered by user on user's assigned print station. | DEP Team | Ready to Test
Inbound | Print 1.5’ x 1’ Jewelry Item Label | Inb1.5 | Label Validation | Print 1.5’ x 1’ Jewelry Item Label Validation | All fields on the label are accurate, format and size are accurate, printing as expected out of printer. | DEP Team | NOT Ready to Test |  | Needs Inbound Printers set up
Receiving | Print 1’ x 0.5’ Jewelry Item Label | Inb1.6
Inbound | Print 1’ x 0.5’ Jewelry Item Label | Inb1.6 | "Print Report" Screen | All Scenarios Tested in Inb1.5 | All Scenarios Tested in Inb1.5 | DEP Team | Invalid
Inbound | Print 1’ x 0.5’ Jewelry Item Label | Inb1.6 | Label Validation | Print 1’ x 0.5’ Jewelry Item Label Validation | All fields on the label are accurate, format and size are accurate, printing as expected out of printer. | DEP Team | NOT Ready to Test |  | Needs Inbound Printers set up
Receiving | Print Clothing Item Label by PO | Inb1.7
Inbound | Print Clothing Item Label by PO | Inb1.7 | "Print Report" Screen | Click "Back" | User is brought back to previous menu screen. | DEP Team | Ready to Test
Inbound | Print Clothing Item Label by PO | Inb1.7 |  | Click "Submit" or hit "Enter" on your keyboard without entering a PO value. | Error Message: "Purchase Order Number: is required.''. | DEP Team | Ready to Test
Inbound | Print Clothing Item Label by PO | Inb1.7 |  | Submit/Enter after inputting invalid PO | Nothing prints | DEP Team | Ready to Test
Inbound | Print Clothing Item Label by PO | Inb1.7 |  | Submit/Enter after inputting valid PO - user is properly assigned to a receiving printer resource | All labels print out for each item on the PO and the number of labels = order pack quantity | DEP Team | Ready to Test
Inbound | Print Clothing Item Label by PO | Inb1.7 |  | Submit/Enter after inputting valid PO - user is NOT properly assigned to a receiving printer resource | Error Message: Cannot find printer for user 'XXX' and report 'XXXX' | DEP Team | Ready to Test
Inbound | Print Clothing Item Label by PO | Inb1.6 | Label Validation | Clothing Item Label by PO Validation | All fields on the label are accurate, format and size are accurate, printing as expected out of printer. | DEP Team | NOT Ready to Test |  | Needs Inbound Printers set up
Receiving | Print Clothing Item Label by Item | Inb1.8
Inbound | Print Clothing Item Label by Item | Inb1.8 | "Print Report" Screen | All Scenarios Tested in Inb1.5 | All Scenarios Tested in Inb1.5 | DEP Team | Invalid
Inbound | Print Clothing Item Label by Item | Inb1.8 | Label Validation | Clothing Item Label by Item Validation | All fields on the label are accurate, format and size are accurate, printing as expected out of printer. | DEP Team | NOT Ready to Test |  | Needs Inbound Printers set up
Receiving | Print LPN Label PAL | Inb1.9
Inbound | Print LPN Label PAL |  | Entity Print Screen | Select Printer and select "Print" | LPN label is printed out of the selected printer | DEP Team | NOT Ready to Test |  | Needs Inbound Printers set up
Inbound | Print LPN Label PAL |  | Label Validation | LPN Label Validation | All fields on the label are accurate, format and size are accurate, printing as expected out of printer. | DEP Team | NOT Ready to Test |  | Needs Inbound Printers set up
Putaway | Build Pallet | Inb2.1
Inbound | Build Pallet | Inb2.1 | "Select or scan new pallet" Screen | Click "Back" | User is brought back to previous handheld menu screen. | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Click "Next" without selecting/scanning an LPN | Error Message: Please enter the destination container. | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Scan an LPN from the list and hit "Next" | User is brought to the "Select Carton LPN" Screen | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Scan an LPN not on the list and hit "Next" | User is brought to the "Select Carton LPN" Screen and an LPN is created with the scanned value as the identifier | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 | "Select Carton LPN" Screen | Click "Back" | User is brought back to "Select or scan new pallet" Screen | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Click "Finish" without scanning any LPNs | User is brought back to "Select or scan new pallet" Screen. No child containers added to pallet. | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Click Add to Pallet or hit "Enter" on keyboard without scanning/entering an LPN number to add | Error Message: Please enter a container. | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Scan/enter an LPN not in the receiving location to add to pallet | Error Message: The container [XXX] is in the [XXX] location. Please move the container to the [Receiving] location. | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Scan/enter an LPN that is in the receiving location to add to pallet | Screen Message: Container [XXX] was added to destination LPN. Scanned LPN is added to parent LPN (pallet) | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Scan/enter an LPN that is already on the pallet | Screen Message: Container [XXX] was removed from destination LPN. Scanned LPN is removed from parent LPN (pallet) | DEP Team | NOT Ready to Test
Inbound | Build Pallet | Inb2.1 |  | Click "Finish" after scanning LPNs onto pallet. | User is brought back to "Select or scan new pallet" Screen. Child containers now exist under pallet container. | DEP Team | NOT Ready to Test
Putaway | Clothing Putaway | Inb2.2
Inbound | Putaway - Clothing | Inb2.2 | "Scan Container To Move" Screen | Click "Back" | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter without scanning an LPN | Error Message: "Container number can not be empty" | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning an invalid LPN | Error Message: "Please use the valid Container Number." | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid Pallet LPN | User is brought to "Scan Destination Location" Screen. User is displayed one lists: - Empty locations in Pallet zones | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid Box LPN | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - Any locations that already have the item in the current LPN stored - Empty locations and what zone they are in | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid LPN when there are other LPNs with stock for that item in the Receiving location | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - NOT EMPTY - Any locations that already have the item in the current LPN stored - Empty locations and what zone they are in | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid LPN when there are no other LPNs with stock for that item in the Receiving location | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - EMPTY - Any locations that already have the item in the current LPN stored - Empty locations and what zone they are in | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid LPN when there are locations that already hold the item to be putaway | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - Any locations that already have the item in the current LPN stored - NOT EMPTY - Empty locations and what zone they are in | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid LPN when there are no locations that already hold the item to be putaway | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - Any locations that already have the item in the current LPN stored - EMPTY - Empty locations and what zone they are in | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid LPN when there no are empty locations | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - Any locations that already have the item in the current LPN stored - Empty locations and what zone they are in - EMPTY | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Continue/Enter with scanning a valid LPN when there are empty locations | User is brought to "Scan Destination Location" Screen. User is displayed three lists: - Any other LPN's in the Receiving location with the same sku inside - Any locations that already have the item in the current LPN stored - Empty locations and what zone they are in - NOT EMPTY | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 | "Scan Destination Location" Screen | Click "Back" | User is brought back to "Scan Container To Move" Screen | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Next/Enter without scanning a destination Location | Error Message: "Please enter a locator." | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Next/Enter scanning any nonvalid LPN-controlled storage location | Error Message: "Please enter a valid locator." | DEP Team | NOT Ready to Test
Inbound | Putaway - Clothing | Inb2.2 |  | Next/Enter scanning any valid LPN-controlled storage location | Screen Message: Container [XXX] has been moved to [XXX] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Putaway | Jewelry Putaway | Inb2.3
Inbound | Putaway - Jewelry | Inb2.3 | "Scan Container To Move" Screen | Click "Back" | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 |  | Continue/Enter without scanning an LPN | Error Message: "Container number can not be empty" | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 |  | Continue/Enter with scanning an invalid LPN | Error Message: "Please use the valid Container Number." | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 |  | Continue/Enter with scanning a valid LPN | User is brought to "Scan Destination Location" Screen. User is displayed no suggested location. | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 | "Scan Destination Location" Screen | Click "Back" | User is brought back to "Scan Container To Move" Screen | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 |  | Next/Enter without scanning a destination LPN | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 |  | Next/Enter scanning any valid staging location | Screen Message: Container [XXX] has been moved to [XXX] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Inbound | Putaway - Jewelry | Inb2.3 |  | Next/Enter scanning any valid LPN-controlled storage location | Screen Message: Container [XXX] has been moved to [XXX] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Putaway | Footwear Putaway | Inb2.4
Inbound | Putaway - Footwear | Inb2.4 | "Move Cart Input Screen" | Scan/enter valid cart | User is brought to "Move Source Screen" and is displayed a summary of items and units present on cart. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan/enter invalid cart | Error Message: Please enter a valid cart number. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Click "Inventory Menu" | User is brought back to handheld menu | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 | "Move Source Screen" | Click "Back" | User is brought back to "Move Cart Input Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Click "Move" with stock on cart | User is brought to "Move Item Screen" and displayed items and quantities to be put away | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 | "Move Item Screen" | Click "Back" | User is brought back to "Move Source Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Click "All" | User is brought to "Move All Destination Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Submit/enter without selecting/scanning an item | Error Message: "Please select a valid entry from the list." | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Submit/enter after scanning an item but not entering a quantity | Error Message: Please enter a valid item quantity. | DEP Team | NOT Ready to Test
|  |  |  | Submit/enter after scanning an item and entering a quantity greater than the quantity shown on the screen. | Error Message: Quantity to move (X) larger than quantity in found stocks (X). | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Submit/enter after scanning an item and entering a quantity less than or equal to the quantity shown on the screen | User is brought to "Move Destination Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 | "Move Destination Screen" | Screen validation | User is brought to enter the quantity first, then autotabs to Item to move | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Click "Back" | User is brought back to "Move item Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Click "Submit" without entering a location | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan/enter a valid storage location (LPN controlled) | Move Destination Screen is refreshed with LPN prompt | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan an invalid location | Error Message: Please enter a valid locator in the current facility. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 | "Move All Destination Screen" | Scan valid staging location | User is brought back to handheld main menu. Screen Message: All Items Moved | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan valid storage location (LPN controlled) | User is brought to "Scan LPN Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan invalid location | Error Message: Please enter a valid locator in the current facility. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 | "Scan LPN Screen" | Scan valid LPN in location and the move is not the last move in the cart | User is brought back to handheld main menu. Screen Message: All Items Moved Stock is added to LPN in location. | DEP Team | NOT Ready to Test
|  |  |  | Scan valid LPN in location and the move is the last of the cart | Move Item Screen | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan invalid LPN | User is brought back to handheld main menu. Screen Message: All Items Moved LPN scanned is created in location scanned. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan valid LPN that exists in a different location | Error Message: LPN is not in the destination location. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 | "Move All Destination Screen" with LPN Prompt | Scan valid LPN in location | User is brought back to handheld main menu. Screen Message: All Items Moved Stock is added to LPN in location. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan invalid LPN | User is brought back to handheld main menu. Screen Message: All Items Moved LPN scanned is created in location scanned. | DEP Team | NOT Ready to Test
Inbound | Putaway - Footwear | Inb2.4 |  | Scan valid LPN that exists in a different location | Error Message: LPN is not in the destination location. | DEP Team | NOT Ready to Test
Putaway | Returns Putaway | Inb2.5
Inbound | Putaway - Returns | Inb2.5 | "Move Cart Input Screen" | All Scenarios Tested in Inb2.4 | All Scenarios Tested in Inb2.4 | DEP Team | Invalid
Inbound | Putaway - Returns | Inb2.5 | "Move Source Screen" | All Scenarios Tested in Inb2.4 | All Scenarios Tested in Inb2.4 | DEP Team | Invalid
Inbound | Putaway - Returns | Inb2.5 | "Move Item Screen" | All Scenarios Tested in Inb2.4 | All Scenarios Tested in Inb2.4 | DEP Team | Invalid
Inbound | Putaway - Returns | Inb2.5 | "Move Destination Screen" | Screen validation | User is brought to enter the item first, quantity is prepopulated with "1". All locations are in pick sequence order and any products that do not have stock have "R1" populated | DEP Team | NOT Ready to Test
Inbound | Putaway - Returns | Inb2.5 |  | Click "Back" | User is brought back to "Move item Screen" | DEP Team | NOT Ready to Test
Inbound | Putaway - Returns | Inb2.5 |  | Click "Submit" without entering a location | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inbound | Putaway - Returns | Inb2.5 |  | Scan/enter a valid staging location | User is brought back to handheld main menu. Screen Message: All Items Moved | DEP Team | NOT Ready to Test
Inbound | Putaway - Returns | Inb2.5 |  | Scan/enter a valid storage location (LPN controlled) | Move Destination Screen is refreshed with LPN prompt | DEP Team | NOT Ready to Test
Inbound | Putaway - Returns | Inb2.5 |  | Scan an invalid location | Error Message: Please enter a valid locator in the current facility. | DEP Team | NOT Ready to Test
Inbound | Putaway - Returns | Inb2.5 | "Move All Destination Screen" | All Scenarios Tested in Inb2.4 | All Scenarios Tested in Inb2.4 | DEP Team | Invalid
Inbound | Putaway - Returns | Inb2.5 | "Scan LPN Screen" | All Scenarios Tested in Inb2.4 | All Scenarios Tested in Inb2.4 | DEP Team | Invalid
Inbound | Putaway - Returns | Inb2.5 | "Move All Destination Screen" with LPN Prompt | All Scenarios Tested in Inb2.4 | All Scenarios Tested in Inb2.4 | DEP Team | Invalid
Inventory Management
Scheduled Counts by Location - Pick Locations |  | INV1.1
Inventory Management | Cycle Count Creation | INV1.1 | Execution Scenarios | Execute: Enable scheduler to run once daily | Successful scheduler task result created on scheduled cadence. Cycle count tasks created if criteria met. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.1 |  | Execute: Manually run scheduler task for Cycle Count Profile | Successful scheduler task result created at time of execution. Cycle count tasks created if criteria met. | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.1 | Data Scenarios | Scheduler runs when all locations flagged as pickable have been counted within the past 30 days | Successful scheduler task result created. No Cycle Count Tasks created. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.1 |  | Scheduler runs when 10 or less locations flagged as pickable have not been counted within the past 30 days | Successful scheduler task result created. Cycle Count Tasks created with priority 5 for each pickable location that has not been counted within the past 30 days | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.1 |  | Scheduler runs when more than 10 locations flagged as pickable have not been counted within the past 30 days | Successful scheduler task result created. Cycle Count Tasks created with priority 5 for the 10 locations which have not been counted in the longest amount of time (must be over 30 days since) | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.1 |  | Scheduler runs when location flagged as pickable has not been counted within the past 30 days but has an existing cycle count task against it that is incomplete | Successful scheduler task result created. No cycle count task created for location with task pre-existing. | DEP Team | NOT Ready to Test
Schedudled Counts by Location - Reserve Locations |  | INV1.2
Inventory Management | Cycle Count Creation | INV1.2 | Execution Scenarios | Execute: Setup scheduler to run once daily | Successful scheduler task result created on scheduled cadence. Cycle count tasks created if criteria met. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.2 |  | Execute: Manually run scheduler task for Cycle Count Profile | Successful scheduler task result created at time of execution. Cycle count tasks created if criteria met. | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.2 | Data Scenarios | Scheduler runs when all locations flagged as reserve have been counted within the past 90 days | Successful scheduler task result created. No Cycle Count Tasks created. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.2 |  | Scheduler runs when 5 or less locations flagged as reserve have not been counted within the past 90 days | Successful scheduler task result created. Cycle Count Tasks created with priority 10 for each reserve location that has not been counted within the past 90 days | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.2 |  | Scheduler runs when more than 5 locations flagged as reserve have not been counted within the past 90 days | Successful scheduler task result created. Cycle Count Tasks created with priority 10 for the 5 locations which have not been counted in the longest amount of time (must be over 90 days since) | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.2 |  | Scheduler runs when location flagged as reserve has not been counted within the past 90 days but has an existing cycle count task against it that is incomplete | Successful scheduler task result created. No cycle count task created for location with task pre-existing. | DEP Team | NOT Ready to Test
Create Cycle Count by Location - Handheld |  | INV1.3
Inventory Management | Cycle Count Creation | INV1.3 | "Cycle Count Location Input Screen" | Click Back | User is brought back to Handheld Menu screen | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.3 |  | Scan/enter a valid location that has cycle count = true without entering a priority | Count task is created with priority = 5 Screen Message: The location [pickloc1] is scheduled for a cycle count. | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.3 |  | Scan/enter a valid location that has cycle count = true and enter an integer as the priority | Count task is created with priority entered Screen Message: The location [pickloc1] is scheduled for a cycle count. | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.3 |  | Scan/enter an invalid location | Error message: Location not found | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.3 |  | Scan/enter a valid location that has cycle count = false | Error message: Cycle counts are not enabled for the location [U-08-26-H-12]. | DEP Team | Ready to Test
Inventory Management | Cycle Count Creation | INV1.3 |  | Scan/enter a valid location that has cycle count = true and enter a non-integer as the priority | Error message: Please enter a valid integer for the cycle count priority. | DEP Team | Ready to Test
Create Cycle Count by Location - Desktop |  | INV1.4
Inventory Management | Cycle Count Creation | INV1.4 | "Create Cycle Count" PAL / Data | Select one location and perform Actions --> Cycle Count where location is cycle count eligible | Count task created for location selected | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Select multiple locations and perform Actions --> Cycle Count where all locations are cycle count eligible | Count tasks created for each location selected | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Select one location and perform Actions --> Cycle Count where location is NOT cycle count eligible | Error message: Cycle counts are not enabled for the locations [U-08-26-H-06]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Select multiple locations and perform Actions --> Cycle Count where some locations are NOT cycle count eligible | Error message: Cycle counts are not enabled for the locations [U-08-26-H-06]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Select multiple locations and perform Actions --> Cycle Count where NO locations cycle count eligible | Error message: Cycle counts are not enabled for the locations [U-08-26-H-06]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 | "Cycle Count Location Input Screen" | Click Back | User is brought to "Popup Confirmation Screen" and can close the tab | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Click Submit without touching anything on the screen | Count task created with priority of 1 and no user assigned. Screen Data: [1] location cycle counts successfully created and [0] updated with priority [1]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Click Submit after changing priority | Count task created with priority assigned. Screen Data: [1] location cycle counts successfully created and [0] updated with priority [1]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.4 |  | Click Submit after assigning a user | Count task created with user assigned. Screen Data: [1] location cycle counts successfully created and [0] updated with priority [1]. | DEP Team | NOT Ready to Test
Create Cycle Count by Item - Handheld |  | INV1.5
Inventory Management | Cycle Count Creation | INV1.5 | "Cycle Count Item Input Screen" | Click "Admin Inventory Menu" | User is brought back to Handheld Menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.5 |  | Scan/enter a valid item that has cycle count = true without entering a priority | Count task is created with priority = 5 Screen Message: The Item [Item1] is scheduled for Cycle Count. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.5 |  | Scan/enter a valid item that has cycle count = true and enter an integer as the priority | Count task is created with priority entered Screen Message: The location [Item1] is scheduled for a cycle count. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.5 |  | Scan/enter an invalid item | Error message: Please enter a valid item. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.5 |  | Scan/enter a valid location that has cycle count = false | Error message: The Item SKU [itemnumber8] is not cycle count item. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | INV1.5 |  | Scan/enter a valid location that has cycle count = true and enter a non-integer as the priority | Error message: The priority [fjadls] is not a valid integer. | DEP Team | NOT Ready to Test
On-Demand Cycle Count |  | INV1.6
Inventory Management | Cycle Count Execution | INV1.6 | "Cycle Count Location Input Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid location that has cycle count = true without entering a priority | User is brought to "Item Screen" for location scanned | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid location that has cycle count = true and enter an integer as the priority | User is brought to "Item Screen" for location scanned | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter an invalid location | Error Message: Location not found. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid location that has cycle count = false | Cycle counts are not enabled for the location [U-08-23-G-08]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid location that has cycle count = true and enter a non-integer as the priority | Error Message: Please enter a valid integer for the cycle count priority. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid location that is LPN Controlled | User is brought to "Parent LPN Screen" for location scanned - "LPN" listbox displays a row per unique LPN in the location | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid location that the system believes to have one or more items in it that are NOT LPN Controlled | User is brought to "Item Screen" for location scanned - "SKU" listbox displays a row per unique sku in the location *EVE does not count Non-LPN Controlled Locations in the warehouse so this flow should not occur. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 | "Parent LPN Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Click Next Location without scanning/touching anything on the screen | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Click Submit without touching anything else on the screen | Error Message: Please select or enter a valid container. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter an invalid container | Error Message: The container could not be found | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid container that the system believes is not in the location being counted | Screen Message: LPN LPN2392 scanned. Row is added to the LPN listbox with two asterisks next to it | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid container that the system believes to exist in the location being counted | Screen Message: LPN CONT1 scanned. Two asterisks added next to the LPN scanned in the LPN listbox. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Click Next Location after scanning all items in location | User is brought back to handheld menu screen - variances created for discrepancies found if present | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 | "Item Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Click Next Location without scanning/touching anything on the screen | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Click Submit without touching anything else on the screen | Error Message: Please enter an item. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter an invalid item | Error Message: The item [9786754321] could not be found. Please try again. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid item that the system does not think is in the location being counted | Additional row is added to the "SKU" listbox with two astericks next to it. Screen Message: [1] was counted for the item [277968]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Scan/enter a valid item that the system does expect to be in the location being counted | Astericks added to the row next to the sku scanned in the "SKU" listbox Screen Message: [1] was counted for the item [277232]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.6 |  | Click Next Location after scanning all items in location | User is brought back to handheld menu screen - variances created for discrepancies found if present | DEP Team | NOT Ready to Test
Cycle Count |  | INV1.7
Inventory Management | Cycle Count Execution | INV1.7 | "Enter Current Location" | Click Back | User is brought back to the handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Hit enter without scanning/entering a start off location | Error Message: The location [null] could not be found. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter an invalid location | Error Message: The location [980765432] could not be found. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter a valid location of any kind in the user's active facility | User is brought to "Location Input Screen" | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 | "Location Input Screen" | Click Back | User is brought back to the handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Hit enter without scanning/entering any location | Error Message: Location is a required field | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter an invalid location | Error Message: Location not found. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter a valid location that does not match the one prompted | Error Message: A cycle count must be performed for the [Stock Location] location | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter the location prompted on the screen when the location prompted is LPN controlled | User is brought to the "Parent LPN Screen" | DEP Team | NOT Ready to Test
| Cycle Count Execution | INV1.7 |  | Scan/enter the location prompted on the screen when the location prompted is not LPN controlled | User is brought to the "Item Screen" *EVE does not count Non-LPN Controlled Locations in the warehouse so this flow should not occur. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 | "Parent LPN Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Click Next Location without scanning/touching anything on the screen | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Click Submit without touching anything else on the screen | Error Message: Please select or enter a valid container. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter an invalid container | Error Message: The container could not be found | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter a valid container that the system believes is not in the location being counted | Screen Message: LPN LPN2392 scanned. Row is added to the LPN listbox with two asterisks next to it | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter a valid container that the system believes to exist in the location being counted | Screen Message: LPN CONT1 scanned. Two asterisks added next to the LPN scanned in the LPN listbox. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Click Next Location after scanning all items in location | User is brought back to handheld menu screen - variances created for discrepancies found if present | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 | "Item Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Click Next Location without scanning/touching anything on the screen | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Click Submit without touching anything else on the screen | Error Message: Please enter an item. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter an invalid item | Error Message: The item [9786754321] could not be found. Please try again. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter a valid item that the system does not think is in the location being counted | Additional row is added to the "SKU" listbox with two astericks next to it. Screen Message: [1] was counted for the item [277968]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Scan/enter a valid item that the system does expect to be in the location being counted | Astericks added to the row next to the sku scanned in the "SKU" listbox Screen Message: [1] was counted for the item [277232]. | DEP Team | NOT Ready to Test
Inventory Management | Cycle Count Execution | INV1.7 |  | Click Next Location after scanning all items in location | User is brought back to handheld menu screen - variances created for discrepancies found if present | DEP Team | NOT Ready to Test
Start Physical Count Admin |  | INV1.8
Inventory Management | Physical Count Admin | INV1.8 | "Physical Count Start Screen" | Click Back | User is brought back to handheld menu | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.8 |  | Click Start without touching anything on the screen |  | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.8 |  | Click Start after selecting "Controlled" |  | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.8 |  | Click Start after entering a "Process Name" |  | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.8 | "Physical Count Stop Screen" | Click Back |  | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.8 |  | Click Finish Physical Count Activity |  | DEP Team | NOT Ready to Test
Perform Physical Count |  | INV1.9
Inventory Management | Physical Count Admin | INV1.9 | "Location Input Screen" | Click Back | User is brought back to handheld menu | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Hit enter without scanning a location | Error Message: Location is a required field | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan an invalid location | Error Message: Location not found. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan a valid location that is LPN controlled | User is brought to the "Parent LPN Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan a valid location that is not LPN controlled | User is brought to the "Item Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 | "Parent LPN Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Next Location without scanning/touching anything on the screen | User is brought to the "Physical Count Summary Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Submit without touching anything else on the screen | Error Message: Please select or enter a valid container. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan/enter an invalid container | Error Message: The container could not be found | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan/enter a valid container that the system believes is not in the location being counted | Screen Message: LPN LPN2392 scanned. Row is added to the LPN listbox with two asterisks next to it | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan/enter a valid container that the system believes to exist in the location being counted | Screen Message: LPN CONT1 scanned. Two asterisks added next to the LPN scanned in the LPN listbox. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Next Location after scanning all items in location | User is brought to the "Physical Count Summary Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 | "Item Screen" | Click Back | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Next Location without scanning/touching anything on the screen | User is brought to the "Physical Count Summary Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Submit without touching anything else on the screen | Error Message: Please enter an item. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan/enter an invalid item | Error Message: The item [9786754321] could not be found. Please try again. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan/enter a valid item that the system does not think is in the location being counted | Additional row is added to the "SKU" listbox with two astericks next to it. Screen Message: [1] was counted for the item [277968]. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Scan/enter a valid item that the system does expect to be in the location being counted | Astericks added to the row next to the sku scanned in the "SKU" listbox Screen Message: [1] was counted for the item [277232]. | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Next Location after scanning all items in location | User is brought to the "Physical Count Summary Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 | "Physical Count Summary Screen" | Click Back | User is taken back to either the "Item Screen" or "LPN Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Recount | User is taken back to either the "Item Screen" or "LPN Screen" | DEP Team | NOT Ready to Test
Inventory Management | Physical Count Admin | INV1.9 |  | Click Apply | Count is recorded User is taken to the "Location Input Screen" to scan the next location | DEP Team | NOT Ready to Test
Variance Approval |  | INV1.10
Inventory Management | Variance Management | INV1.10 | Data Scenarios | Count expected quantity in a location | No variance is created | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Count a quantity greater than what is expected in a location | Variance is created with a positive variance quantity | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Count a quantity less than what is expected in a locatin | Variance is created with a negative variance quantity | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 | Execution Steps | Accept a Variance | Stock is adjusted to match what is counted Inventory Adjustment records created to record the change with type ADJ | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Reject a Variance | Variance is deleted and no stock is adjusted | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Initiate a Recount for a Variance | Variance is deleted and a new cycle count task is created for the location | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Accept multiple variances at once | Stock is adjusted to match what is counted for each variances selected Inventory Adjustment records are created to record the change with type ADJ | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Reject multiple variances at once | Variances are deleted and no stock is adjusted | DEP Team | NOT Ready to Test
Inventory Management | Variance Management | INV1.10 |  | Initiate a Recount for a multiple variances at once | Variances are deleted and new cycle count tasks are created for the locations selected | DEP Team | NOT Ready to Test
Consolidate in 1D |  | INV2.1
Inventory Management | Replenishment | INV2.1 | "Location Input Screen" | Click Back | User is brought back to the handheld menu. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next without scanning a location | Error Message: Please enter the source location. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Enter an invalid location | Error Message: The location [34567890] does not exist. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Enter a valid location that has no LPNs in it | User is brought back to the handheld menu. Screen Message: No containers could be found in [U-08-20-H-03]. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Enter a valid LPN that has one or more LPNs in it | User is brought to the "Pallet to pick from" screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 | "Pallet to pick from" Screen | Click Back | User is brought back to the handheld menu. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next without scanning an LPN when only one LPN is present | User is brought to the "Items In Source Pallet" screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next without scanning an LPN when multiple LPNs are present | Error Message: Please enter the source container. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan an invalid LPN | ErrorMessage: The source container [65879] could not be found. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan a valid LPN that does not exist in the location previously scanned | Error Message: The container [CONT1] is not available. Please try a different container. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan a valid LPN in the location previously scanned (should appear in the listbox) | User is brought to the "Items In Source Pallet" screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 | "Items In Source Pallet" Screen | Click Back | User is brought back to the "Pallet to pick from" screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Move All without entering a DSTN LPN | Error Message: Please enter the destination container. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Move All and enter an LPN as the DSTN LPN that does not yet exist in the system | LPN created with scanned identifier in previously scanned location. Full contents of source LPN moved to newly created LPN. Screen Message: Repalletization is complete. User is brought back to "Pallet to pick from" Screen and newly created LPN is now in the listbox | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Move All and enter an LPN as the DSTN LPN that exists in the same location | Stock merged into DSTN LPN and stays in the same location Screen Message: Repalletization is complete. User is brought back to "Pallet to pick from" Screen and previously scanned LPN is removed from the listbox | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Move All and enter an LPN as the DSTN LPN that exists a different location | Stock merged into DSTN LPN which is brought to the previously scanned location. Screen Message: Repalletization is complete. User is brought back to "Pallet to pick from" Screen and previously scanned LPN now appears in listbox | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next when one item appears in listbox without scanning the item or the DSNT LPN | Error Message: Please enter the destination LPN number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next when one item appears in listbox without scanning the item and only scanning the DSTN LPN | User is brought to the "Packs In Source Pallet For Selected Item" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next when multiple item appear in listbox without scanning an item or the DSNT LPN | Error Message: Please enter the destination LPN number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click Next when multiple items appear in listbox without scanning an item and only scanning the DSTN LPN | Error Message: Please select the pack. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan/enter an invalid item + a valid LPN | Error Message: Item/SKU [4w656i7r857y] does not exist. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan/enter a valid item that does not exist in the source LPN + a valid LPN | Error Message: The item [item1] could not be found in the container. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan/enter a valid item that exists in the LPN + an invalid DSTN LPN | Error Message: The destination container [fgnkjbgjbnf] must have a container type of [Pallet] | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan/enter a valid item that exists in the LPN + an valid DSTN LPN in the same location | User is brought to the "Packs In Source Pallet For Selected Item" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Scan/enter a valid item that exists in the LPN + an valid DSTN LPN in a different location | User is brought to the "Packs In Source Pallet For Selected Item" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 | "Packs In Source Pallet For Selected Item" | Click Back | User is brought back to "Items In Source Pallet" screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click "Move All Packs" without entering anything | Error Message: Quantity needs to be a number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click "Next" without entering anything | Error Message: Quantity needs to be a number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Click "Finish" | Error Message: Quantity needs to be a number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Enter a quantity greater than the quantity of units available to move | Error Message: A total quantity of [19] for the selected pack is in the source container [TESTY1]. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.1 |  | Enter a quantity less than or equal to the quantity of units available to move | User is brought back to "Items In Source Pallet" screen Screen Message: Repalletization is complete. Quantity entered of unit is moved into DSTN LPN in current location | DEP Team | NOT Ready to Test
Move to Upper Zone |  | INV2.2
Inventory Management | Replenishment | INV2.2 | "Scan Container To Move" Screen | Click "Back" | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Continue/Enter without scanning an LPN | Error Message: Container number can not be empty | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Continue/Enter with scanning an invalid LPN | Error Message: Please use the valid Container Number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Continue/Enter with scanning a valid LPN when there are empty locations in the Upper zone | User is brought to "Scan Destination Location" Screen. User is displayed one list: - Empty Locations in the Upper zone | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Continue/Enter with scanning a valid LPN when there are NO empty locations in the Upper zone | User is brought to "Scan Destination Location" Screen. User is displayed one list that is empty. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 | "Scan Destination Location" Screen | Click "Back" | User is brought back to "Scan Container To Move" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Move/Enter without scanning a destination LPN | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Move/Enter scanning any valid staging location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.2 |  | Next/Enter scanning any valid LPN-controlled storage location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Move to 1D |  | INV2.3
Inventory Management | Replenishment | INV2.3 | "Scan Container To Move" Screen | Click "Back" | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Continue/Enter without scanning an LPN | Error Message: Container number can not be empty | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Continue/Enter with scanning an invalid LPN | Error Message: Please use the valid Container Number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Continue/Enter with scanning a valid LPN when there are empty locations in the 1D zone | User is brought to "Scan Destination Location" Screen. User is displayed one list: - Empty Locations in the 1D zone | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Continue/Enter with scanning a valid LPN when there are NO empty locations in the 1D zone | User is brought to "Scan Destination Location" Screen. User is displayed one list that is empty. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 | "Scan Destination Location" Screen | Click "Back" | User is brought back to "Scan Container To Move" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Move/Enter without scanning a destination LPN | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Move/Enter scanning any valid staging location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.3 |  | Next/Enter scanning any valid LPN-controlled storage location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Move to 2D |  | INV2.4
Inventory Management | Replenishment | INV2.4 | "Scan Container To Move" Screen | Click "Back" | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Continue/Enter without scanning an LPN | Error Message: Container number can not be empty | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Continue/Enter with scanning an invalid LPN | Error Message: Please use the valid Container Number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Continue/Enter with scanning a valid LPN when there are empty locations in the 2D zone | User is brought to "Scan Destination Location" Screen. User is displayed one list: - Empty Locations in the 2D zone | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Continue/Enter with scanning a valid LPN when there are NO empty locations in the 2D zone | User is brought to "Scan Destination Location" Screen. User is displayed one list that is empty. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 | "Scan Destination Location" Screen | Click "Back" | User is brought back to "Scan Container To Move" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Move/Enter without scanning a destination LPN | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Move/Enter scanning any valid staging location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.4 |  | Next/Enter scanning any valid LPN-controlled storage location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Replenish to 4D and 2D |  | INV2.5
Inventory Management | Replenishment | INV2.5 | "Scan Container To Move" Screen | Click "Back" | User is brought back to handheld menu screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Continue/Enter without scanning an LPN | Error Message: Container number can not be empty | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Continue/Enter with scanning an invalid LPN | Error Message: Please use the valid Container Number. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Continue/Enter with scanning a valid LPN when there are empty locations in the 2D zone | User is brought to "Scan Destination Location" Screen. User is displayed one list: - Empty Locations in the 2D zone | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Continue/Enter with scanning a valid LPN when there are NO empty locations in the 2D zone | User is brought to "Scan Destination Location" Screen. User is displayed one list that is empty. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 | "Scan Destination Location" Screen | Click "Back" | User is brought back to "Scan Container To Move" Screen | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Move/Enter without scanning a destination LPN | Error Message: Please enter a locator. | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Move/Enter scanning any valid staging location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.5 |  | Next/Enter scanning any valid LPN-controlled storage location | Screen Message: Container [LPN57] has been moved to [staging] location. Container and stock inside now exist in staging location | DEP Team | NOT Ready to Test
Consolidation Report |  | INV2.6
Inventory Management | Replenishment | INV2.6 | Data Scenarios | Location in the 4-Deep Zone has more than 2 containers of the same item | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.6 |  | Location in the 4-Deep Zone has less than or equal to 2 containers of the same item | Location appears in report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.6 |  | Location in the 2-Deep Zone has 2 containers of the same item | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.6 |  | Location in the 2-Deep Zone has 1 container of the same item | Location appears in report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.6 |  | Location in the 1-Deep Zone has an item with a "first receipt date" less than or equal to 120 days prior to the time the report is run | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.6 |  | Location in the 1-Deep Zone has an item with a "first receipt date" more than 120 days prior to the time the report is run | Location appears in report | DEP Team | NOT Ready to Test
Replenishment Report |  | INV2.7
Inventory Management | Replenishment | INV2.7 | Data Scenarios | Location in the 4-Deep Zone has more than 2 containers of the same item | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Location in the 4-Deep Zone has less than or equal to 2 containers of the same item and no inventory in the Upper or Lower Zones | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Location in the 4-Deep Zone has less than or equal to 2 containers of the same item and has inventory in the Upper or Lower Zones | Location appears in report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Location in the 2-Deep Zone has 2 containers of the same item | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Location in the 2-Deep Zone has 1 container of the same item and has no stock in the Upper or Lower Zones | Location does not appear in the report | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Location in the 2-Deep Zone has 1 container of the same item and no stock in the Upper or Lower Zones | Location appears in report | DEP Team | NOT Ready to Test
Aged Pallet Report |  | INV2.8
Inventory Management | Replenishment | INV2.7 | Data Scenarios | All pallet locations have stock |  | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | No pallet locations have stock |  | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Some pallet locations have stock and others don't |  | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Pallet has only one item |  | DEP Team | NOT Ready to Test
Inventory Management | Replenishment | INV2.7 |  | Pallet has multiple items |  | DEP Team | NOT Ready to Test
User Adjust Inventory |  | INV3.1
Inventory Management | Adjust Inventory | INV3.1 |  | Create Inventory in a Location and Capture Reason Code | Inventory levels increment in the system for that specific item and reason code is stamped in the invAdjustment table
Inventory Management | Adjust Inventory | INV3.1 |  | Consume ALL in Location & Capture Reason Code | Location's inventory is depleted and reason code is stamped in the invAdjsutment table
Inventory Management | Adjust Inventory | INV3.1 |  | Consume by Item & Capture Reason Code | Inventory levels decrement in the system for thst specific item and reason code is stamped in the invAdjustment table
Inventory Management | Adjust Inventory | INV3.1 |  | Consume by LPN & Capture Reason Code | LPN inventory is depleted and LPN is removed from the system and reason code is stamped in the InvAdjustment Table
Inventory Management | Adjust Inventory | INV3.1
Admin Adjust Inventory |  | INV3.2
Inventory Management | Adjust Inventory | INV3.2
Inventory Management | Adjust Inventory | INV3.2
Outbound 1
Outbound | Outbound Order Management - Address Validation |  |  | Process order that fails address validation with suggested change | Sales Order goes to status "Hold - AV" and Order Header Note created with suggested address changes - POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - Address Validation |  |  | Process order that fails address validation with NO suggested change | Sales Order goes to status "Hold - AV" and Order Header Note created indicating no suggestions could be found - POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - Address Validation |  |  | Process order that passes address validation | Sales Order stays in New status - POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - POI Done |  |  | POI runs successfully | POI Done flag is set to true |  | Ready to Test
Outbound | Outbound Order Management - POI Done |  |  | POI fails | POI Done flag stays false. Waving does not run on the order. |  | Ready to Test
Outbound | Outbound Order Management - Re-run POI |  |  | Scheduler re-runs POI on orders where POI Done is not true |  |  | Ready to Test
Outbound | Pickwave Management - Waving Execution |  |  | Manually wave one order | Order selected remains in New, moves to Back Ordered, or moves to Released based on profile match and inventory evaluation |  | Ready to Test
Outbound | Pickwave Management - Waving Execution |  |  | Manually wave multiple orders | All orders selected remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation |  | Ready to Test
Outbound | Pickwave Management - Waving Execution |  |  | Scheduled wave multiple orders | All orders in New or Back Ordered status are waved in order of created date ascending. All orders remain in New, move to Back Ordered, or move to Released based on profile match and inventory evaluation. |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  |  | Order matches large order profile conditions | Order waved on Large Order Wave - can only be picked in Single Scan Picking |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  |  | Order matches singles order profile conditions | Order waved on Singles Wave - can only be picked in Single Scan Picking |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  |  | Order matches multis order profile conditions | Order waved on Multis Wave - can only be picked in Batch Picking |  | Ready to Test
Outbound | Pickwave Management - Pickwave Profile |  |  | Order matches no waving criteria | Order stays in New or Back Ordered status |  | Ready to Test
Outbound | Pickwave Management - Back Order Management |  |  | Order waved has sufficient inventory available to release | Order moves to Released and is assigned a Pickwave with work group and pick tasks |  | Ready to Test
Outbound | Pickwave Management - Back Order Management |  |  | Order waved as no sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
Outbound | Pickwave Management - Back Order Management |  |  | Order waved as partially sufficient inventory available to release | Order moves to Back Ordered and pickwave is removed from the order. |  | Ready to Test
Outbound 2
Outbound | Picking - Singles Picking |  |  | Select the top pickwave from the list when multiple waves are available and scan a valid LPN |  |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Select a pickwave from the list that is not at the top of the list when multiple waves are available and scan a valid LPN
Outbound | Picking - Singles Picking |  |  | Select a pickwave from the list and scan a pre-existing, empty LPN to start picking
Outbound | Picking - Singles Picking |  |  | Select a pickwave from the list and scan a pre-existing, non-empty LPN to start picking
Outbound | Picking - Singles Picking |  |  | Select a pickwave from the list and scan a value in the LPN field that is not already tied to any LPN in the system
Outbound | Picking - Singles Picking |  |  | Scan a valid LPN whithout selecting a pickwave from the list of multiple pickwaves
Outbound | Picking - Singles Picking |  |  | Scan a valid LPN whithout selecting a pickwave from the list when only one pickwave exists in list.
Outbound | Picking - Singles Picking |  |  | Scan a location other than the one prompted on location pick screen. | Error message: "The location [x] does not match the required location." |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Scan a location that matches the one prompted on location pick screen. | Takes user to the item selection picking screen to enter in the SKU |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Scan a barcode value that does not match the Item Number or Item UPC prompted on the item pick screen | Error message: "The SKU [x] could not be found. Please enter a valid SKU." |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Scan a barcode value that matches the item number prompted on the item pick screen | Takes user to the quantity picking sreen |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Scan a barcode value that matches the item upc that matches the item prompted on the item pick screen | Takes user to the quantity picking sreen
Outbound | Picking - Singles Picking |  |  | Enter in a quantity greater than quantity prompted on quantity input screen. | Error Message: "The quantity that you entered [x] is more than the quantity that is required [x]. |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Enter in a quantity less than quantity prompted on quantity input screen.
Outbound | Picking - Singles Picking |  |  | Enter in quantity that matches the quantity prompted on quantity input screen | If there are more pick tasks on the wave, it will take the user to the next location to complete the next task. If the task is the last one on the wave, it willt take the user back to the picking menu screen with a message"Picking LPN [x] staged to [Shipping]." |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Select "stage" on location input screen after picking one item on a wave. | Picking cart will be staged to shipping and user will be prompted to scan new picking cart to finish the pick wave |  | Ready to Test
Outbound | Picking - Singles Picking |  |  | Select "stage" on location input screen before picking any items on the wave. | ?
Outbound | Picking - Singles Picking |  |  | Select Exception and choose "No Stock" | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item
Outbound | Picking - Singles Picking |  |  | Suspend a pick Task | The task is now moved to the end of the queue, it is picked last
Outbound | Picking - Singles Picking |  |  | Suspend a Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated
Outbound | Picking - Singles Picking |  |  | End a Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore
Outbound | Picking - Singles Picking |  |  | Select "Back" on picking exception screen
Outbound | Picking - Singles Picking |  |  | Pick one unit of an item that is serial tracked | User is prompted for Serial Number after selecting the quantity
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is serial tracked from the same location | User is prompted for a Serial Number for each unit picked after selecting the quantity
Outbound | Picking - Singles Picking |  |  | Pick one unit of an item that is lot tracked | User is prompted for Lot Number after selecting the quantity
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - only one lot in location
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  |  | Pick one unit of an item that is expiration date tracked | User is prompted for Exp Date after selecting the quantity
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is expiration date tracked from the same location - only one lot in location
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  |  | Pick multiple units of an item that is expiration date tracked from the same location - multiple expiration dates in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Singles Picking |  |  | Pick order with Order Header Note with Title = Picking Note
Outbound | Picking - Singles Picking |  |  | Pick order without Order Header Note with Title = Picking Note
Outbound | Picking - Singles Picking |  |  | Pick order with Order Line Note with Title = Picking Note
Outbound | Picking - Singles Picking |  |  | Pick order with Order Line Note without Title = Picking Note
Outbound | Picking - Multis Picking |  |  | Select pick wave and click "Summary" for an Exception Re-pick Wave | User is given the bin associated with the stock previously picked
Outbound | Picking - Multis Picking |  |  | Select pick wave and click "Summary" for a non-exception re-pick wave
Outbound | Picking - Multis Picking |  |  | Select the top pickwave from the list when multiple waves are available and submit
Outbound | Picking - Multis Picking |  |  | Select a pickwave from the list that is not at the top of the list when multiple waves are available and submit
Outbound | Picking - Multis Picking |  |  | Select the pickwave from the list when only one wave is available and submit
Outbound | Picking - Multis Picking |  |  | Select no pickwave from the list when only one wave is available and submit
Outbound | Picking - Multis Picking |  |  | Select no pickwave from the list when multiple waves are available and submit
Outbound | Picking - Multis Picking |  |  | Scan a location other than the one prompted on location pick screen. | Error message: "Please scan a valid location" |  | Ready to Test
Outbound | Picking - Multis Picking |  |  | Scan a location that matches the one prompted on location pick screen. | Takes user to the item selection picking screen to enter in the SKU |  | Ready to Test
Outbound | Picking - Multis Picking |  |  | Scan a barcode value that does not match the Item Number or Item UPC prompted on the item pick screen | Error message: "Please scan a valid item."
Outbound | Picking - Multis Picking |  |  | Scan a barcode value that matches the item number prompted on the item pick screen | Takes user to the quantity picking sreen
Outbound | Picking - Multis Picking |  |  | Scan a barcode value that matches the item upc that matches the item prompted on the item pick screen | Takes user to the quantity picking sreen
Outbound | Picking - Multis Picking |  |  | Enter in a quantity greater than quantity prompted on quantity input screen. | Error Message: "Quantity entered is greater than required."
Outbound | Picking - Multis Picking |  |  | Enter in a quantity less than quantity prompted on quantity input screen. | user is asked to put the initial quantity into a bin and then brought back to scan the location, quantity, and bin for the reamaining quanitites on the wave
Outbound | Picking - Multis Picking |  |  | Enter in quantity that matches the quantity prompted on quantity input screen | User is brought to the bin selection picking screen
Outbound | Picking - Multis Picking |  |  | Scan LPN for first pick of an order (no suggested LPN) that has stock units in it already | Error Message: "Scanned bin [x] contains other orders
Outbound | Picking - Multis Picking |  |  | Scan LPN for first pick of an order (no suggested LPN) that does not have stock units in it | User is brought to the next pick task and is asked to scan the next location if there are available pick tasks.
Outbound | Picking - Multis Picking |  |  | Scan LPN for a unit that is not the first pick of an order that does not match the suggested LPN displayed | Error Message: The suggested bin is [x].
Outbound | Picking - Multis Picking |  |  | Scan LPN for a unit that is not the first pick of an order that matches the suggested LPN displayed | Item & stock units are moved to the bin. User is brought to the next task if available, else it will bring the user to the Picking Menu screen to select another wave to complete if available
Outbound | Picking - Multis Picking |  |  | Select "New Bin" when prompted to scan into a suggested LPN that is full | Message: "New bin created for Order [x]. and user is able to select another bin to put item into if there is not existing stock in the new bin
Outbound | Picking - Multis Picking |  |  | Select "New Bin" when no suggested LPN is prompted | ?
Outbound | Picking - Multis Picking |  |  | Select Exception and choose "No Stock" | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item
Outbound | Picking - Multis Picking |  |  | Suspend Task | The task is now moved to the end of the queue, it is picked last
Outbound | Picking - Multis Picking |  |  | Suspend Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated
Outbound | Picking - Multis Picking |  |  | End Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore
Outbound | Picking - Multis Picking |  |  | Select "Back" on picking exception screen
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is serial tracked from the same location | User is prompted for a Serial Number for each unit picked after selecting the quantity |  | Ready to Test
Outbound | Picking - Multis Picking |  |  | Pick one unit of an item that is lot tracked | User is prompted for Lot Number after selecting the quantity |  | Ready to Test
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - only one lot in location |  |  | Ready to Test
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is lot tracked from the same location - multiple lots in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  |  | Pick one unit of an item that is expiration date tracked | User is prompted for Exp Date after selecting the quantity
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is expiration date tracked from the same location - only one lot in location
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, each lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is expiration date from the same location - multiple expiration dates in location, only one lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  |  | Pick multiple units of an item that is expiration date tracked from the same location - multiple expiration dates in location, neither lot with enough stock to compelte the pick task
Outbound | Picking - Multis Picking |  |  | Pick order with Order Header Note with Title = Picking Note
Outbound | Picking - Multis Picking |  |  | Pick order without Order Header Note with Title = Picking Note
Outbound | Picking - Multis Picking |  |  | Pick order with Order Line Note with Title = Picking Note
Outbound | Picking - Multis Picking |  |  | Pick order with Order Line Note without Title = Picking Note
Outbound | Packing - Singles Packing |  |  | Scan an invalid or non-existent identifier as the tote lpn | User gets an error and is prompted to scan an existing container
Outbound | Packing - Singles Packing |  |  | Scan a valid tote LPN which is NOT eligible for pack order by item due to the following reasons 1. Multi item orders (Non Ready to Ship packs) 2. Multi quantity order (Non Ready to Ship packs) | User gets an error and is prompted to scan a valid tote lpn with single unit orders
Outbound | Packing - Singles Packing |  |  | Scan a valid tote LPN which is eligible (stock quantities are for singles eligible orders on the pallet). 1. Single item/quantity/order 2. Order with multiple Ready to Ship Items | User is taken to the next screen to see the item selection screen
Outbound | Packing - Singles Packing |  |  | Scan a valid item barcode of an item displayed on the packing screen in the handheld | Scan is accepted and user is taken to the next screen scan the package weight and dims
Outbound | Packing - Singles Packing |  |  | Scan a valid UPC barcode of an item displayed on the packing screen in the handheld | Scan is accepted and user is taken to the next screen to scan the package weight and dims
Outbound | Packing - Singles Packing |  |  | Scan an invalid or non-existent identifier as the Item scan Invalid = not an item displayed on the screen. Non-existent = barcode not in system. | User gets an error and is prompted to scan the item again
Outbound | Packing - Singles Packing |  |  | Click back during packing. Container contains contents for multiple single unit orders | Order is rolled back into shipping container.
Outbound | Packing - Singles Packing |  |  | Pack serial tracked item, scan a serial number that does not exist for an item in the picking container or is tied to stock in a different location/lpn | User gets an error and is forced to scan a valid serial number for the item
Outbound | Packing - Singles Packing |  |  | Pack serial tracked item, scan a serial number that does exist for an item in the picking container or is tied to stock in a different location/lpn | User is able to continue through the process and the system accepts the serial number entry
Outbound | Packing - Singles Packing |  |  | Pack lot tracked item, select a lot number that matches the item being packed when multiple lots exist in picking container for the item | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Singles Packing |  |  | Pack lot tracked item, select a lot number that matches the item being packed when one lot exists in picking container for the item | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Singles Packing |  |  | Pack expiration tracked item, select an expiration date that matches the item being packed when one expiration date exists in picking container for the item | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Singles Packing |  |  | Pack expiration tracked item, select an expiration date that matches the item being packed when multiple expiration dates exists in picking container for the item | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Singles Packing |  |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do not match any stock units in the picking container | Error message - stock unit not found
Outbound | Packing - Singles Packing |  |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do match a stock unit in the picking container | User is able to continue through the process and the system takes the displayed lot and expiration from the drop down list
Outbound | Packing - Singles Packing |  |  | Manually select a carton type on the container weight and dimension screen | User is allowed to proceed and the selected carton type will be used for declaring dimensions in the shipping request
Outbound | Packing - Singles Packing |  |  | Scan an invalid or non-existent identifier as the carton type on the container weight and dimension screen | User gets an error and is prompted to scan an existing carton type
Outbound | Packing - Singles Packing |  |  | Scan a carton type identifier in the carton type input on the container weight and dimension screen | System accepts the selected carton type and will be used for declaring dimensions in the shipping request
Outbound | Packing - Singles Packing |  |  | User manually enters the weight of the shipping container after packing is complete | The package is packed, and takes the weight that the user manually entered
Outbound | Packing - Singles Packing |  |  | User validates the autocalulated weight (weight is auto calculated on the basis of the quantity picked and the pack weight in the master data set up) | System displays the sum of the weight using the pack weight for the items for each order
Outbound | Packing - Singles Packing |  |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non integer value in the package weight entry box | User gets an error due to an invalid entry
Outbound | Packing - Singles Packing |  |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non numeric value in the package weight entry box | User gets an error due to an invalid entry
Outbound | Packing - Singles Packing |  |  | User hits submit, and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). | User gets a packing slip for the orders
Outbound | Packing - Singles Packing |  |  | User hits submit, and shipping labels print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). | User gets a shipping label for the order
Outbound | Packing - Singles Packing |  |  | User hits submit, and shipping label and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). | User gets a shipping label and packing slip for the orders
Outbound | Packing - Multis Packing |  |  | Scan an invalid or non-existent identifier as the tote lpn | User gets an error and is prompted to scan an existing container
Outbound | Packing - Multis Packing |  |  | Scan a valid tote lpn which contains the picks for one order in it. However, the order is in an invalid status and is not eligible for packing (back ordered, released, etc) | User gets an error and is prompted to scan an existing container
Outbound | Packing - Multis Packing |  |  | Scan a valid tote lpn which contains the picks for one order in it, and the order is eligible for packing | User is taken to the next screen to see the item selection screen
Outbound | Packing - Multis Packing |  |  | Scan a valid item barcode of an item displayed on the packing screen in the handheld | Scan is accepted and user is taken to the next screen to scan the package weight and dims, or to continue scanning additional items if additional items remain to be packed
Outbound | Packing - Multis Packing |  |  | Scan a valid UPC barcode of an item displayed on the packing screen in the handheld | Scan is accepted and user is taken to the next screen to scan the package weight and dims, or to continue scanning additional items if additional items remain to be packed
Outbound | Packing - Multis Packing |  |  | Scan an invalid or non-existent identifier as the Item scan Invalid = not an item displayed on the screen. Non-existent = barcode not in system. | User gets an error and is prompted to scan the item again
Outbound | Packing - Multis Packing |  |  | Click back during packing. Container contains contents for multiple single unit orders | Packer exits from the container screen. Can rescan container and pack what is remaining
Outbound | Packing - Multis Packing |  |  | Pack in grocery scan mode (single unit pack per scan) by scanning the item barcode or item UPC barcode | 1. Scan registers 1 qty everytime the item identifier is scanned in the process. 2. If item attributes are required for the item, the user is taken to the item tracking capture screen 3. If more units are required to be packed for the same lpn, the user stays on the item screen to scan the item again 4.If there are no more units left in the picking lpn (tote), the user is directed to the container weight and dims screen to continue packing after any required item tracking attributes have been captured
Outbound | Packing - Multis Packing |  |  | Enter a non numeric value in the quantity input section of the screen (Non Grocery Mode) | User gets an error and is prompted to enter the quantity again
Outbound | Packing - Multis Packing |  |  | Enter a quantity that is higher than the required quantity in the quantity input section of the screen (Non Grocery Mode) | User gets an error suggesting entered qty is greater than required.
Outbound | Packing - Multis Packing |  |  | Enter a negative quantity in the quantity input section of the screen (Non Grocery Mode) | User gets an error and is prompted to enter the quantiy again
Outbound | Packing - Multis Packing |  |  | Enter a quantity that is lesser than the required quantity in the quantity input section of the screen (Non Grocery Mode) | Quantity is registered and the system suggests to pack the remainder quantity to the user
Outbound | Packing - Multis Packing |  |  | Enter a quantity that is exactly the required quantity in the quantity input section of the screen (Non Grocery Mode) | Quantity is registered and the user continues to pick the rest of the picks or is prompted to stage the LPN.
Outbound | Packing - Multis Packing |  |  | Enter a non integer (decimal value) in the quantity input section of the screen (Non Grocery Mode) | User gets an error and is prompted to enter the quantity again
Outbound | Packing - Multis Packing |  |  | Pack serial tracked item, scan a serial number that does not exist for an item in the picking container or is tied to stock in a different location/lpn | User gets an error and is forced to scan a valid serial number for the item
Outbound | Packing - Multis Packing |  |  | Pack serial tracked item, scan a serial number that does exist for an item in the picking container or is tied to stock in a different location/lpn | User is able to continue through the process and the system accepts the serial number entry
Outbound | Packing - Multis Packing |  |  | Pack lot tracked item, select a lot number that matches the item being packed when multiple lots exist in picking container for the item | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Multis Packing |  |  | Pack lot tracked item, select a lot number that matches the item being packed when one lot exists in picking container for the item | User is able to continue through the process and the system takes the displayed lot number from the drop down list
Outbound | Packing - Multis Packing |  |  | Pack expiration tracked item, select an expiration date that matches the item being packed when one expiration date exists in picking container for the item | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Multis Packing |  |  | Pack expiration tracked item, select an expiration date that matches the item being packed when multiple expiration dates exists in picking container for the item | User is able to continue through the process and the system takes the displayed expiration from the drop down list
Outbound | Packing - Multis Packing |  |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do not match any stock units in the picking container | Error message - stock unit not found
Outbound | Packing - Multis Packing |  |  | Pack a lot and expiration tracked item, select a combination of lot and expiration date that do match a stock unit in the picking container | User is able to continue through the process and the system takes the displayed lot and expiration from the drop down list
Outbound | Packing - Multis Packing |  |  | Hit 'New Bin' to continue packing into a new shipping box since the existing box is too full and cannot accept any more items | System registers the new bin scan and user is taken to confirm the weight and dims screen to confirm the dimensions and weight of the previous (full) box before continuing with packing into a new shipping box
Outbound | Packing - Multis Packing |  |  | Manually select a carton type on the container weight and dimension screen | User is allowed to proceed and the selected carton type will be used for declaring dimensions in the shipping request
Outbound | Packing - Multis Packing |  |  | Scan an invalid or non-existent identifier as the carton type on the container weight and dimension screen | User gets an error and is prompted to scan an existing carton type
Outbound | Packing - Multis Packing |  |  | Scan a carton type identifier in the carton type input on the container weight and dimension screen | System accepts the selected carton type and will be used for declaring dimensions in the shipping request
Outbound | Packing - Multis Packing |  |  | User manually enters the weight of the shipping container after packing is complete | The package is packed, and takes the weight that the user manually entered
Outbound | Packing - Multis Packing |  |  | User validates the autocalulated weight (weight is auto calculated on the basis of the quantity picked and the pack weight in the master data set up) | System displays the sum of the weight using the pack weight for the items for each order
Outbound | Packing - Multis Packing |  |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non integer value in the package weight entry box | User gets an error due to an invalid entry
Outbound | Packing - Multis Packing |  |  | If the autocalculated weight is incorrect, the user overrides the weight and enters a non numeric value in the package weight entry box | User gets an error due to an invalid entry
Outbound | Packing - Multis Packing |  |  | User hits submit, and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). | User gets a packing slip for the orders
Outbound | Packing - Multis Packing |  |  | User hits submit, and shipping labels print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). | User gets a shipping label for the order
Outbound | Packing - Multis Packing |  |  | User hits submit, and shipping label and packing slips print for the orders that don't have shipping failures (oldest order first for the scanned item in the picking LPN). | User gets a shipping label and packing slip for the orders
Outbound | Outbound - Cartonization | [5 empty] | Ready to Test
Outbound | Outbound - Rate Shopping | [5 empty] | Ready to Test
Outbound | Outbound - EDI Fulfillment | [5 empty] | Ready to Test
Reporting
Reporting | Dashboard - Inbound
Reporting | Dashboard - Inventory Management Dashboard
Reporting | Dashboard - Outbound
Reporting | Dashboard - User Performance
Reporting | Report Builder -

## Test Cases - End to End
EVE End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 0%
Category | Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Inbound | Receive a full clothing PO | Ready to Test | EVE
Inbound | Receive a full Jewelry PO | Ready to Test | EVE
Inbound | Receive a full Footwear PO | Ready to Test | EVE
Inbound | Receive a partial clothing PO | Ready to Test | EVE
Inbound | Receive a partial Jewelry PO | Ready to Test | EVE
Inbound | Receive a partial Footwear PO | Ready to Test | EVE
Inbound | Over Receive a clothing PO | Ready to Test | EVE
Inbound | Over receive a Jewelry PO | Ready to Test | EVE
Inbound | Over receive a Footwear PO | Ready to Test | EVE
Inbound | Receive a PO placing part of it into studio and damages LPNs/Locations | Ready to Test | EVE
Inbound | Receive a clothing PO adding a note to the order header | Ready to Test | EVE
Inbound | Receive a Jewelry/Footwear PO adding a note to the order header | Ready to Test | EVE
Inbound | Receive a Jewelry/Footwear PO adding a note to an order line | Ready to Test | EVE
Inbound | Receive a clothing PO that has a note to display to an end user | Ready to Test | EVE
Inbound | Receive a Jewelry/Footwear PO that has a note to display to an end user | Ready to Test | EVE
Inbound | Receive an LPN full of returns | Ready to Test | EVE
Inbound | Unreceive a full PO | Ready to Test | EVE
Inbound | Unreceive a PO partially | Ready to Test | EVE
Inbound | Putaway a full pallet of LPNs | Ready to Test | EVE
Inbound | Putaway the LPNs of a clothing SKU partially into a 4 deep location and the rest into a racking location | Ready to Test | EVE
Inbound | Putaway the LPNs of a clothing SKU partially into a 4 deep location | Ready to Test | EVE
Inbound | Putaway the LPNs of a clothing SKU partially into a 2 deep location | Ready to Test | EVE
Inbound | Putaway the LPNs of a clothing SKU partially into a 1 deep location | Ready to Test | EVE
Inbound | Putaway the LPNs of a Jewelry SKU partially into a jewelry location | Ready to Test | EVE
Inbound | Putaway a Footwear SKU partially into a Footwear location | Ready to Test | EVE
Inbound | Putaway returns into multiple locations where they live in the warehouse | Not Ready to Test | EVE
Inbound | Putaway returns into the R1 location | Not Ready to Test | EVE
Inbound | Putaway returns into the R2 location | Not Ready to Test | EVE
Outbound
Outbound | Fulfill "large" orders | Not Ready to Test | EVE
Outbound | Fulfill single unit orders | Not Ready to Test | EVE
Outbound | Fulfill multi unit orders | Not Ready to Test | EVE
Outbound | Fulfill international orders | Not Ready to Test | EVE
Outbound | Fulfill domestic orders | Not Ready to Test | EVE
Outbound | Exception a pick task for "large" order | Not Ready to Test | EVE
Outbound | Exception a pick task for a single unit order | Not Ready to Test | EVE
Outbound | Exception a pick task for a multi unit order | Not Ready to Test | EVE
Outbound | Cancel an order that has not yet been released | Not Ready to Test | EVE
Outbound | Cancel an order that has been released but not picked | Not Ready to Test | EVE
Outbound | Cancel an order that has been picked but not packed or shipped | Not Ready to Test | EVE
Outbound | Cancel an order that has been packed but not shipped | Not Ready to Test | EVE
Outbound | Roll back an order that has been shipped and cancel it | Not Ready to Test | EVE
Outbound | Roll back an order that has not been shipped and re-ship | Not Ready to Test | EVE
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Not Ready to Test | EVE
Inventory Management | Perform scheduled cycle counts by item | Not Ready to Test | EVE
Inventory Management | Perform on demand cycle counts by location | Not Ready to Test | EVE
Inventory Management | Perform scheduled replenishment tasks | Not Ready to Test | EVE
Inventory Management | Perform on demand replenishment tasks | Not Ready to Test | EVE
Inventory Management | Over-replenish | Not Ready to Test | EVE
Inventory Management | Perform exception during replenishment | Not Ready to Test | EVE

## EVE Integration Test Suites
Type | Test Suite Name | Link | Status
Inbound | Purchase Orders | https://docs.google.com/spreadsheets/d/1PBbVOzQoLmwBAl_COgEs0uYNPYbfYiLbKwfcakdhKFo/edit?usp=sharing | In Progress
Outbound | PO Receiving | https://docs.google.com/spreadsheets/d/1PBbVOzQoLmwBAl_COgEs0uYNPYbfYiLbKwfcakdhKFo/edit?usp=sharing | In Progress
Outbound | Inventory Adjustments | https://docs.google.com/spreadsheets/d/1u--PPV0GZBM1dpdK8pIUk2X6EhCyTNz6pUcGXcZ1k54/edit?usp=sharing | To Do
Inbound | Return Authorizations | https://docs.google.com/spreadsheets/d/1Ysrn8ETd5jviqHSob6VGOSQQbRYi4_ycAEvNF4qO6sI/edit?usp=sharing | In Progress
Outbound | Backorders/Reallocation | https://docs.google.com/spreadsheets/d/1Qy9PwnuS0v7DqqOV-5MWDP08r7015QeFuTTuqTYa-pM/edit?usp=sharing | To Do
Inbound | Trendsend Orders | https://docs.google.com/spreadsheets/d/1S6fUsW0NW1rkwxMt-nDVn3qTlt_axYHyR4oEkt3_TZw/edit?usp=sharing | To Do
Outbound | Shipments | https://docs.google.com/spreadsheets/d/1o0VeKp2mR7GCL4Madm218YL95eOVzTXhEAF0pqR8tV0/edit?usp=sharing | In Progress
Outbound | Trendsend Shipments | https://docs.google.com/spreadsheets/d/1DeNhKB5XDELdiwF63mqt9beo3h11xiP67APqd2ipAik/edit?usp=sharing | To Do

## GoNo-Go Decision
EVE Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 0
Deposco Setup | Label Printer Procurement | 10 | Y | EVE | 0% | 0 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printer Procurement | 10 | Y | EVE | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | EVE | 0% | 0 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 | Y | EVE | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | EVE | 0% | 0 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | EVE | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | EVE | 0% | 0 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 0% | 0 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 0% | 0 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 40 |  |  |  | 0
Warehouse Prep | Location Labels | 10 | Y | EVE | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Container Labels | 10 | Y | EVE | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Inventory Labels | 10 | Y | EVE | 0% | 0 | Are all inventory units labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 | Y | EVE | 0% | 0 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 55 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create EVE Returns | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | EVE Order Management | 5 |  | EVE | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 0
Training & Testing | Test Case Scenarios Definition | 10 | Y | DEP / EVE | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and EVE to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | EVE | 0% | 0 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | EVE | 0% | 0 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | EVE | 0% | 0 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | EVE | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 60 |  |  |  | 0
Master Data | Cutover Inventory Validation | 10 | Y | EVE | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Items and Packs | 10 | Y | EVE | 0% | 0 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 | Y | EVE | 0% | 0 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Containers | 10 | Y | EVE | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Kit/Component Relationships | 10 | Y | EVE | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | EVE | 0% | 0 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / EVE | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 55 |  |  |  | 0
Interfaces - Imports to Deposco | Carton Types Upload | 10 | Y | EVE | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 | Y | EVE | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 | Y | EVE | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | EVE | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Item Vendor Upload | 10 | Y | EVE | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 | Y | EVE | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Exports from Deposco | Email confirmation upon shipment | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 190 |  |  |  | 0
Integrations with Deposco | Shopify - Item - Pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Shopify - Customer Order- Pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Shopify - Refund- Pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Shopify - Inventory Sync - Push | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Shopify Ship Notice - Push | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Shopify POS - Retail Activity - Pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Shopify POS - Inventory Sync - Push | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Celerant - PO pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Celerant - Inbound Shipment Pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Celerant - PO receipt push | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Celerant - Customer Order Push | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Celerant - Shipment Pull | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Celerant - Inventory Adjustment Push | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | STAMPS - Get Shipping Label | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | STAMPS - Get Rate Shop Request | 10 | Y | EVE | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 10 | Y | EVE | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 | Y | EVE | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Rate Shop Request | 10 | Y | EVE | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 80 |  |  |  | 0
Reports and Labeling | Shipping Label | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Packing Slip Report | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Location Label | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Item Label | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Cartonized Container Label | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Carton Type Label | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Container Label | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Generic BOL Report | 10 | Y | EVE | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 0
Contingency Plans | Contingency Plans | 10 | Y | DEP / EVE | 0% | 0 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 0
| Total Possible Score: | 640
| Total Percentage: | 0%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan
EVE Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | EVE
3 | Set up Shopify | Set up Shopify Instances in Production environment | FALSE | EVE
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE | DEP/EVE
5 | Test Order Pull | Create a test order in Shopify and bring order into Deposco | FALSE | EVE
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify | FALSE
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify | FALSE
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE
10 | Master Data Check - Items | Look through items in production environment | FALSE
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE
18 | Inventory Push to Shopify | Inventory is pushed to shopify | FALSE
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Shopify Instances to bring in orders | FALSE
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE

## Future ItemsParking Lot
EVE Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | EVE Comments
Order Consolidation | BO Order Consolidation | 2025-06-11
Item level notes for pickers | Note in item.longDescription that if present creates a note for the picker reminding them to do something | 2025-06-12
Blind RMA Receiving Sortation | Additional logic to sort returned product onto putaway carts by zone for quicker putaway | 2025-06-13
Using Markets for Influencer and Employee Orders. | Utilizing shopify to have employee and influencer orders from through the integration | 2025-07-15