## Task Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Due Date | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | FSG Comments | ETA | LINK TASK
Master PO | From the email chain "Follow-Up Conversation about POs," need to determine if the incoming "master PO" can be omitted since FSG does not feel it should be needed for inventory. Please also send the decision in response to John's email on 12/21 - subject "12/20 Weekly Status Notes" Notes: FSG has mapped Master PO into the Inbound 856 with Shapiro, but is unable to have it uploaded to Deposco so we need to align on a new design for Phase 1 on inbound 856. Easiest approach is to treat each inbound shipment container as an individual PO with lines. There will be no visibility against the master PO or the customer order (which is not present in the inbound 856), all receipt lines will be against the totality of each inbound shipment container. |  |  |  | TRUE | TRUE | In Progress | DEP | Andrew | 2023-12-21 |  |  |  |  | 1/24: JDE team feels comfortable with it 1/31: JDE sent master PO sample to Andrew - need response. Claire to follow up
850 Testing with SPS | Confirm 850 XML has been received without issues and respond to email titled "EDI Task List Urgent" |  |  |  | TRUE | TRUE | Completed | DEP | Zach | 2023-12-21 | 2023-01-05 |  |  |  | Will continue to receive and test on an ongoing basis leading up to go live.
Additional requirements for sending ASN information for Cardinal and expected SSCC number generation for Cardinal | Angie and Zach posed questions for Ted in the email chain titled, "Deposco sent for Cardinal Health" |  |  |  | TRUE | TRUE | Completed | FSG | Ted/Angie | 2023-12-20 | 2023-01-05 |  |  |  | Angie and Mike will connect and determine requirements & how it's done today. If they could send the "retailer routing guide" for each trading partner, Deposco can review and see if any detail is provided. FSG is not aware of this requirement and may not require it today. SPS was the one who rasied the concern to Deposco. 1/10: CVS is only trading partner that will need ASNs. Won't need to generate SSCCs for remaining ones, but will need to generate those for CVS. Will continue to generate as Fishbowl does. CVS orders only ship from Akron. Zach will finalize the build
Validate 3PL team's setup and developement to Deposco APIs | DEAN is not following the 3PL deck and has XML formatted for InventoryAdjustment API when Deposco laid out the JSON requirement. DEAN must follow JSON to keep consistent with all other 3PLs |  |  |  | TRUE | TRUE | Completed | FSG | Ted | 2023-12-29 | 2023-01-05 |  |  |  | 1/3 Notes: Cesar (Dean) confirmed they'll send JSON. Regal has not confirmed yet. No issue on the Deposco side with setting up Regal as a location in the system. It's a manual process on the FSG side - would have to "fake pick/ fake pack" on behalf of them (if their testing isn't finished)
Validate 3PL ability to create proper SSCC Compliant Labels - Regal/Dean | Validate 3PL's ability to generate SSCC compliant Labels (Pending SSCC Compliance requirements) |  |  |  | TRUE | TRUE | Closed | FSG | Ted | 2023-12-29 | 2023-01-05 |  |  |  | Deposco is working on configuring, but enforcement with the 3PLs must be owned by FSG. 1/10: CVS only client who needs this; only ship from Akron - closing
Validate 3PL ability to send proper SSCC Compliant Shipments to Deposco - Regal/Dean | Validate 3PL's ability to generate SSCC compliant Shipments in Deposco for SPS ASN's (Pending SSCC Compliance requirements) |  |  |  | TRUE | TRUE | Closed | FSG | Ted | 2023-12-29 | 2023-01-05 | Validate 3PL ability to create proper SSCC Compliant Labels - Regal/Dean | Validate 3PL's ability to generate SSCC compliant Labels |  | Deposco is working on configuring, but enforcement with the 3PLs must be owned by FSG. 1/10: CVS only client who needs this; only ship from Akron - closing |  | TRUE | TRUE | FSG | Ted | 2023-12-29 | 2023-01-05
Validate 3PL team will send Deposco/FSG inventory level attributes | DEAN is not sending expiration/lot data in their inventory adjustment back to Deposco. |  |  |  | TRUE | TRUE | Completed | FSG | Ted | 2023-12-29 | 2023-01-05 |  |  |  | Cesar (Dean) confirmed. Regal has not confirmed yet. Same information as P12. Need other 3PLs to confirm they track lot & expiration date as well 1/10: Seems to be progressing well; will keep open until we test with the files they provide
Have Shapiro/SPS send examples of 850 (Sales Orders) to Deposco as well as provide FSG with Inbound 856 examples |  |  |  |  | TRUE | TRUE | Completed | FSG | Ted | 2023-12-29 | 2023-01-05 |  |  |  | Shapiro has sent to SPS. There is an issue with the data, so we haven't received from SPS. 1/24: No updates; leave open through UAT for testing.
Validate that ASN's will only need to be sent for Cardinal Health, Harvard Drug, and CVS | Validate that ASN's will only need to be sent for Cardinal Health and CVS |  |  |  | TRUE | TRUE | Completed | FSG | Ted | 2024-01-03 | 2023-01-05 |  |  |  | Discussed on weekly status on 1/3/24. Want to ensure that ASN's are only required for Cardinal and CVS
Validate Invoices in Quickbooks Online | Review Deposco created Invoices in Quickbooks Online for accuracy and needed information |  |  |  | TRUE | TRUE | In Progress | FSG | Ted/Lisa | 2023-12-29 | 2023-01-05 |  |  |  | 1/10: Meeting occurred last week. Zach working on adding some items to the invoice. Matt uploaded item master file into QB Online. Will be able to re-test after Zach makes the updates 1/24: Not yet able to generate invoices; will be quick to test once data is loaded 1/31: Items were loaded last week. Matt will look at the invoices today
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## UAT Task Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Due Date | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | FSG Comments | ETA | LINK TASK
Shipping | Set the PO number to the ref field on ups labels (po number should be the external order number) |  |  |  | FALSE | Completed | DEP | Josiah
Images | Add api sql on order to show that it contains an image |  |  |  | FALSE | Completed | DEP | Josiah
Reports | Scheduled report builder to show stock units expiring within x days |  |  |  | FALSE | Completed | DEP | Josiah
Reports | Add an embedded entity report to show orderlines |  |  |  | FALSE | Completed | DEP | Josiah
Receiving | Reduce size of the auto generated lpn number in receiving so it can fit on the pallet |  |  |  | FALSE | Completed | DEP | Josiah
Receiving | Save variables to print the container label for pallets to print before putaway |  |  |  | FALSE | Completed | DEP | Josiah
Receiving | Change suggested locations to show all empty locs in warehouse |  |  |  | FALSE | Completed | DEP | Josiah | [5 empty] | Added this to move container
Receiving | Prevent receiver from receiving lpn to a location with stock already in it |  |  |  | FALSE | Completed | DEP | Josiah
Warehouse Lookup | Only show location number, container number etc to avoid duplicates |  |  |  | FALSE | Completed | DEP | Josiah
Reports | Adjust the packing slip to pass in order number |  |  |  | FALSE | Completed | DEP | Zach
Master Data | Make all cases ready to ship in PII |  |  |  | FALSE | Open | DEP | Zach
PAL | Print packing slip on order |  |  |  | FALSE | Completed | DEP | Josiah
Shipping | Need to print the packing slip PER TRIP during attc closeout |  |  |  | FALSE | Completed | DEP | Josiah | [5 empty] | Tested with order 132 in ua and working as expected
Receiving | Make the pallet number be orderNumber-receiptLine id |  |  |  | FALSE | Completed | DEP | Josiah | [5 empty] | orderNumber-deposco sequence counter
Pallet Picking | Mike wants to be able to pick x units into one pallet, then y units into other pallet. Would need to stage the first pallet then pick units into other pallet, then stage etc |  |  |  | FALSE | Completed | DEP | Josiah | [5 empty] | Want to pick into lpns instead of picking into one pallet then repalletizing after // Setup a "new partial picking" button that follows this requirement. Used order "NewPartialPicking"
Pallet Picking | They need to tell us the total pallets to expect on the partial order using a text field on the orderlines |  |  |  | FALSE | Completed |  | Josiah | [5 empty] | Mike will tell us which lines belong to which pallet numbers and we show the pallet # on the screen during partial picking. Team picks then stages the picked pallet and we print the pdf pallet label, then they move on to the next pallet and we print another pallet label | Logic is completed and in prod for this
Packing slip | Add expiration date, and sku number (item.styleNumber) |  |  |  | FALSE | Completed |  | Josiah | [5 empty] | Currently have the fsg item number, but need to add the fsg sku number
Partial picking | No longer print the temporary pallet label after partial picking |  |  |  | FALSE | Completed |  | Josiah | [5 empty] | Do not print this because Mike wants to pick directly into containers during picking, not repalletize after picking is complete
Packing | Can you ship expired stock? |  |  |  | FALSE | Completed |  | Josiah | [5 empty] | Sometimes they sell expired stock to discount stores | You can ship expired stock. Tested with orders 57 and 58 in prod
Printing | Printer Review - Get Matt and Calyx on phone to review inconsistent Print Jobs |  |  | 1 | TRUE | Completed | DEP/FSG | Zach
QBO | Adjust qbo invoice query to send copied orders to qbo and make invoices |  |  |  | FALSE | Open |  | Zach
3PL/Integrations | Send API Follow Ups and Action Items to DEAN |  |  |  | FALSE | Open | DEP | Zach
3PL/Integrations | Purchase Orders and Receipts Testing |  |  |  | FALSE | Open | FSG
3PL/Integrations | Group Shipments By Pallet in Shipment Request |  |  |  | FALSE | Open | DEAN | DEAN
Picking | Set the palet sequences and print them off at the very end of picking the wave |  |  |  | FALSE | Completed | DEP | Josiah
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Go Live Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Date Completed | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | FSG Comments | ETA | LINK TASK
Upload DEAN inventory | [5 empty] | Ongoing | FSG |  | 2024-03-04 | [5 empty] | Dean will send the 945 back to Deposco end of day 3/6, still a question about the full URL for receipts with all attributes, which Cesar will email questions to Zach 3/6. Ceasar has not sent file eod 3/6??? on 3/6 Jeremy sent 944 XML file with all shipment confirmations created on your end (201). Is this what was needed? No, that is the file for segregating Canada and US items.
Upload Regal Inventory | [5 empty] | Ongoing | FSG |  | 2024-03-04 | [5 empty] | We have inventory it does not make sense to upload into deposco as the inventory will change before sps is ready. Once we are ready to go with SPS we need to input the inventory . Manual, Angie will pull. Will be entered in Deposco on 3/7
Upload Candor Inventory | [5 empty] | Ongoing | FSG |  | 2024-03-04 | [5 empty] | We have inventory it does not make sense to upload into deposco as the inventory will change before sps is ready. Once we are ready to go with SPS we need to input the inventory . Manual, Mike will pull. Will be entered in Deposco on 3/7
CoHeader Rules to Place Canada Dollar Tree On Hold | Place order in review and add a conotice to add canadian packaging |  |  |  |  | Completed | DEP | Josiah | 2024-03-05 | 2024-03-05 |  |  |  | Moved rules to production from ua after testing on 03/05
Send Email to Dean to have ensure all Receipts, Adjustments, Shipments are coming into Deposco | [5 empty] | In Progress | DEP | Zach | 2024-03-05
Work with SPS to get remaining orders | [5 empty] | In Progress | FSG | Matt | 2024-03-05 | [5 empty] | List of old POs has been given to SPS to resync, started 3/5. new list for any remaining POs for resync will be sent 3/6. Waiting to see results of resync on, we will check morning of 3/7, also waiting on location code from John L.
Work with John Lau to get remaining PO's in | [5 empty] | In Progress | FSG | John/Mike/Angie | 2024-03-05 | [5 empty] | John is sending the info on all items for PO's 3/4 and forward. Deposco has 26 total PO's in the system. Angie and Mike have significantly more PO's than that.
Add LPN Number to Location Screen in Warehouse Lookup | Override location screen to show pack,lpn, lot and exp date |  |  |  |  | Completed | DEP | Josiah | 2024-03-04 | 2024-03-05
Create SOP for Customer Sales Orders in Review due to missing item | CoHeaders will be in status "Review" because the item could not be identified |  |  |  |  | Completed | FSG | Elzey | 2024-03-04 | 2024-03-04 |  |  |  |  | SOP is done for receiving, putaway, Picking, and Shipping. I am adding other sections such as reporting, adding skus into the Deposco system, etc.
JDE Send Missing Items - Items not in Deposco | 64430715A,22477060 - These Items are Direct Import Orders which will not be received into Deposco/FSG USA |  |  |  |  | Completed | FSG | John | 2024-03-05 | 2024-03-05 |  |  |  |  | In addtional, sending to John 3/6 the list of Canada item numbers that need to be created in JDE
prepopulate orderline.lotNumber during receiving | [5 empty] | Completed | DEP | Josiah | 2024-03-05 | 2024-03-05
On Hand Qty Report Grouped by Expiration Date | [5 empty] | Completed | DEP | Josiah | 2024-03-05 | 2024-03-05
Report to show storage location utilization | [5 empty] | Completed | DEP | Josiah | 2024-03-06 | 2024-03-06 |  |  |  | Shows how many locations are being utilized with stock in the warehouse
prepopulate orderline.EXPIRATION_DATE during receiving | [5 empty] | Completed | DEP | Zach | 2024-03-06 | 2024-03-06
Have SPS Only Send Orders meant for FSG USA - No Direct Import Orders | FSG needs to provide list of Vendor IDs to Deposco/FSG that are meant for FSG USA |  |  |  |  | Open | FSG | John/Matt | 2024-03-06 | [5 empty] | Vendor IDs have been provided for DT and FDS
Import Dollar Tree Orders | [5 empty] | Open | DEP
Find out from SPS if Harvard Drug Orders will sync from SPS | [5 empty] | In Progress | FSG |  | 2024-03-06 | [5 empty] | Harvard Drug can send PO's, Angie from SPS working on that
Create SOP for Entering Orders through Sales Order Entry | [5 empty] | In Progress | DEP/FSG | Elzey/Mike | 2024-03-07
Widget showing expiring and expired cases in the warehouse by exp date | [5 empty] | Completed | DEP | Josiah | 2024-03-06 | 2024-03-07
Show how many containers received today (PO should = inbound container) | [5 empty] | Open | DEP |  | 2024-03-07
See why Sales Order Entry Order did not go through POI | [5 empty] | Completed | DEP |  |  | 2024-03-07
POI - Create Order Line Note with Body and Title "95147700" for Purchase Orders when orderLine.customAttribute = 95147700 | [5 empty] | Completed | DEP | Josiah | 2024-03-07 | 2024-03-07
Create Rules to Store vendor Number from Trading Partner | Store Vendor Number on OrderHeader if provided on Trading Partner Entity |  |  |  |  | Completed | DEP | Zach | 2024-03-07 | 2024-03-07
Create Rules to put CoHeader in Review if Family Dollar is the TP and CoHeader.accountNumber is not 96905 | [5 empty] | Open | DEP |  | 2024-03-07
Create Additional Dock Doors | [5 empty] | Completed | DEP | Zach | 2024-03-07 | 2024-03-07
Get Bulk Packing slip to print through base | [5 empty] | Completed | DEP |  | 2024-03-07 | 2024-03-08 |  |  |  |  | May need to adjust to pass in container hist instead of order
Training/SOP on how to set up Payment Terms Cross References in Deposco | [5 empty] | Open | DEP/FSG
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## UAT Notes
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
TITLE | DESCRIPTION | TYPE | SEVERITY | PRIORITY | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Due Date | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | FSG Comments | ETA | LINK TASK
Packing | Always print two pallet labels during packing
Inventory | Need to import candor and regal inventory before go live
API | Dean will send file of shipped orders that we won't know about. Angie to use adjust inventory to adjust out of dean location, but need to see if we can add a field to put in which order it belonged to
Shipping | Truck can only hold 30 pallets, if order has > 30 pallets and comes down as one order then they would split this into two orders manually in their old system because they cannot bill the customer in quickbooks until the entire order is shipped but sometimes the second truck won't come for 2 weeks.
Shipping | Assumption is they close one order per trip and we print packing slip at that point
SPS | Cannot access arhcived orders that have been pulled into fishbowl already
QBO | Won't be able to invoice unless we pull direct from sps. Current issue is they have +5 months of orders in fishbowl and their orders are archived
SPS | Can SPS Unarchive and Send "Old" Orders |  |  |  | TRUE | Open | FSG
Go-Live | Discuss Cutover Plans - Old Orders/Inventory |  |  |  | FALSE | Open | DEP/FSG
Picking | Re-work Partial Picking Process for LPN staging and creation |  |  |  | FALSE | Open | DEP
Go-Live | Plan Production Cleanup/Wipe and Discuss "soft receiving' go-live |  |  |  | FALSE | Open | DEP
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Pre-Cutover Activities
FSG Cutover
FSG Cutover
FSG Pre-Cutover Steps
Purpose: Organize all tasks that are to be executed in preparation for deployment.
Ref | Area Owner | Assigned Resource | % | Task Description | Initial ETA | Target Date | Comp Date | Required Comp Date | Dependencies | Comments
| Task Owner |  |  | Pre Deployment Steps
FSG
1 | FSG |  | 0% | Upload/Create all Locations to Deposco
2 | FSG |  | 0% | Scanners at each workstation
3 | FSG |  | 0% | Validate Pack Station laptops/desktops
4 | FSG |  | 0% | Set up pack stations
5 | FSG |  | 0% | Set up printers (Print Client is setup, printers are on same device)
6 | FSG |  | 0% | Set up wifi
7 | FSG |  | 0% | Configure packstations as a resource and assign printers
8 | FSG |  | 0% | Shipping Label - print out and validate
9 | FSG |  | 0% | Packing Slip - print out and validate
10 | FSG |  | 0% | End User Configuration
11 | FSG |  | 0% | Continued Super User Training
12 | FSG |  | 0% | User Training (Happy Path and Exception Scenarios)
13 | FSG |  | 0% | Validate/Test integration schedulers for Deposco are working
14 | FSG |  | 0% | Review Scheduler Frequencies
15 | FSG |  | 0% | Review Waving Logic
16 | FSG |  | 0% | Build SOP document for entire solution. Leave a relevant copy at each given area (packing sections for pack stations)
17 | FSG |  | 0% | Validate all Locations in proper zones
18 | FSG |  | 0% | Test with all set-up Printers
19 | FSG |  | 0% | Repull product data into production
Deposco
1 | DEP |  | 0% | Build system monitoring queries
2 | DEP |  | 0% | Wipe out test orders
3 | DEP |  | 0% | Review each packstation is configured as a resource
4 | DEP |  | 0% | Validate all master data has been configured
5 | DEP |  | 0% | Review Waving Logic
6 | DEP |  | 0% | Purge Transactional Data
7 | DEP |  | 0% | Validate all schedulers are enabled for production environment
8 | DEP |  | 0% | Validate all Integration changes needed are in production environment
9 | DevOps |  | 0% | Build Production environment
10 | DevOps |  | 0% | Add socket credientals to Production environment
11 | DEP |  | 0% | Wipe product data

## GoNo-Go Decision
Factors | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Due Date | Comment | FSG Team Tested | DEP Team Tested
| Deposco Setup | 80 |  |  |  | 79
Deposco Setup | Printer Details | 10 |  | FSG (Matt) | 100% | 10 | Are all printers configured? | 2024-01-11 |  | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | FSG (Matt) | 100% | 10 | Are all print stations setup? Are printer supplies on-hand (ribbons, labels, etc.)? | 2024-01-11 |  | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | FSG (Matt) | 100% | 10 | All reports assigned to printers and resources? | 2024-01-11 |  | TRUE | FALSE
Deposco Setup | RF Scanners/Handheld Devices | 10 |  | FSG (Matt) | 100% | 10 |  | 2024-01-11 | congiured, working thorugh testing with SOP and configuration | FALSE | FALSE
Deposco Setup | Label Printers | 10 |  | FSG (Matt) | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? | 2024-01-11 | 1/24: Installling today and plan to test tomorrow during training session 1/31: Installed but not yet validated. Matt had followed networked printer instructions. Zach to investigate printer setup. Prints test page. 2/2: set up Dock location printer and test prints AOL done on training call to day with Zach and Matt. Matt witl set up second label printer today once it arrives, as a back up and to have one near office area. | TRUE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 |  | FSG (Matt) | 100% | 10 | Are the report documents configured to print on the proper printers? Are some reports configured with device overrides (e.g. processing area printers). | 2024-01-11 | Need to verify what is set by Deposco in system | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | Deposco | 90% | 9 | Have all High and Critical issues from the issues list been resolved? |  |  | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release - Inv Adj - Cycle Counts | 10 |  | Deposco | 100% | 10 | Backups, day, month end jobs. All jobs have been scheduled. CC by Location, PO Import, Waving, Inv Adjustment | 2024-01-11 | Deposco pease show Matt, Elzey, Mike, Angie where this is set up. | FALSE | TRUE
| Warehouse Prep | 20 |  |  |  | 20
Warehouse Prep | Location Labels | 10 |  | FSG | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 0 |  | FSG | 0% | 0 | Procure Carts for moving of inventory and label them |  | N/A - Claire to remove | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 0 |  | FSG | 0% | 0 | Item inventory barcoded and labeled to scan |  | N/A - Claire to remove | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 |  | FSG | 100% | 10 | Is the connectivity strong and cover all necessary scan areas? |  |  | FALSE | FALSE
| Standard Operating Procedure Documentation | 90 |  |  |  | 90
Standard Operating Procedures | Receiving | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Putaway | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Singles Picking | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Multis Picking | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Singles Packing | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Multis Packing | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | LTL Shipping (Wholesale) | 10 | Y | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
Standard Operating Procedures | Customer Order Creation/Updates/Waving | 10 |  | FSG (Elzey) | 100% | 10 | SOP's been written? Online Help, plus FSG-specific. Start with FSG template. | 2024-01-12 | Created, have a few questions sent to Zach 1/11/24 | FALSE | FALSE
| Training & Testing | 50 |  |  |  | 25
Training & Testing | Business Scenarios Definition | 10 | Y | FSG (Angie & Mike) | 50% | 5 | Define all Business scenario including exception processes Unit and End to End Test Case Definition | 2024-01-12 | in process, but will identify during UAT | FALSE | FALSE
Training & Testing | Process Training and Testing - Receiving - Putaway - Cycle Counting - Parcel Picking - Parcel Packing - LTL Shipping - Shipping | 10 | Y | FSG (Angie & Mike) | 75% | 7.5 | Unit and End to End Test Case Execution | 2024-01-12 | in process, but will identify during UAT | FALSE | FALSE
Training & Testing | User Acceptance Testing | 10 | Y | FSG (Angie & Mike) | 75% | 7.5 | Execute all defined business scenarios within Deposco | 2024-01-12 | Address and test all outlined scenarios during UAT. | FALSE | FALSE
Training & Testing | Supervisor/Administrator | 10 | Y | FSG (Angie & Mike) | 50% | 5 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | 2024-01-12 | in process, but supervisors are still in training themselves. Cannot happen until after UAT. | FALSE | FALSE
Training & Testing | End-user | 10 | Y | FSG (Angie & Mike) | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | 2024-01-12 | in process, but supervisors are still in training themselves. Cannot happen until after UAT. | FALSE | FALSE
| Configurations/Master Data | 80 |  |  |  | 77.5
Configurations | Inventory Validation | 10 | Y | FSG (Angie & Mike) | 75% | 7.5 | Putaway Audits | 2024-01-18 | we understand from using handheld modual. We still need to see from Deposco training how Dean receiving will work and is all data captured as if we were to enter it. Inventory Adjustments can be audited and seen under the Inventory Ledger - Inventory Admin -> Inventory Ledger 2/14: Soft go-live activity | FALSE | FALSE
Configurations | Items | 10 |  | FSG (Angie & Mike) | 100% | 10 | Are all items setup? Are all of the units of measure defined for each item? | 2024-01-18 | Need item master up to date from John (JDE) and duplicates removed (Zach). 1/31: Item master sent without the spacing; Zach to review today | FALSE | FALSE
Configurations | Zones | 10 |  | FSG (Angie & Mike) | 100% | 10 | Have all of the Zone and Zone Location records been set up? Has the pick flow been tested? | 2024-01-18 | This is to be uploaded as part of the Location Import | FALSE | FALSE
Configurations | Locations | 10 |  | FSG (Angie & Mike) | 100% | 10 | Are the location types, zones, and location masters configured accurately. | 2024-01-18 | Mike will send Zach all locations by 1/17. | FALSE | FALSE
Configurations | Menu Structures | 10 |  | FSG (Angie & Mike) | 100% | 10 | Have the appropriate menu levels been created for the different departments? | 2024-01-18 | Per Zach this information will need to be uploaded as part of the item master file from John. Number column is used for FSG Item Number, Customer SKU Number should be used for the Customer/Retailer SKU. Part of item master | FALSE | FALSE
Configurations | Packs (UOMs) / Pack UPCs | 10 |  | FSG (Angie & Mike) | 100% | 10 | Have all valid pack types been entered into the system? | 2024-01-18 | Zach to add column to see qty of cases and qty of eaches in views. Still awaiting the full item/pack master data file from John. | FALSE | FALSE
Configurations | Containers | 10 |  | FSG (Angie & Mike) | 100% | 10 | Pallets, bins, carts | 2024-01-18 | Per Zach, no pallets, bins, or carts will need to be uploaded beforehand. Pallets (LPNs) will be auto generated as the result of receiving/picking processes. These can be found under Inventory Admin -> Containers. Zach moved this to complete in the Project Tracker Spreadsheet. | FALSE | TRUE
Configurations | Kit/Component Relationships | 10 | Y | FSG (Angie & Mike) | 100% | 10 | KitHeaders/KitDetails for Kit to Stock Item/Component for Kit to Order | 2024-01-18 | Per Zach, FSG will not use Kit/Component Relationships. Zach has moved this to complete in the Project Tracker Spreadsheet. | FALSE | TRUE
| Cutover and Conversion Plans | 10 |  |  |  | 10
Cutover and Conversion Plans | Cutover plan developed | 10 |  | Deposco | 100% | 10 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  | 2/14: Will discuss as week progresses & we move along w/ soft go-live 2/19: Waiting on Ted to reach out to SPS to provide orders from Fishbowl 2/21: Still waiting on SPS. Matt still waiting on response from John on whether he wants those POs sent to JDE or just to Deposco. Will have SPS complete first thing tomorrow (2/22) 2/26: Angie sent, Zach to confirm it pulls in correctly. Need to discuss w/ FSG whether they want to receive everything through the receiving process or cycle count things in 2/28: Receiving everything into the system (inventory from Dean). Inventory from Akron will have to be entered in. | FALSE | FALSE
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 30
Interfaces - Imports to Deposco | Carton Types from FSG to Deposco | 10 |  | FSG | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? | 2024-02-09 | Part of the cutover process - FSG will need to upload this data into production | FALSE | FALSE
Interfaces - Imports to Deposco | Locations/Zones from FSG to Deposco | 10 |  | FSG | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? | 2024-02-09 | Part of the cutover process - FSG will need to upload this data into production | FALSE | FALSE
Interfaces - Imports to Deposco | Items/Packs from FSG to Deposco | 10 |  | FSG | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? | 2024-02-09 | Part of the cutover process - FSG will need to upload this data into production | FALSE | FALSE
Interfaces - Imports to Deposco | Inventory from FSG to Deposco | 5 |  | FSG | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? | 2024-02-09 | Part of the cutover process - FSG will need to upload this data into production | FALSE | FALSE
Interfaces - Imports to Deposco | Purchase Orders from FSG to Deposco | 10 | Y | FSG | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? | 2024-02-09 | Part of the cutover process - FSG will need to upload this data into production | FALSE | FALSE
| Integrations | 90 |  |  |  | 82.5
Integrations with Deposco | Items | 10 |  | FSG (Matt & Elzey) | 100% | 10 |  | 2024-02-09 | Waiting for new item master from John and Vickie and Zach needs to remove items created from QB in Deposco that columns were not mapped properly. Matt to remove same in QB online sandbox 1/16. 1/31: Production environment will be created & will be wiped clean. | FALSE | FALSE
Integrations with Deposco | Trading Partner | 10 | Y | FSG (Matt & Elzey) | 100% | 10 |  | 2024-02-09 | Elzey to confirm with Mike/Angie that all trading partners that are in FB are in Deposco. Confirmed on 1/31 | FALSE | FALSE
Integrations with Deposco | Purchase Order | 10 | Y | FSG (Matt & Elzey) | 75% | 7.5 |  | 2024-02-09 | Need this put in Deposco, how and when can this happen? 1/31: Thru master PO files | FALSE | FALSE
Integrations with Deposco | Inv Adjustments & Inv Transfer | 10 | Y | FSG (Matt & Elzey) | 75% | 7.5 |  | 2024-02-09 |  | FALSE | FALSE
Integrations with Deposco | Ship Notice | 10 | Y | FSG (Matt & Elzey) | 50% | 5 |  | 2024-02-09 |  | FALSE | FALSE
Integrations with Deposco | Purchase Order (Manual Phase 1 and 856 Phase 2) | 10 | Y | FSG (Matt & Elzey) | 75% | 7.5 |  | 2024-02-09 |  | FALSE | FALSE
Integrations with Deposco | Field Mappings | 10 |  | Deposco | 100% | 10 |  | 2024-02-09 |  | FALSE | TRUE
Integrations with Deposco | Data Exchange Configs - v1 vs v2 | 10 |  | Deposco | 100% | 10 |  | 2024-02-09 |  | FALSE | TRUE
Integrations with Deposco | Carrier FSG Socket Setup and Validated - UPS (Online Tools) | 10 |  | FSG (Matt & Elzey)?? | 100% | 10 |  | 2024-02-09 | Seems should be assigned to Deposco for set up and validation 1/31: Carriers set up in UA | FALSE | FALSE
Integrations with Deposco | Carrier FSG Socket Setup and Validated - FedEx | 5 | Y | FSG (Matt & Elzey)?? | 100% | 5 |  | 2024-02-09 | Seems should be assigned to Deposco for set up and validation 1/31: Carriers set up in UA | FALSE | FALSE
| Interfaces - Exports From Deposco | 0 |  |  |  | 0
Interfaces - Exports From Deposco | Shipment Confirmation from Deposco to Email* | 0 |  | Deposco | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Reports and Labeling | 40 |  |  |  | 50
Reports and Labeling | Shipping Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | TRUE
Reports and Labeling | Location Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | TRUE
Reports and Labeling | Item Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | TRUE
Reports and Labeling | LPN Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  | Will be closed out once label printer is tested | FALSE | TRUE
Reports and Labeling | Carton Type Label | 0 |  | Deposco | 100% | 0 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Generic LPN (TJ Maxx) | 0 |  | Deposco | 100% | 0 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Packing Slip | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | TRUE
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | Deposco FSG | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? | 2024-01-19 | Yes, will run FishBowl in parallel for a few weeks. | TRUE | FALSE
| Total Weighted Score: | 474
| Total Possible Score: | 515
| Total Percentage: | 92.04%
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Activities
FSG Cutover
Assigned Resource | Status | Task Description | Date | Actual Finish | Dependencies | Comments
Task Owner |  | Cutover Day
Cutover Activities
Zach | Open | Clear Production Environment of Transactional Data

## Future ItemsParking Lot
Task Tracker
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | FSG Comments | ETA
Master DFSGgn Doc Review | 6/26: Sheyda and Edward have reviewed Inbound/Inv Mgmt -- need to review with DEP and review outbound and integrations | 2023-06-21
PO vs Inbound ASN vs TO decision for NS inbound order pulls | FSG uses Inbound ASNs in NS but there is no receipt notice touchpoint for these due to NS limitations Next Steps: Sheyda to look into potential use of Transfer Orders instead (used with HGL) | 2023-06-28
Master Data Upload - Locations/Zones | Using Data Exchange "Location w Zones Upload" | 2023-06-26
Master Data Upload - Carton Types | Using Data Exchange "Carton Type Upload" | 2023-06-26
NetSuite Entity Configuration for "Sent to Deposco" | FSG to add the "Sent to Deposco" field to all entities that should be pulled from Netsuite | 2023-06-13 |  |  |  | Inbound ASN, Customer, Item, Sales Order, RMAS all done
Error in NS "Customer" pull | {urn:core_2018_2.platform.webservices.netsuite.com}SearchStringCustomField must be used to search custom field custentity_deposco_pulled | 2023-06-13
Setup UPS Account (for third party shipping) | Use UPS Registration Wizard | 2023-06-13
Phase 2 Item Tracker
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | FSG Comments

## Working Session Recordings
Working Session Recordings
Date | Meeting Link | Passcode
2024-03-14 | https://deposco.zoom.us/rec/share/xmIsoimK83YpSwUnjtAeBJwtS3wjMCxSqmLJYeQuBYjXMEO_JtEjVscYe_cgcf6i.aOUuRNVxnf91hmb-?startTime=1710438577000 | @#M8pjj?
2024-03-14 | https://deposco.zoom.us/rec/share/ZzpE78pe2Oj-U_DkFFsUiurhXp0fZnkjyYaDZAyAUZHNqni8NLbBtSjHHA-ljDuJ.UQtYmlc__Mlt73gY?startTime=1710442907000 | C!4^phmY