## Go Live Item Tracker
Go Live Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
5- NTH (Nice to Have)
# | WORKFLOW | TYPE | TITLE | PRIORITY | DEP Owner | F2R Owner | STATUS | OWNER | Should this be added to portal? | Added to Portal | DESCRIPTION | NOTES | CREATED DATE | COMPLETION DATE | COMPLETE PRE-DESIGN?
1 | Master Data Setup | Issue | Puerto Rico Orders going into review status | 3-High | Kyle/Sam | N/A | Closed | DEP | FALSE | FALSE |  | Added Default Routing Profile to PR Selection | 2024-08-12 | 2024-08-12
2 | Initial Environment Setup | Issue | DC USB Printer Issues | 2-Critical | Henry | Tim | Closed | F2R | FALSE | FALSE | Packing Slip is not printing |  | 2024-08-12 | 2024-08-13
3 | Initial Environment Setup | Task | Trigger Amazon Inv Sync | 4-Medium | Sam | Chris | Cancelled |  | FALSE | FALSE |  | Inventory successfully uploaded to Amazon. | 2024-08-12 | 2024-08-12
4 | Outbound | Task | Smoke Test Amazon Order | 2-Critical | Sam | Don | Closed | F2R | FALSE | FALSE |  |  | 2024-08-12 | 2024-08-13
5 | Outbound | Task | Smoke Test Shopify POS Order | 2-Critical | Sam | Bree | Closed | F2R | FALSE | FALSE |  |  | 2024-08-12 | 2024-08-13
6 | Printers/Hardware | Task | Clean Up Handheld reprint buttons | 5-Low | Sam | David | Closed | DEP | FALSE | FALSE |  |  | 2024-08-12 | 2024-08-13
7 | Inventory | Task | Reconcile DEP inventory (Adjust out Snap) | 3-High | N/A | David | Closed | F2R | FALSE | FALSE |  |  | 2024-08-12
8 | Initial Environment Setup | Task | Waving Schedulers 6am to start | 2-Critical | Sam | David | Closed | DEP | FALSE | FALSE | 6.9.12.3pm |  | 2024-08-13 | 2024-08-13
9 | Outbound | Task | Split Transfer Orders into 100Pick tasks | 1-Blocker | Sam | Don | Closed |  | FALSE | FALSE |  |  | 2024-08-13 | 2024-08-13
10 | Inventory | Task | Send Inventory to Shopify | 2-Critical | Kyle | Chris/David | Monitoring | DEP | No Action Needed | FALSE | every hour |  | 2024-08-13
11 | Inventory | Task | Send Inventory to Amazon SC | 2-Critical | Kyle | Chris | Closed | DEP | To Be Decided | FALSE | event based - Pulled in when Amazon gets order |  | 2024-08-13
12 | Outbound | Request | DEMO New Zone Waving | 2-Critical | Sam | Don | Closed | DEP |  |  |  |  | 2024-08-15
13 | Inventory | Request | Buyer Reports | 2-Critical | Henry/Kyle | Tim | In-Progress | DEP | No Action Needed | TRUE | 2 Reports produced for buyers, consolidation in progress |  | 2024-08-14
14 | Outbound | Issue | Backorder Research | 2-Critical | Kyle/Sam | Chris/David | Validation | DEP | Move to Portal | FALSE |  |  | 2024-08-15
15 | Master Data Setup | Request | Update Order Priority | 4-Medium | Sam |  | Closed | DEP |  |  |  |  | 2024-08-13
16 | Admin | Request | Permissions _ Order Line _CSR | 5-Low | Kyle | David | Closed | DEP |  |  |  |  | 2024-08-13
17 | Inventory | Issue | BOPIS Order 6186985357621, Select Order 2000130094, 2000130091 | 2-Critical | Kyle | David | Closed | DEP/F2R | No Action Needed | FALSE | BOPIS Order David placed, needs to be pulled in with new setup |  | 2024-08-19
18 | Integrations | Issue | shipNotice to AmazonSC | 4-Medium | Sam | Tia | Closed | DEP |  |  | appears to be failing, docStore 3426 |  | 2024-08-14
19 | Outbound | Task | Confirm Fedex/USPS shipping charges | 3-High |  | David | Closed | F2R |  |  | make sure these look correct |  | 2024-08-14
20 | Testing | Task | F2R - Test Cases for BOPIS and order routing | 2-Critical |  | David | Monitoring | DEP | Move to Portal | TRUE | F2R to provide list of test cases anbd desired outcomes; Need test environment. |  | 2024-08-19
21 | Shipping Carriers Setup | Issue | Item Fulfillment to Netsuite - failing | 3-High | Kyle | Tim | Closed | DEP | No Action Needed | FALSE | need to review ship via for Netsuite and map cross ref |  | 2024-08-14
22 | Outbound | Request | Edit Wave/Bin Assignment Screen 'Picking LPN' | 5-Low | Sam/Henry |  | Closed | DEP |  |  | Change to just 'LPN' cause it's being cut off. |  | 2024-08-13 | 2024-08-13
23 | Outbound | Task | Exception Pick Null Error: | 3-High | Kyle | David | Closed | DEP | No Action Needed | FALSE | https://logs.deposco.com/_dashboards/goto/e50e7407263b23b242f253828bf35738 |  | 2024-08-14
24 | Integrations |  | Amazon Cancellation of orders | 3-High | Kyle | Tia | Validation | F2R | Move to Portal | TRUE |  |  | 2024-08-15
25 | Integrations | Issue | Shipping Charges feeding to NS | 3-High | Kyle/Sam | Matt/David | Open | DEP/F2R | Move to Portal | TRUE | Need integration plan for sending shipping charges to NS either via Deposco directly or inclusion to Shopify/Amazon and bridge to NS |  | 2024-08-20
26 | Admin | Request | Outline Process of Sales order BO and how to reprocess | 4-Medium |  | Tia/David | Closed | F2R | No Action Needed | FALSE | Amazon first, then maybe overnight, get list from David/Tia | how to handle order updates. f2r to review if order updates are possible in shopify, in amazon they would just cancel | 2024-08-13
27 | Admin | Task | Associate Users Upload | 5-Low |  | David | Closed | F2R |  |  |  |  | 2024-08-14
28 | Outbound | Issue | TO Waving | 5-Low |  | Don | Closed | DEP |  |  | TO's need to be manually waved by F2R |  | 2024-08-14
29 | Inventory | Task | Physical Count Setup | 4-Medium | Henry/Sam | David/Don | Closed | F2R | No Action Needed | FALSE | Configuration complete, F2R validation pending |  | 2024-08-14
30 | Outbound | Request | Remove quanity on multis | 5-Low |  | David | Closed | DEP |  |  |  |  | 2024-08-15
31 | Master Data Setup | Task | Canceled SO's peristing to the CO | 4-Medium |  |  | Open | DEP | Move to Portal | TRUE | CO427 example order, canceled in SO, not in CO |  | 2024-08-19
32 | Integrations | Task | Netsuite Item Pull | 4-Medium | Kyle | Tim | Closed | F2R |  |  | Need to get to self-sufficient state |  | 2024-08-19
33 | Integrations | Task | Netsuite Purchase Order Pull (save search) | 4-Medium |  | Tim | Validation | F2R | No Action Needed | FALSE | Doing a pull 8/19/24 around 5 pm | Pull appears to be working as intended | 2024-08-19
34 | Outbound | Issue | Order Splitting CO79 | 5-Low | Kyle | Tia/David | Open | DEP | Move to Portal | TRUE |  |  | 2024-08-13
35 | Integrations | Issue | Order 2000129273 pulling in canceled qty | 5-Low | Kyle | Chris | Open | DEP | Move to Portal | TRUE | docStore 1894 |  | 2024-08-13
36 | Admin | Task | F2R53 and F2R13 POS rollout | 3-High | Kyle |  | Closed | DEP |  |  | Need to smoke test and confirm POS is hitting correctly |  | 2024-08-15
37 | Integrations | Task | Shopify Address Validation | 5-Low | Henry | Chris | In-Progress | DEP | Move to Portal | TRUE | SO4 Pulled in w/o address or ship to info - SO4 resolved | need to run some ordrers through | 2024-08-13
38 | Outbound | Task | Multis Picking Screen Updates | 4-Medium | Henry |  | Closed | DEP |  |  | Item details on multis ‘picking screen’, Make sku field larger as well |  | 2025-08-15
39 | Master Data Setup | Request | Add ShipmentNumber to shipLabel ref | 5-Low | Sam |  | Open | DEP | Move to Portal | TRUE |  |  | 2024-08-14
40 | Inbound | Task | WHSE Receiving Troubleshooting | 4-Medium | Henry |  | Closed | DEP |  |  | Send to receiving instead of stock, some handhelds throwing company error |  | 2025-08-15
41 | Shipping Carriers Setup | Discussion | Shopify setup fulfillment for multiple stores | 2-Critical | Kyle |  | Closed | DEP/F2R |  |  | Impacts how remaining stores will be set up |  | 2024-08-16
42 | Master Data Setup | Task | Need gender size etc attributes on all items | 5-Low |  | Sarah | Validation | F2R | Move to Portal | TRUE |  | Check on brand/itemType - either item upload or pull from NS | 2024-08-14
43 | Outbound | Request | Remove the location on Store pick | 5-Low |  | David | Open | DEP | Move to Portal | FALSE |  |  | 2024-08-15
44 | Outbound | Request | Packing have it default to ecom bag | 5-Low |  | David | Open | DEP | Move to Portal | TRUE |  |  | 2024-08-15
45 | Outbound | Request | Pack Slip Edits | 5-Low | Henry/Sam | David | In-Progress | DEP | Move to Portal | TRUE | B&W Logo fixed, fields null from reprint handhelf button (https://deposco.freshdesk.com/a/tickets/179831) | Resolve printing for multi orders | 2024-08-15
46 | Outbound | Request | Weight default to two | 5-Low |  | Don | In-Progress | DEP | Move to Portal | TRUE |  | Update packs to weight value of 2, pull the item.weight to the screen instead of overriding the value | 2024-08-15
47 | Inventory | Task | Transfer Order in Store Picking (amazon fba) | 5-Low | Sam | Don | Closed | F2R | No Action Needed | FALSE | Transfer order showing in store picking |  | 2025-08-15
48 | Printers/Hardware | Issue | Tag printing issues | 5-Low | Henry | Tim | Validation | DEP/F2R | No Action Needed | TRUE | Tag printers are not printing - when they print they print wrong Printer functionality fixed, now working on off-center labels |  | 2024-08-19
50 | Inbound | Request | Adjust moveItem process to be grocery scan, omit qty entry | 3-High | Sam | Don | Validation | DEP | No Action Needed | FALSE | MoveItem used for putaway prompting for qty entry, needs to be grocery scanning |  | 2024-08-22
51 | Integrations | Issue | Purchase Order Pull NS | 3-High |  |  | In-Progress | DEP | Move to Portal | TRUE | PO Backlog is growing, pull from NS is unsuccessful due to timeout issue. Need smaller saved searches to pull, or look at ways to increase the timeout issue. Potentailly clear the queue on the NS side? Same as task # 33
52 | Integrations | Issue | POS Orders in Review due to Facility | 3-High |  |  | Validation | DEP | Move to Portal | TRUE | A number of POS coHeaders are in review due to unrecognized facilityID. Need to test setting up cross-references on the Production POS socket to resolve, then look at moving all POS to an individual socket with all facility cross-references so these can be regognized.
53 |  |  | Cycle count tasking setup | 4-Medium |  |  | Open |  | Move to Portal | TRUE
54 |  |  | Store count setup | 4-Medium |  |  | Open |  | Move to Portal | TRUE
55 | [9 empty] | FALSE
56 | [9 empty] | FALSE
57 | [9 empty] | FALSE
58 | [9 empty] | FALSE
59 | [9 empty] | FALSE
60 | [9 empty] | FALSE
61 | [9 empty] | FALSE
62 | [9 empty] | FALSE
63 | [9 empty] | FALSE
64 | [9 empty] | FALSE
65 | [9 empty] | FALSE
66 | [9 empty] | FALSE
67 | [9 empty] | FALSE
68 | [9 empty] | FALSE
69 | [9 empty] | FALSE
70 | [9 empty] | FALSE
71 | [9 empty] | FALSE
72 | [9 empty] | FALSE
73 | [9 empty] | FALSE
74 | [9 empty] | FALSE
75 | [9 empty] | FALSE
76 | [9 empty] | FALSE
77 | [9 empty] | FALSE
78 | [9 empty] | FALSE
79 | [9 empty] | FALSE
80 | [9 empty] | FALSE
81 | [9 empty] | FALSE
78 | [9 empty] | FALSE
79 | [9 empty] | FALSE
80 | [9 empty] | FALSE
81 | [9 empty] | FALSE
82 | [9 empty] | FALSE
83 | [9 empty] | FALSE
84 | [9 empty] | FALSE
85 | [9 empty] | FALSE
86 | [9 empty] | FALSE
87 | [9 empty] | FALSE
88 | [9 empty] | FALSE
89 | [9 empty] | FALSE
90 | [9 empty] | FALSE
91
92
93
94
95
96
97
98
99
100

## Go-Live Week Goals
Goal Tracker
Date | Goal | Description | Status | EOD Updates
2024-08-20 | Complete physical count | Ensure inventory in system aligns with true inventory | In Progress
2024-08-20 | Backorder management |  | In Progress
2024-08-20 | Shopify / Deposco Setup | Required for remaining store rollouts F2R to determine after internal meeting | In Progress
2024-08-16 | Backorder management |  | In Progress
2024-08-16 | Meet typical throughput | Typically: 250-400 orders | In Progress
2024-08-16 | Shopify / Deposco Setup | Required for remaining store rollouts F2R to determine after internal meeting | Open
2024-08-16 | Warehouse process training | Receiving | Closed
2024-08-16 |  | Putaway | In Progress
2024-08-16 |  | Cycle Counts - Number 2 item | Open
2024-08-16 | Netsuite transactions | Ensure accurate data - Item fulfillment failing as of 8/14 | In Progress
2024-08-15 | Backorder management |  | In Progress
2024-08-15 | Inventory push (Shopify/Amazon) | 8/14: Need to confirm Shopify cadence is set to every 15 minutes | Closed
2024-08-15 | Meet typical throughput | Typically: 250-400 orders | In Progress
2024-08-15 | Transfer Order Process Fulfillment | Need to split work between two buildings across all order types | Closed
2024-08-15 | Address Validation | Low priority | In Progress
2024-08-15 | Warehouse process training | Receiving | Closed
2024-08-15 |  | Putaway | In Progress
2024-08-15 |  | Cycle Counts - Number 2 item | Open
2024-08-15 | Netsuite transactions | Ensure accurate data - Item fulfillment failing as of 8/14 | In Progress
2024-08-14 | Backorder management |  | In Progress | 8/14: Some backorder issues are around inventory availability
2024-08-14 | Inventory push (Shopify/Amazon) | 80% at EOD 8/13 | In Progress | 8/14: Not sure of Shopify cadence, but need to confirm it's set to every 15 minutes
2024-08-14 | Meet typical throughput | Typically: 250-400 orders | In Progress
2024-08-14 | Transfer Order Process Fulfillment | Number 1 Priority | In Progress | 8/14: Need to split work between two buildings across all order types
2024-08-14 | Address Validation |  | In Progress | 8/14: Working on long-term fix
2024-08-14 | Warehouse process training | Receiving | Open
|  | Putaway | Open
|  | Cycle Counts - Number 2 item | Open | Discussing when a physical inventory can be completed with the current open work.
2024-08-14 | Netsuite transactions | Ensure accurate data | In Progress | 8/14: Item fulfillment failing
2024-08-13 | Amazon SC orders in Deposco | Want to get these orders shipped by EOD | Closed
2024-08-13 | Inventory push (Shopify/Amazon) | Sending inventory to Amazon and Shopify | In Progress | 8/13 EOD: 80% pushed
2024-08-13 | Meet typical throughput | Typically: 250-400 orders | In Progress | 8/13 EOD: At 90 shipments
2024-08-13 | Transfer order Process/Fulfillment |  | Closed | 8/13 EOD: One was 500 lines, so similar to like 500 orders
2024-08-13 | POS Transaction |  | Closed | 8/13 EOD: Flowing and pulling in every 30 minutes
2024-08-13 | Printing |  | Closed | 8/13 EOD: Resolved

## Reporting Requirements
Reports
CLIENT REQUESTED REPORTS | TYPE | STATUS | ADDITIONAL DETAILS
widget to see qty of multi orders, single picks, amazon | Widget | Open | would like to be able to see status/ qty of orders by type to be processed.
ability to see all open waves/work books for OTO's | Widget | Open | At a glance in one spot to see what waves/ work groups are open/ being processed

## Task Tracker
Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
CATEGORY | DESCRIPTION | TYPE | STATUS | OWNER | ASSIGNED OWNER | SEVERITY | UAT Critical? | Go Live Critical? | Due Date | DEP Comments | Client Comments
Design | Deposco Introduction Demo | Task | Closed | Deposco |  | Medium | TRUE | TRUE | 2024-06-21
Design | Onsite Design | Task | Closed | Deposco |  | High | TRUE | TRUE | 2024-06-21
Hardware / Physical | Printer Setup Instructions, provide all 34 print clients to F2R | Task | Closed | Deposco |  | Medium | TRUE | TRUE | 2024-06-19 | https://deposco.atlassian.net/browse/F2R001-2. provided on 6/19
Master Data | Facility Upload | Task | Closed | Deposco |  | High | TRUE | TRUE | 2024-06-19 | all 34 facilities uploaded
Integrations | Initial Config Shopify, NetSuite, Amazon | Task | Closed | Deposco | Sam | High | TRUE | TRUE | 2024-06-19 | Netsuite item loading complete, some duplicate UPCs to investigate. Beginning to pull in channelListings for Amazon SC and Shopify connections
Integrations | Celigo NetSuite - Shopify Connector email | Question | Closed | F2R | Matt | High | TRUE | TRUE | 2024-06-21 | Matt Sibley questions on Netsuit/Shopify connector, just need Matt to confirm nothing else is needed from Dep here |  |  |  |  | shipping costs | shipper account?
Design | Confirm all 34 Facilities in Deposco | Task | Closed | F2R | Tim/Sarah | Medium | TRUE | TRUE | 2024-06-27 | Please confirm all 34 facilities/stores in the Deposco Facility Application, addresss, phone etc | looks good. Added a couple missing phone # | shopify order | ups ground | destin | account # ? | account #?
Master Data | Install Print Client for all 34 facillities | Task | Closed | F2R | Tim | High | TRUE | TRUE | 2024-06-28 | All stores have been configured with Deposco Print client
Integrations | Ensure all items are setup in Netsuite, add sent to Deposco flags, ready for deposco | Task | Closed | F2R | Sarah | Critical | TRUE | FALSE | 2024-06-28 | Initial flags are there, but ask here is for F2R to update "sent to deposco" as NULL if an item is updated in Netsuite, so Deposco can repull and update the item Confirm all items are now in DEP. Total count is 145,049. Any items not in the system need to have the 'Sent to Dep' flag unchecked to be re-pulled. List of Duplicate UPCs is under 'DocStore Response' listing. Please review these 425 items (under DocStoreResponse - entity in Deposco). May just need to be marked 'inactive' in NS, or UPC's need to be revised. Flipping to 'Validation' - Have run the NS item pull twice but minimal change to the total item count in DEP system. Have expanded the search criteria to include 'Discount Items', 'Non-Inventory Items' and 'Subtotal'. Still seeing orders come in however with items that are not in the system and are in NS as 'Inventory Items'. | Working with NS to create, Sarah has a ticket for this, will handle manually for go live 7/19: Sarah added "sent to deposco" flag on the item. closing task
Reporting | Need sample packing list | Task | Closed | F2R |  | Low | TRUE | TRUE | 2024-07-05 | use label list, zebra label
Integrations | Need Carrier accounts for each store and each bill to account (1 for each carrier) | Task | Closed | F2R | Sarah | Critical | TRUE | TRUE | 2024-06-28 | need shipper and bill to accounts, need at least 1 for testing - validate all acounts added and no remaining carriers missing 7/16: Fedex and Stamps added, no UPS for go live. | emailed 7.5, good here, have fedex and stamps
Master Data | Need rank of stores for routing | Task | Closed | F2R |  | Medium | TRUE | TRUE | 2024-06-24 | provided, in google folder
Master Data | Gather printer names for all ZPL for all facilities | Task | Closed | F2R | Tim | High | TRUE | FALSE | 2024-07-12 | Initial printer setup, need remaining for all stores | Intial printer needs to be complete 6/28
Master Data | User import, data exchange | Task | Closed | F2R | Henry/David | Low | TRUE | TRUE | 2024-07-12 | template provided on email : Data Exchange Upload Templates - Location Import & User Import
Integrations | Refresh Netsuite Sandbox | Task | Closed | F2R |  | Low | TRUE | TRUE | 2024-07-05 | recomendation to update Netsuite for proper testing, confirm on 7/2 call | Will be using Sandbox 1
Integrations | Deposco Netsuite flags for F2R to setup | Task | Closed | F2R |  | Medium | TRUE | TRUE | 2024-07-05 | Dep to provide steps on Order Flags. Item Flags
Design | Master Design Document delivery | Task | Closed | Deposco |  | Critical | TRUE | TRUE | 2024-06-21
Design | Master Design Document Signature | Task | Closed | F2R |  | High | TRUE | TRUE | 2024-07-01
Master Data | Provide location upload template | Task | Closed | F2R | Henry | Medium | TRUE | TRUE | 2024-07-05 | created, just need to provide instructions in an email (Henry), should be about 4 locations or so per facility/store Provided week of 7/1. Instructions for loading locations across stores included in the email. Please submit any questions regarding this process.
Master Data | Complete location upload template | Task | Closed | F2R | David | High | TRUE | TRUE | 2024-07-10 | emaIL: Data Exchange Upload Templates - Location Import & User Import
Master Data | Data Validation - Item/Pack creation | Task | Closed | F2R | Sarah | Medium | TRUE | TRUE | 2024-07-10 | Ask here if for the F2R team to validate all item/pack fields in Deposco are correct and no additional fields/attributes are needed Can map Brand, may be a few days before this is reflected in DEP. Can have multiple UPCs on an item, but cannot share a UPC across multiple items. Brand and gender are mapping, working on style-color-size but not critical for go live. 7/16: multiple upcs are allowed on 1 item. sarah to upload the 2nd,3rd upcs via data exchange | Can we add Brand? Field ID: custitem_robinson_design_field How many UPC can be added to one item?
Integrations | F2R to setup test Sales Orders in Shopify/Shopify POS/Amazon SC | Task | Closed | F2R | Sarah | High | TRUE | TRUE | 2024-07-10 | Dep to use in testing, can we also create/copy in shop/amz? All different types of orders would be needed. DEP to run order pull from sales channel systems and attempt to grab the created orders. 7/10 update: We've pulled Amazon SC but need all test types of orders for Shopify and Shopify POS, this should 10-20 different types of orders. sarah.keniston@fit2run.com- confirming that the brand field id is: custitem_robinson_design_field - attempting to test pulling this across with the socket - Successfully pulling SO's from Amazon and Shopify - Some test orders containing items that are not currently in the system. Pivot request to set up sales orders with items that are on NS PO's so that received product can be allocated against with customer orders and routings. 7/16: ask for MORE Shopify POS orders, can the POS transactions be for items that are in Deposco | Shopify: 1004, 1017, 1015, 1016, chris sent amazon orders as well, should be good here
Integrations | F2R to setup test PO in Netsuite SB | Task | Closed | F2R | Sarah | Medium | TRUE | TRUE | 2024-07-10 | Dep to use in testing, can we also create/copy in Netsuite? | PO0020448 PO0020449
Configuration | Inbound (General Receiving) | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Inbound receiving configured, initial testing successful. Received inventory is automatically staged to 'Stock' location at users facility. Pending test of receiptConfirmation push to NS
Configuration | Inbound (Returns Receiving) | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Returns receiving configured, initial testing of orderType 'Return Order' needed.
Configuration | Inbound (Blind Receiving) | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Blind receiving configured, initial testing successful. Received unknown inventory is automatically staged to 'Damages' location at users facility.
Configuration | Item/Container Moves | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | MoveItem/MoveContainer processes configured, set up with 'Supervisor Move' logic to allow freedom to transfer stock from any and to any location in users facility
Configuration | Inventory Adjustments | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Initial setup complete, need list of Netsuite Adjustment codes to configure correct reason code list Reason codes added and adjustments ready for testing.
Configuration | Singles Picking | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Configured and tested successfully with sample orders. Need clarity on F2R preference for bin scan or no bin scan at wave selection. Likewise, need to test with true sample orders imported from integration
Configuration | Multis Picking | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Configured and tested successfully with sample orders. Need clarity on F2R preference for bin scan or no bin scan at wave selection. Likewise, need to test with true sample orders imported from integration
Configuration | OTO Picking | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Configured, intial testing pending. Basic sample orders loaded to the system to do this first validation. Will continue with true integration provided orders after.
Configuration | Singles Packing | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Configured and tested successfully with sample orders. Need clarity on F2R preference for system generated or F2R maintained picking bins. Likewise, need to test with true sample orders imported from integration and validate shipConfirmation messaging
Configuration | Multis Packing | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Configured and tested successfully with sample orders. Need clarity on F2R preference for system generated or F2R maintained picking bins. Likewise, need to test with true sample orders imported from integration and validate shipConfirmation messaging
Configuration | OTO Packing | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Should be pick and ship. Need to ensure shipments are created as expected. 7/11 Pick and ship config functioning as expected. Once all orderLines are picked, the shipment is automatically created in a 'Shipped' Status. LPN number autogenerated, will require additional testing of label printing upon pick complete, and integration of valid ship notices sent to NS.
Configuration | Warehouse Waving | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Waving configured, ad-hoc waving tested successfully. Scheduler based wave testing for WHSE Ecom and OTOs occuring this week.
Configuration | Store Waving | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Waving configured, ad-hoc waving tested successfully. Scheduler based wave testing for store Ecom and BOPIS occuring this week.
Configuration | Ecom Order Management Setup | Task | Closed | Deposco | Sam | Medium | TRUE | TRUE | 2024-07-12 | Pending, config occuring this week. Will begin testing once we are able to pull sample orders from integrations 7/12 Config completed. Seeing successful routing of orders based upon store rank and available inventory. Further testing required for order splitting and BOPIS/Ecomm fulfillment order types.
Configuration | Packing Slip Development | Task | Closed | Deposco | Henry | Medium | TRUE | TRUE | 2024-07-12 | Sample provided by F2R - recreation by DEP pending, need to test physical print
Configuration | Item Label Development | Task | Closed | Deposco | Henry | Medium | TRUE | TRUE | 2024-07-12 | Sample provided by F2R - recreation by DEP pending
Configuration | Content Label Development (OTOs) | Task | Closed | Deposco | Henry | Medium | TRUE | TRUE | 2024-07-25 | DEP has shown example CL to F2R, will revise for needs and configure -7/24 update requested by F2R team currently in progress
Configuration | Carrier Account Setup | Task | Closed | F2R | Sarah/Matt | Critical | TRUE | TRUE | 2024-07-12 | Flipping to F2R, DEP provided instructions for setting up carrier accounts in WMS on 7/9 (email F2R:DEP - Weekly Status) See USPS and Fedex Accounts added, missing UPS? Anything else to included? Need clarity on 'Standard' and 'Expedited' shipVias. | Matt working through it on 7/12 Matt completed 7.12
Configuration | Provide Remaining DE Upload Templates | Task | Closed | Deposco | Henry | Medium | TRUE | TRUE | 2024-07-12 | DE templates completed and tested with sample information - sent to F2R team.
Testing | Test provided DE Upload Templates | Task | Closed | F2R | Tim/Sarah | Medium | TRUE | FALSE | 2024-07-12 | F2R team to test out DE upload template, request a meeting or reach out via email if any questions
Question | File provided for F2R shipping accounts | Question | Closed | F2R | Sarah | Critical | TRUE | TRUE | 2024-07-12 | Need clarity on the shipping services tied to the accounts provided. Are these all UPS? DEP will provide a guide to F2R for setting up shipping accounts within the Deposco WMS. UPS. Fedex, Stamps in scope so need all for each store
Design | Create Packing Slip | Task | Closed | Deposco | Henry/Sam | Medium | TRUE | TRUE | 2024-07-18 | DEP to develop packing slip matching template provided by F2R - 7/23 Henry/Sam working on barcode field, packing slip is otherwise complete
Design | Create OTO Content Label | Task | Closed | Deposco | Henry | Medium | TRUE | TRUE | 2024-07-18 | DEP to develop OTO carton content label - 7/23 meeting set up to resolve one last issue
Design | Design | Task | Closed | F2R | Henry | Medium | TRUE | FALSE | 2024-07-18 | DEP to develop item labels matching templates provided by F2R
Testing | Load NS purchase orders for testing | Task | Closed | F2R | Sarah | Critical | TRUE | TRUE | 2024-07-12 | Request for F2R to create several sample PO's for DEP to pull across NS socket. Need at least one immediately so that we can identify the orderAcknowledgementFieldName value for integration responses. | PO0020449 PO0020448 Both sitting in NS
Reporting | [F2R] Item Label Dimensions | Task | Closed | F2R | Sarah | High | TRUE | TRUE | 2024-07-16 | Please confirm dimensions of requested labels (email: [F2R] Item Label Dimensions) | SK-Emailed 7.12
Integrations | Netsuite Sandbox Permissiosn | Task | Closed | F2R | Sarah | Critical | TRUE | TRUE | 2024-07-12 | Upgrade permissions in Sanbox, unable to view go live critical data | Done
Question | [F2R] Please remove users | Task | Closed | Deposco | Sam | Low | FALSE | FALSE |  | Request to delete users. You can only make users inactive
Testing | F2R Team to work through PO/Inbound test cases and provide to Deposco team | Request | Closed | F2R | Tim | High | TRUE | TRUE |  | DEP to provide Test Case Tracker, possible add a tab on this spreadsheet
Hardware / Physical | F2R To confirm all Hardware/Printers have Deposco App Downloaded and can login | Task | Closed | F2R | Don | Critical | TRUE | TRUE | 2024-07-12 | Kyle sent email : F2R - DEP Handheld Reccomendations and UA login instructions. Please confirm you can login via the Deposco APP
Testing | F2R to provide sample Transfer Orders and Deposco run initial validation test for Transfer Orders | Task | Closed | Deposco | Sam | High | TRUE | TRUE | 2024-07-19 |  | Sarah provided: TO0001456 = Ecom to Bradenton TO0001457 = St Pete to Bradenton TO0001458 = Bradenton to Ecom
Master Data | Shipping Service Relationship Key | Request | Closed | F2R | Hig | High | TRUE | TRUE | 2024-07-19 | Need key of shipping service definitions.
Integrations | Add NS field: "custbody_deposco_pulled" to PO, ITO, and OTO | Request | Closed | F2R | Sarah/Chris | High | TRUE | FALSE | 2024-07-19 | Need a custom field added to the 'custom' tab for PO's, ITO's, and OTO's in Netsuite. This is how DEP will acknowledge receipt of the order payload in our system. Similar field to 'custbodypo_exported_to_tw' that does currently exist' - we can use this for now, but believe having our own field will be better long term | PO= Field ID: custbody_exported_to_dep TO= Field ID: custbody_to_exported_to_dep
Master Data | F2R to Upload container/pick carts | Task | Closed | F2R | David | High | TRUE | TRUE | 2024-07-24 | Need F2R to upload these carts to pick into for all the stores/warehouse
Integrations | Investigate channelListings for Shopify POS | Task | Closed | Deposco | Sam | High | TRUE | TRUE | 2024-07-19 | Seeing shopify web channels created successfully, need POS so that item reference id's are mapping correctly to DEP item number values for successful POS retail activity pulls. 7/23: 214k NS item, but only 145k channel listings for Shopify Web/POS, can we confirm total # of items and if all NS items should be in Shopify Web and POS 7/24: items are good in all systems. confirmed from sarah that count of items in Shop will not equal netsuite
Hardware / Physical | Add carriage return function/setting to F2R handhelds | Task | Closed | F2R | Tim | Medium | TRUE | TRUE | 2024-07-25 | Zebra scanners in stores should have a setting to flip to enable automatic carriage retuns for quick product scanning, investigate how to add this functionality/setting to the honeywell scanners at the warehouse | honeywell id good, still working on datacom
Configuration | Resolve CoHeader processing error on tradingpartners | Task | Closed | Deposco | Sam | High | TRUE | TRUE | 2024-07-19 | CoHeader processing requiring a tradingPartner record to be automatic, allocates when re-processed without. Either set up a generic F2R trading partner to apply, or disable this on coprocessing
Configuration | Add NS reference number value to PO general receiving listbox for quick reference. Stamp to oh.otherReferenceNumber for scanning | Task | In Progress | Deposco | Sam | Medium | FALSE | FALSE | 2024-07-25 | Add additional data to the po listbox to show the NS reference number and the brand of the items on the PO. Also stamp the reference number to the oh.otherReferenceNumber for PO's so this can be scanned/entered by the user.
Admin | Finalize Test Case Tracker | Task | Closed | Deposco | Sam | Medium | FALSE | TRUE | 2024-07-23
Master Data | Item Fields to map from Netsuite | Task | Closed | Deposco | Sam | Medium | FALSE | TRUE |  | Item Fields to map: Color = Field ID: custitem_robinson_custom_color Size = Field ID: custitem_psgss_product_size If you want to be super dreamy and width too..Field ID: custitemrobinson_custom_field | Color = Field ID: custitem_robinson_custom_color Size = Field ID: custitem_psgss_product_size If you want to be super dreamy and width too..Field ID: custitemrobinson_custom_field
Master Data | PO "Deposco Pulled" flag | Task | Closed | F2R | Sarah | High | FALSE | FALSE | 2024-07-25 | Need this flag so we dont pull the same PO into Deposco | sarah.keniston@fit2run.com can you add this PO flag as well "custbody_deposco_pulled" added custbody_exported_to_dep on 7/19
Integrations | Populate ShipVia field on all sales orders in Shopfy. | Task | Closed | F2R | Christopher | High | TRUE | TRUE |  | Need F2R team to populate this field so that orders can be packed and shipped in Deposco. | Chris has provided this opn 7/19
Integrations | Fedex Address Validation | Task | Open | Deposco | Kyle | Medium | TRUE | FALSE |  | DEP to setup Address Validation for Fedex Orders
Admin | On-Site UAT Schedule | Task | Closed | Deposco | Henry | High | TRUE | FALSE | 2024-07-25 | Dep to provide UAT schedule by 7/25, times and locations
Testing | F2R Team to work through OB/POS test cases and provide to Deposco team | Task | Closed | F2R | Tim | High | TRUE | TRUE | 2024-07-26 | F2R team to work through "Unit Test Case" tab and provide results
Configuration | DEP to configure OTO process via Netsuite | Task | Validation | Deposco | Sam/Kyle | Critical | TRUE | TRUE | 2024-07-26 | DEP to setup OTO process with NS, SO and PO process 8/9: Initial happy path OTO/ITO has been picked and received
Master Data | Stock Unit Upload | Task | Closed | F2R | Sarah | Critical | TRUE | TRUE | 2024-07-26 | F2R to upload Stock units in Deposco, as this will be how inventory is created for go live | F2R did the initial upload, will need to do again in prod env
Testing | Shopify & Amazon Inventory Sync | Task | Closed | Deposco | Kyle | Critical | TRUE | TRUE | 2024-07-25 | 7/25: Inv sync sent to Shopify, Chris to validate
Configuration | Set up PR Shopify Sockets | Task | Hold | Deposco | Henry | Medium | TRUE | FALSE | 2024-07-29 | 7/24 - Link provided by Tim, will not be available until 7/27
Admin | Create ticket for Prod environment creation | Task | Closed | Deposco | Sam | High | FALSE | TRUE |  | https://deposco.atlassian.net/browse/F2R001-4
Configuration | Prod Item Pull | Task | Closed | F2R | Sarah | Critical | FALSE | TRUE |  | Deposco request for a saved search created to pull items into production
Master Data | Create Resources for every printer |  | Closed |  |  |  | FALSE | FALSE |  | DE Upload?
Master Data | Create Associate Users |  | Closed |  |  |  | FALSE | FALSE |  | DE Upload for Associate Users
Reporting | Confirm Item Labels in ua and changes moved to prod | Task | In Progress | F2R | Tim | Critical | TRUE | FALSE | 2024-08-09 | Item Orientation/printing is not aligned, field values to be added from DE
Admin | Store SOP Inbound | Task | Closed | F2R | David |  | FALSE | FALSE
Admin | Store SOP Outbound | Task | Closed | F2R | David |  | FALSE | FALSE
Inventory Management | Netsuite Inventory Adj | Task | Closed | Deposco | Henry | Critical | FALSE | TRUE |  | Regression testing, provide steps to F2R and/or demo video
Reporting | POS Decrement Report (Retail activity) | Task | Closed | Deposco | Sam | Medium | FALSE | FALSE |  | need to show where POS decrements exist in DEP
Configuration | Handheld Button Clean Up | Task | Closed | Deposco | Sam |  | FALSE | FALSE
Integrations | Netsuite Permissions | Task | Closed | Deposco | Kyle | Critical | FALSE | TRUE |  | Added on 8/9, matched Sandbox
Master Data | Carton Type Upload | Task | Closed |  | Henry |  | FALSE | FALSE
Testing | USPS Sales Order testing (PR) | Task | Closed |  | Henry |  | FALSE | FALSE
Configuration | Inv Measures for Amazon SC | Task | Closed | Deposco | Sam | Critical | FALSE | FALSE |  | need to have a query to send the active facilities, ie ecomm,main street
Testing | Partial PO(pull in and receive) | Task | In Progress | Deposco | Kyle | Critical | FALSE | TRUE |  | 8/9:Kyle added in prod
Testing | Test Integration Provided SO with USPS | Task | Closed | F2R | Henry | High | TRUE | TRUE |  | Need a valid USPS order from one of the sales channels to confirm correct order routing and successful shipping
Testing | Amazon SC channel Listing confirmation | Task | Closed | F2R | Sarah | High | TRUE | TRUE | 2024-08-09 | Sarah to confirm channelListings that are not linked (Deposco doesnt have the item, but Amazon does) example items "1000331D081.060 and 1011B79440316D" " | 8/8: Sarah still working through 8/9: 12k listings linked in Deposco, should be accurate. Chris to confirm
Testing | TO Item Fulfillment request question | Question | Closed | F2R | Tim | Critical | TRUE | TRUE | 2024-08-08 | shipNotices failing when sending to NS, 8/8: update even when trying to fulfill in NS, an error of "An unexpected SuiteScript error has occurred" happens, NS consultant to review 8/9: NS consultant found script error, turned it off and now working as intended
Testing | add color and size to items via Data Exchange | Task | Open | F2R | David | High | TRUE | FALSE | 2024-08-08 | David to upload new fields via DE and test in UA, then the fields would need to be uploaded in Prod by F2R once confimed | 8/8:David to reach out to Sarah 8/9: David still working through
Admin | DC SOP's | Task | Closed | F2R | David | High | TRUE | FALSE | 2024-08-09 | Receiving should be the same, OB some changes, OTO, move item differences | 8/8:Don to review
Admin | Confirm Start Time and Initial Task (Go Live Bridge) | Task | Closed | F2R | Tim/Chris | High | TRUE | TRUE | 2024-08-09 | Asking what is the go live date/time of the website and what is needed from Deposco | 8/8: Tim to confirm with Dep team, 8/9: Plan is to pull first smoke test order at 8am
| When can PO scheduler be turned on? | [5 empty] | FALSE | FALSE
| TO scheduler needs to be turned on after netuite has been cleared of all old items | [5 empty] | FALSE | FALSE
| Where is the best place for us to see at a glance (widget maybe) who is working on what specific waves or workgroups | [5 empty] | FALSE | FALSE
| Would like to discuss best methods for us to trouble shoot and clear aging orders, TO's etc. | [5 empty] | FALSE | FALSE
| Is the only way to clear a "location on hold" by doing a cycle count? | [5 empty] | FALSE | FALSE
| Would like to have quick high level view of available work by building | [5 empty] | FALSE | FALSE
| I do not see the new "build & release wave transfers" option when trying to manually release a TO | [5 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE
[7 empty] | FALSE | FALSE

## ShipViaMatrix
Order | Ship Via | Deposco Ship VIa | Carrier | Account Number | residential
Amazon SC | Standard | FedEx Ground | FEDEX | 543173347
Amazon SC | Standard Expedited | FedEx Standard Overnight | FEDEX | 543173347
Shopify | Fedex Ground |  | FEDEX | 543173347
Shopify | FedEx 2Day |  | FEDEX | 543173347
Shopify | FedEx Home Delivery |  | FEDEX | 543173347
Shopify | FedEx Standard Overnight |  | FEDEX | 543173347
Shopify | StorePickup |  | SOS | N/A
Shopify | USPS - Priority Mail Express |  | STAMPS
Shopify | USPS Priority Mail |  | STAMPS
Shopify | Standard | FedEx Home Delivery

## On-site Design AI
| On-site Design Action Items |  |  | 1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High (Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
ITEM # | DESCRIPTION | CREATE DATE | DUE DATE | OWNER | PRIORITY | STATUS | TEAM | OWNER | CREATED | ETA | NOTES

## Design Parking Lot
Design Parking Lot
ITEM # | DETAILS | PRIORITY | ADDITIONAL DETAILS
Phase 1 - Treat as new facility for phase 1, more best practices for phase 2
Picking multiple zones | Don has a request to split picking into 2 different zones
Separate AmazonFBA TO's | Set up separate AmazonFBA PickWaveBuildProfile to wave these TO's independently. Use individual process button on handheld
| Store Picking, sort pickTasks by gender then brand, color |  | Davids request

## Demo Schedule + Recordings
Recordings
DATE | TOPIC | LINK | PASSWORD
2024-06-11 | F2R:DEP - Introduction Demo | Link | a1ZP9.BG
2024-07-16 | Inbound/Inventory Demo | Link | U?d87?lJ
2024-07-23 | Outbound/POS Demo | Link | %ich5X4#

## Pre-Cutover Activities
PRE-CUTOVER ACTIVITIES
CLIENT PRE-CUTOVER STEPS
Purpose: Organize all tasks that are to be executed in preparation for deployment.
ITEM # | TEAM OWNER | ASSIGNED RESOURCE | % COMPLETE | TASK DESCRIPTION | INITIAL ETA | TARGET DATE | COMPLETION DATE | REQUIRED COMPLETION DATE | DEPENDENCIES | COMMENTS
CLIENT
1 | Client |  | 100% | Upload/Create all Locations to Deposco
2 | Client |  | 100% | Scanners at each workstation
3 | Client |  | 0% | Validate Pack Station laptops/computers
4 | Client |  | N/A | Validate Scales (needed for weight of item to be sent to carrier)
5 | Client |  | 0% | Set up pack stations
6 | Client |  | 0% | Set up printers (Print Client is setup, printers are on same device)
7 | Client |  | 0% | Set up wifi
8 | Client |  | 0% | Configure packstations as a resource and assign printers
9 | Client |  | 0% | Shipping Label - print out and validate
10 | Client |  | 0% | Packing Slip - print out and validate
11 | Client |  | 0% | End User Configuration (permissions for end user, outbound, inbound, inventory groups)
12 | Client |  | 0% | Continued Super User Training
13 | Client |  | 0% | User Training (Happy Path and Exception Scenarios)
14 | Client |  | 0% | Validate/Test integration schedulers for Deposco are working
15 | Client |  | 0% | Review Scheduler Frequencies (how oftern orders are being pulled, etc) | 2024-08-05 |  |  |  |  | David requested every 15 minutes
16 | Client |  | 0% | Review Waving Logic
17 | Client |  | 0% | Build SOP document for entire solution. Leave a relevant copy at each given area (packing sections for pack stations)
18 | Client |  | 0% | Validate all Locations in proper zones
19 | Client |  | 0% | Test with all set-up Printers
20 | Client |  | 0% | Repull product data into production
DEPOSCO
1 | DEP |  | 0% | Build system monitoring queries
2 | DEP |  | 0% | Wipe out test orders
3 | DEP |  | 0% | Review each packstation is configured as a resource
4 | DEP |  | 0% | Validate all master data has been configured
5 | DEP |  | 0% | Review Waving Logic
6 | DEP |  | 0% | Purge Transactional Data
7 | DEP |  | 0% | Validate all schedulers are enabled for production environment
8 | DEP |  | 0% | Validate all Integration changes needed are in production environment
9 | DevOps |  | 0% | Build Production environment
10 | DevOps |  | 0% | Add socket credientals to Production environment
11 | DEP |  | 0% | Wipe product data

## On-site UAT Issue Log (hidden)
On-site UAT Issue Log
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
DATE REPORTED | ISSUE DESCRIPTION | TYPE | STATUS | TEAM | OWNER | SEVERITY | PRIORITY | GO LIVE CRITICAL? | DUE DATE | DEP COMMENTS | CLIENT COMMENTS
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Go Live Issue Log (hidden)
Go - Live Issue Log
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
DATE REPORTED | ISSUE DESCRIPTION | TYPE | STATUS | TEAM | OWNER | SEVERITY | PRIORITY | EXPECTED DELIVERY DATE | DEP COMMENTS | CLIENT COMMENTS

## Cutover Activities
CUTOVER ACTIVITIES
CLIENT CUTOVER TASKS
CUTOVER DAY
ITEM # | TASK OWNER | ASSIGNED RESOURCE | STATUS | TASK DESCRIPTION | PLANNED COMPLETION DATE | TIME | ACTUAL FINISH DATE | DEPENDENCIES | COMMENTS
1 | F2R | David | Complete | Upload Containers into Deposco Prod | 2024-08-09
2 | F2R | David/Don | Complete | Ensure all users are in Prod/can log in, and Handhelds are provided | 2024-08-09 |  |  |  | Don asked to confirm handhelds, david to finish 8/8
3 | F2R | Tim | Complete | Validate each pack station is setup to coresponding printers | 2024-08-09
4 | F2R/DEP | Matt/Sam | Complete | Register Fedex and USPS Account in Production | 2024-08-02
5 | F2R | David | Complete | Upload Warehouse Locations into Deposco | 2024-08-05
6 | F2R | David | Complete | Upload inventory into Deposco via Data Exchange | 2024-08-09 | 22:00 | Sunday 8/11. |  | The inventory upload should match what is reflecting in NS. David and team to sync internally on how they want to push inventory to Deposco
7 | F2R | Sarah | In-Progress | Sarah to let us know once Items are ready to be pulled from Shopify | 2024-08-09 | 9:00 | Initiated Monday 8/12 | On Celigo push of items | Shopify DC items uploaded, Store items pending. CL Pull initiated from DEP
8 | DEP | Sam | In-Progress | Deposco to confirm all Channel Listings/Items from Shopify are in Deposco | 2024-08-09 | TBD | BLOCKED
9 | DEP | Sam | In-Progress | Deposco to PUSH inventory to Shopify | 2024-08-09 | TBD | BLOCKED | Initial INV upload and CL's | Manually uploaded for DC, Store pending. Syncs will initiate at EOD
10 | F2R | Chris | In-Progress | F2R to Stop Amazon SC Orders and these orders pushing to NS | 2024-08-11 | 16:00 | Cutoff occuring Monday 8/12 after CSR fed orders sent to snap.
11 | F2R | Don/David | In-Progress | F2R to Ship all Pulled Orders Clean in Current System | 2024-08-11 | 18:00 | Cutoff occuring Monday 8/12 after CSR fed orders sent to snap. |  | Some orders dropped Monday 8/12 due to CSR activities. These are being picked clean
12 | F2R | David | HOLD | F2R to Upload Inventory in Deposco again, (must REPLACE current inv) | 2024-08-11 | 20:00 | Will complete once CSR orders and FBA transfer completed 8/12 | Everything is shipped and received clean in current system, ideally by Friday 8/9
13 | DEP | Sam | In-Progress | Push Inventory to Amazon SC for the first time | 2024-08-12 | 8:00 | Unchecking the 'SyncInventory' CL flag for items that do not have stock in the system then pushing 8/12 | Dependent upon inventory loaded to Deposco and the celigo connection | Pull amazon CL's 8/6. Pull Shopify CL's once celigo piece confimed. Push invSync's once inv loaded to Deposco. InvSync queued from DEP 8/12
14 | DEP | Sam | HOLD | Push Inventory to Shopify SC since latest Sunday Update | 2024-08-12 | 8:00 |  |  | could possibly do Sunday night Hold, inv reconciliation ongoing. Waiting for Store items to load to shopify then will trigger the sync
15 | DEP | DEP | Open | Pull POS smoke test into Deposco from Shopify/Amazon SC | 2024-08-12 | 9:00 |  | Items are good in Shop/Amazon | Load single-line, single-unit POS order to Shopify for Sarasota Main, pull across in DEP as smoke test
16 | DEP | DEP | Open | Pull open Sales Orders smoke test Deposco from Shopify/Amazon SC | 2024-08-12 | 9:00 |  | Items are good in Shop/Amazon | Load single-line, single-unit Ecom order to Shopify for DC F2R01, pull across to DEP as smoke test
17 | DEP | DEP | Open | Pull open Sales Orders into Deposco from Shopify/Amazon SC | 2024-08-12 | 11:00 |  |  | Go-live with Sales Order
18 | DEP | DEP | Open | Do and end to end smoke test with a PO (Netsuite) | 2024-08-12 | 13:00 |  |  | Sarah to set up a single item, single line PO for F2R01 to smoke test connection
19 | DEP | DEP | Open | Pull New Purchase Orders from Netsuite into Deposco | 2024-08-12 | 14:00 |  |  | Cutoff DC and Sarasota Main PO's August 8th, pull into DEP prod August 12
20 | DEP | DEP | Open | Do and end to end smoke tests with some POs and SOs | 2024-08-12 | 14:00 |  |  | This will consist on doing the actual receiving for a PO and then picking/packing for an SO
21 | DEP | DEP | Open | Enable Sockets and Schedulers for Netsuite | 2024-08-13 | 8:00
22 | DEP | DEP | Open | Enable Sockets and Schedulers for Shopify/Amazon | 2024-08-13 | 8:00
23
17
18

## Facility Cutover Activities
NEW FACILITY CUTOVER ACTIVITIES
CLIENT CUTOVER TASKS
CUTOVER DAY
ITEM # | TASK OWNER | ASSIGNED RESOURCE | STATUS | TASK DESCRIPTION | PLANNED COMPLETION DATE | TIME | ACTUAL FINISH DATE | Deposco Confirmed | COMMENTS
1 | F2R | Don | Complete | Create new facility in Deposco Production under "facility" | 2025-04-18 |  | 2025-04-18 | Complete | Start receiving on weds 4/23, first order in on 4/25
2 | F2R | Don | Complete | Create F2R176--Shipping, F2R176--Returns, F2176--Receiving and tie new zones to them, match F2R. Don to confirm these locations are added to facility settings | 2025-04-18 |  |  | Complete | make sure they match exactly as 01, and facility settings are configured Confirm on 4/21
3 | F2R | Don | Complete | Create New Containers in the New facility | 2025-04-18 |  |  | Open | DE upload for this
4 | F2R | Don/Henry | Complete | Create Locations and Zones(use existing zones besides 111 rec) for new facility (meeting scheduled morning on 4/17) | 2025-04-18 |  |  | Complete | Do in UA first to confirm DE upload, then repeat in production. Meeting held with Don on 4.17
5 | F2R | Tim | Complete | Confirm Wifi in new facility, login to handhelds in prod and connect and do a printer validation for all whse printers | 2025-04-18 |  |  | Complete | same server/network, so just need to confirm connection, all completed besides printer move 4/21: looking to test/move on Weds 4/25: need to add WHPACK01
6 | F2R | Don | Complete | Label report for the new warehouse: New labels needed for new warehouse (8.5 x11, 30 labels) Don to create a ticket for this report(192060) | 2024-04-19 |  |  | Complete | I have created a report for these barcodes titled: "F2R - Location Barcodes", please confirm if there are any more formatting changes required
7 | F2R | Don | Complete | Physically Label the new warehouse |  |  | 2025-04-23 | Complete | Use the report from above
8 | F2R | Tim | Complete | Tim to setup the new Printer needed for new warehouse labels | 2025-04-18 |  | 2025-04-18 | Complete | Don is good here, need to confirm that it scans correctly
9 | F2R | Sarah | Complete | Create Facility in Netsuite Production, mirror 144 and 29 and provide the NEW ids to Deposco | 2025-04-18 |  | 2025-04-17 | Complete | (176) Fit2Run Warehouse 313 313 Manatee Ave W Bradenton FL 34205 sarah.keniston@fit2run.com will there be a new damage/defects location? we are sending 144 now @Kyle- continue to use 144 (it is Defs for all FL stores) Noted and thank you!(Kyle)
10 | DEP | Sam | Complete | Create NEW ChannelLookup Values for the new facility in Deposco Prod using Zones that Don Created | 2025-04-23 |  |  | Complete | Will need new ID's from #4 above from Sarah - This is now complete and all records added (SAM)
11 | DEP | Sam | Complete | Stop Sending inventory for old facility on 4/22 at 1pm (need to ensure the F2R01 inventory is not in the overall ATP)Pending FIRE MARSHALL Signoff | 2025-04-23 | 13:00 |  | Complete | Need to ensure inventory levels are reduced due to the F2R01 warehouse being closed. Send to Shopify and AMazon needs to be re-ran and new numbers (minues whse inventory) sent. verfified a couple of items, that show inventory for ONLY the stores (110391404115D) for shopify, and 172100BKW11B is good for Amazon. Facility flagged as inactive on 4/23 ar 2pm ET
12 | DEP | Sam | Complete | DEP to turn off F2R01 in Order Routing(all new orders will now go to STORES) | 2025-04-23 | 13:00 |  | Complete
13 | F2R | Don | In-Progress | Receive inventory into new facility(starting on 4.23)- will use Physical Count process in new facility to count this inventory in. Stop filling shelves, and then Start count 2 hrs before EOD and scan/count everything in, then stop count and approve. | 2025-04-25 |  |  | Open | plan is to load inventory into large gaylords physcially and then cycle count the inventory into the new facility. Then F2R will cycle count out inventory from F2r01
14 | DEP | Sam | Complete | Change ChannelXref primaryKey to NEW facility in Dep Prod (98594881845), need to ensure SHopify and Amazon is looking at New facility. also needs to add new warehouse into the routing profile | 2025-04-24 |  |  | Open
15 | DEP | Sam | Complete | Turn on inventory sync for NEW facility on 4/24 at 4pm, ensure routing for F2R176 is good and at the top of the routing profile | 2025-04-25 | 13:00 |  | Complete | ensure the new warehouse inventory is being captured in the new unv sync to shopify and amazon , should just need to set F2R176 to active
16 | F2R | Don | Complete | Inital Smoke Test of a Sales Order for the new Facility | 2025-04-25 |  |  | Complete | would like to confirm the new flow works end to end after the order is shipped 4/25: Don to receive in a couple of skus, Kyle to send inventory and turn on 176, Sarah to create an order, kyle to setup 176 in routing profile, order comes in, routes to 176, turn 176 back to inactive, Don would ship the order
17 | F2R | Don | Open | Initial Smoke Test of a Purchase Order for the new Facility | 2025-04-28 |  |  | Open | woudl like to ensure the PO is received and sent successfully to Netsuite
|  | Kyle | Open | BULKSHOEPLT1 (don is requesting a MOVE PALLET process to simply just move the inventory), need to setup and prod test | 2025-04-28
18 | F2R | Don | Open | Initial Smoke Test of a Transfer Order (End to End) from the new Facility, into a store | 2025-04-28 |  |  | Open | would like to confirm the OTO is picked and received successfully
19 | F2R | Tim/Sarah | Complete | Tim and Sarah to confirm that sending + and - adjustments to Netsuite is OK, this will happen due to the cycle count method happening for the move. Any finanical impacts to consider here in Netsuite. | 2025-04-19 |  | 2025-04-18 | Complete | Confirmed via Sarah on 4.18 call
20 | F2R | Don | Complete | Users moving to the new facility (need to ensure they are assigned to the facility and to the new zones). this can be bulk edited under user | 2025-04-19 |  |  | Complete
21 | DEP | Kyle | Complete | DEP to provide a DE upload for user- zone (copy old zones and re-upload for new facility) | 2025-04-21 |  |  | Complete
22 | F2R | Don | Complete | F2R- Events and FBA facility- wil remain the same - no physical inventory to be moved, will adjust all out | -- |  |  | Complete | Just a callout
23 | F2R | Sarah | Complete | All PO's, OTO's,SO's, RTV's etc from Netsuite need to have 176 as the ID (new netsuite ID on them) not F2R01 | -- |  | 2025-04-18 | Validation | Just a callout
24 | F2R | Sarah | Validation | To receive in old PO's you must change the facility on them in NS and DEP to the new one (311) | -- |  |  | Validation | Just a callout
25 | F2R | Sam | Open | Reporting updates | 2025-04-23 |  |  | Open | Need to review queries in widgets that have F2R01 in them
26 | F2R | DON | Open | F2R Team to update views to look at F2R176 | 2025-04-23 |  |  | Open
27 | F2R | Tim | Open | Change Facility on every Printer Resource for F2R01 to be F2R311 | 2025-04-22 |  |  | Open | needs to be completed once printers are physicallty moved to new warehouse

## GoNo-Go Decision
Go/No-Go Decision
FACTORS | DETAILS | WEIGHT | CRITICAL? | OWNER | % COMPLETE | SCORE | ANALYSIS | DUE DATE | COMMENT | CLIENT TEAM TESTED | DEP TEAM TESTED
| Deposco Setup | 80 |  |  |  | 72.5
Deposco Setup | Printer Details | 10 |  | Client | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | Client | 100% | 10 | Are all printers staions/resources set up with the appropriate printers? |  |  | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | Client | 100% | 10 | Are all printer assignments set up on the appropriate printers (shipping label, packing slip, customs docs, item label, LPN label)? |  |  | FALSE | FALSE
Deposco Setup | RF Scanners/Handheld Devices | 10 |  | Client | 100% | 10 | Are all handheld units configured? Are all of the handhelds working correctly? |  |  | FALSE | FALSE
Deposco Setup | Label Printers | 10 |  | Client | 100% | 10 | Are all printers setup? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 | Y | Client | 70% | 7 | Are the report documents configured to print on the proper printers? Are some reports configured with device overrides (e.g. processing area printers). |  |  | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | Deposco | 60% | 6 | Have all High and Critical issues from the issues list been resolved? |  | 8/1: Transfer orders still a risk | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release - Order - Item - Incremental Inv Sync - POI for PO's - Cycle Counts | 10 |  | Deposco | 95% | 9.5 | Backups, day, month end jobs. All jobs have been scheduled. Order Pull, Item Pull, Inventory Sync, Cycle Counts, Replenishments, Waving |  | 7/31: Need to add waving schedulers | FALSE | FALSE
| Warehouse/Store Prep | 40 |  |  |  | 40
Warehouse Prep | Location Labels | 10 |  | Client | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 10 |  | Client | 100% | 10 | Procure Carts for moving of inventory |  |  | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 10 |  | Client | 100% | 10 | Item inventory barcoded and labeled to scan |  |  | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 |  | Client | 100% | 10 | Is the connectivity strong and cover all necessary scan areas? |  |  | FALSE | FALSE
| Standard Operating Procedure Documentation | 80 |  |  |  | 76.5
Standard Operating Procedures | Receiving | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Putaway | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 10 | Y | Client | 80% | 8 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Picking | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Picking | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Packing | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Packing | 10 |  | Client | 100% | 10 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
Standard Operating Procedures | Customer Order Creation/Updates/Waving | 10 | Y | Client | 85% | 8.5 | SOP's been written? Online Help, plus Client-specific. Start with Client template. |  |  | FALSE | FALSE
| Training & Testing | 50 |  |  |  | 32
Training & Testing | Business Scenarios Definition | 10 |  | Client | 100% | 10 | Define all Business scenario including exception processes Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Process Training and Testing - Receiving - Putaway - Cycle Counting - Parcel Picking - Parcel Packing - Transfer Orders - Shipping | 10 | Y | Client | 70% | 7 | Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | User Acceptance Testing | 10 | Y | Client | 70% | 7 | Execute all defined business scenarios within Deposco |  |  | FALSE | FALSE
Training & Testing | Supervisor/Administrator | 10 | Y | Client | 80% | 8 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | End-user | 10 | Y | Client | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
| Configurations/Master Data | 70 |  |  |  | 68
Configurations | Inventory Validation | 10 |  | Client | 90% | 9 | Putaway Audits |  |  | FALSE | FALSE
Configurations | Items | 10 |  | Client | 100% | 10 | Are all items setup? Are all of the units of measure defined for each item? |  |  | FALSE | FALSE
Configurations | Zones | 10 |  | Client | 100% | 10 | Have all of the Zone and Zone Location records been set up? Has the pick flow been tested? |  |  | FALSE | FALSE
Configurations | Locations | 10 |  | Client | 100% | 10 | Are the location types, zones, and location masters configured accurately. |  |  | FALSE | FALSE
Configurations | Menu Structures | 10 |  | Client | 90% | 9 | Have the appropriate menu levels been created for the different departments? |  |  | FALSE | FALSE
Configurations | Packs (UOMs) | 10 |  | Client | 100% | 10 | Have all valid pack types been entered into the system? |  |  | FALSE | FALSE
Configurations | Containers | 10 |  | Client | 100% | 10 | Pallets, bins, carts |  |  | FALSE | FALSE
| Cutover and Conversion Plans | 10 |  |  |  | 9
Cutover and Conversion Plans | Cutover plan developed | 10 |  | Deposco | 90% | 9 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  |  | FALSE | FALSE
| Interfaces - Imports/Exports with Deposco | 40 |  |  |  | 40
Interfaces - Imports to Deposco | Items from Client to Deposco | 10 |  | Client | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Customer Orders from Client to Deposco | 10 |  | Client | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Locations/Zones from Client to Deposco | 10 |  | Client | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Items/Packs from Client to Deposco | 10 |  | Client | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Integrations | 40 |  |  |  | 35
Integrations with Deposco | Shopify Socket - Item/Channel Listing - Customer Order - Inventory Sync | 10 |  | Client | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Field Mappings | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Data Exchange templates - UPCs - Pack Clientnsions/Weights - Locations/Zones - Item Image and ABC Classification - PO Upload | 10 |  | Deposco | 100% | 10 |  |  |  | FALSE | FALSE
Integrations with Deposco | Carrier Client Socket Setup and Validated - UPS (Online Tools) - FedEx - USPS | 10 | Y | Client | 50% | 5 |  |  |  | FALSE | FALSE
| Interfaces - Exports From Deposco | 10 |  |  |  | 10
Interfaces - Exports From Deposco | Shipment Notice from Deposco to Shopify/Seller Central | 10 |  | Deposco | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Reports and Labeling | 40 |  |  |  | 37
Reports and Labeling | Shipping Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Location Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Item Label | 10 | Y | Deposco | 70% | 7 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | LPN Label | 10 |  | Deposco | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
| Contingency Plans | 10 |  |  |  | 9
Contingency Plans | Contingency Plans | 10 |  | Deposco Client | 90% | 9 | Is there a backwards migration strategy planned in case of emergency rollback? |  |  | FALSE | FALSE
| Total Weighted Score: | 429
| Total Possible Score: | 470
| Total Percentage: | 91.28%
| Go Live Recommendation: | Yes | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## DEP Cutover Activities
CUTOVER ACTIVITIES
CLIENT CUTOVER TASKS
CUTOVER DAY
ITEM # | TASK OWNER | ASSIGNED RESOURCE | STATUS | TASK DESCRIPTION | PLANNED COMPLETION DATE | ACTUAL FINISH DATE | DEPENDENCIES | COMMENTS
1 | DEP | Kyle | Closed | Shopify Socket | 2024-08-05 |  |  | Need to enable and run, waiting on F2r confirmation on item pull
2 | DEP | Sam | Closed | Shopify POS Socket | 2024-08-05
3 | DEP | Kyle | Closed | Inventory Measures (f2r26 and f2r01) | 2024-08-05 |  |  | confirm locations ids
4 | DEP | DEP | Closed | Packing slip | 2024-08-05
5 | DEP | Henry | Closed | Item label Permissions/PALS | 2024-08-05
6 | DEP | Sam | Open | Transfer Order End to End Process | 2024-08-05
7 | DEP | Sam | Closed | Update Return Process in Prod | 2024-08-06 |  |  | Also create CSR specific user group for HH
8 | DEP | Sam | Closed | Confirm Store Rank in Prod | 2024-08-06
9 | DEP | Sam | Closed | Turn off adhoc container setting | 2024-08-06
10 | DEP | Sam | Closed | Add warehouse receiving process | 2024-08-06
11 | DEP | Sam | Closed | Confirm picking process in prod match ua | 2024-08-06
12 | DEP | Henry | Closed | Move NEW content label to prod
13 | DEP | Kyle/Sam | Closed | Confirm Ship VIa /automations |  |  |  | Went ahead and took care of this config Kyle - Sam
14 | DEP | Henry | Closed | Move phone Number automations to Prod
15 | DEP | Sam | Closed | Amazon SC Socket | 2024-08-05 |  |  | Socket added. Will validate connection with a test item-channel pull
16 | DEP | Sam | Closed | Email team/Matt request for setting up prod shipping accounts | 2024-08-02 |  |  | Matt Sibley to re-register - working through USPS validation in UA then will move to prod
17 | DEP | Sam | Closed | Add facility cross-references to sockets (POS/WEB/NS) | 2024-08-05
18 | DEP | Henry | Closed | Migrate created widgets to PROD, migrate report buiilders | 2024-08-05
19 | DEP | Henry | Closed | Update location zones - still missing | 2024-08-05
20 | DEP | Henry | Closed | Create BnR Waving schedulers for each Store/Facility | 2024-08-06

## Project Teams & Links
Project Team Members
TEAM | NAME | ROLE | EMAIL
F2R | Parks Robinson | President | parks.robinson@fit2run.com
F2R | Sarah Keniston | Merchandising support manager/netsuite Admin | sarah.keniston@fit2run.com
F2R | Don Keller | Director of Warehousing | don.keller@fit2run.com
F2R | Tim Macking | CIO | tim.macking@fit2run.com
F2R | Matt | Controller | matts@fit2run.com
F2R
F2R | David Bildstein | VP Ops (warehouse and stores) | david.bildstein@fit2run.com
F2R | Christopher Palumbo | Omni Manager | christopher.palumbo@fit2run.com
DEP | Deposco Team | Full Team | F2R@Deposco.com
DEP | Gerry Daniel | Executive Sponsor
DEP | Kyle Beauchamp | Team Lead | kbeauchamp@deposco.com
DEP | Jackie Morsberger | Project Manager | jackie.morsberger@deposco.com
DEP | Sam Nichols | Design Lead | sam.nichols@deposco.com
F2R Store Go Live Checklist |  | Link

## Unit Test Cases
Test Number | Scenario | Assignee | Don Test | Sarah Test | David Test | Tim Test | Status | Test Data | Suggested Due Date | Date Complete | F2R Comments | Deposco Comments | In SOP Document?
| Inbound | [7 empty] | 2024-07-23
EXAMPLE | Receive full PO into 1 LPN | F2R Team |  |  |  |  | Pass | PO123 | 2024-07-23 | 2024-07-19 | Passed, showing as closed in Netsuite
| Receive full PO | F2R Team |  |  | Pass |  |  | PO0004357, 4395, 0251 | 2024-07-23 | 2024-07-20 |  | receive in DEP and should show pending billing in NS
| Over receive PO, send over receipt, this should fail as we are not allowing | F2R Team |  | Pass | Pass | Pass |  | PO0004357, 4395, 0251 | 2024-07-23 | 2024-07-20
| Receive partial PO and leave open - receive more product later | F2R Team | Pass | Pass | Pass | Pass |  | PO0004357, 4395, 0251, 0313 | 2024-07-23 | 2024-07-20
| Receive Customer Return - Returns Receiving Button | F2R Team | Pass | Pass | Pass | Pass |  | so234 | 2024-07-23 | 2024-07-25 | returned amazon order 234 as damaged and passed.
| PO partial receive and manual update in dep to Received, also need to archive in NS | F2R Team | Pass | Pass | Pass | Pass |  | P0020476 | 2024-07-23 | 2024-07-25
| Move Stock | [7 empty] | 2024-07-25
| Putaway from Receiving | F2R Team |  |  | Pass |  |  |  | 2024-07-25
| Move stock - add multiple units of different products to cart and put away to the same location | F2R Team |  |  | Pass |  |  |  | 2024-07-25
| Move stock - add multiple units of different products to cart and put away to two different locations | F2R Team |  |  | Pass |  |  |  | 2024-07-25
| Move Container | [7 empty] | 2024-07-25
| Putaway from Receiving | F2R Team |  |  | Pass |  |  |  | 2024-07-25
| Move container - use move only stock to move contents of the pallet into to a new location | F2R Team |  |  | Pass |  |  |  | 2024-07-25
Cycle Count
| Create Cycle Count task via scheduler - Count by Item | DEP Team
| Create Cycle Count task via scheduler - Count by Location | DEP Team
| Create Cycle Count task via picking exception | DEP Team
| Create Cycle Count task manually via Handheld to be performed later - Count by Item | DEP Team
| Create Cycle Count task manually via Handheld to be performed later - Count by Location | DEP Team
| Create Cycle Count task manually via Handheld and perform immediately (on demand) | DEP Team
| Perform a cycle count and capture same value found in location | DEP Team
| Perform a cycle count and capture value different from quantity found in location (double confirm) | DEP Team
| Perform a cycle count and skip a location that you are prompted to count | DEP Team
| Accept cycle count variances | DEP Team
| Reject cycle count variances | DEP Team
| Trigger a recount of a completed cycle count task via Manage Cycle Count Variances | DEP Team
| Adjust Inventory | [7 empty] | 2024-07-25
| Consume some quantity of a particular item in a location | F2R Team | [6 empty] | 2024-07-25
| Consume all inventory in a specific container (LPN) | F2R Team | [6 empty] | 2024-07-25
| Returns*** | [7 empty] | 2024-07-25
| Create inventory in a specific location | F2R Team | [6 empty] | 2024-07-25
Replenishment
| Perform an on demand replenishment | DEP Team
| Create a Replenishment task via scheduler | DEP Team
| Create a replen based on Min Threshold | DEP Team
| Replenish a Split Case Picking location from a Reserve Location | DEP Team
| Perform exception during Replenishment Picking | DEP Team
| Perform exception during Replenishment Putaway | DEP Team
| Replace pulled stock to source location when desitantion location full | DEP Team
| Build and Release Wave | [7 empty] | 2024-07-26
| Build and Release wave manually by selecting orders | F2R Team |  |  | Pass |  |  | SO266, SO250, SO249, SO248, SO264, SO252 | 2024-07-26 | 2024-07-25
| Build and Release wave automatically via scheduler | F2R Team | [6 empty] | 2024-07-26
| Build and Release Singles Order (No Split) | F2R Team | [6 empty] | 2024-07-26
| Build and Release Priority Singles Order (No Split) | F2R Team | [6 empty] | 2024-07-26
| Build and Release Multi Order (No Split) | F2R Team | [6 empty] | 2024-07-26
| Build and Release Priority Multi Order (No Split) | F2R Team | [6 empty] | 2024-07-26
| Build and Release Transfer Order (No Split) | F2R Team | [6 empty] | 2024-07-26
| Import multi-line order - split between two or more facilities. Fulfill orders individually | F2R Team | [6 empty] | 2024-07-26
| Import multi-line priority order - split between two or more facilities. Ensure both orders wave's move to top of listbox for selection. Fulfill orders individually | F2R Team | [6 empty] | 2024-07-26
| Order with Intagible item, ensure autopick | F2R Team |  |  | Needs Info |  |  | SO250, SO249 | 2024-07-26 | 2024-07-25 | When club is attached, it places these in multis, would be helpful to have them go to singles if they are a single item + club.
| Test with Each Ship VIa Stamps, and Fedex | F2R Team | [9 empty] | 7 Shipping methods total to test. Fedex Ground, Fedex 2Day, Fedex Home Delivery, Fedex Standard Overnight, StorePickup, USPS - Priority Mail Express. USPS Priority Mail
| Single Scan Picking | [7 empty] | 2024-07-26
| Pick wave of single unit orders onto one cart | F2R Team | [6 empty] | 2024-07-26 |  |  | Wave multiple single-line single unit orders either by manually selecting from the order list and using the BnR PAL, or run the scheduler for the facility you intend to pick at.
| Perform exception during picking when stock not found/damaged | F2R Team | [6 empty] | 2024-07-26 |  |  | This should place the stock on hold. Will need to resolve either by removing the stock hold (inventory found scenario) or by adjusting the stockUnit out using the adjustInventory process. Will not be able to proceed with the order until stock is added to fulfill the demand.
| Stage picking cart when full and continue picking | F2R Team | [6 empty] | 2024-07-26 |  |  | Can be done with either singles or multis orders.
| Attempt to scan invalid item during picking | F2R Team | [6 empty] | 2024-07-26
| Attempt to scan invalid location during picking | F2R Team | [6 empty] | 2024-07-26
| Attempt to pick quantity larger than allocated | F2R Team | [6 empty] | 2024-07-26
| Batch Picking | [7 empty] | 2024-07-26
| Pick wave of multi unit orders into designated bins | F2R Team | [6 empty] | 2024-07-26 |  |  | Orders and waves are 1:1. Will require a new bin for each order/wave
| Perform exception during picking when stock not found/damaged | F2R Team | [6 empty] | 2024-07-26 |  |  | This should place the stock on hold. Will need to resolve either by removing the stock hold (inventory found scenario) or by adjusting the stockUnit out using the adjustInventory process. Will not be able to proceed with the order until stock is added to fulfill the demand.
| Use New Bin functionality to pick an order into multiple bins | F2R Team | [6 empty] | 2024-07-26 |  |  | Order can be split across multiple bins if physically large enough to require this. Each bin should be an individual shipment/trackingNumber during packing
| Attempt to scan invalid item during picking | F2R Team | [6 empty] | 2024-07-26
| Attempt to scan invalid location during picking | F2R Team | [6 empty] | 2024-07-26
| Attempt to scan invalid container/bin during picking | F2R Team | [6 empty] | 2024-07-26 |  |  | Scanning a container of type 'Shipping' will trigger this error. Otherwise, can create bin's on the fly as needed without prior record in the system. In a real setting, this should still be tied to an LPN placard or printout so the bin number is not lost.
| Attempt to pick quantity larger than allocated | F2R Team | [6 empty] | 2024-07-26
| Pick a Re-Pick Batch Wave | F2R Team | [6 empty] | 2024-07-26 |  |  | Pick a wave/order, then use the 'Roll back after picking' Admind menu option to reset the stock. Ensure the order moves to backorder status. Re-wave, and repick.
| Singles Packing | [7 empty] | 2024-07-26
| Pack order from cart picked via Single Scan Picking | F2R Team | [6 empty] | 2024-07-26 |  |  | Ensure each packed item creates a shipment and ship label with tracking upon packout.
| Capture box dimensions during packing for Pack Order by Item (Preferred Pack if it is assigned) | F2R Team | [6 empty] | 2024-07-26 |  |  | Set up packout container dims
| Print shipping label at the conclusion of packing | F2R Team | [6 empty] | 2024-07-26 |  |  | Add a 'shippinglabel' printer assignment to a zpl printer at the packing facility prior to perfomring
| Attempt to pack a multi unit order via Pack Order by Item (should not allow) | F2R Team | [6 empty] | 2024-07-26
| Back out of container during packing and re-scan container to continue | F2R Team | [6 empty] | 2024-07-26
| Scan invalid items during Pack Order by Item | F2R Team | [6 empty] | 2024-07-26
| Change carton type from suggested | F2R Team | [6 empty] | 2024-07-26
| Print shipping label at the conclusion of packing (FEDEX and STAMPS) | F2R Team | [6 empty] | 2024-07-26 |  |  | Need valid shipVia assigned to the order being packed, and a printer assignment for 'ShippingLabel' at the facility where packing is occuring.
| Print packing list at the conclusion of packing | F2R Team | [6 empty] | 2024-07-26 |  |  | Ensure there is a printer assignment for the packSlip 'F2R_PACKING_LIST_v1' at the facility where this test is perfomed. Should print automatically.
| Multis Packing | [7 empty] | 2024-07-26
| Pack order from bin used during Multi's picking | F2R Team | [6 empty] | 2024-07-26 |  |  | Simple packout test
| Pack Order into multiple containers | F2R Team | [6 empty] | 2024-07-26 |  |  | Use 'New Bin' button at packout. Should create a shipment and trackingNumber for each bin packed.
| Scan invalid items during Multis Packing | F2R Team | [6 empty] | 2024-07-26
| Print shipping label at the conclusion of packing | F2R Team | [6 empty] | 2024-07-26 |  |  | Need valid shipVia assigned to the order being packed, and a printer assignment for 'ShippingLabel' at the facility where packing is occuring.
| Print packing list at the conclusion of packing | F2R Team | [6 empty] | 2024-07-26 |  |  | Ensure there is a printer assignment for the packSlip 'F2R_PACKING_LIST_v1' at the facility where this test is perfomed. Should print automatically.
Wholesale Packing
| Pack an order picked into a bin via Wholesale Packing | F2R Team
| Pack a large order picked alone to a cart via Wholesale Packing | F2R Team
| Capture box dimensions during Wholesale Packing | F2R Team
| Use New Bin functionality to create multiple shipping containers for one order | F2R Team
| Print container label(s) at conclusion of packing | F2R Team
| Scan invalid items during Single Scan Packing | F2R Team
| Void and Reprocess Shipment | [7 empty] | 2024-07-26
| Void and Reprocess one Shipment | F2R Team | [6 empty] | 2024-07-26
POS TESTING
| Shopify Order Intgeration Testing | [7 empty] | 2024-07-26
| Ecom order to route to the ecom warehouse (inventory only avail in ecom) | F2R Team | [6 empty] | 2024-07-26
BOPIS order to Sarasota main Street
Ecom Order only to Main street

## Future (hidden)
Potential Future Cases
ITEM # | DETAILS | NOTES | TIMELINE

## Test Case Summary (hidden)
Client Testing Summary
Client: |  | Client
Client Code: |  | Client
Buiness Unit: |  | Multiple
Test Cases Required: |  | #REF!
Test Cases Executed: |  | #REF!
Test Cases Remaining: |  | #REF!
Test Cases Passed: |  | #REF!
Test Cases Failed: |  | #REF!
% Complete: |  | #REF!
Process | Test Cases Required | Test Cases Complete | Test Cases Failed | % Complete
Receiving | 0 | 0 | 0 | #DIV/0!
Inventory Management | 0 | 0 | 0 | #DIV/0!
Picking | 0 | 0 | 0 | #DIV/0!
Packing | 0 | 0 | 0 | #DIV/0!
Waves (Build and Release Logic) | #REF! | #REF! | #REF! | #REF!
Data Imports | 5 | 0 | 0 | 0%
Integration | 0 | 0 | 0 | #DIV/0!
Order Management | #REF! | #REF! | #REF! | #REF!
UAT/Go-Live Checklist | Status
Test Cases | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Inbound (hidden)
Client: |  | Client
Client Code: |  | Client
Process: |  | Receiving
Date Updated: |  | 2025-08-11
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receiving Purchase Order Test Cases
1 | PO Receiving | 1.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen
|  | 1.02 |  | Select Purchase Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 1.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 1.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 1.05 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 1.06 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 1.07 |  | Keep repeating step 1.03 - 1.05 if there are multiple items in the order that you are receiving until all items have been received | PO is fully received
2 | ITO Receiving | 2.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen
|  | 2.02 |  | Select Inbound Transfer Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 2.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 2.04 |  | Scan/Key Item you are receiving (list of items on the ITO will be provided in the list box) | item is entered
|  | 2.05 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 2.06 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 2.07 |  | Keep repeating step 2.03 - 2.05 if there are multiple items in the order that you are receiving until all items have been received | ITO is fully received
3 | Blind Order Receiving | 3.01 |  | Select Blind Receiving from Admin menu on Handheld | moves to general receiving screen
|  | 3.02 |  | Select Blind Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 3.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 3.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 3.05 |  | Hit Enter | If Print Label was checked yes, user is prompted print item label screen
|  | 3.06 |  | Keep repeating step 3.03 - 3.05 if there are multiple items in the order that you are receiving until all items have been received
|  | 3.07 |  | Hit Finish
4 | Hot Pick Putaway | 4.01 |  | Select Move Stock from the Inbound menu
|  | 4.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 4.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 4.04 |  | Scan/Enter the Hot Pick Item you are moving | item is entered
|  | 4.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 4.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 4.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 4.08 |  | Enter the Item and the Quantity that will be moved
|  | 4.09 |  | User will then see a listbox of eligible Hot Pick locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 4.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
5 | Reserve Putaway | 5.01 |  | Select Move Stock from the Inbound menu
|  | 5.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 5.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 5.04 |  | Scan/Enter the Items you are moving to a Reserve location | item is entered
|  | 5.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 5.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 5.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 5.08 |  | Enter the Item and the Quantity that will be moved
|  | 5.09 |  | User will then see a listbox of eligible Reserve locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 5.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
6 | Speed Cell Putaway | 6.01 |  | Select Move Stock from the Inbound menu |  | All results as expected
|  | 6.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 6.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 6.04 |  | Scan/Enter the Hot Pick Item you are moving | item is entered
|  | 6.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 6.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 6.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 6.08 |  | Enter the Item and the Quantity that will be moved
|  | 6.09 |  | User will then see a listbox of eligible Hot Pick locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 6.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
7 | Miniatures Putaway | 7.01 |  | Select Move Stock from the Inbound menu
|  | 7.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 7.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 7.04 |  | Scan/Enter the Items you are moving to a Miniatures location | item is entered
|  | 7.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 7.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 7.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 7.08 |  | Enter the Item and the Quantity that will be moved
|  | 7.09 |  | User will then see a listbox of eligible Miniatures locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 7.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
8 | Product Category Putaway | 8.01 |  | Select Move Stock from the Inbound menu
|  | 8.02 |  | Enter/Scan the cart you will be loading the items into | moves to next screen
|  | 8.03 |  | Enter/Scan the location or the LPN that you will be moving your items from
|  | 8.04 |  | Scan/Enter the Item you are moving | item is entered
|  | 8.05 |  | Select the pack type of the item and enter in the quantity being moved.
|  | 8.06 |  | Once user hits enter, they will be directed back to the Item sleelction screen where they can scan more items to move. User will then select Move Source Screen
|  | 8.07 |  | User will be taken to the Move Source Screen where they will see the SKUs and Quantity in their cart. Select Move
|  | 8.08 |  | Enter the Item and the Quantity that will be moved
|  | 8.09 |  | User will then see a listbox of eligible Category Zone locations to move the items to. Scan/Enter a location | Enter the locator of the location
|  | 8.1 |  | After stock is moved, User will be taken to the Main Menu | Screen Message: All Items Moved
9 | PO Receiving (with Item Image Display) | 9.01 |  | Select General Receiving from Inbound menu on Handheld | moves to general receiving screen
|  | 9.02 |  | Select Purchase Order as Identifier Type. Enter/Scan the Order Number under Identifier Number Field. Enter/Scan the Container you are receiving into. Check Yes for Summary if you want to print PO for receipt and check Yes for Putaway if you want to direct stock to a location other than the default receiving location. | moves to next screen
|  | 9.03 |  | Hit Enter or Click Next | If Summary Screen was checked yes, user is prompted to summary screen
|  | 9.04 |  | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box) | item is entered
|  | 9.05 |  | On the bottom right of your screen, you will see "View Item" button. If you want to display the item image, click "View Item" | "View Item" screen will pop up. You will be able to see item image
|  | 9.06 |  | Select the pack type of the item and key in the quantity being received. Check Yes option for Print Labels if you want an item label printed upon reciept.
|  | 9.07 |  | Once user hits enter, they will be directed to the putaway screen where they can choose which location to move the received stock to | If Print Label was checked yes, user is prompted print item label screen
|  | 9.08 |  | Keep repeating step 1.03 - 1.05 if there are multiple items in the order that you are receiving until all items have been received | PO is fully received
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receive by item
1 | Receive By Item | 1.01 |  | Select Receive By item from Inbound menu on Handheld
|  | 1.02 |  | Scan/Key Item you are receiving | User is Prompted to Receiveing order screen to select order
|  | 1.03 |  | Select Order from order list | User is Prompted to Receive Item screen to receive item
|  | 1.04 |  | Select Pack type and enter quantity | selected item is received and move back to Receiving Item Screen
|  | 1.05 |  | Keep repeating step 1.03 - 1.04 if there are multiple items in the order that you are receiving until all items have been received
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Print Item label
1 | Print Item Label Through Process Action Link | 1.01 |  | Go to Master Data-> Items-> Select an item | Message: Succesfully printed 1 of report [Item Label] for each Item
|  | 1.02 |  | Select the Actions drop down menu-> Print Item Label
|  | 1.03 |  | Select your printer-> Print
2 | Print Item Label Through Handheld | 2.01 |  | Handheld-> Admin-> Print Item Label | Message: Report [Item Label] succesfully printed. | All Results as Expected
|  | 2.02 |  | Scan/ Enter the Item Number
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Receiving Edge Cases
1 | Incorrect PO# Entry | 1.01 |  | Navigate to the General Receiving button found in the Inbound Menu | A message should dispay reading, "Purchase Order _____ does not exist" | Result as Expected
|  | 1.02 |  | Enter a PO Number that does not exist
2 | Scanning Already Received PO | 2.01 |  | User enters Receiving Process | Error message appears reading, "There are no lines eligible to receive for this order". | Result as Expected
|  | 2.02 |  | User scans a Purchase Order that has already been received instead of a new Purchase Order
|  | 2.03 |  | User will be prevented from continuing with the process
3 | Attempt to Finish without Receiving Item | 3.01 |  | User will enter General Receiving button | Message will populate indicating nothing has been received from the associated PO | Result as Expected
|  | 3.02 |  | User hits "Finish/Exit"
|  | 3.03 |  | If nothing has been received, user will receive message "You have not received any item for order [_____]"
4 | Receiving an existing Item not on a PO | 4.01 |  | User will enter receiving transaction | Error message appears reading, "Please enter a valid SKU for [PO Number]." | Result as Expected
|  | 4.02 |  | User scans/Keys an Item not on PO for receiving
|  | 4.03 |  | User will be prevented from receiving the item in the process
5 | Negative Item Qty Entry | 6.01 |  | During General Receiving, user keys in a negative quantity to be received | Error message appears reading, "Please enter a valid quantity." | Result as Expected
|  | 6.02 |  | User will be prompted to re-enter quantity
6 | Invalid Item Qty Entry | 7.01 |  | During General Receiving, user keys in an invalid number like "2YN" | Error message appears reading, "Please enter a valid quantity." | Result as Expected
|  | 7.02 |  | User will be prompted to re-enter quantity
7 | Over-Receive a PO | 7.01 |  | During General Receiving, user keys in quantity that is greater than the order pack quantity | Message should appear reading "You can only receive up to the max amount (QTY) of Each."
9 | Attempt to Over-Receive over 25% | 9.01 |  | During General Receiving, user keys in quantity that is greater than the order pack quantity (over 25%) | Error message appears reading "You can only receive up to a maximum of [125%] of Each" | Message stated "You can only receive up to the max amount of 6 of each" when attempting to receive 20
|  | 9.02 |  | User will be prevented from receiving the item in the process as it exceeds the over-receipt threshold of 25%
8 | Undo Receipt | 8.01 |  | Navigate to the 'Undo Receipt' button in the Inbound menu on the handheld
|  | 8.02 |  | Enter the order header number of the order needed to be unreceivied
|  | 8.03 |  | Scan the item to be unreceived and enter the quantity to be decremented from the current received quantity. Container is not required but can be scanned to put the item into when unreceiving
|  | 8.04 |  | Press enter or select submit

## Data Exchange (hidden)
Client: |  | Client
Client Code: |  | Client
Process: |  | Imports
Date Updated:
Test Cases Required: |  | 5
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | 0%
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Test Notes | Pass/Fail | Tester
1 | Container Import | 1.01 |  | In the application menu, navigate to the Field Mapping tab under Data Exchange | 1) Containers/LPN's should be created in 'Ready' status in the location specified (if applicable) | CSV Imported as Expected
|  | 1.02 |  | Select the "Container Import" field mapping and select 'Download Sample CSV'
|  | 1.03 |  | Complete the template. Required fields: Container Number, LPN Number, Location, Type
|  | 1.04 |  | Save the template to your local device
|  | 1.05 |  | In the application menu, navigate to the Data Exchange tab under Data Exchange
|  | 1.06 |  | Select the "3 dots" at the end of the row for 'Picking Container/LPN Import' and select 'Run'
|  | 1.07 |  | Select the saved template from the local device and select 'Upload'
|  | 1.08 |  | In the application menu, navgate to the Transmission tab under Data Exchange
|  | 1.09 |  | Verify the import's status by checking the 'Status' column
2 | Zone Import | 2.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Zones should be created | CSV Imported as Expected
|  | 2.02 |  | Select the Zone Import field mapping and select 'Download Sample CSV'
|  | 2.03 |  | Complete the template. Required fields: Code
|  | 2.04 |  | Save the template to your local device
|  | 2.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 2.06 |  | Select the "3 dots" at the end of the row for 'Product Category Import' and select 'Run'
|  | 2.07 |  | Select the saved template from the local device and select 'Upload'
|  | 2.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 2.09 |  | Verify the import's status by checking the 'Status' column
3 | Location Import | 3.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Locations should be created as 'Ready' type with corresponding Zones (if applicable) | CSV Imported as Expected
|  | 3.02 |  | Select the Location Import field mapping and select 'Download Sample CSV'
|  | 3.03 |  | Complete the template. Required fields: Location(l) Number, l.Facility, l.Locator, l.storageType, l.Type, l.multiItemThreshold, l.Pickable Optional: Zone(z) Facility, z.Name, Storage(s)
|  | 3.04 |  | Save the template to your local device
|  | 3.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 3.06 |  | Select the "3 dots" at the end of the row for 'Location Import' and select 'Run'
|  | 3.07 |  | Select the saved template from the local device and select 'Upload'
|  | 3.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 3.09 |  | Verify the import's status by checking the 'Status' column. Reference the 'Errors' column if status is 'Failed'
4 | Pack Import | 4.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) Packs should be created with corresponding Items | CSV Imported as Expected
|  | 4.02 |  | Select the Pack Import field mapping and select 'Download Sample CSV'
|  | 4.03 |  | Complete the template. Required fields: Item Number, Pack Quantity
|  | 4.04 |  | Save the template to your local device
|  | 4.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export
|  | 4.06 |  | Select the "3 dots" at the end of the row for 'Item/Pack Import' and select 'Run'
|  | 4.07 |  | Select the saved template from the local device and select 'Upload'
|  | 4.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 4.09 |  | Verify the import's status by checking the 'Status' column
5 | Purchase Order Import | 5.01 |  | In the application menu, navigate to the Field Mapping tab under Import Export | 1) OrderHeaders should be created as 'Purchase Order' type with corresponding OrderLines | Initial upload attempts were failures due to an incorrect Business Unit.
|  | 5.02 |  | Select the Purchase Order Import field mapping and select 'Download Sample CSV'
|  | 5.03 |  | Complete the template. Required fields: OrderHeader(oh) Number, oh.currentStatus, OrderLine (ol) Number, ol.customerLineNumber, ol.orderLineStatus
|  | 5.04 |  | Save the template to your local device |  | Single line PO uploaded successfully
|  | 5.05 |  | In the application menu, navigate to the Data Exchange tab under Import Export |  | Multi-line PO failure due to Customer Line Number being set as a Business Key
|  | 5.06 |  | Select the "3 dots" at the end of the row for 'Purchase Order Import' and select 'Run' |  | Multi-line PO uploaded successfully
|  | 5.07 |  | Select the saved template from the local device and select 'Upload'
|  | 5.08 |  | In the application menu, navgate to the Transmission tab under Import Export
|  | 5.09 |  | Verify the import's status by checking the 'Status' column. Reference the 'Errors' column if status is 'Failed'

## Inventory Management (hidden)
Client: |  | Client
Client Code: |  | Client
Process: |  | Inventory Management
Date Updated:
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Cycle Count
2 | Create Cycle Count Task by Location | 1.01 |  | Make sure Cycle Count checkbox is checked for both Item and the Location that contains its stock units (Inventory). | Using the location cycle count creation handheld process will create cycle count tasks for a specific location Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING. When cycle counting via handheld "Perform Cycle Count" process, user will be prompted to count all specified items in the location.
|  | 1.02 |  | Navigate to "Create Cycle Count By Location" under Inventory in handheld menu
|  | 1.03 |  | Scan or enter the location to count
|  | 1.04 |  | Optionally enter a priority for the cycle count. If no priority is entered, then the priority will default to five (Medium).
|  | 1.05 |  | Cycle count tasks for the location will appear in the Cycle Count Queue table. (located in Inventory Admin menu option on the desktop UI)
3 | Perform Cycle Count (with Item Image Display) | 3.01 |  | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. More info on this in the next test script.
|  | 3.02 |  | Scan or enter starting location (any location in the warehouse) and hit enter
|  | 3.03 |  | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 3.04 |  | User will scan the location they're directed to
|  | 3.05 |  | User will be shown a list box with items in location needing to be cycle counted.
|  | 3.06 |  | User will scan SKU and hit enter
|  | 3.07 |  | On the next screen, user will select the pack type and enter the quantity they counted. **User will see item image on this screen
|  | 3.08 |  | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  | 3.09 |  | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  | 3.1 |  | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
4 | Manage Cycle Count Variances | 4.01 |  | User (typically a supervisor or manager) will enter the "Approve Variances" UI through a laptop or desktop | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances".
|  | 4.02 |  | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system.
|  | 4.03 |  | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted.
|  | 4.04 |  | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted).
5 | On Demand Cycle Count | 5.01 |  | User will select "On Demand Location Cycle Count" from Inventory menu | If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. (ref seq. 7) Note: Be sure to delete and clear all entries in the CycleCountQueue, located within the Inventroy Admin tab BEOFRE TESTING.
|  | 5.02 |  | User will be prompted to enter a location and priority (1-10 w/1 being highest priority). Priority defaults to 5 if left empty.
|  | 5.03 |  | User creates cycle count task and will immediately begin task (reference seq. 3, steps 3.04-3.10) and will be assigned to the user to complete.
6 | Physical Count | 6.01 |  | Select "Physical Count" from Inventory Menu | 1) When Physical Count Activity is started from Physical Count Admin button, message will appear saying "[controlled/non-controlled] Physical Count Activity [process name] is started on [date time] and is active". 2) Non-controlled Physical Count Activity will be able to create and delete inventory. Stock units will be updated with whatever is counted for that location. 3) If controlled, discrepancies will be recorded in "Manage Cycle Count Variances" . 4) Once physical count activity is complete, screen will return to MainMenu and will display a message saying "[controlled/non-controlled] Physical Count Activity [process name] is finished at [date time]". 5) Adjustments to item's SU will show up in Inventory General Ledger Table
|  | 6.02 |  | Scan/Enter a location
|  | 6.03 |  | User counts items in location
|  | 6.04 |  | To go onto the next location, User can select "Next Location"
|  | 6.05 |  | If phys count activity is non-controlled, user is taken to phys count summary screen and can click "Recount" or "Apply" before finally confirming.
|  | 6.06 |  | When done with physical count activity, navigate to "Physical Count Admin" button and click "Finish Physical Count Activity"
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Putaway
1 | Move Item | 1.01 |  | Navigate to "Move Item" under Inbound on handheld MainMenu | This process allows a user to move unique items individually out of a location and into a different location Stock units that were moved are decremented from their source location, and are created in the destination location
|  | 1.02 |  | Enter the location that contains the stock you want to move
|  | 1.03 |  | A listbox of available SKUs to move display. User must scan or select item to move
|  | 1.04 |  | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  | 1.05 |  | User is prompted to putaway screen. User must scan or select a location in which to put the stock away.
|  | 1.06 |  | If user wants to continue moving items from this location, user can repeat steps 1.03-1.05
|  | 1.07 |  | Otherwise, user can exit the process
2 | Move Stock | 2.01 |  | Navigate to "Move Stock" under Inbound on handheld MainMenu | This process allows a user to move multiple items instead of one unique SKU 1) When all stock has been moved successfully, a message displays on menu saying "All Items Moved." 2) Picking Cart is now empty and remains in its original location 3) Stock units that were moved are decremented from their source location, and are created in the destination location |  |  | Not Ready for Testing
|  | 2.02 |  | Enter/scan the container in which you want to put the stock you are wanting to move
|  | 2.03 |  | Enter or scan location with the stock you want to move
|  | 2.04 |  | A listbox of available SKUs to move display. User must scan or select item to move
|  | 2.05 |  | Select Pack UOM and enter in quantity to move and select Submit
|  | 2.06 |  | Repeat steps 2.04-2.05 to move more items in the location
|  | 2.07 |  | When finished, select Move Source Screen
|  | 2.08 |  | User is given a summary of the number of unique Skus and quantity in cart. If user wants to move stock in a different location, User can scan another location.
|  | 2.09 |  | Otherwise, User can select "Move" or "Move Full" to move the stock to a directed location
|  | 2.10 |  | User enters quantity and selects/scans item
|  | 2.11 |  | A listbox of suggested putaway locations is displayed. User must select or scan a location to move the stock
|  | 2.12 |  | User repeats 2.10-2.11 to move the rest of the stock, if any
|  | 2.13 |  | Otherwise, User can select All to move all of the stock in the cart and then scan the destination location of where the stock should be moved
2 | Move Container | 2.01 |  | Navigate to "Move Container" under Inventory on handheld MainMenu | This process allows a user to move an entire container (LPN) out of a location and into a different location The container (LPN) that container the stock (inventory) is decremented from the source location, and created in the destination location
|  | 2.02 |  | Enter/Scan the container (LPN) that contains the stock (inventory) you want to move. Container type must be Pallet or Transient
|  | 2.03 |  | A listbox of suggested locations should populate. The user should now navigate to one of the suggested locations, scanning that location they wish to put the container away to
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Adjust Inventory
1 | Adjust Inventory: Decrement Inventory out of a Location | 1.01 |  | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 4) Updates made to Item's SU in location
|  | 1.02 |  | Scan/key in Location
|  | 1.03 |  | Select "Consume by Item"
|  | 1.04 |  | Scan Item SKU
|  | 1.05 |  | Enter quantity of item's SU you want to consume
|  | 1.06 |  | If you have more than one item's SU you want to consume in the location, click next and repeat steps 2.04 and 2.05
|  | 1.07 |  | Once finished, click Confirm
|  | 1.08 |  | Once final reviewing all items, select Reason Code and click Commit
2 | Adjust Inventory: Add Inventory to a Location | 2.01 |  | Select "Adjust Inventory" from the Inventory menu | 1) After items have been confirmed and the user clicks commit, user is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" 2) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 3) Updates made to Item's SU in location
|  | 2.02 |  | Scan/key in Location
|  | 2.03 |  | Select "Create Inventory"
|  | 2.04 |  | Scan Item SKU
|  | 2.05 |  | Enter quantity of item's SU you want to create. User can optionally enter serial, lot, and LPN #.
|  | 2.06 |  | If you have more than one item's SU you want to create, click next and repeat steps 3.04 and 3.05
|  | 2.07 |  | Once finished, click Confirm
|  | 2.08 |  | Once final reviewing all items, select Reason Code and click Commit
3 | Adjust Inventory: Consume All Inventory in Location | 3.01 |  | Select "Adjust Inventory" from the Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location
|  | 3.02 |  | Scan/key in Location
|  | 3.03 |  | Select "Consume All in Location"
|  | 3.04 |  | Select Reason Code and Click Commit
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Adjust Inventory
1 | Replenishment Based on Open Orderline Quantity | 1.01 |  | Replenishments are generated on a scheduled basis for every location-item combination where current inventory levels for an item in a picking location is LESS than the the Open Orderlines for that item. The replenishment task will try to push the inventory level in the location to be enough to fulfill the open orders plus 20% more. All replenishments can be viewed in the "ReplenishmentTaskNew" entity
|  | 1.02 |  | Set up test data to where there is an open orderline qty for an item that is greater than the quantity of that item in a pickable location. Ensure that the item exists in a Reserve location
|  | 1.03 |  | Run the Open Orderline Replen Scheduler
|  | 1.02 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 1.03 |  | Scan a container that is Type=Cart
|  | 1.04 |  | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 1.05 |  | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 1.06 |  | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 1.07 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 1.08 |  | User will scan the destination location, the SKU, and the replen quantity
|  | 1.09 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
2 | Replenishment Based on Open Orderline Quantity | 2.01 |  | Replenishments are generated on a scheduled basis for every location-item combination where the stock unit quantity in a location is at 25% of the past two week volume in order to get the location back to maintaining a two week supply. All replenishments can be viewed in the "ReplenishmentTaskNew" entity
|  | 2.02 |  | Run the Two Week Demand Replen Scheduler
|  | 2.03 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 2.04 |  | Scan a container that is Type=Cart
|  | 2.05 |  | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 2.06 |  | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 2.07 |  | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 2.08 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 2.09 |  | User will scan the destination location, the SKU, and the replen quantity
|  | 2.1 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Inventory Edge Cases
1 | Ad-Hoc Cycle Count - Counting Less than the Item's Qty | 1.01 |  | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances" UI for a manager or supervisor to review 2) If qty count entered is less than the system's qty, a negative variance qty will be displayed for that item in "Approve Variances"
|  | 1.02 |  | User will enter quantity less than the item's SU quantity currently in Deposco's system
|  | 1.03 |  | User will be asked to recount and will proceed to re-enter the quantity.
2 | Ad-Hoc Cycle Count - Counting More than the Item's Qty | 2.01 |  | User selects "On Demand Cycle Count" from Inventory menu | 1) Tasks will be generated in the "Approve Variances UI for a manager or supervisor to review 2) If qty count entered is more than the system's qty, a positive variance qty will be displayed for that item in "Approve Variances"
|  | 2.02 |  | User will enter quantity more than the item's SU quantity currently in Deposco's system
|  | 2.03 |  | User will be asked to recount and will proceed to re-enter the quantity.
3 | Perform Cycle Count - Scanning incorrect Location | 3.01 |  | Select "Perform Cycle Count" button in handheld menu from Inventory | 1) Error message saying "You must cycle count the given location [required location]". 2) User will be prevented from ever counting in an incorrect location.
|  | 3.02 |  | Scan or enter starting location and hit enter
|  | 3.03 |  | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 3.04 |  | User scans an incorrect location
User is prompted to re-enter correct location. Proceed as normal.
4 | Perform Cycle Count - Scanning Item that does not exist in Location | 4.01 |  | Select Perform Cycle Count button in handheld menu from Inventory | 1) Variance be generated in the "Approve Variances" UI for a manager or supervisor to review
|  | 4.02 |  | Scan or enter starting location and hit enter
|  | 4.03 |  | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  | 4.04 |  | User will incorrectly scan an item not listed nor existing in the location
|  | 4.05 |  | On the next screen they'll select the pack type and enter the quantity they counted
|  | 4.06 |  | User will be brought back to the screen displaying the list box of items and can proceed as normal
5 | Physical Count- Physical Count Activity not Started | 5.01 |  | User makes sure there is no physical count activity started by navigating to Physical Count Admin button. If there is one existing, user should select "Finish Physical Count Activity". | 1) User will get an error on MainMenu saying "PHYSICAL_COUNT Activity has not started." 2) User will not be able to start physical count process unless the activity has been started in Physical Count Admin.
|  | 5.02 |  | Select "Physical Count" button in Admin Folder
|  | 5.03 |  | User will not be able to start physical count
7 | Move Item / Move Stock - Incorrect Source Location Scan | 7.01 |  | During Move Item/Move Stock, user scans a source location that does not exist | User should see an error on MainMenu saying "[....] is not a valid location" or "No such location or LPN in the current facility." depending on process
|  | 7.02 |  | The user should be prevented from moving forward with the process
8 | Move Item / Move Stock - Putaway to non Suggested Location | 8.01 |  | During Move Item/Move Stock user wants to put away to a location other than the suggested location | 1) Stock unit will be created in the putaway location the user entered 2) Message will appear reading, "All items Moved." if using Move Item
|  | 8.02 |  | User will leave the suggested location list box alone and scan the desired putaway location
9 | Move Item / Move Stock - Incorrect Item Qty Entry | 9.01 |  | During Move Item/Move Stock, user enters in more than the item's current SU quantity to move | 1) Message will appear reading, "The entered quantity exceeds the total movable Each quantity of [...]." and "Quantity to move [..] larger than quantity in found stocks [...]." depending on process. 2) User should not be allowed to enter more than the item's current SU quantity.
|  | 9.02 |  | User will be prompted to re-enter quantity and scan putaway location
10 | Move Item / Move Stock - Negative Item Qty Entry | 10.01 |  | During Move Item/Move Stock, user enters in a negative value for the item's current SU quantity to move | 1) Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process. 2) User should not be allowed to enter or move a negative quantity in this process.
|  | 10.02 |  | User will be prompted to re-enter quantity and scan putaway location
11 | Move Item / Move Stock - Invalid Item Qty Entry | 11.01 |  | During Move Item/Move Stock, user enters in for the item's current SU quantity to move an invalid number like "2YN". | 1) Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process. 2) User should not be allowed to enter an invalid item's SU quantity.
|  | 11.02 |  | User will be prompted to re-enter quantity and scan putaway location
12 | Replen edge cases | 12.01 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 12.02 |  | In the Picking screen, select "Exception"
|  | 12.03 |  | The user is directed to "Replenishment Picking Exception" screen
|  | 12.04 |  | Hit Complete
|  | 12.05 |  | The replenishment task is marked with a status of "Full", this replenishment task is skipped and the user is taken to the next replenishment task
13 | Replen edge cases | 13.01 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen | The location that the Exception occured at will then have a status of "On Hold"
|  | 13.02 |  | In the Picking screen, select "Exception"
|  | 12.03 |  | The user is directed to "Replenishment Picking Exception" screen
|  | 13.04 |  | Select No Stock and hit Exception
|  | 13.05 |  | The replenishment task is marked with a status of "Exception", this replenishment task is skipped and the user is taken to the next replenishment task
14 | Replen edge cases | 14.01 |  | Navigate to the Handheld-> Inventory-> Replenishments-> Directed Replen
|  | 14.02 |  | Scan a container that is Type=Cart
|  | 14.03 |  | User is taken to the "Pull Summary Screen" showing the Items, quantity, and location to replenish from. Select Next
|  | 14.04 |  | The user will be taken to "Picking Screen" to scan and pick the item(s) to replenish
|  | 14.05 |  | Step 1.05 will be repeated to complete all picks needed for all replenishment tasks (unless the user selects Exception or Cart is Full)
|  | 14.05 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 14.05 |  | User will scan the destination location, the SKU, and the replen quantity
|  | 14.05 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."
|  | 14.05 |  | Select Suspend Task and hit Exception
|  | 14.05 |  | The replenishment task is skipped and the user is taken to the next replenishment task
|  | 14.06 |  | Once all picks are complete, the user is directed to "Replenishment Entry Screen" to replenish location with the picked items
|  | 14.07 |  | Select Exception, and user will be directed to the Replenishment putaway exception screen. Select Location Full and then click "Exception" again
|  | 14.08 |  | User will then be directed to put the stock back to where they pick it from
|  | 14.09 |  | Once all replenishment tasks are completed, the user will be taken to the main screen and will see the following message: "Nothing to replenish."

## Picking (hidden)
Client: |  | Client
Client Code: |  | Client
Process: |  | Picking
Date Updated: |  | 2025-08-11
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking
1 | Batch Picking | 1.01 |  | User will select Batch Picking button from Outbound menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 1.02 |  | User will see a list of waves and can select or enter the wave
|  | 1.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 1.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 1.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 1.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
2 | High Value Orders | 2.01 |  | User will select High Value Orders button from Admin menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 2.02 |  | User will see a list of waves and can select or enter the wave
|  | 2.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 2.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 2.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 2.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
3 | Single Scan Picking | 3.01 |  | User will select Singles Picking in corresponding facility menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location | Good | selcted works bundle sku to test item componets imported
|  | 3.02 |  | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking cart to be used |  | Good
|  | 3.03 |  | User will scan location, SKU, bin and enter in quantity to complete pick task(s). |  | Good
|  | 3.04 |  | Once all pick tasks have been completed, user is returned to the wave selection screen |  | Good
4 | Outbound Transfer Picking | 4.01 |  | User will select Outbound Transfer Picking button from Outbound menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container(s) 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 4.02 |  | User will see a list of waves and can select or enter the wave
|  | 4.03 |  | User will be taken to a screen showing location, SKU, bin, and qty for item to be picked.
|  | 4.04 |  | User will scan location, SKU, bin and enter in quantity to complete pick task.
|  | 4.05 |  | If more tasks exist, user will be prompted to scan next location, SKU, bin, and enter in quantity
|  | 4.06 |  | Once the wave has been completed, user is returned to the list of waves and the process can be repeated.
5 | Single Scan Picking (with Item Image Display) | 5.01 |  | User will select Singles Picking in corresponding facility menu | 1) Picking cart will be staged to default Shipping location to be packed/shipped 2) Stock added to picking container 3) Updates made to container pick details 4) Updates made to item's stock unit location and decremented from its picking location
|  | 5.02 |  | User will see a list of waves to choose from or can enter a wave as well as a field to scan the picking cart to be used
|  | 5.03 |  | User will see picking screen and item image
|  | 5.04 |  | User will scan location, item SKU, and quantity
|  | 5.05 |  | Once all pick tasks have been completed, user is returned to the wave selection screen
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Picking Edge Cases
1 | Batch Picking - New Bin | 1.01 |  | During picking, if a picking container becomes too full to put any more items in, the user can select the New Bin button to continue the picking process | Current picking bin will unassign from the order to allow the user to pick into a new container. Picking will proceed as expected | Received an error stating, "Using multi-bins is not allowed." **Resolved** Tested on SO614 with no issues.
|  | 1.02 |  | Selecting New Bin will unassign the current picking bin from the order to allow the user to pick into a new container
|  | 1.03 |  | The picking screen should update to show no suggested bin to pick into
|  | 1.04 |  | User will proceed to complete the pick task in any empty container available
2 | Singles Picking - Stage | 2.01 |  | During picking, if the picking container becomes too full to put any more items in, the user can stage the bin to be packed. | Pick wave can be completed with multiple picking carts that are staged to the Shipping location upon completion | I initially picked x6 of x10 copies of AMGSWL89 from SO468 into BIN-022. I then selected "Stage", which took me to the screen to select a new container. I selected BIN-023, but the picking screen had me pick the original x10 copies into this bin. Looking at the data on SO468, there is only product located in BIN-023.
|  | 2.02 |  | Selecting Stage will prompt the user to select a new cart to continue picking
|  | 2.03 |  | User can proceed with picking as expected in new container
3 | Batch Picking - Entering Less Quantity | 3.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed
|  | 3.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
4 | Singles Picking - Entering Less Quantity | 4.01 |  | During picking, if the pick task cannot be fully completed for whatever reason, the user may enter a quantity less than the complete amount | Pick task is now effectively split. The first quantity has been completed while the remaining quantity will display on the screen. From here, the user has several options to proceed
|  | 4.02 |  | After entering in less than complete quantity, the screen should update to continue picking the remaining quantity
5 | Batch Picking - User Scans Incorrect Location | 5.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen | Message notes: please scan a valid location
|  | 5.02 |  | User scans a location other than the one listed on the screen during picking
|  | 5.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 5.04 |  | User should proceed to correct location and continue as normal
6 | Batch Picking - User Scans Incorrect Item | 6.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. | Message notes: please scan valid item
|  | 6.02 |  | User scans the wrong item
|  | 6.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
7 | Batch Picking - User Enters too Much Quantity | 7.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left.
|  | 7.02 |  | User accidentally enters more than the pick quantity
|  | 7.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 7.04 |  | User will again be prompted to enter location, SKU, and quantity.
8 | Batch Picking - Scanning Incorrect Container/Bin | 8.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin
|  | 8.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
9 | Batch Picking - Exceptions (no stock, damaged, etc.) | 9.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from.
|  | 9.02 |  | User can select "exception" button
|  | 9.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 9.04 |  | Select "exception" again from that screen after selecting a reason
|  | 9.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 9.06 |  | If no other stock exists for that item, it will go to back ordered status.
10 | Batch Picking - Suspend Task | 10.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped.
|  | 10.02 |  | User can select "exception" button
|  | 10.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 10.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
11 | Batch Picking - Suspend Workgroup | 11.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete"
|  | 11.02 |  | User can select "exception" button
|  | 11.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 11.04 |  | User is taken back to MainMenu screen
|  | 11.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
12 | Batch PIcking - Suspend Workgroup and Keep Assigned User | 12.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group.
|  | 12.02 |  | User can select "exception" button
|  | 12.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 12.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 12.05 |  | Assigned user can select wave again to continue picking
13 | Singles Picking - User Scans Incorrect Location | 13.01 |  | During picking, the user will see the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen
|  | 13.02 |  | User scans a location other than the one listed on the screen during picking
|  | 13.03 |  | Error message will appear "Please scan a valid location."
|  | 13.04 |  | User should proceed to correct location and continue as normal
14 | Singles Picking - User Scans Incorrect Item | 14.01 |  | During picking, the user scans the wrong item | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item.
|  | 14.02 |  | Screen message will appear stating "Please scan a valid item"
15 | Singles Picking - User Enters Too Much Quantity | 15.01 |  | User enters locatiton and SKU | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left.
|  | 15.02 |  | User accidentally enters more than what is called for to pick
|  | 15.03 |  | Screen message will appear as follows: "Quantity entered is greater than required."
|  | 15.04 |  | User will again be prompted to enter location, SKU, and quantity.
16 | Singles Picking - Exceptions (no stock, damaged, etc.) | 16.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order will go to back ordered status. Also, the stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from.
|  | 16.02 |  | User can select "exception" button
|  | 16.03 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 16.04 |  | If no other stock exists for that item, it will go to back ordered status.
17 | Singles Suspend WorkGroup | 17.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete"
|  | 17.02 |  | User can select "exception" button
|  | 17.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 17.04 |  | User is taken back to MainMenu screen
|  | 17.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
14 | RTV Picking - User Scans Incorrect Location | 14.01 |  | During picking, the user will see on the screen the location they're being directed to pick from | User will not be able to scan a location other than the one they're directed to on the screen |  |  | Not Tested
|  | 14.02 |  | User scans a location other than the one listed on the screen during picking
|  | 14.03 |  | Error message will appear "The scanned location: [location entered] is incorrect."
|  | 14.04 |  | User should proceed to correct location and continue as normal
15 | RTV Picking - User Scans Incorrect Item | 15.01 |  | During picking, the user will see on the screen what item is being picked | User will not be able to scan an item other than what they're directed to scan for any reason. This won't let them proceed until they scan the correct item. |  |  | Not Tested
|  | 15.02 |  | User scans the wrong item
|  | 15.03 |  | Screen message will display "[scanned item] is not valid. Please enter a valid SKU."
16 | RTV Picking - User Enters too Much Quantity | 16.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Not Tested
|  | 16.02 |  | User accidentally enters more than the pick quantity
|  | 16.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 16.04 |  | User will again be prompted to enter location, SKU, and quantity.
17 | RTV Picking - Scanning Incorrect Container/Bin | 17.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Not Tested
|  | 17.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
18 | RTV Picking - Exceptions (no stock, damaged, etc.) | 18.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Not Tested
|  | 18.02 |  | User can select "exception" button
|  | 18.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 18.04 |  | Select "exception" again from that screen after selecting a reason
|  | 18.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 18.06 |  | If no other stock exists for that item, it will go to back ordered status.
19 | RTV Picking - Suspend Task | 19.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Not Tested
|  | 19.02 |  | User can select "exception" button
|  | 19.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 19.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
20 | RTV Picking - Suspend Workgroup | 20.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Not Tested
|  | 20.02 |  | User can select "exception" button
|  | 20.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 20.04 |  | User is taken back to MainMenu screen
|  | 20.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
21 | RTV PIcking - Suspend Workgroup and Keep Assigned User | 21.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Not Tested
|  | 21.02 |  | User can select "exception" button
|  | 21.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 21.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 21.05 |  | Assigned user can select wave again to continue picking

## Packing (hidden)
Client: |  | Client
Client Code: |  | Client
Process: |  | Packing
Date Updated: |  | 2025-08-11
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
1 | Build Transfer Order | 1.01 |  | Select Build Outbound Transfer Order from Store Operations menu | 1)Ensure your user's Facility is set to the DPR or STPR facility. Screen should read 'Ship-To Facility'
|  | 1.02 |  | Enter the Ship-To Facility Number
|  | 1.03 |  | Select a Transfer Purpose and scan the location with the stock to transfer
|  | 1.04 |  | Scan the container user will be picking into
|  | 1.05 |  | Scan the Items and on the next screen, enter the Quantity that user intends to transfer
|  | 1.06 |  | User will be brought to a sumamry screen showing all items added to the Transfer Order. Confirm order by selecting "Next."Stage your container to a location | User will see the following message: "Container (Container#) staged to (StagingLocation) for ship-to HZLHQ"
|  | 1.07 |  | Pack out the Transfer Order using the Transfer Order Packing button from the Store Operations menu
|  | 1.08 |  | Scan the LPN label of the picking container, and select Next.
|  | 1.09 |  | The Item Screen appears with a list of items in the container. Scan an item in container OR select the "Pack Remainder" button to pack out all items in the container
1.1
2 | Cubed Packing | 2.01 |  | Select Cubed Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container.
|  | 2.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 2.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container.
|  | 2.04 |  | Shipping label and packing list will print
|  | 2.05 |  | User will be returned to the Scan Container Screen and see the following message: "Order [ ] has been successfully packed."
3 | Single Scan Packing | 3.01 |  | Select Single Scan Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order. 3) The picking container is updated to remove the stock unit that was packed. In addition, a shipping container is created as the item is packed. 4) A shipping label and packing slip is printed for the shipping container.
|  | 3.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 3.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container, then enter the quantity that will be packed on the next screen
|  | 3.04 |  | Select the box from the Box list
|  | 3.05 |  | Shipping label and packing list will print
|  | 3.06 |  | If there are more items in the picking bin, then you are returned to the Item Screen to scan/select another item.
4 | Outbound Transfer Packing | 4.01 |  | Select Outbound Transfer Packing from Outbound menu | 1) Order's shipping status shows status "Shipped" 2) A shipment record is created for the order and an Inbound Transfer Order is created for the store to receive against
|  | 4.02 |  | Scan the LPN label of the picking container, and select Next.
|  | 4.03 |  | The Item Screen appears with a list of items in the container. Scan an item in container or use the pack remainder button to pack out all items in the container
|  | 4.04 |  | Packing list will print once all items are packed
|  | 4.06 |  | User will then be brought back to the Scan Container screen
5 | Bulk Packing | 5.01 |  | Select Bulk Packing from the Outbound Menu | User will see the following message at the end of packing: [The request has been placed to ship orders.] Please check the notification center for error messages. | Receiving an error on the Scan Container step stating, "For input string: "" ' Used BIN-060 for testing
|  | 5.02 |  | User will be prompted to scan/enter a container (a container that was just picked into)
|  | 5.03 |  | User will see an order summary screen showing all orders in the container, as well as the items that those orders have in common
|  | 5.04 |  | Select Enter CLIENTnsions
|  | 5.05 |  | Weight will autopopulate, but select the carton type to pack the order out into
|  | 5.06 |  | Select Ship All
|  | 5.07 |  | User will be returned to the container entry screen
6 | BOPIS Packing | 6.01 |  | Select BOPIS Packing from Outbound Menu | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's status shows status "Staged" and Order's shipping status shows "Not Shipped" | Re-tested with SO630
|  | 6.02 |  | User will be prompted to scan/enter a container (a container that was just picked into)
|  | 7.03 |  | User will then be prompted with a list of items that are in said container.
|  | 7.04 |  | Scan each item in container or use the Pack Remainder button to pack all items
|  | 7.05 |  | After all items have been scanned, Select a box from the Box list to pack your order into
|  | 7.06 |  | User will be returned to the container entry screen
| Move Container | 7.07 |  | Navigate to "Move Container" under Inventory on handheld MainMenu | Because BOPIS will be picked and packed through the main warehouse facility, and then moved to the store- this will be the next step. The order will be transported outside system. The "mover" will need to enter the device, and go to move container- where they will enter the container number and be given the option to change facility. Operator must change to destination facility, in order to receive product. From there, scan the location to drop off, and proceed to next step.
|  | 7.08 |  | Enter/Scan the container (LPN) that contains the stock (inventory) you want to move.
|  | 7.09 |  | User will change their facility to the facility the order is going to, then enter a store location (ex. Receiving)
| BOPIS Pickup | 7.1 |  | Select Close BOPIS Order from Store Operations Menu | 1) Screen message should appear saying "Packed [Order] containing x items.." 2) Order's status shows status "Complete" and Order's shipping status shows "Ship Complete"
|  | 7.11 |  | User will be prompted to scan/enter a container (the container that was packed)
|  | 7.12 |  | User will enter the CLIENTnsions of the box,
|  | 7.13 |  | User will be returned to the container entry screen
Test Case ID | Test Case Description | Process Steps |  | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Packing Edge Cases
1 | Single Scan Packing - Scanning a Non Existing Container | 1.01 |  | User enters Single Scan Packing process from facility menu | 1) Screen message should appear saying "Cannot find container [#]." 2) User will always be prevented from starting the packing process if they scan a non existent container
|  | 1.02 |  | User enters a container that does not exist in the system
|  | 1.03 |  | User is prevented from proceeding
2 | Single Scan Packing - New Bin | 2.01 |  | During packing, the user may select New Bin if items in picking container cannot be shipped in one shipping box | 1) Screen message should appear saying "Packing completed for order: [Order Number]." 2) Order's shipping status shows status "Shipped" 3) Shipping label and Packing slip are printed and visible on Shipment Line. 4) Shipment record is created.
|  | 2.02 |  | On item screen, user will select New Bin
|  | 2.03 |  | User will be prompted to enter the CLIENTnsions of the first shipping box
|  | 2.04 |  | Process will return back to items screen to now pack remaining items in new shipping box
|  | 2.05 |  | This process can be repeated as many times as needed
3 | Single Scan Packing - Scanning an Empty Container | 2.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "There are no items to pack." 2) User will always be prevented from starting the packing process if they scan an empty container
|  | 2.02 |  | User is prevented from proceeding
4 | Single Scan Packing - Scanning Wrong Item | 3.01 |  | User scans item that is not on the listbox / not in the container that the user scanned | 1) Screen message should appear saying "Item scanned does not exist in this Order" 2) User should not be able to scan a non existing item for the order and container
|  | 3.02 |  | User is prevented from proceeding
|  | 3.03 |  | User scans the correct item and proceeds as normal
5 | Batch Packing - Scanning a Container with a Partially Picked Order (unfinished pick task) | 4.01 |  | User enters a container that does not have all items picked into it | 1) Screen message should appear saying "Order not fully picked." 2) User will always be prevented from starting the packing process if they scan an incomplete container
|  | 4.02 |  | User is prevented from proceeding
6 | Singles Packing - Scanning a Non Existing Container | 6.01 |  | User enters Singles Packing from facility menu | 1) Screen message should appear saying "Container does not exist or data issue." 2) User will always be prevented from starting the packing process if they scan a non existent container
|  | 6.02 |  | User enters a container that does not exist in the system
|  | 6.03 |  | User is prevented from proceeding
7 | Singles Packing - Scanning an Empty Container | 7.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "Scanned container contains no items" 2) User will always be prevented from starting the packing process if they scan an empty container
|  | 7.02 |  | User is prevented from proceeding
8 | Singles Packing - Scanning Wrong Item | 8.01 |  | User scans item that is not on the listbox / not in the container that the user scanned | 1) Screen message should appear saying "Invalid item number" 2) User should not be able to scan a non existing item for the order and container
|  | 8.02 |  | User is prevented from proceeding
|  | 8.03 |  | User scans the correct item and proceeds as normal
9 | Batch Packing - Scanning an Empty Container | 9.01 |  | User enters a container that does not have items picked into it | 1) Screen message should appear saying "Container [#] does not have any stock units." 2) User will always be prevented from adding the empty container to the trip
|  | 9.02 |  | User is prevented from proceeding

## Integration (hidden)
Client: |  | Client
Client Code: |  | Client
Process: |  | Integration
Date Updated: |  | 2025-08-11
Test Cases Required: |  | 0
Test Cases Executed: |  | 0
Test Cases Passed: |  | 0
Test Cases Failed: |  | 0
% Complete: |  | #DIV/0!
Test Case ID | Test Case Description | Process Steps | Owner | Step Details | Expected Result | Actual Result | Test Data | Pass/Fail | Test Notes | Tester
Integration
1 | - Item Pull | 1.01
1.02
1.03
1.04
1.05
1.06
2 | Sales Order Pull | 2.01
2.02
2.03
2.04
2.05
2.06
3 | Inventory Sync | 3.01
3.02
3.03
3.04
3.05
3.06
3.07
4 | Ship Notice | 4.01
4.02
4.03
5 | - Item Pull | 5.01
5.02
5.03
5.04
5.05
5.06
16 | RTV Picking - User Enters too Much Quantity | 16.01 |  | During picking, the user will see on the screen how much quantity to pick for an item | User should not be able to enter more than what is called for. If they do, they'll receive the screen message listed in the cell to the left. |  |  | Not Tested
|  | 16.02 |  | User accidentally enters more than the pick quantity
|  | 16.03 |  | Screen message will appear as follows: "Quantity entered [entered qty] is greater than required [actual pick qty]."
|  | 16.04 |  | User will again be prompted to enter location, SKU, and quantity.
17 | RTV Picking - Scanning Incorrect Container/Bin | 17.01 |  | User enters Batch PIcking process and enters a bin other than the one suggested on the screen | User will be prevented from picking into the wrong assigned bin |  |  | Not Tested
|  | 17.02 |  | If user scans a container not assigned to the picked item for the order, they'll see the following error message: "Please scan suggested bin."
18 | RTV Picking - Exceptions (no stock, damaged, etc.) | 18.01 |  | User goes to location as directed by the handheld and finds that there is either no stock available to pick, or stock is damaged. | If there are no other locations with sufficient stock to fulfull that order, then that order and any other order on the same wave will go to back ordered status. The stock unit for that item/location combo will go on hold since the assumption is that it could not be picked from. |  |  | Not Tested
|  | 18.02 |  | User can select "exception" button
|  | 18.03 |  | User will be prompted to give a reason (stock missing, stock damaged)
|  | 18.04 |  | Select "exception" again from that screen after selecting a reason
|  | 18.05 |  | If there is stock for that item in another location, User will be directed to fulfill that same order from a the other location where that stock exists
|  | 18.06 |  | If no other stock exists for that item, it will go to back ordered status.
19 | RTV Picking - Suspend Task | 19.01 |  | User goes to location as directed by the handheld and needs to suspend the picking task for whatever reason | 1) When user selects "Suspend task", picking task state will update to "Suspend" 2) When a picking task is supsended, user is automatically prompted to complete the next picking task 3) After the remaining pick tasks for the work group are complete, user is prompted again to pick the item that was skipped. |  |  | Not Tested
|  | 19.02 |  | User can select "exception" button
|  | 19.03 |  | User will select "Suspend Task" on Item Exception screen
|  | 19.04 |  | User is returned to the picking screen to pick the next item in the Workgroup
20 | RTV Picking - Suspend Workgroup | 20.01 |  | User goes to location as directed by the handheld and needs to permanently stop work on the pick wave | 1) User is returned to MainMenu 2) The status of the work group for the pick wave changes to Suspended, and user is unassigned from the Workgroup 3) User can start the picking process again to continue the picking task if they decide to do so 4) When picking is complete, Orderheader and Workgroup status will then be updated to "Complete" |  |  | Not Tested
|  | 20.02 |  | User can select "exception" button
|  | 20.03 |  | User will select "Suspend Workgroup" on Item Exception screen
|  | 20.04 |  | User is taken back to MainMenu screen
|  | 20.05 |  | User or another user can select the pick wave and complete the remaining picking tasks
21 | RTV PIcking - Suspend Workgroup and Keep Assigned User | 21.01 |  | User goes to location as directed by the handheld and needs to temporarily stop work on the pick wave | 1) A WorkGroup suspended message appears saying "WorkGroup suspended, select the wave again to pick." and user is returned to the Picking Menu screen. 2) The status of the work group for the pick wave changes to Suspended, and is unassigned or remains assigned to the same user depending on selecting "Suspend Workgroup" or "Suspend Workgroup and Keep Assigned User" button. 3) When user wants to resume work on the pick wave, user can select the pick wave and complete the remaining pick tasks. If user is kept the assigned user, only the assigned user can continue work on the work group. |  |  | Not Tested
|  | 21.02 |  | User can select "exception" button
|  | 21.03 |  | User will select "Suspend Workgroup and Keep Assigned User" on Item Exception screen
|  | 21.04 |  | User is taken back to MainMenu screen with message saying "WorkGroup suspended, select the wave again to pick."
|  | 21.05 |  | Assigned user can select wave again to continue picking
6 | POS Order Pull | 6.01
6.02
6.03
6.04
6.05
6.06
7 | Inventory Sync | 7.01
7.02
7.03
7.04
7.05
7.06
7.07

## Copy of Go Live Checklist
F2R STORE GO-LIVE CHECKLIST
TASK | DETAILS | COMPLETE? | COMMENTS
GENERAL SETUP
Deposco | Alert Deposco of store roll out schedule. | FALSE
Users | All users are in system. Users can log in. Owner can setup users in Deposco. | FALSE
Groups/Menus | All users are assigned to correct groups/have the correct menus on their handheld. Owner understands functionality related to group configuration. Owner understands how to add/remove applications for groups. | FALSE
Items | All items are loaded in Deposco. Owner can add/remove/change items and understand key attributes on items (shippable, inventory tracking, etc.) Item UPCs (or other scannable values) are loaded in Deposco. | FALSE
Inventory | Upload store inventory to Deposco. | FALSE
Zones | Zones are configured. | FALSE
Locations | All locations are in system. Owner understands how to add/remove locations. Owner understands key attributes on locations (type, storage type, locator, etc.) | FALSE
Containers | Containers are loaded into system | FALSE
PRINTERS
Printer Owner | Owner confirms printer server is setup correctly. Owner can perform basic diagnosis/maintainence of printer server. Resources, Printer Details, and Printer Assignments are set up in Deposco. | FALSE
Paper Printers | All required paper printers are connected to Deposco. | FALSE
STORE SETUP
Devices | Handheld devices are tested and working. Desktop Computers are tested and sucessfully loading the UI. Owner understands how to setup/access Deposco on devices. | FALSE
Internet | Wifi is verified in all areas of the store. | FALSE
Locations | Locations are labeled as needed. | FALSE
Containers | Carts and other containersa are labeled as needed. | FALSE
Items | Items are labeled with relevant item numbers or UPCs. | FALSE
PROCESSES AND SOPs
Putaway | All processes are documented and/or business scenarios have been captured/tested. Owner confirms that the processes in use have been tested and perform the functionality required to handle all business scenarios. | FALSE
Replenishments |  | FALSE
Picking |  | FALSE
Shipping |  | FALSE
Adjustments |  | FALSE
Misc |  | FALSE
TRAINING
Super Users | Owner confirms that Super Users have been adequately trained. Super Users have spent "enough" time in Deposco to feel comfortable in using and support End Users. | FALSE
End Users | End Users have been trained on all relevant functionality/SOPs for their job function. | FALSE
INTEGRATION
Sales Orders | Owner confirms all fields are being pushed to Deposco correctly. | FALSE
Items | Owner confirms all fields are being pushed to Deposco correctly. | FALSE
Adjustments | Owner confirms all fields are being pushed to Deposco correctly. | FALSE
Shipment Confirmation | Owner confirms all fields are being pushed to Shopping Cart correctly. | FALSE
Inventory Sync | Owner confirms all fields are being pushed to Shopping Cart correctly. | FALSE

## Fit2Run Tracking issues
Fit2Run Tracker
5- NTH (Nice to Have)
DESCRIPTION | STATUS | OWNER | Owner | SEVERITY | ETA | Comments
NetSuite to Shopify Celigo Connection | Closed | F2R | Zack | Critical | 2024-08-14 | 1. Zach has identified duplicates, will Delete
NetSuite to Shopify Celigo Connection | Closed | F2R | Sarah | Critical | 2024-08-14 | 2. Delete dupes first that will mark it inactive in netsuite
NetSuite to Shopify Celigo Connection | In Progress | F2R | Sarah | Critical | 2024-08-14 | 3. Mass Update Flow - looking for inventory item id, if it has, it skips, will only get things that are missing
NetSuite to Shopify Celigo Connection | Open | F2R | Sarah | Critical | 2024-08-15 | 4. New creations in NetSuite syncing to Shopify correctly?
Buying team requirements | Closed | F2R | Tim | High | 2024-08-14 | 1. Deposco accounts for all buyers
Buying team requirements | Closed | F2R | Tim | High | 2024-08-14 | 2. Shopify accounts for all buyers
Buying team requirements | Closed | F2R | Tim | High | 2024-08-14 | 3. Initial reporting to Linda
Buying team requirements | Open | F2R | Tim / Deposco | High | 2024-08-16 | 4. Deposco creation of reports
TO's turn on in NetSuite | Open | F2R | Tim | Critical |  | 1. Need confirmation that it's OK to turn on TO synch to Deposco based on flag
Tag printer printing issues | In Progress | F2R | Tim | High | 2024-08-19 | Issue with tags printing correctly on tag printers partly due to custom printer configuration by AllPoint for CHQ printing. Workaround for now is to use CHQ to print tags
Ecom orders being sent to store instead of Deposco | In Progress | F2R | Tim / Deposco | Critical | 2024-08-16 | Ecom orders are being sent to stores for fulfillment instead of Deposco
Amazon seller central inventory | In Progress | Deposco | Tim / Deposco | Critical | 2024-08-16 | Inventory update to Amazon seller central after Shopify sales
Shipping carrier coming into Amazon as Fedex more | Closed | Deposco | Tim / Deposco | Critical | 2024-08-16 | Shipping carrier isn't reflecting correctly in Amazon Seller Central
Tracking number not showing in NetSuite for | In Progress | F2R | Tim / Deposco | High |  | Tracking number not showing in NetSuite
Backorders | In Progress | Deposco | Deposco | Critical | 2024-08-15 | Why orders from before we went live going from Amazon to Deposco
Backorders | In Progress | Deposco | Deposco | Critical | 2024-08-15 | 112 backorders, Deposco receives it, shows we have inventory, go there, no inventory
Backorders | In Progress | Deposco | Deposco | Critical | 2024-08-15 | 49 backorders come in when we had no inventory