## Schedule
JSA Project Tracker
Orientation - Success Criteria/Goals
Goal | Metric | Status
Client Goal #1 | Metric we will use to track | Open
Client Goal #2 | Metric we will use to track | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions | 2025-03-17
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports | 2025-03-25
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | LINK | 2025-03-18 | 2025-03-27
Master Design Document | LINK
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Integrations | ERP/WebStore/ShippingCarrier/ChannelAggregator/EDI - data requirements, troubleshooting steps etc. |  | #REF!
Order Orchestration | Sourcing, Routing, Exception and Backorder Management |  | 0%
Inbound | General Receiving(PO, Blind Receipt, Customer Returns), Move Item, Move Stock, Move Container |  | 100%
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Kit to Stock |  | 86.36%
Outbound II | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking |  | 57.14%
Other - WMS | Transfer orders, 3PL Billing, etc. |  | 0%
Reporting | Report Builder, Dashboard Widgets |  | 0%
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Completion Date
End to End Testing | Testing all process flows with live data end to end | 0%
UAT Onsite Agenda | LINK | 0%
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0%
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0%
Deploy - Go Live
Task/Activity | Description | Delivery Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned.
Deposco Onsite Support | Travel booked for cutover and go-live week.
Project Closeout | Agreement of final deliverables provided.

## Recordings
JSA Demo Videos |  |  |  |  | @
Date | Category | DESCRIPTION | Owner | LINK
Baseline Education
Deposco User Exerience
Master Data / Data Exchange
Process Demos
| Inbound | Copy a PO | Matthew | https://www.loom.com/share/9375ba912f5f4863a1da75705cacfb35
| Inbound | Receiving | Matthew | https://www.loom.com/share/9375ba912f5f4863a1da75705cacfb35
| Inbound | Directed Putaway | Matthew | https://www.loom.com/share/9375ba912f5f4863a1da75705cacfb35
| Inbound | Customer Order Data Exchange | Matthew | https://www.loom.com/edit/dd0348dcacf54333aad3a873f77ba6b6
| Inventory Management | Cycle Count Profile/Copying and Running Scheduler | Matthew | https://www.loom.com/share/5afef6c9ce604d36a2fb328d359a6abb
| Inventory Management | Cycle Count Execution/On Demand Cycle Count | Matthew | https://www.loom.com/share/5afef6c9ce604d36a2fb328d359a6abb
| Inventory Management | Adjust Inventory | Emily | https://www.loom.com/share/0fa8477a7ceb42f4940e0a28ca14b78f?sid=daa147a5-e15d-41e1-91f1-55575afa8402
| Inventory Management | Move Container | Emily | https://www.loom.com/share/f21249a8a775455a838fec8a30ea22e7?sid=b8ec36e2-7087-42ef-aabc-f971dde25b4b
| Inventory Management | Move Stock | Emily | https://www.loom.com/share/46e95a6ebe4f40ffbc9c7db1620823b7?sid=e5fbe1cf-d66b-4ad8-863f-8511035e7f91
| Inventory Management | Create Cycle Count by Item task | Matthew | https://www.loom.com/share/0cbcd979001644878eac924a63a08771
| Outbound | Create Cutomer Orders using COW | Matthew | https://www.loom.com/share/27f57964d2a44b9fbf4f5db426ed7614
| Outbound | Pick a freight order | Matthew | https://www.loom.com/share/b96abc3e5d47499b8035f2e1ee8e6058
| Outbound | Pick a UPS/ Fed Ex order | Matthew | https://www.loom.com/share/9c2d5c9f8b094e0fbe8a6e9b9060a81b
| Outbound | Packing freight and UPS/FedEx | Matthew | https://www.loom.com/share/794a10c59627488491f25b6e6fea1f8e
| Outbound | Freight end to end process | Matthew | https://www.loom.com/share/4d6c38c0649e43e4b1cfeb200bb31894
| Outbound | Customer Order in Review Status | Matthew | https://www.loom.com/share/430db3b93ff045a296278ad8448f955c
Miscellaneous Demos
Testing/Training Support

## Task Tracker
JSA Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | LOE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | DEP Comments | XXX Comments
Design | Reporting | Gather Current Hazmat documents, Packing Slips, BOLS | Task |  |  | FALSE | FALSE | Resolved | DEP/JSA |  |  | 2025-04-02 | DEP to review during the status call 4/2. Received the details DEP needs
Design | Billing | Gather Rate Card/Example invoice | Task |  |  | FALSE | FALSE | Completed | DEP/JSA
Orientation | Integrations | UPS set up | Task |  |  | FALSE | FALSE | Open | JSA
Orientation | Integrations | Fedex Set Up | Task |  |  | FALSE | FALSE | Open | JSA
Orientation | Integrations | Single Netsuite Instance Set up | Task |  |  | FALSE | FALSE | Open | JSA
Orientation | Printing | Print Client/Server Set up | Task |  |  | FALSE | FALSE | Open | JSA
Orientation | Data Exchange | Item DE Updates for Hazmat | Task |  |  | FALSE | FALSE | Open | JSA
Orientation | Demo | Demo prep. Example scripts and demo | Receiving, Batch Picking, Single Scan Picking |  |  | FALSE | FALSE | Completed
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task |  |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Setup Client Mavenlink Account | Setup SX with tenant code and General / Project Management tasks | Task |  |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task |  |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task |  |  | FALSE | FALSE | Completed | DEP | PM
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task |  |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task |  |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task |  |  | FALSE | FALSE | Completed | DEP | Business Consultant
Orientation | Begin development for new socket APIs | Deposco Socket team begins development for new socket APIs as per initial project SOW | Task |  |  | FALSE | FALSE | Open | DEP | Business Consultant
Orientation | Setup Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network 2) Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task |  |  | FALSE | FALSE | Open | DEP/JSA | Business Consultant / Technical Lead
Orientation | Setup Exisiting Sockets | Client utilizes Deposco help site guides to setup existing socket connections | Task |  |  | FALSE | FALSE | Open | XXX | Technical Lead
Orientation | General Application and UI Overview | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Message Center Overview - Handheld Menu Access | Task |  |  | FALSE | FALSE | Open | DEP/XXX | Full team
Orientation | Begin Master Data Gathering | Sample Master Data templates for items, packs, locations, zones, storages, etc. to be provided by Deposco to be used by client | Task |  |  | FALSE | FALSE | Open | XXX | Client team
Orientation | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task |  |  | FALSE | FALSE | Open | XXX | Warehouse Leads
Orientation | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task |  |  | FALSE | FALSE | Open | XXX | Inbound Lead
Orientation | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task |  |  | FALSE | FALSE | Open | XXX | Outbound Lead / Customer Service Lead
Orientation | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task |  |  | FALSE | FALSE | Open | XXX | Outbound Lead
Orientation | Schedule recurring project calls | Weekly status call Bi-weekly executive steering call | Task |  |  | FALSE | FALSE | Open | DEP | PM
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task |  |  | FALSE | FALSE | Completed | DEP | Emily
Design | Master Design Document Delivery | Deliver master design document for client team to review | Task |  |  | FALSE | FALSE | Completed | DEP | Solution Lead |  | 2025-04-09
Design | Review and Sign Master Design Document | Client to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task |  |  | FALSE | FALSE | Completed | DEP/JSA | Full Team |  | 2025-04-23 | 5/1: Submitted for signature 4/29: Received approval to be submitted for signature
Configuration | Screen Adjustments | Standardize screen language across all processes. ex. make everything that could be lpn say LPN: | Task | 2 |  | FALSE | FALSE | Completed | DEP | Matthew
Configuration | Layout Adjustments | Remove id from every entity layout/view | Task | 0.5 |  | FALSE | FALSE | Completed | DEP | Matthew
Configuration | Group Management | Set up group permissions for JSA (general picking/restricted picking) | Task | 0.5 |  | FALSE | FALSE | In Progress | DEP | Matthew |  | 2025-05-30 | 5/6: Matthew to review and complete by EOW 5/13: Still in progress
Configuration | Data Exchange | Carrier Special Services Data Exchange | Task | 0.5 |  | FALSE | FALSE | Completed | DEP | Matthew
Configuration | Data Exchange | Add lpn number to stock unit import | Task | 0.5 |  | TRUE | FALSE | Completed | DEP | Matthew |  | 2025-04-03
Admin | New Integrations | Research integrations needed by JSA - if do not exist, then find alternatives. Work with sales and eventually create new SOW | Task |  |  | FALSE | FALSE | Completed | DEP | Isaac |  | 2025-04-04 | 4/8: DEP to schedule meeting once Fernando is back
Admin | CoWorkbench | Work internally/review JSA's requirements | Task |  |  | FALSE | FALSE | Hold | DEP | Isaac |  | 2025-04-04 | 5/27: On hold, DEP is following up internally. Unlikely to be picked up by Product
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task |  |  | FALSE | FALSE | Open | XXX | Inbound Lead
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task |  |  | FALSE | FALSE | Open | XXX | Inventory Lead
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  |  | FALSE | FALSE | Open | XXX | Outbound Lead
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task |  |  | FALSE | FALSE | Open | XXX | Outbound Lead
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task |  |  | FALSE | FALSE | Open | XXX | Technical Lead
Validation | End to End Test Case Execution | Complete end to end test cases | Task |  |  | FALSE | FALSE | Open | XXX | Warehouse Leads + Technical Lead
Validation | Deliver Onsite UAT Agenda |  | Task |  |  | FALSE | FALSE | Open | DEP | Implementation Lead
Validation | Train End Users | During UAT and any additional training as needed | Task |  |  | FALSE | FALSE | Open | XXX | Warehouse Leads
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task |  |  | FALSE | FALSE | Open | DEP/XXX | Full team
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task |  |  | FALSE | FALSE | Open | DEP | PM
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task |  |  | FALSE | FALSE | Open | DEP | Implementation Lead
Deployment | Execute Cutover Plan Steps |  | Task |  |  | FALSE | FALSE | Open | DEP/XXX | Full team
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task |  |  | FALSE | FALSE | Open | DEP | PM
Configuration | Master Data | Upload Locations and Zones | Task |  |  | FALSE | FALSE | Completed | JSA | Claudia |  | 2025-04-09 | 5/6: Claudia in process of review of MD and will let DEP team know once she is ready 5/13: Items and Location uploaded, at least to be able to start testing. Need to import Hazmat items and Carrier Special Services.
Configuration | Master Data | Upload AZELIS Items, packs, upcs | Task |  |  | FALSE | FALSE | Completed | JSA | Claudia |  | 2025-04-09 | 5/6: Claudia in process of review of MD and will let DEP team know once she is ready 5/13: Items and Location uploaded, at least to be able to start testing. Need to import Hazmat items and Carrier Special Services.
Configuration | Master Data | Upload other Business Units Items, packs, upcs | Task |  |  | FALSE | FALSE | Completed | JSA | Claudia |  | 2025-04-09 | 5/6: Claudia in process of review of MD and will let DEP team know once she is ready 5/13: Items and Location uploaded, at least to be able to start testing. Need to import Hazmat items and Carrier Special Services.
Configuration | Waving | Complex wave - Confirm that this is only orders with a drum or IBC pack type should be complex Confirm 3 wave types: Complex LTL Orders, Simple LTL Orders, Parcel orders | Task |  |  | FALSE | FALSE | Resolved | JSA |  |  | 2025-04-09 | Need JSA to confirm if this is good? 4/8: DEP received the details last week and good to close
Configuration | Putaway Logic | Define instructions you tell your users when restricting where items can be placed. Example: Cold items need in cold room, flammables cannot go next to corrosives etc. | Task |  |  | FALSE | FALSE | Resolved | JSA | Claudia |  | 2025-04-09 | 4/8: DEP able to confirm Putaway and Waving during the call 4/4
Configuration | Deposco Universtiy | Complete DEP university | Task |  |  | FALSE | FALSE | In Progress | JSA | JSA Team |  | 2025-04-09
Configuration | Reporting | BOL Creation | Task | 4 |  | FALSE | FALSE | Validation | DEP | Matthew |  | 2025-05-30 | 5/20: Emily to review 5/6: Emily to review by EOW 4/8: Emily to review the BOL
Configuration | Reporting | Billing Invoice Creation | Task | 4 |  | FALSE | FALSE | Closed | DEP | Matthew |  | 2025-04-04
Configuration | Reporting | Pre-generated lpn label/handheld button (add # copies in hh) | Task | 2 |  | FALSE | FALSE | Completed | DEP | Matthew |  | 2025-04-03
Configuration | Reporting | Item label |  | 1 |  | FALSE | FALSE | Completed | DEP | Matthew |  | 2025-05-13 | 5/13: Emily to make final changes/updates ETA: 4/25
Admin | Post Design | Schedule putaway and waving discussion | Task |  |  | FALSE | FALSE | Completed | DEP/JSA | Emily |  | 2025-04-04
Configuration | Printers | Work with Verity to set up print client | Task | tbd |  | TRUE | FALSE | In Progress | DEP | Claudia |  | 2025-04-11 | 5/27: Emily to schedule meeting 5/20: No update, DEP waiting for confirmaiton for Printers onsite 5/13: Need JSA team to confirm printers 5/6: Documentation provided, waiting for feedback from JSA team 4/8: Emily to send documentation for setup, once reviewed, DEP to schedule to meeting as needed
Configuration | Data Exchange | - Update a field on item to be used as Carbon Black Item - add to item field mapping - Update a field on company to be used as Priority - add to company field mapping | Task | 0.5 |  | FALSE | FALSE | Completed | DEP | Matthew |  | 2025-06-06 | 5/6: Matthew to review
Configuration | Reporting | Inventory Report | Task | 0.5 |  | FALSE | FALSE | Validation | DEP | Matthew |  | 2025-05-09 | 5/6: Work completed, in Validation
Configuration | Reporting | Waiting to putaway report | Task | 0.5 |  | FALSE | FALSE | Validation | DEP | Matthew |  | 2025-05-09 | 5/6: Work completed, in Validation
Configuration | Reporting | Stock on Dock report | Task | 0.5 |  | FALSE | FALSE | Validation | DEP | Matthew |  | 2025-05-09 | 5/6: Work completed, in Validation
Configuration | Socket Alerts | Failed shipnotice/order updates socket alert set up | Task | 1 |  | FALSE | FALSE | Completed | DEP | Matthew
Deployment |  | Ad hoc cycle count recording for Fernando | Request | 1 | 4.Low | FALSE | FALSE | Open | DEP | Matthew |  | 2025-06-02
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE
[6 empty] | FALSE | FALSE

## DEP Config Tasks
Deposco Configuration Task List
Product / Task Group | Task | SOW Notes | In Scope | Post Design - Configuration Notes | Owner | Status | % Complete | LOE | Questions/Concerns
Bright Warehouse Configuration (T&M)
Master Data | Data Exchange |  | FALSE | Review existing master data - do we need a working session with Claudia to get master data uploaded? - draft email to check in on status of master data upload |  |  |  | 0.5
Inbound | Receiving |  | FALSE | Set up receiving process according to assuptions in mdd | Matthew | Complete | 0% | 3 | Need to discuss item label fields containing SU information
Inbound | Receiving |  | FALSE | Image capture in receiving | Emily | Complete | 0% | 2 | in identifer input screen, but can be added after each item is received. screen xaml and rules updated
Inbound | Returns |  | FALSE | Set up returns receiving process according to assuptions in mdd | Matthew | Complete | 0% | 1
Inbound | Directed Putaway |  | FALSE | - Matthew to see if zone limiations can be accomplished through SI's or if rules are needed | Matthew | Complete | 0% | 1
Inbound | Unit Test Cases |  | FALSE | Test case creation | Matthew | Complete | 0% | 2
Inbound | Post demo task |  | FALSE | Deposco to change the Receiving process so the Print Labels button defaults to "Yes". | Matthew | Complete |  | 1
Inbound | Post Demo Task |  | FALSE | Listbox override to display item description and qty | Emily | To-Do
Inventory Management | Cycle Counting |  | FALSE | Configure/validate CC by BU works as expected | Matthew | Complete | 0% | 2
Inventory Management | Cycle Counting |  | FALSE | Configure/validate all cc processes based on assumptions in mdd - on demand - execute cc by item/location | Matthew | Complete | 0% | 2 | How can I assigned a user to do a cycle count? Fernando
Inventory Management | Inventory Adjustment |  | FALSE | Configure/validate adjustment processes based on assumptions in mdd - limit to a more inventory admin group - update reason codes | Matthew | Complete | 0% | 1
Inventory Management | Unit Cases |  | FALSE | Test case creation | Matthew | Complete | 0% | 2
Outbound | Outbound Order Management |  | FALSE | Configure sourcing/routing profiles (pg 58 mdd) | Emily | Complete | 0% | 5
Outbound | Outbound Order Management |  | FALSE | Configure POI/automation to define order restrictions/priority | Emily | Complete | 0% | 10
Outbound | Pickwave Management |  | FALSE | Edit WorkTask.getSingleTangiblePickTaskByLocationOrder is a config query we can customize so we can change the order by clause to look at pack types | Kevin | To-Do | 0% | 10
Outbound | Pickwave Management |  | FALSE | Create pickwaves using order fulfillment profiles - if this doesnt work we can go back to pwbp | Matthew | Complete | 0% | 10 | ETA from dev- wednesday DEPWMS-5290
Outbound | Picking |  | FALSE | Batch Picking - add oh.customAttribute4, BU, shipVia to the picking screen - print item code label | Emily | In Validation | 0% | 8
Outbound | Picking |  | FALSE | Single Scan Picking - add oh.customAttribute4, BU, shipVia to the picking screen - - print item code label | Matthew | In Validation | 0% | 8
Outbound | Picking |  | FALSE | repurpose line for item code on orderline | Emily | Complete
Outbound | Picking |  | FALSE | Create item code label and printing rules | Emily | In Validation
Outbound | Unit Cases |  | FALSE | Test Cases pt1 |  | Complete
Outbound | Packing and Shipping |  | FALSE | Single Scan Packing - bol printing rules (print 2 copies) | Matthew | In Validation | 0% | 4
Outbound | Packing and Shipping |  | FALSE | Assign Trip (soft close) - bol printing rules (print 2 copies) | Matthew | In Validation | 0% | 4
Outbound | Packing and Shipping |  | FALSE | Manual close Trip | Matthew | Complete | 0% | 1
Outbound | Packing and Shipping |  | FALSE | Repalletize | Matthew | Complete | 0% | 1
Outbound | Packing and Shipping |  | FALSE | void and reprocess shipment | Matthew | Complete | 0% | 0.5
Outbound | Packing and Shipping |  | FALSE | rollback order |  | Complete | 0% | 0.5
Outbound | Unit Cases |  | FALSE | Test Cases pt2 |  | Complete
Other | 3PL Billing |  | FALSE | Handling Hazmat |  | In Validation | 0% | 4
Other | 3PL Billing |  | FALSE | Handling Non Hazmat |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | Lot Reporting |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | Labeling.Marking, Tagging |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | Order Processing |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | Recurring Storage |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | Initial Storage |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | Initial Split Month Storage |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | UPSfedex box |  | In Validation |  | 4
Other | 3PL Billing |  | FALSE | UPS/fedex prep |  | In Validation |  | 4
|  |  | FALSE | Ad hoc billing |  | In Validation |  | 4
Integrations | Quickbooks Online |  | FALSE | Set up quick books online
Outbound | Rate Shopping |  | FALSE |  | Matthew, _ | To-Do | 0% | 10
Outbound | EDI Fulfillment |  | FALSE |  |  |  | 0%
Other | Transfer Orders |  | FALSE |  |  |  | 0%
Other | Shipping Documents/Labels |  | FALSE |  |  |  | 0%
Other | 3PL Billing |  | FALSE |  |  |  | 0%
Setup | System Admin |  | FALSE |  |  |  | 0%
Setup | Data Maintenence |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M)
Configure | Web Store |  | FALSE |  |  |  | 0%
Configure | Retailer |  | FALSE |  |  |  | 0%
Configure | EDI Fulfillment |  | FALSE |  |  |  | 0%
Configure | Marketplace |  | FALSE |  |  |  | 0%
Configure | ERP/Accounting |  | FALSE |  |  |  | 0%
Configure | Carrier |  | FALSE |  |  |  | 0%
Configure | Shopify |  | FALSE |  |  |  | 0%
Configure | Quickbooks Online |  | FALSE |  |  |  | 0%
Configure | UPS |  | FALSE |  |  |  | 0%
Configure | FedEx |  | FALSE |  |  |  | 0%
Bright Performance Configuration (T&M)
Standard Dashboard and Reporting | Global Reports |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Company Reports/Report Builder |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Report Scheduling |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Dashboards |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Report Models |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Report Scheduling |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Data Archive |  | FALSE |  |  |  | 0%
Bright Order Configuration (T&M)
Configure - Order Orchestration | Preprocessing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Sourcing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Routing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Release |  | FALSE |  |  |  | 0%
Configure - Order Processing | Order Management |  | FALSE |  |  |  | 0%
Configure - Order Processing | Order Exception Management |  | FALSE |  |  |  | 0%
Configure - Enterprise Inventory | Enterprise Inventory Management |  | FALSE |  |  |  | 0%
Configure - INventory Segmentation | Manage Segments |  | FALSE |  |  |  | 0%

## Test Cases - Unit
JSA Unit Test Cases |  | Category | % Complete
|  | Order Orchestration | 0%
|  | Inbound | 100%
|  | Inventory Management | 86.36%
|  | Outbound | 57.14%
|  | Other WMS | 0%
|  | Reporting | 0%
|  | TOTAL | 19.3%
Category | Subcategory | Scenario | Steps | Step Details | Expected Outcome | Owner | Status | Test Data | Comments
Order Orchestration
Order Orchestration | Preprocessing - Data Validations | Ship Via missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual)
Order Orchestration | Preprocessing - Data Validations | Ship To Address info missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual)
Order Orchestration | Preprocessing - Data Validations | Trading Partner missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual)
Order Orchestration | Preprocessing - Data Validations | Line Item info missing on CO |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual)
Order Orchestration | Preprocessing - Data Validations | Multiple data validations are triggered on CO |  | Order goes to Review status until all data is fixed and re-processing has been run (scheduled or manual)
Order Orchestration | Preprocessing - Data Validations | Duplicate order warning is triggered |  | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  |  | Ready to Test
Order Orchestration | Preprocessing - Data Validations | No data validation is triggered |  | Order is either Back Ordered or Released automatically upon creation |  |  | Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection | Order/order line meets ____ criteria |  | Order sources to Sourcing Group A based on sourcing profile. |  |  | Ready to Test
Order Orchestration | Order Sourcing - Sourcing Group Selection | Order/order line meets no matching Sourcing Selection Criteria |  | Order goes to Review with CoNotice message that sourcing could not be completed |  |  | Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile | Order meets ____ criteria |  | Order uses Routing Profile A based on routing selection profile. |  |  | Ready to Test
Order Orchestration | Order Routing - Routing Selection Profile | Order meets no matching Routing Selection Criteria |  | Order goes to Back Order |  |  | Ready to Test
Order Orchestration | Order Release - Available Inventory | Inventory not available to fulfill entire CO in facility A |  | CO Back Orders |  |  | Ready to Test
Order Orchestration | Order Release - Available Inventory | Inventory is available to fulfill entire CO in facility A |  | CO Releases to facility A and creates an SO |  |  | Ready to Test
Order Orchestration | Order Management - Scheduled Routing | Scheduled re-route attempt on orders in Back Order status |  | Orders in Back Order automatically re-routed ever x hours. Order either stays in Back Order or moves to Released if inventory now available. |  |  | Ready to Test
Order Orchestration | Order Exception Management - Reprocess | Manual Reprocess CO in Review status |  | Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  |  | Ready to Test
Order Orchestration | Order Exception Management - Reprocess | Scheduled Reprocess CO in Review status |  | Orders in Review automatically reprocessed every x hours. Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  |  | Ready to Test
Order Orchestration | Enterprise Inventory Management | Inventory by Facility |  | Reports execute timely and accurately for all skus |  |  | Ready to Test
Order Orchestration | Inventory Segmentation - Manage Segments | [5 empty] | Ready to Test
Inbound
Inbound | Purchase Orders | Receive a Purchase Order | 1.01 | Select Receiving from Inbound menu on Handheld | User will notice that Stock has been created within the system. | JSA Team | Pass |  | on the handheld we noticed that it wont let you go to th next step after hitting enter after entering qty of printing labels it takes you back to package type – please provide test order /// When receiving damage material what would be the procces, for example the PO is for 10 bags and one bag was found damage. What would it be the proccess, to add a comment / receive on the Handheld. (Fernando) - -Need and option for exceptions/comments: on the receiving side- just incase a material comes in damaged. (Fernando) How can we put items on Hold, sometimes we received material with missing seals not damage. (fernando) -- Also, I wanted to ask—since we typically take photos of damaged products, is it possible to upload those pictures directly into Deposco? It would be really helpful to have everything in one place, so we can easily reference the photos and share them from within Deposco when needed.(Fernando) [DEP]: For damaged goods, you will need to receive onto a new pallet and then put that pallet of damaged goods into a "Damaged Goods" location. You can then use Adjust Inventory to remove the inventory from stock as needed. - You can now add notes to recepts (by order line) in the receiving process - To put items on hold, you can change the Stock Unit Status to Hold so the inventory does not allocate to outbound orders
|  |  | 1.02 | Enter/Scan the Order Number / Order Identifier
|  |  | 1.03 | Hit Enter or Click Submit
|  |  | 1.04 | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box)
|  |  | 1.05 | Select the pack type of the item and key in the quantity being received.
|  |  | 1.06 | Hit Enter
|  |  | 1.07 | Keep repeating step 1.04 - 1.06 if there are multiple items in the order that you are receiving until all items have been received
Inbound | Blind Receipt / Blind RMA Receiving (as Necessary) | Receive a Blind Order | 2.01 | Navigate to Receiving | User will notice that Stock has been created within the system. | JSA Team | Pass |  | we need to be able to search item by descrition and not by SKU as product comes in with description and not the SKU DEP: This is changed
|  |  | 2.02 | Enter identifier for blind order. A message will pop up that says "No records found matching that identifier, click Next to continue as Blind Order"
|  |  | 2.03 | Click Next
|  |  | 2.04 | Scan the item barcode of the item being received (no items will appear in list box) Scan also the LPN that the item is being received onto
|  |  | 2.05 | Select the pack type of the item and key in the quantity being received
|  |  | 2.06 | Enter the LOT number and EXP of the item being received
|  |  | 2.07 | Repeat steps 2.04-2.06 until all items on the PO have been received and select Finish when done
|  |  | 2.08 | After user scans all Items to receive, the inentory will be cedited to the Receiving location for staging.
Inbound | UnReceiving | Unreceive previously received order | 3.01 | Select UnReceiving from Inbound menu on Handheld | User will see a validation message on the same Select Item to UnReceive screen letting them know that they have successfully UnReceived the selected item. | JSA Team | Pass |  | how can i unreceive a blind shipment? (Edgar) Quick question, how can I see the pictures that we take? were in Deposco? (fernando)
|  |  | 3.02 | Scan/Key in a PO # that a user has previously received
|  |  | 3.03 | Scan the item and input the quantity in which the user would like to UnReceive
|  |  | 3.04 | Select Submit
Inbound | Directed Putaway | Putaway of received items to pickable locations | 4.01 | Navigate to "Directed Putway" under JSA Inbound on handheld MainMenu | This process allows a user to move items on an LPN out of a location and into a different location determined by the system Stock units that were moved are decremented from their source location, and are created in the destination location | JSA Team | Pass |  | Unable to use locations for multiple put aways. (Edgar) - I'm trying to entered PO#7014, LPN#106 but it would not let entered because it has multiple items. (Fernando) please check JSA@deposco email DEP: For LPNs that have multiple items, please refer to the Move LPN process in the Inventory Management section of this sheet for putaway
|  |  | 4.02 | Press "Putaway" button
|  |  | 4.03 | Scan/ enter LPN number (pallet that you are putting away)
|  |  | 4.04 | 6
|  |  | 4.05 | See and confirm Task, Location, and putaway LPN counts. Press Submit button
|  |  | 4.06 | Scan/ enter location locator displayed on putaway screen, or enter alternate location
|  |  | 4.07 | Confirm Putaway Load Complete information (this summarizes what you just completed). Press Continue button
Inbound | Returns Receiving | Receive returns order | 5.01 | Navigate to the "Receiving" button under Inbound | User will notice that Stock has been created within the system. | JSA Team | Pass | `
|  |  | 5.02 | User enters Customer Return Order number they wish to receive (The number that is entered cannot match that of any existing order).
|  |  | 5.03 | Scan/Enter the Item(s) you are receiving. Confirm the Pack in the List Box. Scan/ enter the LPN the inventory is being received on (scan LPN label)
|  |  | 5.04 | Select the pack. Key in the quantity of the receipt. If the item is lot/expiration tracked, the user must also key in the lot/expiration date for the inventory they are receiving.
|  |  | 5.05 | Keep repeating step 5.03 and 5.04 if there are multiple items in the order that you are receiving.
|  |  | 5.06 | After user scans all Items to receive, the inventory will be cedited to the Returns location for staging.
Inbound | Purchase Order | Incorrect PO# Entry | 6.01 | Select Receiving from Inbound menu on Handheld | A message should dispay reading, "No records found matching that identifier, click Next to continue as Blind Order." | JSA Team | Pass
|  |  | 6.02 | Enter a PO Number that does not exist
Inbound | Purchase Order | Scanning Already Received PO | 7.01 | User enters Receiving Process | User will be prevented from continuing with the process. Error message appears reading, "". | ] | Pass |  | error messge on handheld no record found that idrentifer click next to continue as blind order - this is a pass bc you were not able to receive against the original PO
|  |  | 7.02 | User scans a Purchase Order that has already been received instead of a new Purchase Order
Inbound | Purchase Order | Receiving an Item not on a PO | 9.01 | User will enter receiving transaction | Error message appears reading, "Unable to find order line for item: [PO Number]." | JSA Team | Pass | Edgar and Fernando tested, and it was a Pass "got error measage as expected" | handheld entered po and let us enter product not on the po and asked for LPN - can you please provide the order number. we did not see this behavior and assume you saw this because you were receiving a blind order
|  |  | 9.02 | User scans/Keys an Item not on PO for receiving
|  |  | 9.03 | User will be prevented from receiving the item in the process
Inbound | Purchase Order/ Returns Receiving | Negative Item Qty Entry | 10.01 | During Receiving, user keys in a negative quantity to be received | Error message appears reading, "Please enter a valid quantity." | JSA Team | Pass
|  |  | 10.02 | User will be prompted to re-enter quantity
Inbound | Purchase Order/ Returns Receiving | Invalid Item Qty Entry | 11.01 | During Receiving, user keys in an invalid number like "2YN" | Error message appears reading, "Please enter a valid quantity." | JSA Team | Pass
|  |  | 11.02 | User will be prompted to re-enter quantity
Inventory Management
Inventory Management | On Demand Cycle Count via Handheld | Cycle Counting on demand | 1.01 | User notices a location that may need to be cycle counted | A cycle count task with status NEW should be generated for the specified location with the specified priority. After counting, if a variance is detected, then a new entry is created in the Approve Variances screen (Under Inventory Admin in the Application Menu) |  | Pass |  | One user at JSA had trouble with the back button but mine worked when hitting return on the keyboard
|  |  | 1.02 | User enters "On Demand Cycle Count" through the JSA Inventory handheld menu
|  |  | 1.03 | User enters the location and priority (1-10 w/1 being highest priority) for the cycle count. Priority defaults to 5 if left empty.
|  |  | 1.04 | The Parent LPN Screen will show the Location along with the LPN in the Location and # of items. User will scan the LPN barcode on the pallet's label
|  |  | 1.05 | User will be shown a list box with items on the scanned LPN that can be cycle counted
|  |  | 1.06 | User will scan SKU and hit enter
|  |  | 1.07 | On the next screen, user will select the pack type and enter the quantity they counted. They will also be prompted to enter the LOT number of the item they are counting.
|  |  | 1.08 | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  |  | 1.09 | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  |  | 1.1 | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
Inventory Management | Manage Cycle Count Variances | Accept, Reject, or Recount Variances | 2.01 | User (typically a supervisor or manager) will enter the "Manage Cycle Count Variances" UI through a laptop or desktop, located under Inventory Admin in the Application Menu | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances". |  | Pass
|  |  | 2.02 | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system.
|  |  | 2.03 | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted.
|  |  | 2.04 | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted).
Inventory Management | Location Cycle Count Creation via Scheduler | Create Cycle Count tasks by location | 3.01 | In order for the scheduler to create cycle count queue tasks, make sure Cycle Count checkbox is checked for the locations that support cycle counting. Scheduler will look at Iocation's Last Counted Date and Cycle Count Frequency fields. |  |  | Pass |  | What would be the next step, execute cycle count on that epecific loacation? who can create location cycle count? (order pickers or upper management?) Can you give us an example of why would a WHSE order picker will need to do create location cycle count. For example we did create a location cycle count
|  |  | 3.02 | Run the scheduler "Create Cycle Count Tasks by Location ()" under SchedulerTask application (under Setup in the application menu)
|  |  | 3.03 | Cycle count tasks for locations that require a cycle count will appear in the Cycle Count Queue table with status NEW
Inventory Management | Item Cycle Count Creation via Scheduler | Create Cycle Count tasks by Item | 4.01 | In order for the scheduler to create cycle count queue tasks, make sure Cycle Count checkbox is checked for the items and locations that support cycle counting. Scheduler will look at Iocation's Last Counted Date and Cycle Count Frequency fields. | For item counts, the scheduler task evaluates which items require a cycle count based on business unit and generates the task in the Cycle Count Queue table |  | Pass
|  |  | 4.02 | Run the scheduler "Create Cycle Count Tasks by Item ()" under SchedulerTask application (under Setup in the application menu)
|  |  | 4.03 | Cycle count tasks for items that require a cycle count will appear in the Cycle Count Queue table with status NEW
Inventory Management | Perform Item Cycle Count | Perform previously created cycle count tasks (by item) | 5.01 | Cycle Count task is already created via scheduler | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. 3) If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. |  | Pass |  | I tried to create a cycle count for Nagase and I dont see the Cycle count Profile List I see it in the Schedular and record selector but not in the Cycle count profile What am I missing CL DEP: You were missing the Cycle Count Profile. This has now been added and joins the Scheduler to the Record Selector
|  |  | 5.02 | Navigate to handheld menu and select "Execute Cycle Count" under JSA Inventory.
|  |  | 5.03 | Enter user's start off location.
|  |  | 5.04 | User is prompted to go to the first location to count.
|  |  | 5.05 | After scanning the location, user is shown a listbox of available SKUS to cycle count. User must scan or select which item to cycle count and hit enter.
|  |  | 5.06 | User selects pack type and enters counted qty.
|  |  | 5.07 | The counted item is marked with an asterisk to track what has been counted. User can repeat steps 4 and 5 if more items need to be counted.
|  |  | 5.08 | After user is finished cycle counting items, user can hit Next Location and will be prompted to the next location that requires a cycle count, if any
Inventory Management | Perform Location Cycle Count | Perform previously created cycle count tasks (by location) | 6.01 | Cycle Count task is already created via scheduler | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. More info on this in the next test script. |  | Pass
|  |  | 6.02 | Select "Execute Cycle Count" button in handheld menu from JSA Inventory
|  |  | 6.03 | Scan or enter starting location and hit enter
|  |  | 6.04 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  |  | 6.05 | User will scan the location they're directed to
|  |  | 6.06 | User will be shown a list box with items in location needing to be cycle counted.
|  |  | 6.07 | User will scan SKU and hit enter
|  |  | 6.08 | On the next screen, user will select the pack type and enter the quantity they counted
|  |  | 6.09 | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  |  | 6.1 | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  |  | 6.11 | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
Inventory Management | Manage Cycle Count Variances | Accept, Reject, or Recount Variances | 7.01 | User (typically a supervisor or manager) will enter the "Manage Cycle Count Variances" UI through a laptop or desktop, located under Inventory Admin in the Application Menu | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances". |  | Pass
|  |  | 7.02 | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system. |  |  | Pass
|  |  | 7.03 | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted. |  |  | Pass
|  |  | 7.04 | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted). |  |  | Pass
Inventory Management | Adjust Inventory | Add Inventory to a Location | 8.01 | Select "Adjust Inventory" from the JSA Inventory menu | 1) After items have been confirmed and the user clicks commit, user is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" 2) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 3) Updates made to Item's SU in location |  | Pass |  | I tested and had no problems CL
|  |  | 8.02 | Scan/key in Location
|  |  | 8.03 | Select "Create Inventory"
|  |  | 8.04 | Select the Business Unit that the user will be creating Inventory for
|  |  | 8.05 | Scan Item SKU
|  |  | 8.06 | Enter quantity of item's SU you want to create. User can optionally enter serial, lot, and LPN #.
|  |  | 8.07 | If you have more than one item's SU you want to create, click next and repeat steps 8.04 and 8.05
|  |  | 8.08 | Once finished, click Confirm
|  |  | 8.09 | Once final reviewing all items, select Reason Code and click Commit
Inventory Management | Adjust Inventory | Consume All Inventory in Location | 9.01 | Select "Adjust Inventory" from the JSA Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location |  | Pass |  | I tested and had no problems CL
|  |  | 9.02 | Scan/key in Location
|  |  | 9.03 | Select "Consume All in Location"
|  |  | 9.04 | Select Reason Code and Click Commit
Inventory Management | Adjust Inventory | Consume by LPN | 10.01 | Select "Adjust Inventory" from the JSA Inventory menu | 1) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location |  | Pass |  | I tested and had no problems CL
|  |  | 10.02 | Scan/key in Location
|  |  | 10.03 | Select "Consume By LPN"
|  |  | 10.04 | Scan/ Enter LPN Number
|  |  | 10.05 | See and confirm SKU(s) on LPN Press Confirm
|  |  | 10.06 | Review SKU's and quantities Press Commit
Inventory Management | Move Inventory | Move Stock | 11.01 | Navigate to "Move Stock" under JSA Inventory on handheld MainMenu |  |  | Pass
|  |  | 11.02 | Container field displays the cart in which you want to put the stock you are wanting to move (default cart will be user's username)
|  |  | 11.03 | Enter or scan location with the stock you want to move
|  |  | 11.04 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 11.05 | Select Pack UOM and enter in quantity to move and select Submit
|  |  | 11.06 | Repeat steps 11.04-11.05 to move more items in the location
|  |  | 11.07 | When finished, select Move Source Screen
|  |  | 11.08 | User is given a summary of the number of unique Skus and quantity in cart. If user wants to move stock in a different location, User can scan another location.
|  |  | 11.09 | Otherwise, User can select "Move" or "Move Full" to move the stock to a directed location
|  |  | 11.1 | User enters quantity and selects/scans item
|  |  | 11.11 | A listbox of suggested putaway locations is displayed. User must select or scan a location to move the stock | When all stock has been moved successfully, a message displays on menu saying "All Items Moved."
|  |  | 11.12 | User repeats 11.10-11.11 to move the rest of the stock, if any
|  |  | 11.13 | Otherwise, User can select All to move all of the stock in the cart and then scan the destination location of where the stock should be moved | Picking Cart (user's username) is now empty and remains in its original location. Stock units that were moved are decremented from their source location, and are created in the destination location
Inventory Management | Move Inventory | Move LPN | 12.01 | Navigate to "Move Container" under JSA Inventory on handheld MainMenu |  |  | Pass
|  |  | 12.02 | Scan the container that you want to move.
|  |  | 12.03 | Move the container to the destination location. Then scan the destination location and select Move | The location field for the container is updated to the location to which the container was moved and the location field for any stock units in the container is updated to the location to which the container was moved.
Inventory Management Edge Cases
Inventory Management | Cycle Counting | Ad-Hoc Cycle Count - Counting Less than the Item's Qty | 1.01 | User selects "On Demand Cycle Count" from Inventory menu | Tasks will be generated in the "Manage Cycle Count Variances" UI for a manager or supervisor to review. If qty count entered is less than the system's qty, a negative variance qty will be displayed for that item in "Manage Cycle Count Variances" |  | Pass
|  |  | 1.02 | User will enter quantity less than the item's SU quantity currently in Deposco's system
|  |  | 1.03 | User will be asked to recount and will proceed to re-enter the quantity.
Inventory Management | Cycle Counting | Ad-Hoc Cycle Count - Counting More than the Item's Qty | 2.01 | User selects "On Demand Cycle Count" from Inventory menu |  |  | Pass
|  |  | 2.02 | User will enter quantity more than the item's SU quantity currently in Deposco's system
|  |  | 2.03 | User will be asked to recount and will proceed to re-enter the quantity. | Tasks will be generated in the "Manage Cycle Count Variances" UI for a manager or supervisor to review. If qty count entered is more than the system's qty, a negative variance qty will be displayed for that item in "Manage Cycle Count Variances"
Inventory Management | Cycle Counting | Cycle Counting - Scanning incorrect Location | 3.01 | Select Execute Cycle Count button in handheld menu from Inventory |  |  | Pass |  | Is it possible to search by Item Description? For example, item 100679371 corresponds to Argimel, but if the bag is missing the item code label, there's no way to identify it unless we can search by the description. Currently, when searching for items under the "Item List" in Deposco, the item description does not appear. This makes it difficult to identify items without their codes. (Fernando)
|  |  | 3.02 | Scan or enter starting location and hit enter
|  |  | 3.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  |  | 3.04 | User scans an incorrect location | Error message saying "You must cycle count the given location [required location]". |  |  |  | I was able to create a cycle count for one item in Deposco. The only thing I wasn’t able to figure out is how to assign it to a counter. (fernando)
|  |  | 3.05 | User is prompted to re-enter correct location. Proceed as normal.
Inventory Management | Cycle Counting | Create Location Cycle Count - Scanning a Location that is not a Cycle Count Location | 4.01 | User enters "Create Location Cycle Count" through inventory menu |  |  | Pass |  | In our current system, I’m able to search by Lot Number, and this is a really important tool that I use on a daily basis. Is there a similar feature or toolbar in Deposco that allows searching by Lot#? (Fernando)
|  |  | 4.03 | User should re enter location and priority
|  |  | 4.04 | Proceed with correct location as normal or on the location cycle count field, check its box
Inventory Management | Cycle Counting | Cycle Counting - Scanning Item that does not exist in Location | 5.01 | Select Execute Cycle Count button in handheld menu from Inventory |  |  | Not Tested
|  |  | 5.02 | Scan or enter starting location and hit enter
|  |  | 5.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  |  | 5.04 | User will incorrectly scan an item not listed nor existing in the location | Tasks will be generated in the "Manage Cycle Count Variances" UI for a manager or supervisor to review
|  |  | 5.05 | On the next screen, select the pack type and enter the quantity they counted | Variance qty will equal counted qty for the incorrectly entered item in "Manage Cycle Count Variances"
|  |  | 5.06 | User will be brought back to the screen displaying the list box of items and can proceed as normal
Inventory Management | Move Stock | Move Stock - Incorrect Destination Location Scan | 8.01 | Navigate to "Move Stock" under JSA Inventory on handheld MainMenu |  |  | Pass
|  |  | 8.02 | Enter the location that contains the stock you want to move
|  |  | 8.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 8.04 | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  |  | 8.05 | User is prompted to putaway screen and a listbox of suggested locations is displayed. User must scan or select a location in which to put the stock away. Enter a location that doesn't exist. | User should see an error on MainMenu saying "[....] is not a valid location" or "No such location or LPN in the current facility."
Inventory Management | Move Stock | Move Stock - Putaway to non Suggested Location | 9.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Pass
|  |  | 9.02 | Enter the location that contains the stock you want to move
|  |  | 9.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 9.04 | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  |  | 9.05 | User is prompted to putaway screen and a listbox of suggested locations is displayed. User must scan or select a location in which to put the stock away. Enter a location that is not in the suggested locations list. | Stock unit will be created in the putaway location the user entered. Message will appear reading, "All Items Moved."
Inventory Management | Move Stock | Move Stock - Incorrect Item Qty Entry | 10.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Pass |  | You click on "Move Stock" and the next screen is "Enter Cart", not "location".
|  |  | 10.02 | Enter the location that contains the stock you want to move
|  |  | 10.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 10.04 | User selects pack type and pack UOM. Enter in more than the item's current SU quantity to move | Message will appear reading, "The entered quantity exceeds the total movable Each quantity of [...]." and "Quantity to move [..] larger than quantity in found stocks [...]." depending on process.
Inventory Management | Move Stock | Move Stock - Negative item Qty Entry | 11.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Not Tested
|  |  | 11.02 | Enter the location that contains the stock you want to move
|  |  | 11.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 11.04 | User selects pack type and pack UOM. Enter in a negative value for the item's current SU quantity to move | Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process.
Inventory Management | Move Stock | Move Stock - Invalid Item Qty Entry | 12.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Not Tested
|  |  | 12.02 | Enter the location that contains the stock you want to move
|  |  | 12.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 12.04 | User selects pack type and pack UOM. Enter iin for the item's current SU quantity to move an invalid number like "2YN". | Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process.
Outbound
Order Entry
Outbound | Order Entry | Create a Customer Order with Customer Order Workbench | 1.01 | Navigate to the Customer Order Workbench and press New Customer Order | Co will be created and processed. If inventory exists for the order lines, the CoHeader will move to a Released status with Sales Order created. |  | Pass | When creating a new ship-to customer, we typically do not include a person’s name, last name, or email address. This information is often unavailable to us, as these ship-to customers are our customers’ customers.Would it be possible to make these fields optional instead of required? Fernando
|  |  | 1.02 | Select Company from the drop down list |  |  |  | I created a new ship-to customer, but now I’m unable to submit the order. A message pops up saying "Please select a Shipping Rate. This option appears when working in Azelis, but not in Nagase. fsaucedo@jensen-souders.com This has been resolved for Nagase
|  |  | 1.03 | User will need to select customer from Customer Lookup or add a new customer if needed. |  |  |  | There is no field to add a Code#,3rd Pary information, and the Lot# (fernando)
|  |  | 1.04 | User will add items to the Order Line section by entering the item number or by using the drop down
|  |  | 1.05 | User will need to select N/A for Shipping Rate
|  |  | 1.06 | User will enter the PO Number and select ship via
|  |  | 1.07 | Press submit
Waving
Outbound | Order Processing | Release a Fedex Wave | 1.01 | Create Sales Orders with status as New. Automations Complete is true Order has a Fedex ground ship via. Order is not already associated with a Pickwave Min number of orders is 1 and Max number of orders is 5. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) 1 Wave created per order 3) Wave is available for selection in the handheld menu under Outbound -> TL Picking |  | Pass | ALL GOOD | I need help getting pass order proccesing. It would not let me release the orders. It's stock on status "New"
|  |  | 1.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over FedEx Profile - 'Process' button appears -> Select Process
|  |  | 1.03 | Wave should be Released if sufficient stock
Outbound | Order Processing | Release a UPS Pickwave | 2.01 | Create multiple Sales Orders with status as New. Automations Complete is true Order has a UPS ground ship via. Order is not already associated with a Pickwave Max number of orders is 5. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass | Per our meeting, we need to pick a lot number 1st before releasing the wave.
|  |  | 2.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over UPS Profile - 'Process' button appears -> Select Process
|  |  | 2.03 | Wave should be Released
Outbound | Order Processing | Release an Carbon Black Bag Pickwave | 3.01 | Create multiple Sales Orders with status as New. Carbon Black Bag field (item.customAttribute4) is set to true Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Invalid |  | We deceided on the call yesterday to eliminate the carbon black pick wave.
|  |  | 3.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Carbon Black Bag Profile - 'Process' button appears -> Select Process
|  |  | 3.03 | Wave should be Released
Outbound | Order Processing | Release an IBC Pickwave | 4.01 | Create multiple Sales Orders with status as New. Order contains orderLine with a packType = IBC Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Failed |  | When releasing the order "order proccesing" under IBC it did not release the order. But if I release manally pick the order under "orders" it will release the order. Maybe it has to something with how the item was import? item#3023011513
|  |  | 4.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over IBC Profile - 'Process' button appears -> Select Process
|  |  | 4.03 | Wave should be Released
Outbound | Order Processing | Release a Drums. Pails, Boxes Pickwave | 5.01 | Create Sales Orders with status as New. Order contains orderLine with a packType = 50DR, 30DR, PL or BX Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass | All good
|  |  | 5.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Drums, Pails, Boxes Profile - 'Process' button appears -> Select Process
|  |  | 5.03 | Wave should be Released
Outbound | Order Processing | Release an Less than 100 bags Pickwave | 6.01 | Create multiple Sales Orders with status as New. Order contains an orderLine with a packType = Bag Total orderLine.orderPackQuantity contains less than 100 bags None are Carbon Black Bags Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 6.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Less Than 100 bags Profile - 'Process' button appears -> Select Process
|  |  | 6.03 | Wave should be Released
Outbound | Order Processing | Release a More than 100 bags Pickwave | 7.01 | Create Sales Orders with status as New. Order contains an orderLine with a packType = Bag Total orderLine.orderPackQuantity contains more than 100 bags None are Carbon Black Bags Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 7.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over More than 100 Bagas Profile - 'Process' button appears -> Select Process
|  |  | 7.03 | Wave should be Released
Outbound | Order Processing | Release a Truck Load Pickwave | 8.01 | Create multiple Sales Orders with status as New. Total order weight is greater than 12,000 pounds Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Failed |  | Order keeps falling into "Backorder" status/ #D160 (fernando)
|  |  | 8.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Truck Load Profile - 'Process' button appears -> Select Process
|  |  | 8.03 | Wave should be Released
Outbound | Order Processing | Release a Restack Pickwave | 9.01 | Create Sales Orders with status as New. Order contains a note with a title of ‘Restack’ Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Ready to Test
|  |  | 9.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Restack Profile - 'Process' button appears -> Select Process
|  |  | 9.03 | Wave should be Released
Outbound | Order Processing | Release a Red River Pickwave | 10.01 | Create multiple Sales Orders with status as New. Order Business Unit = Red River Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Invalid
|  |  | 10.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Red River Profile - 'Process' button appears -> Select Process
|  |  | 10.03 | Wave should be Released
Outbound | Order Processing | Release a Standard Freight Pickwave | 11.01 | Create Sales Orders with status as New. These sales orders will be put on their own wave per order (1 order, 1 wave). Any non Parcel order that has not been accounted for in the above categories (Standard Freight orders) | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 11.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Standard Frieight Profile - 'Process' button appears -> Select Process
|  |  | 11.03 | Wave should be Released
Picking
Outbound | Order Processing | Pick Freight Order | 1.01 | User enters/selects wave and enters picking pallet number |  |  | Pass | Picking: As discussed in the meeting. "Accessorial Charges" 1. Can we change all the Accessorial charges from checkboxes to manual input fields. 2. We have two types of pallets charges: HT Pallets /#1 Pallet ( special Pallet) , and the regular Pallets. Currently, the handheld only shows an option for “Special Pallet.” Can we add an option for “Regular Pallet” as well? 3. Can we change “Add Carboard” to “Carboard around pallet or Corrugated Wrap” 4. We have two types of labels: Custom labels and regular stencil “Labels”. On the handheld it only shows “Custom Labels” 5. Can we include a comment or notes field to explain certain charges? For example: “Had to restack 300 bags into 40x48 pallets.” (fernando and Edgar)
|  |  | 1.02 | User enters / scans location, SKU, quantity, and pallet they are pulling from and presses enter
|  |  | 1.03 | User selects the Lot they are picking from and presses confirm
|  |  | 1.04 | On the Stage Item screen, user will make selections based on what needs to be completed before LPN can be staged and shipped. User will also enter the location they are staging to and press Next
Outbound | Order Processing | Pick Fedex/UPS Order | 3.01 | User enters/selects wave |  |  | Ready to Test
|  |  | 3.02 | User enters / scans location, SKU, quantity, and pallet they are pulling from and presses enter
|  |  | 3.03 | User selects the Lot they are picking from and presses confirm
Outbound | Order Processing | Enter Incorrect wave number | 4.01 | User navigates to a picking process and scans wave not present in the list box |  |  | Pass
|  |  | 4.02 | Error "The pick wave [] could not be found." is displayed
Packing
Outbound | Order Processing | Single Scan Packing | 1.01 | User scans the LPN they are packing | User will see message saying "Packing is complete for the following orders: []." The order updates to Shipped |  | Pass
|  |  | 1.02 | User enters/ selects the item they are packing from the LPN
|  |  | 1.03 | User enter the quantity they are packing
|  |  | 1.04 | User is asked to fill in all dimentions, including weight, and box
|  |  | 1.05 | User hits enter or selects the 'Next' button.
Outbound | Order Processing | Pack Order by Item | 2.01 | User scans the LPN they are packing | The order updates to Shipped |  | Pass
|  |  | 2.02 | User enters/ selects the item they are packing from the LPN
|  |  | 2.03 | User will be asked to confirm the lot number
User will enter dimensions / box / weight
Outbound | Order Processing | Assign Trip to Container | 3.01 | User enters the Assign Trip process and selects the shipping door | Trip is now created and open in the system. The trip will not be closed until the close trip process is completed |  | Pass
|  |  | 3.02 | User scans/ enters the pallet and presses enter. Pallet shows in list box called Pallets
|  |  | 3.03 | User enters all information needed for Shipment / Trip creation
Outbound | Order Processing | Close Trip | 4.01 | User enters the Close Trip process and selects the trip they would like to close and presses Next | Trip is now closed The order updates to Shipped |  | Pass |  | I closed a order but it did not update to "shipped" on hanheld
Outbound | Order Processing | Enter incorrect item when packing | 5.01 | User scans the LPN they are packing | User will need to enter valid item to continue |  | Ready to Test
|  |  | 5.02 | User scans/ enters item not present on order
|  |  | 5.03 | Message "The item could not be found on this order." is displayed
Outbound | Order Processing | Enter LPN that does not exist when packing | 6.01 | User scans LPN that does not exist | User will need to enter valid LPN to continue |  | Pass
|  |  | 6.02 | Message "The container [] could not be found." is displayed
Other WMS
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Other WMS | [6 empty] | Ready to Test
Reporting
Reporting | Dashboard - Inbound | -- |  | Report returns timely and accurately for customer needs
Reporting | Dashboard - Inventory Management Dashboard | -- |  | Report returns timely and accurately for customer needs
Reporting | Dashboard - Outbound | -- |  | Report returns timely and accurately for customer needs
Reporting | Dashboard - User Performance | -- |  | Report returns timely and accurately for customer needs
Reporting | Report Builder - | -- |  | Report returns timely and accurately for customer needs

## UAT TEST CASES
JSA Unit Test Cases |  | Category | % Complete
|  | Inbound | 100%
|  | Inventory Management | 100%
|  | Outbound | 84.21%
|  | Reporting | #DIV/0!
|  | TOTAL | 93.88%
Category | Subcategory | Scenario | Steps | Step Details | Expected Outcome | Owner | Status | Test Data | Comments
Receiving
Inbound | Purchase Orders | Receive a Purchase Order | 1.01 | Select Receiving from Inbound menu on Handheld | User will notice that Stock has been created within the system. |  | Pass
|  |  | 1.02 | Enter/Scan the Order Number / Order Identifier
|  |  | 1.03 | Hit Enter or Click Submit
|  |  | 1.04 | Scan/Key Item you are receiving (list of items on the PO will be provided in the list box)
|  |  | 1.05 | Select the pack type of the item and key in the quantity being received.
|  |  | 1.06 | Hit Enter
|  |  | 1.07 | Keep repeating step 1.04 - 1.06 if there are multiple items in the order that you are receiving until all items have been received
Inbound | Blind Receipt / Blind RMA Receiving (as Necessary) | Receive a Blind Order | 2.01 | Navigate to Receiving | User will notice that Stock has been created within the system. |  | Pass
|  |  | 2.02 | Enter identifier for blind order. A message will pop up that says "No records found matching that identifier, click Next to continue as Blind Order"
|  |  | 2.03 | Click Next
|  |  | 2.04 | Scan the item barcode of the item being received (no items will appear in list box) Scan also the LPN that the item is being received onto
|  |  | 2.05 | Select the pack type of the item and key in the quantity being received
|  |  | 2.06 | Enter the LOT number and EXP of the item being received
|  |  | 2.07 | Repeat steps 2.04-2.06 until all items on the PO have been received and select Finish when done
|  |  | 2.08 | After user scans all Items to receive, the inentory will be cedited to the Receiving location for staging.
Inbound | UnReceiving | Unreceive previously received order | 3.01 | Select UnReceiving from Inbound menu on Handheld | User will see a validation message on the same Select Item to UnReceive screen letting them know that they have successfully UnReceived the selected item. |  | Pass
|  |  | 3.02 | Scan/Key in a PO # that a user has previously received
|  |  | 3.03 | Scan the item and input the quantity in which the user would like to UnReceive
|  |  | 3.04 | Select Submit
Inbound | Returns Receiving | Receive returns order | 5.01 | Navigate to the "Receiving" button under Inbound | User will notice that Stock has been created within the system. |  | Pass | `
|  |  | 5.02 | User enters Customer Return Order number they wish to receive (The number that is entered cannot match that of any existing order).
|  |  | 5.03 | Scan/Enter the Item(s) you are receiving. Confirm the Pack in the List Box. Scan/ enter the LPN the inventory is being received on (scan LPN label)
|  |  | 5.04 | Select the pack. Key in the quantity of the receipt. If the item is lot/expiration tracked, the user must also key in the lot/expiration date for the inventory they are receiving.
|  |  | 5.05 | Keep repeating step 5.03 and 5.04 if there are multiple items in the order that you are receiving.
|  |  | 5.06 | After user scans all Items to receive, the inventory will be cedited to the Returns location for staging.
Inbound | Purchase Order | Incorrect PO# Entry | 6.01 | Select Receiving from Inbound menu on Handheld | A message should dispay reading, "No records found matching that identifier, click Next to continue as Blind Order." |  | Pass
|  |  | 6.02 | Enter a PO Number that does not exist
Inbound | Purchase Order | Scanning Already Received PO | 7.01 | User enters Receiving Process | User will be prevented from continuing with the process. Error message appears reading, "". |  | Pass
|  |  | 7.02 | User scans a Purchase Order that has already been received instead of a new Purchase Order
Inbound | Purchase Order | Receiving an Item not on a PO | 9.01 | User will enter receiving transaction | Error message appears reading, "Unable to find order line for item: [PO Number]." |  | Pass
|  |  | 9.02 | User scans/Keys an Item not on PO for receiving
|  |  | 9.03 | User will be prevented from receiving the item in the process
Inbound | Purchase Order/ Returns Receiving | Negative Item Qty Entry | 10.01 | During Receiving, user keys in a negative quantity to be received | Error message appears reading, "Please enter a valid quantity." |  | Pass
|  |  | 10.02 | User will be prompted to re-enter quantity
Inbound | Purchase Order/ Returns Receiving | Invalid Item Qty Entry | 11.01 | During Receiving, user keys in an invalid number like "2YN" | Error message appears reading, "Please enter a valid quantity." |  | Pass
|  |  | 11.02 | User will be prompted to re-enter quantity
Inventory Management
Inventory Management | On Demand Cycle Count via Handheld | Cycle Counting on demand | 1.01 | User notices a location that may need to be cycle counted | A cycle count task with status NEW should be generated for the specified location with the specified priority. After counting, if a variance is detected, then a new entry is created in the Approve Variances screen (Under Inventory Admin in the Application Menu) |  | Pass
|  |  | 1.02 | User enters "On Demand Cycle Count" through the JSA Inventory handheld menu
|  |  | 1.03 | User enters the location and priority (1-10 w/1 being highest priority) for the cycle count. Priority defaults to 5 if left empty.
|  |  | 1.04 | The Parent LPN Screen will show the Location along with the LPN in the Location and # of items. User will scan the LPN barcode on the pallet's label
|  |  | 1.05 | User will be shown a list box with items on the scanned LPN that can be cycle counted
|  |  | 1.06 | User will scan SKU and hit enter
|  |  | 1.07 | On the next screen, user will select the pack type and enter the quantity they counted. They will also be prompted to enter the LOT number of the item they are counting.
|  |  | 1.08 | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  |  | 1.09 | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  |  | 1.1 | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
Inventory Management | Manage Cycle Count Variances | Accept, Reject, or Recount Variances | 2.01 | User (typically a supervisor or manager) will enter the "Manage Cycle Count Variances" UI through a laptop or desktop, located under Inventory Admin in the Application Menu | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances". |  | Pass
|  |  | 2.02 | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system.
|  |  | 2.03 | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted.
|  |  | 2.04 | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted).
Inventory Management | Location Cycle Count Creation via Scheduler | Create Cycle Count tasks by location | 3.01 | In order for the scheduler to create cycle count queue tasks, make sure Cycle Count checkbox is checked for the locations that support cycle counting. Scheduler will look at Iocation's Last Counted Date and Cycle Count Frequency fields. |  |  | Pass
|  |  | 3.02 | Run the scheduler "Create Cycle Count Tasks by Location ()" under SchedulerTask application (under Setup in the application menu)
|  |  | 3.03 | Cycle count tasks for locations that require a cycle count will appear in the Cycle Count Queue table with status NEW
Inventory Management | Item Cycle Count Creation via Scheduler | Create Cycle Count tasks by Item | 4.01 | In order for the scheduler to create cycle count queue tasks, make sure Cycle Count checkbox is checked for the items and locations that support cycle counting. Scheduler will look at Iocation's Last Counted Date and Cycle Count Frequency fields. | For item counts, the scheduler task evaluates which items require a cycle count based on business unit and generates the task in the Cycle Count Queue table |  | Pass
|  |  | 4.02 | Run the scheduler "Create Cycle Count Tasks by Item ()" under SchedulerTask application (under Setup in the application menu)
|  |  | 4.03 | Cycle count tasks for items that require a cycle count will appear in the Cycle Count Queue table with status NEW
Inventory Management | Perform Item Cycle Count | Perform previously created cycle count tasks (by item) | 5.01 | Cycle Count task is already created via scheduler | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. 3) If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. |  | Pass
|  |  | 5.02 | Navigate to handheld menu and select "Execute Cycle Count" under JSA Inventory.
|  |  | 5.03 | Enter user's start off location.
|  |  | 5.04 | User is prompted to go to the first location to count.
|  |  | 5.05 | After scanning the location, user is shown a listbox of available SKUS to cycle count. User must scan or select which item to cycle count and hit enter.
|  |  | 5.06 | User selects pack type and enters counted qty.
|  |  | 5.07 | The counted item is marked with an asterisk to track what has been counted. User can repeat steps 4 and 5 if more items need to be counted.
|  |  | 5.08 | After user is finished cycle counting items, user can hit Next Location and will be prompted to the next location that requires a cycle count, if any
Inventory Management | Perform Location Cycle Count | Perform previously created cycle count tasks (by location) | 6.01 | Cycle Count task is already created via scheduler | 1) After each item has been counted in a location, ** will appear left to the item number 2) If the correct quantity (according to Deposco) is entered, the task in CycleCountQueue will be changed to "Completed" status. If a variance is detected, tasks will be generated in the "Manage Cycle Count Variances UI for a manager or supervisor to review. More info on this in the next test script. |  | Invalid
|  |  | 6.02 | Select "Execute Cycle Count" button in handheld menu from JSA Inventory
|  |  | 6.03 | Scan or enter starting location and hit enter
|  |  | 6.04 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  |  | 6.05 | User will scan the location they're directed to
|  |  | 6.06 | User will be shown a list box with items in location needing to be cycle counted.
|  |  | 6.07 | User will scan SKU and hit enter
|  |  | 6.08 | On the next screen, user will select the pack type and enter the quantity they counted
|  |  | 6.09 | If they enter the quantity that Deposco thinks is in the system, they'll be returned to the previous screen with the list of items to be counted. If they enter a different quantity, they will be asked to re-count and re-enter since a variance was detected.
|  |  | 6.1 | User will be asked to re-count as many times as necessary until they either enter the same quantity twice in a row, or enter the quantity Deposco believes is in the system.
|  |  | 6.11 | User will be returned to the item listbox screen to select another item at that location if necessary. If not, they can select "Next Location" and repeat the process if there are more tasks
Inventory Management | Manage Cycle Count Variances | Accept, Reject, or Recount Variances | 7.01 | User (typically a supervisor or manager) will enter the "Manage Cycle Count Variances" UI through a laptop or desktop, located under Inventory Admin in the Application Menu | Depending on which action was taken, stock units will be updated to reflect what was counted, remain the same and cycle count task will be complete, or remain the same but generate a new cycle count task for the same location. The process will be repeated until either there is no variance detected, or the variance is accepted in "manage cycle count variances". |  | Pass
|  |  | 7.02 | A list of variances will be displayed. A variance is any time a qty is entered that differs from what Deposco has listed in the system.
|  |  | 7.03 | For each record you will see the item, counted qty, variance qty, reason code, and other relevant data. The columns listed can be adjusted.
|  |  | 7.04 | Whoever is managing the variances can select the tasks and accept (stock units for that item/location will be updated based on what was counted), reject (stock unit for that location/item will remain with the same qty they had before the cycle count), or re-count (no change is made to the stock unit yet, and cycle count task is sent back to the floor to be re-counted).
Inventory Management | Adjust Inventory | Add Inventory to a Location | 8.01 | Select "Adjust Inventory" from the JSA Inventory menu | 1) After items have been confirmed and the user clicks commit, user is returned to the Location Screen and a screen message will display on the MainMenu saying "[qty pack type], are created as new" 2) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code) 3) Updates made to Item's SU in location |  | Pass
|  |  | 8.02 | Scan/key in Location
|  |  | 8.03 | Select "Create Inventory"
|  |  | 8.04 | Select the Business Unit that the user will be creating Inventory for
|  |  | 8.05 | Scan Item SKU
|  |  | 8.06 | Enter quantity of item's SU you want to create. User can optionally enter serial, lot, and LPN #.
|  |  | 8.07 | If you have more than one item's SU you want to create, click next and repeat steps 8.04 and 8.05
|  |  | 8.08 | Once finished, click Confirm
|  |  | 8.09 | Once final reviewing all items, select Reason Code and click Commit
Inventory Management | Adjust Inventory | Consume All Inventory in Location | 9.01 | Select "Adjust Inventory" from the JSA Inventory menu | 1) After entering quantity of item you want to consume, a screen message will display on the MainMenu saying "[qty] stocks are added to the pending list" 2) After items have been confirmed and the user clicks commit, it will return to the Location Screen and a screen message will display on the MainMenu saying "Consumed [qty pack type] stocks". 3) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location |  | Pass
|  |  | 9.02 | Scan/key in Location
|  |  | 9.03 | Select "Consume All in Location"
|  |  | 9.04 | Select Reason Code and Click Commit
Inventory Management | Adjust Inventory | Consume by LPN | 10.01 | Select "Adjust Inventory" from the JSA Inventory menu | 1) Updates to Inventory Ledger List (Action Type Code: ADJ and associated Reason Code)) 4) Updates made to Item's SU in location |  | Pass
|  |  | 10.02 | Scan/key in Location
|  |  | 10.03 | Select "Consume By LPN"
|  |  | 10.04 | Scan/ Enter LPN Number
|  |  | 10.05 | See and confirm SKU(s) on LPN Press Confirm
|  |  | 10.06 | Review SKU's and quantities Press Commit
Inventory Management | Move Inventory | Move Stock | 11.01 | Navigate to "Move Stock" under JSA Inventory on handheld MainMenu |  |  | Pass
|  |  | 11.02 | Container field displays the cart in which you want to put the stock you are wanting to move (default cart will be user's username)
|  |  | 11.03 | Enter or scan location with the stock you want to move
|  |  | 11.04 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 11.05 | Select Pack UOM and enter in quantity to move and select Submit
|  |  | 11.06 | Repeat steps 11.04-11.05 to move more items in the location
|  |  | 11.07 | When finished, select Move Source Screen
|  |  | 11.08 | User is given a summary of the number of unique Skus and quantity in cart. If user wants to move stock in a different location, User can scan another location.
|  |  | 11.09 | Otherwise, User can select "Move" or "Move Full" to move the stock to a directed location
|  |  | 11.1 | User enters quantity and selects/scans item
|  |  | 11.11 | A listbox of suggested putaway locations is displayed. User must select or scan a location to move the stock | When all stock has been moved successfully, a message displays on menu saying "All Items Moved."
|  |  | 11.12 | User repeats 11.10-11.11 to move the rest of the stock, if any
|  |  | 11.13 | Otherwise, User can select All to move all of the stock in the cart and then scan the destination location of where the stock should be moved | Picking Cart (user's username) is now empty and remains in its original location. Stock units that were moved are decremented from their source location, and are created in the destination location
Inventory Management | Move Inventory | Move LPN | 12.01 | Navigate to "Move Container" under JSA Inventory on handheld MainMenu |  |  | Pass |  | Need LPN contents listbox
|  |  | 12.02 | Scan the container that you want to move.
|  |  | 12.03 | Move the container to the destination location. Then scan the destination location and select Move | The location field for the container is updated to the location to which the container was moved and the location field for any stock units in the container is updated to the location to which the container was moved.
Inventory Management Edge Cases
Inventory Management | Cycle Counting | Ad-Hoc Cycle Count - Counting Less than the Item's Qty | 1.01 | User selects "On Demand Cycle Count" from Inventory menu | Tasks will be generated in the "Manage Cycle Count Variances" UI for a manager or supervisor to review. If qty count entered is less than the system's qty, a negative variance qty will be displayed for that item in "Manage Cycle Count Variances" |  | Pass
|  |  | 1.02 | User will enter quantity less than the item's SU quantity currently in Deposco's system
|  |  | 1.03 | User will be asked to recount and will proceed to re-enter the quantity.
Inventory Management | Cycle Counting | Ad-Hoc Cycle Count - Counting More than the Item's Qty | 2.01 | User selects "On Demand Cycle Count" from Inventory menu |  |  | Pass
|  |  | 2.02 | User will enter quantity more than the item's SU quantity currently in Deposco's system
|  |  | 2.03 | User will be asked to recount and will proceed to re-enter the quantity. | Tasks will be generated in the "Manage Cycle Count Variances" UI for a manager or supervisor to review. If qty count entered is more than the system's qty, a negative variance qty will be displayed for that item in "Manage Cycle Count Variances"
Inventory Management | Cycle Counting | Cycle Counting - Scanning incorrect Location | 3.01 | Select Execute Cycle Count button in handheld menu from Inventory |  |  | Pass
|  |  | 3.02 | Scan or enter starting location and hit enter
|  |  | 3.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  |  | 3.04 | User scans an incorrect location | Error message saying "You must cycle count the given location [required location]".
|  |  | 3.05 | User is prompted to re-enter correct location. Proceed as normal.
Inventory Management | Cycle Counting | Create Location Cycle Count - Scanning a Location that is not a Cycle Count Location | 4.01 | User enters "Create Location Cycle Count" through inventory menu |  |  | Pass
|  |  | 4.03 | User should re enter location and priority
|  |  | 4.04 | Proceed with correct location as normal or on the location cycle count field, check its box
Inventory Management | Cycle Counting | Cycle Counting - Scanning Item that does not exist in Location | 5.01 | Select Execute Cycle Count button in handheld menu from Inventory |  |  | Pass
|  |  | 5.02 | Scan or enter starting location and hit enter
|  |  | 5.03 | User will be directed to the nearest location that has a cycle count task waiting to be executed
|  |  | 5.04 | User will incorrectly scan an item not listed nor existing in the location | Tasks will be generated in the "Manage Cycle Count Variances" UI for a manager or supervisor to review
|  |  | 5.05 | On the next screen, select the pack type and enter the quantity they counted | Variance qty will equal counted qty for the incorrectly entered item in "Manage Cycle Count Variances"
|  |  | 5.06 | User will be brought back to the screen displaying the list box of items and can proceed as normal
Inventory Management | Move Stock | Move Stock - Incorrect Destination Location Scan | 8.01 | Navigate to "Move Stock" under JSA Inventory on handheld MainMenu |  |  | Pass
|  |  | 8.02 | Enter the location that contains the stock you want to move
|  |  | 8.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 8.04 | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  |  | 8.05 | User is prompted to putaway screen and a listbox of suggested locations is displayed. User must scan or select a location in which to put the stock away. Enter a location that doesn't exist. | User should see an error on MainMenu saying "[....] is not a valid location" or "No such location or LPN in the current facility."
Inventory Management | Move Stock | Move Stock - Putaway to non Suggested Location | 9.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Pass
|  |  | 9.02 | Enter the location that contains the stock you want to move
|  |  | 9.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 9.04 | User selects pack type, pack UOM, and enters quantity of how much stock to move
|  |  | 9.05 | User is prompted to putaway screen and a listbox of suggested locations is displayed. User must scan or select a location in which to put the stock away. Enter a location that is not in the suggested locations list. | Stock unit will be created in the putaway location the user entered. Message will appear reading, "All Items Moved."
Inventory Management | Move Stock | Move Stock - Incorrect Item Qty Entry | 10.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Pass
|  |  | 10.02 | Enter the location that contains the stock you want to move
|  |  | 10.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 10.04 | User selects pack type and pack UOM. Enter in more than the item's current SU quantity to move | Message will appear reading, "The entered quantity exceeds the total movable Each quantity of [...]." and "Quantity to move [..] larger than quantity in found stocks [...]." depending on process.
Inventory Management | Move Stock | Move Stock - Negative item Qty Entry | 11.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Pass
|  |  | 11.02 | Enter the location that contains the stock you want to move
|  |  | 11.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 11.04 | User selects pack type and pack UOM. Enter in a negative value for the item's current SU quantity to move | Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process.
Inventory Management | Move Stock | Move Stock - Invalid Item Qty Entry | 12.01 | Navigate to "Move Stock" under Inbound on handheld MainMenu |  |  | Pass
|  |  | 12.02 | Enter the location that contains the stock you want to move
|  |  | 12.03 | A listbox of available SKUs to move display. User must scan or select item to move
|  |  | 12.04 | User selects pack type and pack UOM. Enter iin for the item's current SU quantity to move an invalid number like "2YN". | Message will appear reading, "Quantity needs to be a number." or "Quantity should be positive number" depending on process.
Outbound
Order Entry
Outbound | Order Entry | Create a Customer Order with Customer Order Workbench | 1.01 | Navigate to the Customer Order Workbench and press New Customer Order | Co will be created and processed. If inventory exists for the order lines, the CoHeader will move to a Released status with Sales Order created. |  | Pass
|  |  | 1.02 | Select Company from the drop down list
|  |  | 1.03 | User will need to select customer from Customer Lookup or add a new customer if needed.
|  |  | 1.04 | User will add items to the Order Line section by entering the item number or by using the drop down
|  |  | 1.05 | User will need to select N/A for Shipping Rate
|  |  | 1.06 | User will enter the PO Number and select ship via
|  |  | 1.07 | Press submit
Waving
Outbound | Order Processing | Release a Fedex Wave | 1.01 | Create Sales Orders with status as New. Automations Complete is true Order has a Fedex ground ship via. Order is not already associated with a Pickwave Min number of orders is 1 and Max number of orders is 5. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) 1 Wave created per order 3) Wave is available for selection in the handheld menu under JSA Picking -> FedEx/UPS Picking |  | Pass
|  |  | 1.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over FedEx Profile - 'Process' button appears -> Select Process
|  |  | 1.03 | Wave should be Released if sufficient stock
Outbound | Order Processing | Release a UPS Pickwave | 2.01 | Create multiple Sales Orders with status as New. Automations Complete is true Order has a UPS ground ship via. Order is not already associated with a Pickwave Max number of orders is 5. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 2.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over UPS Profile - 'Process' button appears -> Select Process
|  |  | 2.03 | Wave should be Released
Outbound | Order Processing | Release an Carbon Black Bag Pickwave | 3.01 | Create multiple Sales Orders with status as New. Carbon Black Bag field (item.customAttribute4) is set to true Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Ready to Test
|  |  | 3.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Carbon Black Bag Profile - 'Process' button appears -> Select Process
|  |  | 3.03 | Wave should be Released
Outbound | Order Processing | Release an IBC Pickwave | 4.01 | Create multiple Sales Orders with status as New. Order contains orderLine with a packType = IBC Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 4.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over IBC Profile - 'Process' button appears -> Select Process
|  |  | 4.03 | Wave should be Released
Outbound | Order Processing | Release a Drums. Pails, Boxes Pickwave | 5.01 | Create Sales Orders with status as New. Order contains orderLine with a packType = 50DR, 30DR, PL or BX Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 5.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Drums, Pails, Boxes Profile - 'Process' button appears -> Select Process
|  |  | 5.03 | Wave should be Released
Outbound | Order Processing | Release an Less than 100 bags Pickwave | 6.01 | Create multiple Sales Orders with status as New. Order contains an orderLine with a packType = Bag Total orderLine.orderPackQuantity contains less than 100 bags None are Carbon Black Bags Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 6.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Less Than 100 bags Profile - 'Process' button appears -> Select Process
|  |  | 6.03 | Wave should be Released
Outbound | Order Processing | Release a More than 100 bags Pickwave | 7.01 | Create Sales Orders with status as New. Order contains an orderLine with a packType = Bag Total orderLine.orderPackQuantity contains more than 100 bags None are Carbon Black Bags Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 7.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over More than 100 Bagas Profile - 'Process' button appears -> Select Process
|  |  | 7.03 | Wave should be Released
Outbound | Order Processing | Release a Truck Load Pickwave | 8.01 | Create multiple Sales Orders with status as New. Total order weight is greater than 12,000 pounds Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 8.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Truck Load Profile - 'Process' button appears -> Select Process
|  |  | 8.03 | Wave should be Released
Outbound | Order Processing | Release a Restack Pickwave | 9.01 | Create Sales Orders with status as New. Order contains a note with a title of ‘Restack’ Automations Complete is true Order is not already associated with a Pickwave Max number of orders is 1. | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Ready to Test
|  |  | 9.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Restack Profile - 'Process' button appears -> Select Process
|  |  | 9.03 | Wave should be Released
Outbound | Order Processing | Release a Standard Freight Pickwave | 11.01 | Create Sales Orders with status as New. These sales orders will be put on their own wave per order (1 order, 1 wave). Any non Parcel order that has not been accounted for in the above categories (Standard Freight orders) | 1) Wave(s) went to released status (this can be viewed on the Order Header table or the PickWave table) 2) Depending on the amount of orders released, one or many batch waves will be created. 3) Wave is available for selection in the handheld menu under Batch Picking |  | Pass
|  |  | 11.02 | Go to "Order Processesing" Entity. Find this by navigating to Distribution -> Order Processing -> Hover Over Standard Frieight Profile - 'Process' button appears -> Select Process
|  |  | 11.03 | Wave should be Released
Picking
Outbound | Order Processing | Pick Freight Order | 1.01 | User enters/selects wave and enters picking pallet number |  |  | Pass
|  |  | 1.02 | User enters / scans location, SKU, quantity, and pallet they are pulling from and presses enter
|  |  | 1.03 | User selects the Lot they are picking from and presses confirm
|  |  | 1.04 | On the Stage Item screen, user will make selections based on what needs to be completed before LPN can be staged and shipped. User will also enter the location they are staging to and press Next
Outbound | Order Processing | Pick Fedex/UPS Order | 3.01 | User enters/selects wave |  |  | Pass
|  |  | 3.02 | User enters / scans location, SKU, quantity, and pallet they are pulling from and presses enter
|  |  | 3.03 | User selects the Lot they are picking from and presses confirm
Outbound | Order Processing | Enter Incorrect wave number | 4.01 | User navigates to a picking process and scans wave not present in the list box |  |  | Ready to Test
|  |  | 4.02 | Error "The pick wave [] could not be found." is displayed
Packing
Outbound | Order Processing | Single Scan Packing | 1.01 | User scans the LPN they are packing | User will see message saying "Packing is complete for the following orders: []." The order updates to Shipped |  | Pass
|  |  | 1.02 | User enters/ selects the item they are packing from the LPN
|  |  | 1.03 | User enter the quantity they are packing
|  |  | 1.04 | User is asked to fill in all dimentions, including weight, and box
|  |  | 1.05 | User hits enter or selects the 'Next' button.
Outbound | Order Processing | Assign Trip to Container | 3.01 | User enters the Assign Trip process and selects the shipping door | Trip is now created and open in the system. The trip will not be closed until the close trip process is completed |  | Pass
|  |  | 3.02 | User scans/ enters the pallet and presses enter. Pallet shows in list box called Pallets
|  |  | 3.03 | User enters all information needed for Shipment / Trip creation
Outbound | Order Processing | Close Trip | 4.01 | User enters the Close Trip process and selects the trip they would like to close and presses Next | Trip is now closed The order updates to Shipped |  | Pass |  | I closed a order but it did not update to "shipped" on hanheld
Outbound | Order Processing | Enter incorrect item when packing | 5.01 | User scans the LPN they are packing | User will need to enter valid item to continue |  | Pass
|  |  | 5.02 | User scans/ enters item not present on order
|  |  | 5.03 | Message "The item could not be found on this order." is displayed
Outbound | Order Processing | Enter LPN that does not exist when packing | 6.01 | User scans LPN that does not exist | User will need to enter valid LPN to continue |  | Pass
|  |  | 6.02 | Message "The container [] could not be found." is displayed

## GoNo-Go Decision
JSA Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 55
Deposco Setup | Label Printers | 10 | Y | XXX | 50% | 5 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Document Printers | 10 |  | XXX | 100% | 10 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | XXX | 50% | 5 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | End users | 10 | Y | XXX | 25% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Details | 10 | Y | XXX | 50% | 5 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Resources | 10 | Y | XXX | 50% | 5 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Printer Assignments | 10 | Y | XXX | 50% | 5 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | DEP | 100% | 10 | Have all Go-Live Critical issues from the task tracker been resolved?
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave | 10 |  | DEP | 100% | 10 | Have all jobs have been scheduled and enabled?
| Warehouse Prep | 40 |  |  |  | 25
Warehouse Prep | Location Labels | 10 |  | XXX | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | LPN Labels | 10 | Y | XXX | 50% | 5 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT
Warehouse Prep | Inventory Labels | 10 | Y | XXX | 0% | 0 | Are all inventory units labeled and scannable? | Recommend 100% by UAT
Warehouse Prep | Network Connectivity | 10 |  | XXX | 100% | 10 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT
| Standard Operating Procedure Documentation | 55 |  |  |  | 38.5
SOP Documents | Receiving/Unreceiving | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Parcel Picking | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Parcel Shipping | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Freight Picking | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Freight Shipping | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | XXX | 70% | 3.5 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 38
Training & Testing | Test Case Scenarios Definition | 10 |  | DEP / XXX | 100% | 10 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and XXX to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound | 10 |  | XXX | 100% | 10 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 |  | XXX | 90% | 9 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT
Training & Testing | Supervisor/Administrator Training | 10 |  | XXX | 90% | 9 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT
Training & Testing | End-user Training | 10 | Y | XXX | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT
| Production Master Data | 60 |  |  |  | 55
Master Data | Cutover Inventory Validation | 10 |  | XXX | 100% | 10 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload via Data Exchange, Full physical count
Master Data | Trading Partner/Third Party Accounts | 10 |  | XXX | 50% | 5
Master Data | Items and Packs | 10 |  | XXX | 100% | 10 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-post via API, Re-pull via integration, Re-upload via Data Exchange
Master Data | Locations and Zones | 10 |  | XXX | 100% | 10 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | LPNs | 10 |  | XXX | 100% | 10 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange
Master Data | Menu Structures | 10 |  | XXX | 100% | 10 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 5
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / XXX | 50% | 5 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date.
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 45
Interfaces - Imports to Deposco | Carton Types Upload | 10 |  | XXX | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 |  | XXX | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Items/Packs Upload | 10 |  | XXX | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | XXX | 100% | 5 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | LPN Upload | 10 | Y | XXX | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Exports from Deposco | Customer Order Upload | 10 |  | XXX | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 20 |  |  |  | 19
Integrations with Deposco | UPS - Get Shipping Label | 10 |  | XXX | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 |  | XXX | 100% | 10 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 40 |  |  |  | 38
Reports and Labeling | Location Label | 10 |  | XXX | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Item Label | 10 |  | XXX | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | LPN Label | 10 | Y | XXX | 100% | 10 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
Reports and Labeling | Generic BOL Report | 10 | Y | XXX | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | DEP / XXX | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 328.5
| Total Possible Score: | 420
| Total Percentage: | 78.21%
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Test Cases - End to End
JSA End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 0%
Category | Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Inbound | Receive PO full | Ready to Test | XXX
Inbound | Receive Partial PO | Ready to Test | XXX
Inbound | Create RMA from shipped SO and receive in full | Ready to Test | XXX
Inbound | Create RMA from shipped SO and receive partially | Ready to Test | XXX
Inbound | Create RMA from shipped SO and do not receive immediately | Ready to Test | XXX
Inbound | Unreceive full PO | Ready to Test | XXX
Inbound | Unrecieve partial PO | Ready to Test | XXX
Inbound | Blind receive additional units found after receiving | Ready to Test | XXX
Inbound | Over receive PO | Ready to Test | XXX
Inbound | Over receive RMA | Ready to Test | XXX
Inbound | Putaway single item containers | Ready to Test | XXX
Inbound | Putaway mixed item containers | Ready to Test | XXX
Inbound | Putaway containers to reserve locations | Ready to Test | XXX
Inbound | Putaway containers to pickable locations | Ready to Test | XXX
Inbound | Putaway loose stock to reserve locations | Ready to Test | XXX
Inbound | Putaway loose stock to pickable locations | Ready to Test | XXX
Outbound
Outbound | Fulfill "large" orders | Ready to Test | XXX
Outbound | Fulfill single unit orders | Ready to Test | XXX
Outbound | Fulfill multi unit orders | Ready to Test | XXX
Outbound | Fulfill international orders | Ready to Test | XXX
Outbound | Fulfill domestic orders | Ready to Test | XXX
Outbound | Exception a pick task for "large" order | Ready to Test | XXX
Outbound | Exception a pick task for a single unit order | Ready to Test | XXX
Outbound | Exception a pick task for a multi unit order | Ready to Test | XXX
Outbound | Cancel an order that has not yet been released | Ready to Test | XXX
Outbound | Cancel an order that has been released but not picked | Ready to Test | XXX
Outbound | Cancel an order that has been picked but not packed or shipped | Ready to Test | XXX
Outbound | Cancel an order that has been packed but not shipped | Ready to Test | XXX
Outbound | Roll back an order that has been shipped and cancel it | Ready to Test | XXX
Outbound | Roll back an order that has not been shipped and re-ship | Ready to Test | XXX
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Ready to Test | XXX
Inventory Management | Perform scheduled cycle counts by item | Ready to Test | XXX
Inventory Management | Perform on demand cycle counts by location | Ready to Test | XXX
Inventory Management | Perform scheduled replenishment tasks | Ready to Test | XXX
Inventory Management | Perform on demand replenishment tasks | Ready to Test | XXX
Inventory Management | Over-replenish | Ready to Test | XXX
Inventory Management | Perform exception during replenishment | Ready to Test | XXX

## Cutover Plan
JSA Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | XXX
3 | Set up Shopify | Set up Shopify Instances in Production environment | FALSE | XXX
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE | DEP/XXX
5 | Test Order Pull | Create a test order in Shopify and bring order into Deposco | FALSE | XXX
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Shopify | FALSE
7 | Test Inventory Push | Send an inventory push from Deposco to Shopify | FALSE
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE
10 | Master Data Check - Items | Look through items in production environment | FALSE
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE
18 | Inventory Push to Shopify | Inventory is pushed to shopify | FALSE
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Shopify Instances to bring in orders | FALSE
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE

## Pre-UAT Tasks
JSA UAT Check List
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE | Comments
1 | Master Data | Items, Locations, LPNs are labeled with scannable barcodes (locations are barcoded) | FALSE | JSA |  | 2025-06-20
2 | Orders Created | Real orders are created with items that have scannable stock that exists in scannable locations (JSA to send Deposco yesterday/today's orders, Deposco to send completed Data Exchange template) | FALSE | JSA |  | 2025-06-20
3 | Carrier Account Set Up | Confirm UPS and Fedex accounts are registered | FALSE | DEP |  | 2025-06-20
4 | Printer Detail Set Up | Atleast one Hip printer, pdf printer, regular zpl printer should be set up | TRUE | DEP/JSA |  | 2025-06-20
5 | Printer Assignment Creation | Assigning what documents should be printed on each printer (Deposco to confirm this week) | FALSE | DEP/JSA |  | 2025-06-20
6 | Define super users | Define super users (Edgar, Eduardo) | TRUE | JSA |  | 2025-06-20
7 | Create UAT Test Cases | DEP to create base test cases / JSA to think of potential edge cases to stress test the system | TRUE | DEP/JSA |  | 2025-06-20
8 | Charge the handhelds | Charge the handhelds | TRUE | JSA |  | 2025-06-20
9 | Set up Pack Stations | Configure packstations as a resource and assign printers | TRUE | JSA |  | 2025-06-20
10 | Ensure shipping doors are created in Deposco | Ensure shipping doors are created in Deposco | TRUE | JSA |  | 2025-06-20
11 | Ensure all locations are assigned to a zone | Ensure all locations are assigned to a zone | TRUE | DEP/JSA |  | 2025-06-20
12 | User Set Up | User Set Up | FALSE | JSA |  | 2025-06-20
13 |  |  | FALSE
14 |  |  | FALSE
15 |  |  | FALSE
16 |  |  | FALSE
17 |  |  | FALSE
18 |  |  | FALSE
19 |  |  | FALSE
20 |  |  | FALSE
21 |  |  | FALSE
22 |  |  | FALSE
23 |  |  | FALSE
24 |  |  | FALSE
25 |  |  | FALSE
26 |  |  | FALSE
27 |  |  | FALSE
28 |  |  | FALSE
29 |  |  | FALSE
30 |  |  | FALSE
31 |  |  | FALSE
32 |  |  | FALSE
33 |  |  | FALSE
FALSE
FALSE

## UAT Task List
JSA Onsite Config/Future Phase Initiatives
| TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | XXX Comments
Completed | Move Container | Display stock in container | 2025-05-29
Completed | Assign Trip | Potentially display assigned pallets location | 2025-06-19
| Assign trip | Override SCAC with Ship Via | 2025-06-19
| Repurposing fields | validate with JSA that all necessary fields are available and relabeled as expected | 2025-06-19
| Quickbooks Testing |  | 2025-06-19
Completed | Pick Sequence Query | WorkTask.getSingleTangiblePickTaskByLocationOrder needs to be adjusted to order picktasks by pack type | 2025-06-19
| Listbox/Screen overrides | validate with JSA that all necessary fields are available in the handheld. | 2025-06-19
| Handheld Tabbing | ensure after each scan the next box makes sense | 2025-06-19
| Billing Profiles | are all adhoc charges and scheduled charges available | 2025-06-19
UAT day one 6/23/25
Open | LOT included ATP | Edit ATP query to consider lot | 2025-06-23
Completed | CO Header Data exchange includes notes | CO Header Data exchange includes notes and material info | 2025-06-23
In Progress | Delete dummy locations | Delete dummy locations | 2025-06-23
In Progress | Third party information | When Freight Terms Type = Third Party --> need to be able to enter 3rd party info on COW and DE and have that info populate on the BOL WAREHOUSE NOTES , CODE NUMBER, BOL NOTES REMOVE NMFC IF NO NMFC | 2025-06-23
Completed | CO Notes (entered on CoWorkbench) to display on the picking screen (SingleScanPicking) | CO Notes to display on the picking screen | 2025-06-23
Completed | Add TL option to assign trip DD | Add TL option to assign trip DD | 2025-06-23
Completed | Remove Estimated DD and Scheduled DD from Assign Trip | Remove Estimated DD and Scheduled DD from Assign Trip | 2025-06-23
In Validation | Take Picture of BOL on Assign Trip process | Take Picture of BOL on Assign Trip process | 2025-06-23
UAT day TWO 6/24/25
In Progress | BOL formatting | Need to add Notes and Hazmat info + 3rd party billing info + more | 2025-06-24
Completed | Single scan picking tabbing | Should transition to next screen (possible hand held issue) | 2025-06-24
Completed | Item code printing | Code | 2025-06-24
Open | Trigger Review on CoHeader | Trigger if Sales Order number (entered on CoWorkbench) if on duplicate order | 2025-06-24
Completed | Show 'Outbound LPN' on Single Scan Picking screen | Show 'Outbound LPN' on Single Scan Picking screen | 2025-06-24
Completed | item label qty on ss picking screen | item label qty on ss picking screen number of copies | 2025-06-24
Completed | Need to see if OFP will pick up incorrect orders | Create freight order and try to wave as a UPS parcel order and vice versa | 2025-06-24
Completed | Phone number default value | Ship to phone on orders should default to (6307731830) same as on facility | 2025-06-24
Completed | Enable inventory ledger | Enable inventory ledger | 2025-06-24
UAT day THREE 6/25/25
Open | LPN number in single scan picking needs more height s o the full text shows |  | 2025-06-25
N/A | SHIPPING REPORT PRINT ON ORDER PAL | Not possible to print a report in report builder with a PAL - will need to demo how JSA can export this data from within report builder | 2025-06-25
Open | Validate Hazmat info can ship on FedEx Ground |  | 2025-06-25
Completed | Develop POI rules to map third party address info based on the freight bill to acount number entered during CO Workbench and/or Data Exchange |  | 2025-06-25
Open | Finalize Billing Invoice and Quickbooks integration |  | 2025-06-25
Open | Confirm hazmat details when shipping FedEx Ground |  | 2025-06-25
In Progress | Report to schedule the LTL pick ups |  | 2025-06-25
Completed | Attachments, currently the attachments are not printing |  | 2025-06-25 |  |  |  |  | Can you double check. Is no longer printing the attachements again.
In Validation | Adding a note when you are done picking an order “New Order” need to pop out |  | 2025-06-25
Completed | Batch Picking Lot Number | Display the lot number on the picking screen | 2025-07-02

## Go-Live Tasks
JSA Go Live Tracker
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE | Comments
1 | Staging location when completing an exception | ensure staging location scanned during exception is saved as a staging location not a pickable locaiton | FALSE | DEP | Matthew
2 | Add itemcode and PO number to picking screens |  | FALSE | DEP | Matthew
3 | Add validation to prevent mixed BU pallets during picking |  | FALSE | DEP | Kevin
4 | Save images taken in ATTC of bol to orderheader |  | FALSE | DEP
5 | Validate billing rates look accurate | These are the contracts - https://drive.google.com/drive/folders/1Z9X5aK_93lsK-1CzsOvAGwX2y0GRr7Az Add cardboard is not in most contracts but the price is always 5.50 | TRUE | DEP/JSA | Emily
6 | Add tracking number on orderHeader view |  | TRUE | DEP | Emily
7 | Make loom video on how to copy billing profiles |  | FALSE | DEP | Emily
8 | Adjust Adhoc billing charges in single scan picking |  | TRUE | DEP | Kevin
9 | add current container api sql to orderheader |  | TRUE | DEP | Emily
10 | add socket rules for fedex op950 form | contact number/ shipper name | TRUE | DEP | Kevin
11 | move bol printing rules to end of sspacking |  | TRUE | DEP | Emily
12 | look into ways to optimize picking drums | example from lalo: he had to pick 2 drums from a location, then was sent back to the same locaiton to pick 2 more of the same drum [SO45]. Would like to see total item count | TRUE | DEP
13 | Inventory report |  | TRUE | DEP | Kevin
14 | Check on enter vs clicking create trip in ATTC | doesnt save the image if they clikc create trip | FALSE
15 | warehouse look up | scan container and display order tied to contaienr | TRUE
16 | bol | add lpn to bol, and case statements to exclude ground orders from tare | FALSE
17 | attc | trip created message | FALSE
18 |  |  | FALSE
19 |  |  | FALSE
20 |  |  | FALSE
21 |  |  | FALSE
22 |  |  | FALSE
23 |  |  | FALSE
24 |  |  | FALSE
25 |  |  | FALSE
26 |  |  | FALSE
27 |  |  | FALSE
28 |  |  | FALSE
29 |  |  | FALSE
30 |  |  | FALSE
31 |  |  | FALSE
32 |  |  | FALSE
33 |  |  | FALSE
FALSE
FALSE