## Schedule
Pitted Logistics Project Tracker - Key Dates and Documents
Orientation - Success Criteria/Goals
Goal | Metric
Increase Daily Order Volume Capacity > 500 Orders Per Day | Widget: Sales Orders Shipped Per Day (Last 14 Days) Success Criteria: Ability to fulfill >500 orders in one day during a monthly drop and/or peak season
Decrease # of days behind during peak season (bring down to less than 1 week) | Widget: Order Backlog by Created Date Success Criteria: No open orders older than 7 days old during peak a monthly drop and/or peak season
Decrease # of cancellations per week due to overselling/inventory inaccuracy | Widget: Customer Order Cancelation Rate Success Criteria: TBD
Orientation - Baseline Education Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions | 2025-01-14
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports | 2025-02-03
Socket Set Up | How to set up socket integrations per facility. | 2025-02-03
Design - Documentation
Document | Description | Delivery Date
Onsite Design Agenda | Link - Agenda for 2 day onsite design visit to Pitted warehouse | 2025-01-13
Master Design Document | Link - Solution Outline for Pitted to be used as guide for Configuration/Validation phases of the project. | 2025-02-03
Configuration and Validation - Delivery and Testing Schedule
Topic | Description | Config Delivery Date | Testing % Complete | Testing Due Date
Inbound/Putaway | General Receiving (Purchase Order, Customer Return, Blind RMA), Move Item/Container/Stock, Unreceive | 2025-02-06 |  | 2025-02-11
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Product Conversion with Workorder, Kit to Stock | 2025-02-11 |  | 2025-02-13
Outbound I | Outbound Order Management, Waving, Singles Picking, Batch Picking, Undo Release Wave, Exceptions in Picking, Kit to Order, Kit To Stock | 2025-02-13 |  | 2025-02-18
Outbound II | Packing and Shipping, Repalletize, Rollback After Picking, Void and Reprocess Shipment, Assign Trip to Container, Packing Slip | 2025-02-18 |  | 2025-02-20
3PL Billing | Billing Profiles, Configs, and Invoices | 2025-02-18 |  | 2025-02-20
Integrations - Sockets | All endpoints/user scenarios for Shopify, Walmart, Quickbooks Online, and Shipping Carriers | 2025-02-20 |  | 2025-02-25
Integrations - DEP API | Gabb and Velvet API setup | 2025-02-21 |  | 2025-02-28
Reporting | Report Builder, Dashboard Widgets (typically completed post UAT) | 2025-02-25 |  | 2025-03-03
End to End Testing | Testing all process flows with live data end to end | 2025-02-27 |  | 2025-02-28
Validation - User Acceptance Training
Task/Activity | Description | Delivery Date | Execution Start Date | Execution End Date
UAT Onsite Agenda | Link - Schedule for 3 day Deposco onsite visit to Pitted for User Acceptance Training | 2025-02-27 | 2025-03-04 | 2025-03-06
SOP Documentation | Link - Recommended SOP Creation Tool - to be used throughout Configuration/Validation Phases in order to have SOP's in place for UAT and Go Live
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 2025-03-06 | 2025-03-06 | 2025-03-06
Deploy - Go Live
Task/Activity | Description | Delivery Date | Execution Start Date | Execution End Date
Cutover Steps | Review roles and responsibiliteis for pre-cutover week as well as cutover day.
Deposco Onsite Support | 4-5 Days of Deposco onsite support for cutover activities and stabilization support
Project Closeout | Review delivered solution compared to original project plan and close implementation phase / begin Continuous Improvement phase
Go live Agenda | Link - Schedule for 4 day Deposco onsite visit to Pitted for Go live | 2025-03-07 | 2025-03-07 | 2025-03-07
Go live | Implement Deposco with a phased rollout | 2025-03-18 | 2025-03-18 | 2025-03-21

## Task Tracker
Pitted Logistics Task Tracker
1-Blocker (Blocking progress on the project within next week)
2-Critical (Critical to go-live and our path to completion)
3-High(Impacting our path to go-live but able to work around or deal)
4-Low (No impact to path to completion)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | Priority | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Date Opened | Due Date | DEP Comments | Pitted Comments
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task | 2. Critical | FALSE | FALSE | Completed | DEP |  | 2024-12-06 | 2024-12-10
Orientation | Setup Client Mavenlink Account | Setup Mavenlink with tenant code and General / Project Management tasks | Task | 2. Critical | FALSE | FALSE | Completed | DEP |  | 2024-12-06 | 2024-12-10
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task | 2. Critical | FALSE | FALSE | Completed | DEP |  | 2024-12-06 | 2024-12-10
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task | 2. Critical | FALSE | FALSE | Completed | DEP |  | 2024-12-06 | 2024-12-10
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task | 2. Critical | FALSE | FALSE | Completed | DEP |  | 2024-12-06 | 2024-12-10
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task | 2. Critical | FALSE | FALSE | Completed | DEP |  | 2024-12-06 | 2024-12-10
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task | 2. Critical | FALSE | FALSE | Open | DEP |  | 2024-12-17 | 2025-01-03
Orientation | Purchase Printers *if applicable* | Purchase wifi printers that fit with all of Deposco's required parameters | Task | 3. High | TRUE | TRUE | Completed | Pitted | Tyler | 2024-12-17 | 2025-02-28 | Help Site Recommendations
Orientation | Purchase Handhelds *if applicable* | Purchase handheld devices that fit with all of Deposco's required parameters | Task | 3. High | TRUE | TRUE | Completed | Pitted | Tyler | 2024-12-17 | 2025-02-28 | Help Site Recommendations
Orientation | Setup Parcel Carrier Accounts | Set Up USPS carrier account | Task | 3. High | TRUE | TRUE | Validation | Pitted | Tyler | 2024-12-17 | 2025-01-03 | Help Site Link
Orientation | Setup Parcel Carrier Accounts | Set Up UPS carrier account | Task | 3. High | TRUE | TRUE | Validation | Pitted | Tyler | 2024-12-17 | 2025-01-03 | Help Site Link
Design | Design Doc Delivery - Pt 2 | Deliver Outbound Section of Master Design Doc | Task | 2. Critical | TRUE | TRUE | Open | DEP |  | 2024-12-17 | 2025-01-31
Orientation | Setup Parcel Carrier Accounts | Set Up eHub carrier account | Task | 3. High | TRUE | TRUE | Validation | Pitted | Tyler | 2024-12-17 | 2025-01-03 | Help Site Link
Orientation | Setup Exisiting Sockets | Set Up Quickbooks Online Integration | Task | 3. High | TRUE | TRUE | Needs Info | Pitted | Pat | 2024-12-17 | 2025-01-17 | Set up using the help site link
Design | Design Doc Review - Pt 1 | Review Inbound, Inventory Management, Picking/Waving, and Integrations sections of Master Design Doc | Task | 2. Critical | TRUE | TRUE | Completed | DEP/Pitted |  | 2024-12-17 | 2025-02-04 | Link
Orientation | Setup Print Client (Windows) | Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team | Task | 3. High | TRUE | TRUE | Open | Pitted | Mark | 2024-12-17 | 2025-01-24 | Help Site Link
Validation | Test Case | Completion of Inbound Unit Test Cases | Task | 3. High | TRUE | TRUE | Completed | DEP/Pitted | Karina | 2024-12-17 | 2025-02-07 | Please record test orders or any comments in the "Test Data/ Client Notes" column in the "Test Cases - Unit" Tab
Orientation | Setup Exisiting Sockets | Set Up Shopify Integration | Task | 3. High | TRUE | TRUE | Completed | Pitted | Pat | 2024-12-17 | 2025-01-17 | Set up using the help site link
Orientation | Setup Exisiting Sockets | Set Up Walmart.com Integration | Task | 3. High | TRUE | TRUE | Completed | Pitted | Pat | 2024-12-17 | 2025-01-17 | Set up using the help site link
Orientation | General Application and UI Overview Demo | Topics Include: - Help Site - UI Navigation (Menus/Views/Layouts/Searching) - Settings and User Management - Message Center Overview - Handheld Menu Access | Task | 3. High | TRUE | FALSE | Open | DEP |  | 2024-12-17 | 2025-01-03
UAT | Barcode Warehouse Locations | Label all locations in warehouse | Task | 3. High | TRUE | TRUE | Completed | Pitted | Karina | 2024-12-17 | 2025-03-07 |  | If this is talking about physically labeling locations in the warehouse, this is complete
Validation | Master Data Gathering | Shopify Item Updates | Task | 3. High | TRUE | TRUE | Completed | Pitted | Pat | 2024-12-17 | 2025-02-10
Configuration | Master Data Gathering | Case Pack Uploads | Task | 3. High | TRUE | TRUE | Needs Info | Pitted | Pat | 2024-12-17 | 2025-02-10 | All pack information that will need to be in Deposco
Configuration | Master Data Gathering | Product Categories | Task | 4. Low | TRUE | TRUE | Closed | Pitted | Pat | 2024-12-17 | 2025-02-10
Configuration | Master Data Gathering | Kit Header/ Kit Detail | Task | 3. High | TRUE | TRUE | Validation | Pitted | Pat | 2024-12-17 | 2025-02-10 | Using for product conversion to build stock
Configuration | Master Data Gathering | Component | Task | 3. High | TRUE | TRUE | In Progress | Pitted | Pat | 2024-12-17 | 2025-02-10
Design | Master Data Gathering | Create Business units | Task | 3. High | TRUE | TRUE | Completed | Pitted | Tyler | 2024-12-17 | 2025-01-21 | Please create all business units/customers. Keep in mind once the code is set we cannot change it later
UAT | Master Data Gathering | Locations/Zones | Task | 4. Low | TRUE | TRUE | Completed | Pitted | Karina | 2024-12-17 | 2025-02-10 | Label locations and determine zones for locations | Tyler needs Deposco support in configuring zones, specifically the strategy and Pitted's current warehouse layout. How do you mass assign locations to zones? jogier@deposco.com Will we need to assign in the zone to locations in system or do we need to provide you a file with zones?
Validation | Test Case | Completion of Inventory Unit Test Cases | Task | 3. High | TRUE | TRUE | Completed | DEP/Pitted | Karina | 2024-12-17 | 2025-02-14 | Please record test orders or any comments in the "Test Data/ Client Notes" column in the "Test Cases - Unit" Tab
UAT | Warehouse zones | Determine reserve, pickable, receiving, shipping and reserve-pickable zones (for velvet freight) | Task | 2. Critical | TRUE | TRUE | Completed | Pitted | Karina | 2024-12-17 | 2025-02-17 |  | jogier@deposco.com Do I need to edit these in depsoco or do I need to send you a file with this information?
Validation | Test Case | Completion of Outbound I Unit Test Cases | Task | 3. High | TRUE | TRUE | Completed | DEP/Pitted | Karina | 2024-12-17 | 2025-02-21 | Please record test orders or any comments in the "Test Data/ Client Notes" column in the "Test Cases - Unit" Tab
UAT | Location Pick sequence | Determine location pick sequence prior to UAT | Task | 2. Critical | TRUE | TRUE | Completed | Pitted | Karina | 2024-12-17 | 2025-02-24 | First location start with 100,000 and leave atleast 10,000 numbers in between each location to leave the ability to add locations in the future | jogier@deposco.com sara.kulkarni@deposco.com Can we mass update and import the pick seq.?
UAT | Create storage details | Storage details are required for all pickable locations and will be needed for replenishments | Task | 2. Critical | TRUE | TRUE | Completed | Pitted | Karina | 2024-12-17 | 2025-02-24 | This is a requirement to use base replenishments | jogier@deposco.com sara.kulkarni@deposco.com Can we mass update and import the storage details.?
Design | Gather Non Base Fields | Get all fields from Shopify needed in Deposco, determine if they are tags or fields | Task | 1. Blocker | TRUE | TRUE | Open | DEP/Pitted | Pat | 2024-12-17 | 2025-02-28
Validation | Test Case | Completion of Integrations Unit Test Cases | Task | 3. High | TRUE | TRUE | Open | DEP/Pitted | Pat | 2024-12-17 | 2025-02-28 | Please record test orders or any comments in the "Test Data/ Client Notes" column in the "Test Cases - Unit" Tab
UAT | Create kit/component field mappings | Used for AMZ FBM skus | Task | 3. High | FALSE | FALSE | Open | Pitted | Pat | 2025-02-13 | 2025-03-04
UAT | Warehouse Setup | Set up printers | Task | 4. Low | TRUE | FALSE | Open | Pitted | Mark | 2024-12-17 | 2025-03-07 | Link to Printer Set Up
UAT | Warehouse Setup | Set up printer assignments | Task | 4. Low | TRUE | FALSE | Open | Pitted | Mark | 2024-12-17 | 2025-03-07 | Link to Printer Assignment Set Up
UAT | Warehouse Setup | Set up printer resources | Task | 4. Low | TRUE | FALSE | Open | Pitted | Mark | 2024-12-17 | 2025-03-07 | Link to Printer Resource Set Up
UAT | Create carrier special services records for hazmat items | Carrier special services records tell ups what is in the shipment for hazmat items | Task | 3. High | FALSE | FALSE | Completed | Pitted | Karina | 2025-02-18 | 2025-03-04 |  | jogier@deposco.com Where do I complete this task?
UAT | Add billing profiles and configs | Copy the existings billing profiles to create for all customers and adjust prices | Task | 3. High | FALSE | FALSE | Open | Pitted | Pat | 2025-02-19 | 2025-03-04
Configuration | Outbound Set Up | Ship Translations are created | Task | 4. Low | TRUE | TRUE | Open | DEP |  | 2024-12-17 | 2025-03-07
Validation | Test Case | Completion of Outbound 2 Unit Test Cases | Task | 3. High | TRUE | TRUE | Completed | DEP/Pitted | Karina | 2024-12-17 | 2025-03-07 | Please record test orders or any comments in the "Test Data/ Client Notes" column in the "Test Cases - Unit" Tab
Go Live | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task | 4. Low | FALSE | TRUE | In Progress | Pitted | Karina | 2024-12-17 | 2025-03-14
Go Live | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task | 4. Low | FALSE | FALSE |  | Pitted | Karina | 2024-12-17 | 2025-03-14
Go Live | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task | 4. Low | FALSE | FALSE | Open | Pitted | Pat | 2024-12-17 | 2025-03-14
Configuration | Setup Fedex Account | Tyler to setup fedex shipping account | Task | 3. High | FALSE | FALSE | Completed | Pitted | Tyler | 2025-02-01 | 2025-02-12
Configuration | Setup Seller Central Account | Tyler to setup Amazon seller central account | Task | 3. High | FALSE | FALSE | Completed | Pitted | Tyler | 2025-02-01 | 2025-02-12
UAT | Setup Users and User Groups | Create users and assign them to specific user groups | Task | 3. High | FALSE | FALSE | Open | Pitted | Tyler | 2025-02-12 | 2025-03-04
Go Live | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task | 4. Low | FALSE | FALSE | Open | Pitted | Karina | 2024-12-17 | 2025-03-14
UAT | Determine frequency of integration pulls | How often should we pull orders, items, returns, and push inventory? | Question | 2. Critical | FALSE | FALSE | Open | Pitted | Tyler | 2025-02-13 | 2025-03-04 |  | jogier@deposco.com what are the standards? As a default, I am thinking order pulls should happen every minute, items daily, returns every minute (?), and inventory every minute. pat@pittedlogistics.com may have specific overrides to this for certain customers.
Go Live | Determine from email | When sending receipt emails and return shipping labels we cannot use the "system@deposco.com" email for legal reasons. Which email should we use? | Question | 3. High | FALSE | FALSE | Completed | Pitted | Tyler | 2025-02-18 | 2025-03-04 |  | jogier@deposco.comoperations@pittedlogistics.com
Go Live | Master Data Gathering | Carton Types | Task | 4. Low | TRUE | TRUE | Open | Pitted | Pat | 2024-12-17 | 2025-03-14
Go Live | Container Labels | Labels printed and labeled on containers | Task | 3. High | FALSE | FALSE | Completed | Pitted | Karina | 2024-12-17 | 2025-03-14
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
UAT | Set non shopify order tax to 0 during poi | Tax should not send to qbo unless shopify orders | Task | 3. High | FALSE | TRUE | Closed | DEP | Josiah | 2024-10-14
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Recordings
Pitted Logistics Demo Videos
# | Date | Category | DESCRIPTION | LINK
Misc DEMOS
1 |  | Baseline Education Sessions | Deposco User Exerience | PITTED & DEP _ General UI & Data Exchange demos, 3PL Customer Matrix Review-20250113_143311-Meeting Recording.mp4
2 |  | Baseline Education Sessions | Master Data / Data Exchange
3 |  | MDD Review | Master Design Document Review 1 - 2/4/25 | https://drive.google.com/file/d/1eZEh147mCpSlmRor1lEb1C7N0hfzO0kY/view?usp=drive_link
4
Process DEMOS
1 |  | Integrations | Shopify, Walmart and Deposco API
2 |  | Inbound/Putaway | PO Receiving | Pitted Receiving and Putaway Demo-20250206_153153-Meeting Recording.mp4
3 |  | Inbound/Putaway | Receive PO with Order Notes & Direct Putaway
4 |  | Inbound/Putaway | Unreceiving
5 |  | Inbound/Putaway | Blind RMA Receiving
6 |  | Inbound/Putaway | Receiving Putaway
7 |  | Inventory Management | Cycle Counts | PITTED & Deposco Demo - 2.11.25 - Recording.mp4
8 |  | Inventory Management | Cycle Counts Continued
9 |  | Inventory Management | Adjust Inventory
10 |  | Inventory Management | Replenishment:
11 |  | Inventory Management | Product Conversion:
12 |  | Inventory Management | Kit To Stock:
13 |  | Outbound I | Build & Release Wave | https://drive.google.com/file/d/1GUJXaH8YKiWB3BGLDKsWB9mYcElmjN_Y/view?usp=drive_link
14 |  | Outbound II | Singles Picking | PITTED & Deposco Demo - 2.18.25 - Recording.mp4
15 |  | Outbound II | Multi Picking
16 |  | Outbound II | SIngles Packing (Pack Order by Item)
17 |  | Outbound II | Multis Packing
18 |  | Outbound II | Wholesale Packing & Assign Trip

## Timeline Considerations
March 4 Go Live | March 17 Go Live
UAT 25th - 27th | Gabb and Velvet have their API completed
Go live March 4th-7th | Josiah will be onsite the following week and may not be available if any issues come up until later in the day
No week between uat and go live | Team has a full week between uat and go live to adjust/correct any errors
Josiah is available the following two weeks for support | Would better align with bi-monthly billing
Gabb and Velvet may not be ready and are the most complex clients

## Test Cases - Unit (hidden)
Spellbinders Unit Test Cases
Topic | Test # | Scenario | Expected Outcome | Owner | Status | Test Data/Client Notes | Deposco Notes
Inbound/Putaway | 1.01 | Receive against a Purchase Order (PO) |  |  | 93.33%
Inbound/Putaway | 1.01.01 | When prompted to scan the purchase order identifier to receive the purchase, the user scans or enters an invalid purchase order to receive against | The user is displayed an error that the identifier is invalid | Pitted Team | Pass
Inbound/Putaway | 1.01.02 | When prompted to scan the purchase order identifier, the user scans a valid purchase order identifier that exists and has quantity left to receive | The user is taken to the screen to receive the items. The item summary screen is displayed | Pitted Team | Pass
Inbound/Putaway | 1.01.03 | When configured to display notes during receiving, the user scans or enters a purchase order that has notes populated at the header level with title = "Receiving" | The user is displayed the note before the summary screen for the PO is shown | Pitted Team | Pass
Inbound/Putaway | 1.01.04 | Receive an item that is not originally on the PO. Enter an item on the receive item screen that is not apart of the PO | Receive an error message that the SKU is invalid | Pitted Team | Pass
Inbound/Putaway | 1.01.05 | Receive an item that is on the PO. Enter an item on the receive item screen that is in the available SKU list box | The user is taken to the screen to receive the specifc pack and quantity. The receive item config screen is displayed. | Pitted Team | Pass
Inbound/Putaway | 1.01.06 | Receive an overage against a PO item. Enter a quantity that exceeds the order line quantity | Receive an error message that the quantity exceeds the threshold. | Pitted Team | Pass
Inbound/Putaway | 1.01.07 | Receive an underage against a PO item. Enter a quantity that is less than the order line quantity | The user is taken to the screen to receive the items. The item summary screen is displayed. The item quantity that was previously received will be decremented from the total left to be received on the PO | Pitted Team | Pass
Inbound/Putaway | 1.01.08 | User partially receives the purchase order and hits the 'finish' button to temporarily exit the purchase order | The user is exited from the PO receiving screen. The PO goes to 'Partial Receipt' status. All stock received is in Receiving location | Pitted Team | Pass
Inbound/Putaway | 1.01.09 | User completes receiving the entire purchase order | The user is exited from the PO receiving screen. The PO goes to 'Received' status, all stock is in Receiving location | Pitted Team | Pass
Inbound/Putaway | 1.01.10 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | Pitted Team | Ready to Test
Inbound/Putaway | 1.01.11 | User selects "Yes" on Putaway dropdown when confirming item quantity to receive | User is prompted on next screen to confirm quanitity to print | Pitted Team | Pass
Inbound/Putaway | 1.01.12 | User selects "No" on Putaway dropdown when confirming item quantity to receive | User is prompted to put the item directly away after each line is received | Pitted Team | Pass
Inbound/Putaway | 1.01.13 | User selects "Yes" on Print dropdown when confirming item quantity to receive | User is not prompted for number of labels to print | Pitted Team | Pass
Inbound/Putaway | 1.01.14 | User selects "No" on Print dropdown when confirming item quantity to receive | User continues receiving next item | Pitted Team | Pass
Inbound/Putaway | 1.01.15 | User enters quantity > 0 in quantity to print | Number of labels entered are printed | Pitted Team | Pass
Inbound/Putaway | 1.02 | Receive against an Inbound Transfer Order (ITO) |  |  | 0%
Inbound/Putaway | 1.02.01 | When prompted to scan the ITO identifier to receive the Inbound Transfer, the user scans or enters an invalid purchase order to receive against | The user is displayed an error that the identifier is invalid | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.02 | When prompted to scan the ITO identifier, the user scans a valid Inbound Transfer identifier that exists and has quantity left to receive | The user is taken to the screen to receive the items. The item summary screen is displayed | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.03 | When configured to display notes during receiving, the user scans or enters an ITO that has notes populated at the header level | The user is displayed the note before the summary screen for the ITO is shown | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.04 | Receive overage against an ITO for an item that does not have the over receipt tolerance set at the item level. Enter a quantity that exceeds the threshold set at the workflow process level | Receive an error message that the quantity exceeds the threshold. The workflow setting is invoked | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.05 | User partially receives the ITO and hits the 'finish' button to temporarily exit the Inbound Transfer | The user is exited from the ITO receiving screen. The ITO goes to 'Partial Receipt' status | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.06 | User completes receiving the entire Inbound Transfer Order | The user is exited from the ITO receiving screen. The ITO goes to 'Received' status | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.07 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.08 | User receives against a non-each pack for an item that does not have item attribute capture requirements | The receipt is completed at the non-each pack level | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.09 | User selects "Yes" on Print dropdown when confirming item quantity to receive | User is prompted on next screen to confirm quanitity to print | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.10 | User selects "No" on Print dropdown when confirming item quantity to receive | User continues receiving next item | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.11 | User enters non-numeric or non-positive integer (decimal, negative number, alphanumeric value) in quantity to print. | Error | Pitted Team | Ready to Test
Inbound/Putaway | 1.03 | Receive against a Customer Return (RMA) |  |  | 0%
Inbound/Putaway | 1.03.01 | When prompted to scan the RMA identifier to receive the Customer Return, the user scans or enters an invalid purchase order to receive against | The user is displayed an error that the identifier is invalid | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.02 | When prompted to scan the RMA identifier, the user scans a valid Customer Return identifier that exists and has quantity left to receive | The user is taken to the screen to receive the items. The item summary screen is displayed | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.03 | When configured to display notes during receiving, the user scans or enters an RMA that has notes populated at the header level | The user is displayed the note before the summary screen for the RMA is shown | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.04 | When configured to display notes during receiving, the user scans or enters an RMA that has notes populated at the line level | The user is displayed the note after the line item is selected, and before the item is physically received | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.05 | Receive overage against an RMA for an item that does not have the over receipt tolerance set at the item level. Enter a quantity that exceeds the threshold set at the workflow process level | Receive an error message that the quantity exceeds the threshold. The workflow setting is invoked | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.06 | User partially receives the RMA and hits the 'finish' button to temporarily exit the Customer Return | The user is exited from the RMA receiving screen. The RMA goes to 'Partial Receipt' status | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.07 | User completes receiving the entire Customer Return | The user is exited from the RMA receiving screen. The RMA goes to 'Received' status | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.08 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.09 | User receives against a non-each pack for an item that does not have item attribute capture requirements | The receipt is completed at the non-each pack level | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.10 | User selects "Yes" on Print dropdown when confirming item quantity to receive | User is prompted on next screen to confirm quanitity to print | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.11 | User selects "No" on Print dropdown when confirming item quantity to receive | User continues receiving next item | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.12 | User enters non-numeric or non-positive integer (decimal, negative number, alphanumeric value) in quantity to print. | Error | Pitted Team | Ready to Test
Inbound/Putaway | 1.04 | Receive a Blind Customer Return (Blind RMA) |  |  | 100%
Inbound/Putaway | 1.04.01 | When prompted to scan the RMA identifier to receive the Blind Return, the user scans or enters a previously used Blind Return Number | The user is brought to a new screen that validates if they would like to proceed with the duplicate RMA order number | Pitted Team | Pass | used rma1, rma2 & rma3. all for e3d-081. mw
Inbound/Putaway | 1.04.02 | When prompted to scan the RMA identifier to receive the Blind Return, the user scans or enters a never used Blind Return Number | The user is taken to the screen to receive the items. The item summary screen is displayed | Pitted Team | Pass
Inbound/Putaway | 1.04.03 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | Pitted Team | Pass
Inbound/Putaway | 1.04.04 | User receives against a non-each pack for an item that does not have item attribute capture requirements | The receipt is completed at the non-each pack level | Pitted Team | Pass
Inbound/Putaway | 1.04.05 | User selects "Yes" on Print dropdown when confirming item quantity to receive | User is prompted on next screen to confirm quanitity to print | Pitted Team | Pass
Inbound/Putaway | 1.04.06 | User selects "No" on Print dropdown when confirming item quantity to receive | User continues receiving next item | Pitted Team | Pass
Inbound/Putaway | 1.04.07 | User enters non-numeric or non-positive integer (decimal, negative number, alphanumeric value) in quantity to print. | Error message is thrown | Pitted Team | Pass
Inbound/Putaway | 1.04.08 | User select "Finish" to complete Blind RMA | RMA is moved to a Received status | Pitted Team | Pass
Inbound/Putaway | 1.05 | Putaway - Move Item
Inbound/Putaway | 1.05.01 | User scans or enter an invalid source location from which to move inventory in users assigned facility | Receive an error message that no such location exists in user's assigned facility | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.02 | User scans or enter a valid source location fromk which to move inventory where the location has no stock units present | Receive a screen message that there is no stock in location available to move | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.03 | User scans or enter a valid source location fromk which to move inventory where the location has stock units present | User is directed to the Item Summary screen to display all Items in the specified Location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.04 | User scans or enters an item that doesn't exist in the location | The user is displayed an error that the Item is invalid | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.05 | User scans or enters a valid item to move | User is directed to the "Quantity Input Screen" to specify the Pack/Qty to Move | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.06 | User scans, enters, or selects an item that has multiple stock units in the location. Some of the stock units are allocated to pick tasks | The Stock Unit that is NOT tied to a Pick Task should display on the item listbox with the associated Qty | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.07 | Move multiple quantity for an item in one transaction | User is able to successfully move item/qty to destination location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.08 | Move stock for an item from a return location to a picking location | User is able to successfully move item/qty to specified Picking location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.09 | Move stock for an item from a staging location to a picking location | User is able to successfully move item/qty to specified Picking location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.10 | If stock unit at the pick face location is under the minimum in storage details for the item, the location will populate first in the handheld | User is able to view the location at the top of the list ("Pick Face Consolidate") and is successful when moving the item/qty to the suggested location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.11 | If stock unit at pick face location is above the minimum iin storage details for the item, and the item has existing stock units in the back stock location, those locations will populate first in the handheld | Useer is able to view the locations at the top of the list ("Back Stock Consolidate" and is successful when moving the item/qty to the suggested location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.12 | Locations without a stock unit associated within them will populate as "Empty Location" | User is successful moving item/qty to these suggested locations | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.13 | When moving an item, move it to a different location than one of the suggested locations in the 'Suggested Locations' list box | User is able to successfully move item/qty to a non-suggested location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.14 | Move stock to a mixed-item location. The location contains stocks for other items | User is able to successfully move item/qty to a multi-item Location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.15 | Move stock to a single-item location. The location contains stock for a different item | User receives an error message "the location contains other items already" | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.16 | Move stock to a single-item location. The location contains stock for the same item. | User is allowed to move stock to the scanned location. | Pitted Team | Ready to Test
Inbound/Putaway | 1.06 | Unreceive (PO, ITO, RMA, Blind RMA)
Inbound/Putaway | 1.06.01 | Enter invalid order number to be un-received | User receives error message to input a correct order number | Pitted Team | Pass
Inbound/Putaway | 1.06.02 | Enter valid order number to be un-received | User is directed to the "Select Item to Unreceive" screen | Pitted Team | Pass
Inbound/Putaway | 1.06.03 | Enter valid order number in invalid status to be un-received | User receives error message "Please enter a valid order number to un-receive." | Pitted Team | Pass
Inbound/Putaway | 1.06.04 | Unreceive order with one item received against it | User is able to successfully unreceive the order and is directed back to the Handheld menu with a successful message | Pitted Team | Pass
Inbound/Putaway | 1.06.05 | Unreceive order with multiple items received against it | User is able to select each Item/Qty and continue this process until all affected items/qty is selected | Pitted Team | Pass
Inbound/Putaway | 1.06.06 | Scan valid item to unreceive for order | User receives a message that the selected item was unreceived successfully | Pitted Team | Pass
Inbound/Putaway | 1.06.07 | Scan invalid item to unreceive for order | User receives error "Please enter valid item number/UPC or select pack type to un-receive." | Pitted Team | Pass
Inbound/Putaway | 1.06.08 | Enter a non numeric value in the quantity input section of the screen | The user is displayed an error to "Please enter a valid integer for quantity" | Pitted Team | Pass
Inbound/Putaway | 1.06.09 | Enter a quantity that is higher than the allowed quantity in the quantity input section of the screen | The user is displayed an error that "The specified quantity for the item is greater than the quantity that is available" | Pitted Team | Pass
Inbound/Putaway | 1.06.10 | Enter a negative quantity in the quantity input section of the screen | The user is displayed an error to "Please enter a valid integer for quantity" | Pitted Team | Pass
Inbound/Putaway | 1.06.11 | Enter a quantity that is lesser than the allowed quantity in the quantity input section of the screen | The selected item will remain in the "Items Remaining" listbox with an updated Qty to display how many more units can be unreceived | Pitted Team | Pass
Inbound/Putaway | 1.06.12 | Enter a quantity that is exactly the allowed quantity in the quantity input section of the screen | User receives a message that the selected item was unreceived successfully | Pitted Team | Pass
Inbound/Putaway | 1.06.13 | Enter a non integer (decimal value) in the quantity input section of the screen | The user is displayed an error to "Please enter a valid integer for quantity" | Pitted Team | Pass
Inbound/Putaway | 1.06.14 | Exit process without unreceiving all items on order | Order "status" updates to "Partial Receipt" and the user can re-enter the order to continue unreceiving as needed | Pitted Team | Pass
Inventory Management | 2.01 | Perform Cycle Counts |  |  | 100%
Inventory Management | 2.01.01 | Enter invalid start off location | Enter invalid start off location | Pitted Team | Pass
Inventory Management | 2.01.02 | Enter valid start off location | User is prompted to first location to be cycle counted (should be task with lowest priority and/or pick sequence closest to startoff location) | Pitted Team | Pass
Inventory Management | 2.01.03 | Enter expected location on Location input screen | User is prompted to count items that exist in location | Pitted Team | Pass
Inventory Management | 2.01.04 | Enter unexpected/invalid location on Location input screen | Error message to please scan recommended location | Pitted Team | Pass
Inventory Management | 2.01.05 | Count single item location with stock in it | Should only be allowed to count 1 item in location | Pitted Team | Pass
Inventory Management | 2.01.06 | Count multi item location with stock for multiple skus in it | Should be allowed to count as many items into the location as needed | Pitted Team | Pass
Inventory Management | 2.01.07 | Count multi item location without stock in it | Should be allowed to count as many items into the location as needed | Pitted Team | Pass
Inventory Management | 2.01.08 | Scan item that exists in location to begin counting | User is prompted to type in quantity of item present | Pitted Team | Pass
Inventory Management | 2.01.09 | Scan item that is not in location to begin counting | User is prompted to type in quantity of item present | Pitted Team | Pass
Inventory Management | 2.01.10 | Select next location without counting any items to count zero for the location | User is prompted to walk to and scan next location - count zeros for location skipped | Pitted Team | Pass
Inventory Management | 2.01.11 | Count quantity in eaches | Count stock units in lowest pack quantity (each) | Pitted Team | Pass
Inventory Management | 2.01.12 | Count quantity in non-each pack | Count stock units in selected pack quantity | Pitted Team | Pass
Inventory Management | 2.01.13 | Count quantity that is expected in location | No variance is created | Pitted Team | Pass
Inventory Management | 2.01.14 | Count quantity other than what is expected in location | User is asked to confirm counted quantity for a second time | Pitted Team | Pass
Inventory Management | 2.01.15 | Confirm variance when counting quantity other than what is expected in location | Variance is captured | Pitted Team | Pass
Inventory Management | 2.01.16 | Select Next Item/Location to skip counting an item once scanned | Zero is counted for an item - variance is created | Pitted Team | Pass
Inventory Management | 2.02 | Adjust Inventory - Location Entry |  |  | 100%
Inventory Management | 2.02.01 | Scan Invalid location | Error message | Pitted Team | Pass
Inventory Management | 2.02.02 | Scan valid location with no stock in it | Brought to inventory adjustment menu | Pitted Team | Pass
Inventory Management | 2.02.03 | Scan valid location with stock in it | Brought to inventory adjustment menu | Pitted Team | Pass
Inventory Management | 2.03 | Adjust Inventory - Consume by Item |  |  | 100%
Inventory Management | 2.03.01 | Consume by Item --> Select Back | Brought to inventory adjustment menu | Pitted Team | Pass
Inventory Management | 2.03.02 | Consume by Item --> Scan Invalid Item and click Next | Error message | Pitted Team | Pass
Inventory Management | 2.03.03 | Consume by Item --> Scan Valid Item that exists in location and click Next | User is prompted to enter quantity of item to consume | Pitted Team | Pass | Used loc H9-9. Consumed 3pcs of S5-619
Inventory Management | 2.03.04 | Consume by Item --> Scan Valid Item that does not exists in location and click Next | Error message | Pitted Team | Pass
Inventory Management | 2.03.05 | Consume by Item --> Enter non-numeric qty of item to consume | Error message | Pitted Team | Pass
Inventory Management | 2.03.06 | Consume by Item --> Enter a qty that is higher than available qty to consume | Error message | Pitted Team | Pass
Inventory Management | 2.03.07 | Consume by Item --> Enter a negative quantity in the quantity input section of the screen | Error message | Pitted Team | Pass
Inventory Management | 2.03.08 | Consume by Item --> Enter a quantity that is lesser than the available quantity in the quantity input section of the screen | Quantity entered is added to consume item list | Pitted Team | Pass
Inventory Management | 2.03.09 | Consume by Item --> Enter a quantity that is exactly the allowed quantity in the quantity input section of the screen | Quantity entered is added to consume item list | Pitted Team | Pass
Inventory Management | 2.03.10 | Consume by Item --> Enter a non integer (decimal value) in the quantity input section of the screen | Error message | Pitted Team | Pass
Inventory Management | 2.03.11 | Consume by Item --> Select Confirm after Scanning Valid Items and | User is shown list of all items/quantities to be consumed along with reason code selection & option to add a note | Pitted Team | Pass
Inventory Management | 2.03.12 | Consume by Item --> Select Back after reviewing items to consume | User may start over and recreate list to consume | Pitted Team | Pass
Inventory Management | 2.03.13 | Consume by Item --> Select Reason Code and Submit after reviewing items to consume | Stock is deleted and Inventory Ledger record is created with corresponding reason code for item/location/quantity deleted | Pitted Team | Pass
Inventory Management | 2.04 | Adjust Inventory - Consume All in Location |  |  | 100%
Inventory Management | 2.04.01 | Consume All in Location --> For location with no stock | There are NO Stock Units in the "Review" screen so nothing will get consumed | Pitted Team | Pass
Inventory Management | 2.04.02 | Consume All in Location --> For location with stock that has open pick tasks against it | Receive error message since there is an incomplete Pick Tasks for at least (1) Stock Unit | Pitted Team | Pass | tested on location 57.04.02 which had open tasks against it.
Inventory Management | 2.04.03 | Consume All in Location --> For location with stock that has no open pick tasks | User is directed to the Review screen to display all Stock Units in the Location to Consume All | Pitted Team | Pass
Inventory Management | 2.04.04 | Consume All in Location --> Select Back after reviewing items to consume in location | User is directed back to the "Options" screen to determine which Adjust Inventory process to select | Pitted Team | Pass
Inventory Management | 2.04.05 | Consume All in Location --> Select Reason Code and Commit after reviewing items to consume in location | Receive confirmation message that all Stock Units in Location has been consumed > no Stock Units are available in Location > IGL record created with Reason Code | Pitted Team | Pass | consumed all inventory in H9-9
Inventory Management | 2.05 | Adjust Inventory - Create Inventory |  |  | 100%
Inventory Management | 2.05.01 | Scan Invalid Item | Receive error message that the Item could not be found | Pitted Team | Pass
Inventory Management | 2.05.02 | Scan valid Item | User is directed to the "Attribute" screen to input a Container (if applicable) and to specify the Qty | Pitted Team | Pass | entered S5-619. MW
Inventory Management | 2.05.03 | Create Inventory for Each pack | Since all Items will only have a Pack "Each" - this will add the Stock Unit to the listbox via "ScanItem" screen | Pitted Team | Pass
Inventory Management | 2.05.04 | Enter non-numeric qty of inventory to create | User remains in the "Attribute" screen with a warning message "For input string: xxxx | Pitted Team | Pass
Inventory Management | 2.05.05 | Enter a negative quantity of inventory to create | Receive error message "Quantity must be greater than 0" | Pitted Team | Pass
Inventory Management | 2.05.06 | Enter a non integer (decimal value) of inventory to create | User remains in the "Attribute" screen with a warning message "For input string: xxxx | Pitted Team | Pass
Inventory Management | 2.05.07 | Add multiple items to inventory list to be created for single item locations | Error message | Pitted Team | Pass | Entered S5-619, and tried to add DD110, but got error message. MW
Inventory Management | 2.05.08 | Add additional items to inventory list to be created for multi item locations | User is brought to AttributeScreen to enter in pack & location for item being added | Pitted Team | Pass
Inventory Management | 2.05.09 | Select Confirm | User is directed to the "Review" screen for type "Add Stock" to display all Items/Containers > user to select a Reason Code | Pitted Team | Pass
Inventory Management | 2.05.10 | Select Back after reviewing items to create | User is directed back to the "Options" screen to determine which Adjust Inventory process to select | Pitted Team | Pass | was not directed to "Options" screen. it completed task. | Optoins screen is the screen where you're able to select the type of adjust inventory process
Inventory Management | 2.05.11 | Select Reason Code and Commit after reviewing items to create | Receive confirmation message that all Stock Units in Location have been created > Stock Units are available in Location > IGL record created with Reason Code | Pitted Team | Pass | received message: "1 Each, are created as new. Item(s): [S5-619/1/SF]"
Inventory Management | 2.06 | Directed Replenishments |  |  | 15.38%
Inventory Management | 2.06.01 | Directed Replen, scan valid container to use for replenishments when replenishment tasks are available to complete | Brought to replenishment summary screen | Pitted Team | Pass
Inventory Management | 2.06.02 | Directed Replen, scan valid container when there are no open replenishment tasks to complete | Screen message - nothing to replenish | Pitted Team | Pass
Inventory Management | 2.06.03 | Scan the correct item barcode in the item scan section of the picking screen | Item scan accepted | Pitted Team | Ready to Test
Inventory Management | 2.06.04 | Enter a quantity that is lesser than the required quantity in the quantity input section of the picking screen (Non Grocery Mode) | Quantity entered is decremented from the quantity to pick - remaining quantity is prompted to pick | Pitted Team | Ready to Test
Inventory Management | 2.06.05 | Enter a quantity that is exactly the required quantity in the quantity input section of the picking screen (Non Grocery Mode) & no more replenishment tasks left | Quantity is picked and user is prompted to scan location & item qty to replenish for pick face location | Pitted Team | Ready to Test
Inventory Management | 2.06.06 | Picking Exception - No Stock | Replenishment Task is set to a status "Exception" > IF there are other Reserve Locations that have eligible stock then will create a new Replenishment Task and will prompt the user to the new location - If not, then the Stock Unit at the Location will be placed in a "On Hold" status > a Cycle Count will get generated with a type "Picking Audit" > if there are more Replenishment Tasks, user is directed to another tasks | Pitted Team | Ready to Test
Inventory Management | 2.06.07 | Select "Cart Is Full" on picking screen | User is prompted to begin putaway of items on cart to storage locations | Pitted Team | Ready to Test
Inventory Management | 2.06.08 | Scan the correct item barcode in the item scan section of the replenishment screen | User is directed to specify the Replenish Qty | Pitted Team | Ready to Test
Inventory Management | 2.06.09 | Enter a quantity that is lesser than the required quantity in the quantity input section of the picking screen (Non Grocery Mode) | Quantity entered is decremented from the quantity to replenish - remaining quantity is prompted to replenish | Pitted Team | Ready to Test
Inventory Management | 2.06.10 | Enter a quantity that is exactly the required quantity in the quantity input section of the picking screen (Non Grocery Mode) | Quantity is replenished and user is prompted to replenish next item/location | Pitted Team | Ready to Test
Inventory Management | 2.06.11 | Exception on Replenishment - Location Full | Replenishment Task is set to a status of Destination Full > A new (reverse) replenishment task is created to return the stock to the source reserve location | Pitted Team | Ready to Test
Inventory Management | 2.06.12 | Finish putaway of cart when more replenishment tasks are available to complete | User is presented summary screen of remaining tasks and can start a new replenishment cycle | Pitted Team | Ready to Test
Inventory Management | 2.06.13 | Finish putaway of cart when no more replenishment tasks are available to complete | "Nothing to replenish" | Pitted Team | Ready to Test
Inventory Management | 2.07 | Product Conversion (Work Order) |  |  | 0%
Inventory Management | 2.07.01 | User goes into the "Product Conversion w/ Workorder and enters in the correct kitting location without any open workorders available | Error message: "There are no open workorders to build" | Pitted Team | Ready to Test
Inventory Management | 2.07.02 | User goes into the "Product Conversion w/ Workorder and enters in the correct kitting location with open workorders available | User is brought to the next screen: "Work Order List" and is able to choose from of a list of open workorders to complete | Pitted Team | Ready to Test
Inventory Management | 2.07.03 | User selects available workorder | User is brought to the "Work Order Details" with a summary of the workorder and a list of components and an output SKU | Pitted Team | Ready to Test
Inventory Management | 2.07.04 | User selects "Pause WO" button | User is brought back to the "Work Order List" screen, with the workorder still being available to be completed | Pitted Team | Ready to Test
Inventory Management | 2.07.05 | User selects "End WO" button wihtout any other available WOs | User is brought back to the initial screen with message "There are no open workorders to build." Previous WO will be in a "Partial Complete" status | Pitted Team | Ready to Test
Inventory Management | 2.07.06 | User selects "End WO" button wiht available open WOs | User is brought back to the "Work Order List" screen and is able to select next open WO to complete | Pitted Team | Ready to Test
Inventory Management | 2.07.07 | User selects "Start WO" | User is brought to: "Build Product" with a view of details for the workorder | Pitted Team | Ready to Test
Inventory Management | 2.07.08 | User enters in quantity to build that's larger than the quantity for the workorder | Error message: "Cannot build more than X" | Pitted Team | Ready to Test
Inventory Management | 2.07.09 | User enter in a quantity less than the quantity to build for the workorder | User is brought back to the "Work Order Details" screen with the quantity build & quantity to build values being updated to reflect the amount that was built and is prompted to continue building out the item until the quantity built reaches the conversion # | Pitted Team | Ready to Test
Inventory Management | 2.08 | Kit to Stock (Non-Workorder) |  |  | 0%
Inventory Management | 2.08.01 | User enter in correct kitting location & kitted item | Brings user to next screen "Kit Item Config" | Pitted Team | Ready to Test
Inventory Management | 2.08.02 | User enters correct kitting location but not a kitted item | Error Message: "Item entered is not a kit item" | Pitted Team | Ready to Test
Inventory Management | 2.08.03 | User enters in quantity to build greater than the suggested quantity shown on the screen | Error Message: "No more than suggested number of kits can be built." | Pitted Team | Ready to Test
Inventory Management | 2.08.04 | User enters in quantity to build less than or equal to the suggested quantity shown on the screen | Brings user to next screen "Kitting Summary" | Pitted Team | Ready to Test
Inventory Management | 2.08.05 | User clicks "Next" on the screen with kit summary | User is brought back to the "Kit Item Config" with a new message on the bottow of the scrren "New kit items "X" created." and the suggested quantity should reflect how many left can be built. User is able to continue to build kits with the remainding components left in the kitting location | Pitted Team | Ready to Test
Inventory Management | 2.08.06 | User clicks "Done" on the "Kit Item Config" screen | User is brought back to the main menu screen for product conversion | Pitted Team | Ready to Test
Outbound I | 3.01 | Order Management |  |  | 0%
Outbound I | 3.01.01 | User pulls in order where order has stock in the facility | Order should be routed to its according facility based on the parameters set in order routing | PittedTeam | Ready to Test
Outbound I | 3.01.02 | User pulls in order where order has no stock in the facility | Order should be backordered, and Pitted can go in and cancel the order or force allocate | PittedTeam | Ready to Test
Outbound I | 3.01.03 | User pulls in order where there are some order lines that are able to be fulfilled and some that don't have available stock in the facility | Lines that are availble to be fulfilled are routed to its facility, the other lines are backordered, and Pitted can go in and cancel the order lines | PittedTeam | Ready to Test
Outbound I | 3.01.04 | Partially cancel a CoLine | Noncancelled order line quantities will be routed to its according facility if there are enough stock units to fulfill the customer order line | PittedTeam | Ready to Test |  | Test with order: CO36726, Partially cancel 8 units of item SCS-244. Reprocess customer order
Outbound I | 3.01.05 | Fully cancel CoLine | Cancelled coLines will be backorders, Pitted can go in and cancel. The other lines associated with the same coHeader will be routed to its according facility | PittedTeam | Ready to Test |  | Test with order: CO36723, Cancel order line with the item T-016 on the orer
Outbound I | 3.01.06 | Cancel an entire CoHeader | CoHeader will be put into a back ordered status, Pitted can go in and cancel the order | PittedTeam | Ready to Test |  | Test with order: CO36727
Outbound I | 3.01.07 | Pull in UK order | Order should route to UK facility regardless if there is available stock in the PHX facility | PittedTeam | Ready to Test
Outbound I | 3.01.08 | Pull in order where there is stock for one orderline has stoclk in PHX facility and another orderline where there is no stock in PHX but there are availble stock in UK | Order should not be split between facilities, and orderlines withut stock in PHX will be cancelled, the rest will be routed to PHX | PittedTeam | Ready to Test
Outbound I | 3.01.09 | Force allocate coLine using Force Allocate Process Action Link Button | Regardless of available stock, order should be routed to the according facility | PittedTeam | Ready to Test |  | Test with order: CO36728, force allocate to PHX facility
Outbound I | 3.02 | Build & Release Wave |  |  | 60%
Outbound I | 3.02.01 | User manually waves a single order from the order entity using the correct process action link | Order is waved based on its parameters |  | Pass | TESTED ORDER 29588 AND PASSED | 29565: Orders have to have "POI?" field check in order to be waved. This field will be automatically checked for all new orders pulled in the system. For testing, you can manually run POI through the process action drop down or manually checking the box. 29628: Order will wave as Walmart since the order source is Walmart. WEB1168401: Order needs to be run through POI so that the order profile is stamped, ince the field is stamped then it will wave occirdoing to the profile
Outbound I | 3.02.02 | User manually waves multiple orders from the order entity | Orders are waved based on their parameters |  | Pass |  | Orders need to be ran through POI so that the field is checkd, and then the order will be waved
Outbound I | 3.02.03 | User manually runs Build and Release Wave scheduler | Orders that are not club orders should be waved based on their parameters |  | Pass
Outbound I | 3.02.04 | User manually waves club orders (Build and Release - Club) through order entity | only club orders should be waved |  | Needs Info | I couldn't find any club orders to wave, and I am not sure how to filter this by sku | Club orders are any orders that have the exact same SKU, quantity, and number of lines. The profile is set so that there needs to be at least 25 of these identical orders, but you are able to lower the threshold for testing purposes in Pick Wave Profile --> Identical --> max number of orders
Outbound I | 3.02.05 | User manually rus "Waving - Identicals" scheduler | only club orders should be waved |  | Needs Info | I couldn't find any club orders to test | Club orders are any orders that have the exact same SKU, quantity, and number of lines. The profile is set so that there needs to be at least 25 of these identical orders, but you are able to lower the threshold for testing purposes in Pick Wave Profile --> Identical --> max number of orders
Outbound I | 3.02 | Undo Release Wave |  |  | 50%
Outbound I | 3.02.01 | User manually unrelease wave through Pick Waves entity for a wave in 'Released' status | Orders on the wave are successfully rolled back | Pitted Team | Pass | TESTED ORDER 29588 AND PASSED | PAL Button is called "Undo Release" on the Pick Wave Entity (Found in Distribution Application Menu)
Outbound I | 3.02.02 | User manually unrelease wave through Pick Waves entity for a wave in not 'Released' status | Order fails to roll back since work group for the wave is active | Pitted Team | Failed | tested order Single Small-240917_5 message"pick wave single small Single Small-240917_5 not released" | is wave supposeed to fail? Test should be passed if expected outcome is what happens
Outbound II | 3.03 | Singles Picking |  |  | 100%
Outbound II | 3.03.01 | Enter in picking LPN that does not exist in the system | New container is created in the system & user is able to pick items into new container | Pitted Team | Pass | TESTED ORDER 29588 AND PASSED
Outbound II | 3.03.02 | Enter in location not on the picking screen | Error message: "The location [x] does not match the required location." | Pitted Team | Pass | testing on order 28530. mw / tested on Single Small-240924_1 GSZ
Outbound II | 3.03.03 | Enter in location on the picking screen | Takes user to the item selection picking screen to enter in the SKU | Pitted Team | Pass | testing on order 28530. mw / Single Small-240924_1 GSZ
Outbound II | 3.03.04 | Enter in SKU not on picking screen | Error message: "The SKU [x] could not be found. Please enter a valid SKU." | Pitted Team | Pass | testing on order 28530. mw / Single Small-240924_1 GSZ
Outbound II | 3.03.05 | Enter SKU on picking screen | Takes user to the quantity picking sreen | Pitted Team | Pass | testing on order 28530. mw / Single Small-240924_1 GSZ
Outbound II | 3.03.06 | Enter in a quantity greater than 1 | Error Message: "The quantity that you entered [x] is more than the quantity that is required [x]. | Pitted Team | Pass | testing on order 28530. mw/ Single Small-240924_1 GSZ
Outbound II | 3.03.07 | Enter in quanntity on screen | If there are more pick tasks on the wave, it will take the user to the next location to complete the next task. If the task is the last one on the wave, it willt take the user back to the picking menu screen with a message"Picking LPN [x] staged to [Shipping]." | Pitted Team | Pass | testing on order 28530. mw/ Single Small-240924_1 GSZ
Outbound II | 3.03.08 | Select "stage" on item input screen | Picking cart will be staged to shipping and user will be prompted to scan new picking cart to finish the pick wave | Pitted Team | Pass | I don't see a "stage" button on item input screen. Only exception. mw
Outbound II | 3.03.09 | Select Exception and choose "No Stock" | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item | Pitted Team | Pass | GSZ
Outbound II | 3.03.10 | Suspend Task | The task is now moved to the end of the queue, it is picked last | Pitted Team | Pass | GSZ
Outbound II | 3.03.11 | Suspend Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated | Pitted Team | Pass | GSZ
Outbound II | 3.03.12 | End Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore | Pitted Team | Pass | GSZ
Outbound II | 3.04 | Multis Picking |  |  | 100%
Outbound II | 3.04.01 | Enter in location not on the picking screen | Error message: "Please scan a valid location" | Pitted Team | Pass | GSZ
Outbound II | 3.04.02 | Enter in location on the picking screen | Takes user to the item selection picking screen to enter in the SKU | Pitted Team | Pass | GSZ
Outbound II | 3.04.03 | Enter in SKU not on picking screen | Error message: "Please scan a valid item." | Pitted Team | Pass | GSZ
Outbound II | 3.04.04 | Enter SKU on picking screen | Takes user to the quantity picking sreen | Pitted Team | Pass | GSZ
Outbound II | 3.04.05 | Enter in a quantity greater than the one shown on the screen | Error Message: "Quantity entered is greater than required." | Pitted Team | Pass | GSZ
Outbound II | 3.04.06 | Enter in quanntity that's less than what is on the screen | user is asked to put the initial quantity into a bin and then brought back to scan the location, quantity, and bin for the reamaining quanitites on the wave | Pitted Team | Pass | GSZ
Outbound II | 3.04.07 | Enter in quanntity on screen | User is brought to the bin selection picking screen | Pitted Team | Pass | GSZ
Outbound II | 3.04.08 | User enters a bin that has preexisting stock units in it | User is brought to the next pick task and is asked to scan the next location if there are available pick tasks. | Pitted Team | Pass | GSZ
Outbound II | 3.04.09 | User enters a bin that doesn't have any preexisting stock units in it | Error Message: "Scanned bin [x] contains other orders | Pitted Team | Pass | GSZ
Outbound II | 3.04.10 | Enter suggested Bin number | Item & stock units are moved to the bin. User is brought to the next task if available, else it will bring the user to the Picking Menu screen to select another wave to complete if available | Pitted Team | Pass | GSZ
Outbound II | 3.04.11 | Enter a bin that is not the suggested bin number | Error Message: The suggested bin is [x]. | Pitted Team | Pass | GSZ
Outbound II | 3.04.12 | User selects 'New Bin' | Message: "New bin created for Order [x]. and user is able to select another bin to put item into if there is not existing stock in the new bin | Pitted Team | Pass | GSZ
Outbound II | 3.04.13 | Suspend Task | The task is now moved to the end of the queue, it is picked last | Pitted Team | Pass | GSZ
Outbound II | 3.04.14 | Suspend Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated | Pitted Team | Pass | GSZ
Outbound II | 3.04.15 | End Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore | Pitted Team | Pass | GSZ
Outbound II | 4.01 | Singles Packing |  |  | 100%
Outbound II | 4.01.01 | Scan a container that doesn't exist in the sytem | Error Message: Scanned container [x] does not exist or data issue | Pitted Team | Pass | GSZ
Outbound II | 4.01.02 | Scan container that has a multi's order in the bin | Takes user to ites screen --> Error message: Order [x] has more than one order line: x. | Pitted Team | Pass | GSZ
Outbound II | 4.01.03 | Scan container that was used to pick single orders | Takes user to Item screen where they can see all the items associated with the container | Pitted Team | Pass | GSZ
Outbound II | 4.01.04 | Scans an item that is not in the container | Error message: The item could not be found | Pitted Team | Pass | GSZ
Outbound II | 4.01.05 | Scan an item that is in the container | Takes user to the Enter Bin Dimensions Screen and is prompted to select or scan the carton type to pack the item into | Pitted Team | Pass | GSZ
Outbound II | 4.01.06 | User selects a bin from the drop down or scans a barcode associated with the carton type | User is taken to the Rate Shop Parameters screen and is able to select No Change or Rate Shop dependent on if the Ship Via field has "Rate Shop - [X]" or an exisitng shipping service | Pitted Team | Pass | GSZ
Outbound II | 4.01.07 | User selects Rate Shop (if ship via is Rate - Shop [X] | User is able to select the best rate and close out the shipment | Pitted Team | Pass | GSZ
Outbound II | 4.01.08 | User selects "No Change" if the ship via is a valid shipping service | User is taken back to the Scan Container Screen and is able to select a new container to start packing proces with a message saying "Order [x] is shipped" | Pitted Team | Pass | GSZ
Outbound II | 4.02 | Multis Packing |  |  | 100%
Outbound II | 4.02.01 | Scan a container that doesn't exist in the sytem | Error Message: Scanned container [x] cannot be found | Pitted Team | Pass | GSZ
Outbound II | 4.02.02 | Scan a container that has an order that is split across multiple picking bins | Error Message: "Order is split into different containers. [x] Please use repack to merge before packing." | Pitted Team | Pass | GSZ
Outbound II | 4.02.03 | Scan container with order that's been repalletized or is only in one picking bin | User is taken to the "ItemsInOrderScreen" and is prompted to select the items in the bin to pack out | Pitted Team | Pass | GSZ
Outbound II | 4.02.04 | Scans an item that is not in the container | Error message: The item could not be found on this order | Pitted Team | Pass | GSZ
Outbound II | 4.02.05 | Scan an item that is in the container | User is able to grocery scan each item that is available in the bin (qty will deprecate as user scans each unit) | Pitted Team | Pass | GSZ
Outbound II | 4.02.06 | Use 'pack remainder button' | User is able to bulk pack the remaining items in the bin and is brought to the dimension screen to select the carton to put the packed items into | Pitted Team | Pass | GSZ
Outbound II | 4.02.07 | Use 'start new box' button | User is taken to the dimension screen to pack out the items that they have already selected, and after selected carton type for initial items, user is brought back to the items in order screen and is able to select the rest of the items to pack out into a new container | Pitted Team | Pass | GSZ
Outbound II | 4.02.08 | User selects a carton in the system | user is brought to the rate shop parameters screen where they are able to choose 'no change' or 'rate shop' | Pitted Team | Pass | GSZ
Outbound II | 4.02.09 | User selects Rate Shop (if ship via is Rate - Shop [X] | User is able to select the best rate and close out the shipment | Pitted Team | Pass | GSZ
Outbound II | 4.02.10 | User selects "No Change" if the ship via is a valid shipping service | User is taken back to the Scan Container Screen and is able to select a new container to start packing proces with a message saying "Order [x] is shipped" | Pitted Team | Pass | GSZ
Outbound II | 4.03 | Repalletize |  |  | 100%
Outbound II | 4.03.01 | Enter LPN number that is not in the shipping locaiton | Error Message: The source container [x] could not be found | Pitted Team | Pass | GSZ
Outbound II | 4.03.02 | User enters LPN that exists in the shipping location | User is brought to the Items in Source Pallet screen and is prompted to enter in the items being moved and the destination location | Pitted Team | Pass | GSZ
Outbound II | 4.03.03 | User enters in an item that does not exist in the source location | Error Message: The item [x] could not be found in the container. | Pitted Team | Pass | GSZ
Outbound II | 4.03.04 | User enters a destination location not in shipping | System will generate a container and move stock units, pick tasks, and pick details from source location to destination location | Pitted Team | Pass | GSZ
Outbound II | 4.03.05 | User enters destintaion location in shipping and has the same order associated as the source location | User is brought to the Packs In Source Pallet For Selected Item and is prompted to enter in a quantity to move | Pitted Team | Pass | GSZ
Outbound II | 4.03.06 | User enters quantity that is greater than what is availble in the source container | Error Message: A total quantity of [x] for the selected pack is in the source container [x]. | Pitted Team | Pass | GSZ
Outbound II | 4.03.07 | User enters in a quantity less than what is available in the source container | User is brought back to the Items in Source Pallet screen and is able to select the same item and move the remaining quanitites. | Pitted Team | Pass | GSZ
Outbound II | 4.03.08 | User enters the exact number of units in the source location and there are no more remaining items to select from the source location | User is brought back to the Pallet to Pick From screen to select a new source location to repack | Pitted Team | Pass | GSZ
|  | User enters the exact number of units in the source location and there are remaining items to select from the source location | User is brought back to the Items in Source Pallet and is able to select more items to move from source to destination location | Pitted Team | Pass | GSZ
Outbound II | 4.03.09 | User attempts to repack items from one order into a container associated with a different order | Error Message: The Ship To postal code for the destination container must be the same as the source container. | Pitted Team | Pass | GSZ
Outbound II | 4.04 | Assign Trip to Container |  |  | 0%
Outbound II | 4.04.01 | user inputs a location not in the location input screen | error message: The door [x] could not be found | Pitted Team | Ready to Test
Outbound II | 4.04.02 | user selects or scans available location from the location input screen | user is brought to the pallets assigned to trip screen | Pitted Team | Ready to Test
Outbound II | 4.04.03 | user inputs an invalid or non existing shipping container into the pallet | error message: The container [x] could not be found. | Pitted Team | Ready to Test
Outbound II | 4.04.04 | user inputs valid shipping carton into the pallet | pallet is added to the listbox | Pitted Team | Ready to Test
Outbound II | 4.04.05 | User rescans the same container they scanned onto the pallet | the container is removed from the pallet listbox | Pitted Team | Ready to Test
Outbound II | 4.04.06 | user selects 'close trip' after building pallet | user is brought to the rate shop parameters screen and is able to select 'no change' or 'rate shop' | Pitted Team | Ready to Test
Outbound II | 4.04.07 | User selects Rate Shop (if ship via is Rate - Shop [X] | User is able to select the best rate and close out the shipment | Pitted Team | Ready to Test
Outbound II | 4.04.08 | User selects "No Change" if the ship via is a valid shipping service | User is taken back to the Location Input Screen and is able to select a new container to start packing proces with a message saying "Order [x] is shipped" | Pitted Team | Ready to Test
Outbound II | 4.05 | Void and Reprocess Shipment |  |  | 0%
Outbound II | 4.05.01 | user enters a valid order number, shipment numbner, or tracking number | error message: Please enter either a valid Tracking, Shipment, or Order number. | Pitted Team | Ready to Test
Outbound II | 4.05.02 | user enters an invalid order number, shipment numbner, or tracking number | user is brought to the Void Containers Confirmation Screen and is able to select container to void shipment | Pitted Team | Ready to Test
Outbound II | 4.05.03 | user selects a valid container to void shipment | user is brought back to the Identifier Entry Screen with a message noting the containers in which the system created to put the voided items into. User is able to input another new order/shipment to void | Pitted Team | Ready to Test
Outbound II | 4.06 | Rollback After Picking |  |  | 0%
Outbound II | 4.06.01 | user enters invalide LPN Number | error message: The selected container could not be found. Please enter a valid container number. | Pitted Team | Ready to Test
Outbound II | 4.06.02 | user enters valid LPN Number | user is brough to the Select PickDetail To RollBack Screen and is able to select the item to rollback | Pitted Team | Ready to Test
Outbound II | 4.06.03 | user selects valid item to roll back | user is brought to the Select PickDetail Qty To RollBack Screen and is prompted to select the qty to cancel | Pitted Team | Ready to Test
Outbound II | 4.06.04 | user enters in quantity greater than what is available to cancel | error message: The entered quantity should be less than or equal to the picked quantity. | Pitted Team | Ready to Test
Outbound II | 4.06.05 | user enters qty less than what is available | user is brough to the RollBack Location Screen and is prompted to select/scan location where the item exists and then brought back to the quantity screen with the scanned qty deprecated from the availlable qty | Pitted Team | Ready to Test
Outbound II | 4.06.06 | user enters a location that doesn't exist in the warehouse | error message: The location [x] could not be found. Please enter a valid location | Pitted Team | Ready to Test
Outbound II | 4.06.07 | user selects a valid location in the warehouse that isn't populated in the location listbox | item is moved to the location the user inputted | Pitted Team | Ready to Test
Outbound II | 4.06.08 | user rolls back all remaining items in the container | user is brought back to the RollBack Order screen and is able to select a new container | Pitted Team | Ready to Test
Integrations | 5.01 | Shopify ECOMM |  |  | 0%
Integrations | 5.01.01 | User pulls in item from Shopify | Creates items in channel listings & populates expected item fields (reference helpsite) | PittedTeam | Ready to Test
Integrations | 5.01.02 | User pulls in item in active status from Shopify | ensure only active items are pulling in | PittedTeam | Ready to Test
Integrations | 5.01.03 | Order Pull | Ony orders in paid & unfiilfulled status are pulled in | PittedTeam | Ready to Test
Integrations | 5.01.04 | User attempts to pull in order after updates are made | Previous order is voided & new order is created with updates from Shopify, ensure that the channel listing exists for the sales order | PittedTeam | Ready to Test
Integrations | 5.01.05 | User attempts to pull in customer returns | returns is created & ensure that the channel listing exists for the return | PittedTeam | Ready to Test
Integrations | 5.01.06 | Send a shipnotice to shopify | Tracking number sends and order marked as fulfilled | PittedTeam | Pass | Successful test with order SO29725 // DSID: 15765
Integrations | 5.02 | Shopify UK |  |  | 0%
Integrations | 5.02.01 | User pulls in item for Shopify | Item creates if the item didn't exist in ECOMM Shopify, ensure that no updates are made if item already existed, only creates a channel listing | PittedTeam | Ready to Test
Integrations | 5.02.02 | User pulls in item in active status from Shopify | ensure only channel listings for active items are being created | PittedTeam | Ready to Test
Integrations | 5.02.03 | Order Pull | Ony orders in paid & unfiilfulled status are pulled in | PittedTeam | Ready to Test
Integrations | 5.02.04 | User attempts to pull in order after updates are made | Previous order is voided & new order is created with updates from Shopify, ensure that the channel listing exists for the sales order | PittedTeam | Ready to Test
Integrations | 5.03 | Shopify WS |  |  | 0%
Integrations | 5.03.01 | User pulls in item for Shopify | Item creates if the item didn't exist in ECOMM Shopify, ensure that no updates are made if item already existed, only creates a channel listing | PittedTeam | Ready to Test
Integrations | 5.03.02 | User pulls in item in active status from Shopify | ensure only channel listings for active items are being created | PittedTeam | Ready to Test
Integrations | 5.03.03 | Order Pull | Ony orders in paid & unfiilfulled status are pulled in | PittedTeam | Ready to Test
Integrations | 5.03.04 | User attempts to pull in order after updates are made | Previous order is voided & new order is created with updates from Shopify, ensure that the channel listing exists for the sales order | PittedTeam | Ready to Test
Integrations | 5.04 | Amazon Vendor Central |  |  | 0%
Integrations | 5.04.01 | User runs stage EDI | ensure that successful docstores are created for orders pulled into stage EDI | PittedTeam | Ready to Test
Integrations | 5.04.02 | User runs process EDI | ensure that successful docstores are created for orders pulled into Deposco | PittedTeam | Ready to Test
Integrations | 5.04.03 | PO Acknowledgemnet | Whenever stage & process are ran for orders, an acknowledgement is sent to AMZ to avoid duplicate order pulls | PittedTeam | Ready to Test
Integrations | 5.05 | Amazon Seller Central |  |  | 25%
Integrations | 5.05.01 | User pulls in Item from ASC touchpoint | ensure only channel listings are created | PittedTeam | Ready to Test
Integrations | 5.05.02 | User pulls in sales order | ensure orders are being pulled into system | PittedTeam | Ready to Test
Integrations | 5.05.03 | Order acknowledgemnet | any orders that are pulled into system is sending an order acknowledgement to Amazon to avoid duplicate orders | PittedTeam | Ready to Test
Integrations | 5.05.04 | Ship Notice | test if docstores generates for tracking (tracking will not export currently in sandbox environment, no orders will be updated) | PittedTeam | Pass | Successful test with order SO29728 // DSID: 15779
Integrations | 5.06 | Walmart |  |  | 0%
Integrations | 5.06.01 | User pulls in item from Walmart | items are not created from item pulls, and ensure channel listings are created | PittedTeam | Ready to Test
Integrations | 5.06.02 | User pulls in sales order | Ensure order is coming in from Walmart | PittedTeam | Ready to Test
Integrations | 5.06.03 | Ship Notice | test if docstores generates for tracking (tracking will not export currently in sandbox environment, no orders will be updated) | PittedTeam | Ready to Test
Integrations | 5.07 | Orderful |  |  | 0%
Integrations | 5.07.01 | Customer Order Pull | Ensure that orders are created in the system | PittedTeam | Ready to Test
Integrations | 5.07.02 | Customer Order Acknowlodgment | Ensure that acknowledgements are sent back to Orderful for every order pulled in to avoid duplicate orders | PittedTeam | Ready to Test
Integrations | 5.07.03 | Export Ship Notice | check docstore for successful payloads | PittedTeam | Ready to Test
Integrations | 5.08 | Quickbooks Desktop |  |  | 0%
Integrations | 5.08.01 | Import Customer | Ensure TP is created with type of customer | PittedTeam | Ready to Test
Integrations | 5.08.02 | Import Vendor | Ensure TP is created with type of vendor | PittedTeam | Ready to Test
Integrations | 5.08.03 | Import Item | Ensure channel listings is created, no items will be created | PittedTeam | Ready to Test
Integrations | 5.08.04 | Import PO | Ensure PO is related and verify channel listing | PittedTeam | Ready to Test
Integrations | 5.08.05 | PO Receipts | Ensure for every receivied PO, a receipt is sent back to QBD | PittedTeam | Ready to Test
Integrations | 5.08.06 | Export Invoice | For every sales orders that are shipped, ensure that invoices are created & sent to QBD | PittedTeam | Ready to Test
Shipping | 6.01 | UPS |  |  | 0%
Shipping | 6.01.01 | Orders are shipped via UPS Next Day Air | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.02 | Orders are shipped via UPS 2nd Day Air | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.03 | Orders are shipped via UPS Surepost 1lb or Greater | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.04 | Orders are shipped via UPS Ground | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.05 | Orders are shipped via UPS 3 Day Select | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.06 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.07 | Ship an International Order | Shipping Account changes. Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02 | FEDEX |  |  | 0%
Shipping | 6.02.01 | Orders are shipped via FedEx Ground | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02.02 | Orders are shipped via FedEx First Overnight | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02.03 | Orders are shipped via FedEx Home Delivery | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02.04 | Orders are shipped via FedEx Priority Overnight | Tracking number and shipping label is generated |  | Ready to Test
Shipping | 6.02.05 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03 | STAMPS (USPS) |  |  | 0%
Shipping | 6.03.01 | Orders are shipped via USPS First Class Mail | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.02 | Orders are shipped via USPS Priority Mail Express | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.03 | Orders are shipped via USPS Priority Mail | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.04 | Orders are shipped via USPS Ground Advantage | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.05 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.04 | EPOST |  |  | 0%
Shipping | 6.04.01 | Orders are shipped via EPG Courier Service | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.04.02 | Orders are shipped via EPG ePacket Service | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.04.03 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.05 | Royal Mail |  |  | 0%
Shipping | 6.05.01 | Orders are shipped via Royal Mail | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.05.02 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.06 | DHL |  |  | 0%
Shipping | 6.06.01 | Orders are shipped via DHL Express Worldwide | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.06.02 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test

## UAT TEST CASES (hidden)
Spellbinders Unit Test Cases
Topic | Test # | Scenario | Expected Outcome | Owner | Status | Test Data/Client Notes | Deposco Notes
PO Creation | 1.01 | Receive against a Purchase Order (PO) |  |  | 13.33%
PO Creation | 1.01.01 | Create a PO Through DE | PO is created through DE will all lines and accurate quantities | Pitted Team | Pass
PO Creation | 1.01.02 | Create a PO Through PO Entry | PO is created through DE will all lines and accurate quantities | Pitted Team | Ready to Test
PO Creation | 1.01.03 | Add a note through PO entry to an existing PO | PO is created through DE will all lines and accurate quantities, note is attached | Pitted Team | Pass
PO Creation | 1.01.04 | Generate a PO Report | Report is able to be downloaded, everything is accurate | Pitted Team | Failed | Need changes to report, noted in task tracker
PO Creation | 1.01.05 | Create a return through CreateRMA | Return is created with accurate lines | Pitted Team | Ready to Test
PO Creation | 1.01.06 | Create a return label through Deposco | Return is created with accurate lines | Pitted Team | Ready to Test
Inbound/Putaway | 1.02 | Inbound Process |  |  | 0%
Inbound/Putaway | 1.02.01 | Receive PO full | Qty is recevied into associated locations for each item. PO in received status | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.02 | Receive PO with notes | User is brought to note screen and user is able to use direct putaway | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.03 | Receive partial PO | Qty is received into associacted locations for each item. PO in partially received status | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.04 | Receive a customer return for a wholesale | Qty is received into associacted locations for each item. | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.05 | Unrecieve partial PO | stock units on unreceived PO in receiving loaction will be deprecated from the locatiom | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.06 | Unreceive full PO | stock units on unreceived PO in receiving loaction will be deprecated from the locatiom | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.07 | Blind receive return that arrives without RMA | Qty is recevied into associated locations for each item. PO in received status & associated RMA is created | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.08 | Recieve Items where some are damaged and should not be putaway | Items are moved into the damages location and the others are ready to be putaway | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.09 | Recieve Items where you need case labels for the item | Items are received and the number of case labels are printed accurately | Pitted Team | Ready to Test
Inbound/Putaway | 1.02.10 | Recieve Items where you need to directly put the items into the kitting workcell | The user is able to select yes to direct putaway and place the items directly into the kitting workcell | Pitted Team | Ready to Test
Inbound/Putaway | 1.03 | Receive against a Customer Return (RMA) |  |  | 0%
Inbound/Putaway | 1.03.01 | When prompted to scan the RMA identifier to receive the Customer Return, the user scans or enters an invalid purchase order to receive against | The user is displayed an error that the identifier is invalid | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.02 | When prompted to scan the RMA identifier, the user scans a valid Customer Return identifier that exists and has quantity left to receive | The user is taken to the screen to receive the items. The item summary screen is displayed | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.03 | When configured to display notes during receiving, the user scans or enters an RMA that has notes populated at the header level | The user is displayed the note before the summary screen for the RMA is shown | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.04 | When configured to display notes during receiving, the user scans or enters an RMA that has notes populated at the line level | The user is displayed the note after the line item is selected, and before the item is physically received | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.05 | Receive overage against an RMA for an item that does not have the over receipt tolerance set at the item level. Enter a quantity that exceeds the threshold set at the workflow process level | Receive an error message that the quantity exceeds the threshold. The workflow setting is invoked | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.06 | User partially receives the RMA and hits the 'finish' button to temporarily exit the Customer Return | The user is exited from the RMA receiving screen. The RMA goes to 'Partial Receipt' status | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.07 | User completes receiving the entire Customer Return | The user is exited from the RMA receiving screen. The RMA goes to 'Received' status | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.08 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.09 | User receives against a non-each pack for an item that does not have item attribute capture requirements | The receipt is completed at the non-each pack level | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.10 | User selects "Yes" on Print dropdown when confirming item quantity to receive | User is prompted on next screen to confirm quanitity to print | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.11 | User selects "No" on Print dropdown when confirming item quantity to receive | User continues receiving next item | Pitted Team | Ready to Test
Inbound/Putaway | 1.03.12 | User enters non-numeric or non-positive integer (decimal, negative number, alphanumeric value) in quantity to print. | Error | Pitted Team | Ready to Test
Inbound/Putaway | 1.04 | Receive a Blind Customer Return (Blind RMA) |  |  | 100%
Inbound/Putaway | 1.04.01 | When prompted to scan the RMA identifier to receive the Blind Return, the user scans or enters a previously used Blind Return Number | The user is brought to a new screen that validates if they would like to proceed with the duplicate RMA order number | Pitted Team | Pass | used rma1, rma2 & rma3. all for e3d-081. mw
Inbound/Putaway | 1.04.02 | When prompted to scan the RMA identifier to receive the Blind Return, the user scans or enters a never used Blind Return Number | The user is taken to the screen to receive the items. The item summary screen is displayed | Pitted Team | Pass
Inbound/Putaway | 1.04.03 | User scans an item that has multiple packs in it's master data set up | The user is displayed a screen with all the packs for the item. The user selects the appropriate pack to receive | Pitted Team | Pass
Inbound/Putaway | 1.04.04 | User receives against a non-each pack for an item that does not have item attribute capture requirements | The receipt is completed at the non-each pack level | Pitted Team | Pass
Inbound/Putaway | 1.04.05 | User selects "Yes" on Print dropdown when confirming item quantity to receive | User is prompted on next screen to confirm quanitity to print | Pitted Team | Pass
Inbound/Putaway | 1.04.06 | User selects "No" on Print dropdown when confirming item quantity to receive | User continues receiving next item | Pitted Team | Pass
Inbound/Putaway | 1.04.07 | User enters non-numeric or non-positive integer (decimal, negative number, alphanumeric value) in quantity to print. | Error message is thrown | Pitted Team | Pass
Inbound/Putaway | 1.04.08 | User select "Finish" to complete Blind RMA | RMA is moved to a Received status | Pitted Team | Pass
Inbound/Putaway | 1.05 | Putaway - Move Item
Inbound/Putaway | 1.05.01 | User scans or enter an invalid source location from which to move inventory in users assigned facility | Receive an error message that no such location exists in user's assigned facility | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.02 | User scans or enter a valid source location fromk which to move inventory where the location has no stock units present | Receive a screen message that there is no stock in location available to move | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.03 | User scans or enter a valid source location fromk which to move inventory where the location has stock units present | User is directed to the Item Summary screen to display all Items in the specified Location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.04 | User scans or enters an item that doesn't exist in the location | The user is displayed an error that the Item is invalid | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.05 | User scans or enters a valid item to move | User is directed to the "Quantity Input Screen" to specify the Pack/Qty to Move | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.06 | User scans, enters, or selects an item that has multiple stock units in the location. Some of the stock units are allocated to pick tasks | The Stock Unit that is NOT tied to a Pick Task should display on the item listbox with the associated Qty | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.07 | Move multiple quantity for an item in one transaction | User is able to successfully move item/qty to destination location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.08 | Move stock for an item from a return location to a picking location | User is able to successfully move item/qty to specified Picking location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.09 | Move stock for an item from a staging location to a picking location | User is able to successfully move item/qty to specified Picking location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.10 | If stock unit at the pick face location is under the minimum in storage details for the item, the location will populate first in the handheld | User is able to view the location at the top of the list ("Pick Face Consolidate") and is successful when moving the item/qty to the suggested location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.11 | If stock unit at pick face location is above the minimum iin storage details for the item, and the item has existing stock units in the back stock location, those locations will populate first in the handheld | Useer is able to view the locations at the top of the list ("Back Stock Consolidate" and is successful when moving the item/qty to the suggested location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.12 | Locations without a stock unit associated within them will populate as "Empty Location" | User is successful moving item/qty to these suggested locations | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.13 | When moving an item, move it to a different location than one of the suggested locations in the 'Suggested Locations' list box | User is able to successfully move item/qty to a non-suggested location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.14 | Move stock to a mixed-item location. The location contains stocks for other items | User is able to successfully move item/qty to a multi-item Location | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.15 | Move stock to a single-item location. The location contains stock for a different item | User receives an error message "the location contains other items already" | Pitted Team | Ready to Test
Inbound/Putaway | 1.05.16 | Move stock to a single-item location. The location contains stock for the same item. | User is allowed to move stock to the scanned location. | Pitted Team | Ready to Test
Inbound/Putaway | 1.06 | Unreceive (PO, ITO, RMA, Blind RMA)
Inbound/Putaway | 1.06.01 | Enter invalid order number to be un-received | User receives error message to input a correct order number | Pitted Team | Pass
Inbound/Putaway | 1.06.02 | Enter valid order number to be un-received | User is directed to the "Select Item to Unreceive" screen | Pitted Team | Pass
Inbound/Putaway | 1.06.03 | Enter valid order number in invalid status to be un-received | User receives error message "Please enter a valid order number to un-receive." | Pitted Team | Pass
Inbound/Putaway | 1.06.04 | Unreceive order with one item received against it | User is able to successfully unreceive the order and is directed back to the Handheld menu with a successful message | Pitted Team | Pass
Inbound/Putaway | 1.06.05 | Unreceive order with multiple items received against it | User is able to select each Item/Qty and continue this process until all affected items/qty is selected | Pitted Team | Pass
Inbound/Putaway | 1.06.06 | Scan valid item to unreceive for order | User receives a message that the selected item was unreceived successfully | Pitted Team | Pass
Inbound/Putaway | 1.06.07 | Scan invalid item to unreceive for order | User receives error "Please enter valid item number/UPC or select pack type to un-receive." | Pitted Team | Pass
Inbound/Putaway | 1.06.08 | Enter a non numeric value in the quantity input section of the screen | The user is displayed an error to "Please enter a valid integer for quantity" | Pitted Team | Pass
Inbound/Putaway | 1.06.09 | Enter a quantity that is higher than the allowed quantity in the quantity input section of the screen | The user is displayed an error that "The specified quantity for the item is greater than the quantity that is available" | Pitted Team | Pass
Inbound/Putaway | 1.06.10 | Enter a negative quantity in the quantity input section of the screen | The user is displayed an error to "Please enter a valid integer for quantity" | Pitted Team | Pass
Inbound/Putaway | 1.06.11 | Enter a quantity that is lesser than the allowed quantity in the quantity input section of the screen | The selected item will remain in the "Items Remaining" listbox with an updated Qty to display how many more units can be unreceived | Pitted Team | Pass
Inbound/Putaway | 1.06.12 | Enter a quantity that is exactly the allowed quantity in the quantity input section of the screen | User receives a message that the selected item was unreceived successfully | Pitted Team | Pass
Inbound/Putaway | 1.06.13 | Enter a non integer (decimal value) in the quantity input section of the screen | The user is displayed an error to "Please enter a valid integer for quantity" | Pitted Team | Pass
Inbound/Putaway | 1.06.14 | Exit process without unreceiving all items on order | Order "status" updates to "Partial Receipt" and the user can re-enter the order to continue unreceiving as needed | Pitted Team | Pass
Inventory Management | 2.01 | Cycle Counts |  |  | 100%
Inventory Management | 2.01.01 | Enter invalid start off location | Enter invalid start off location | Pitted Team | Pass
Inventory Management | 2.01.02 | Enter valid start off location | User is prompted to first location to be cycle counted (should be task with lowest priority and/or pick sequence closest to startoff location) | Pitted Team | Pass
Inventory Management | 2.01.03 | Enter expected location on Location input screen | User is prompted to count items that exist in location | Pitted Team | Pass
Inventory Management | 2.01.04 | Enter unexpected/invalid location on Location input screen | Error message to please scan recommended location | Pitted Team | Pass
Inventory Management | 2.01.05 | Count single item location with stock in it | Should only be allowed to count 1 item in location | Pitted Team | Pass
Inventory Management | 2.01.06 | Count multi item location with stock for multiple skus in it | Should be allowed to count as many items into the location as needed | Pitted Team | Pass
Inventory Management | 2.01.07 | Count multi item location without stock in it | Should be allowed to count as many items into the location as needed | Pitted Team | Pass
Inventory Management | 2.01.08 | Scan item that exists in location to begin counting | User is prompted to type in quantity of item present | Pitted Team | Pass
Inventory Management | 2.01.09 | Scan item that is not in location to begin counting | User is prompted to type in quantity of item present | Pitted Team | Pass
Inventory Management | 2.01.10 | Select next location without counting any items to count zero for the location | User is prompted to walk to and scan next location - count zeros for location skipped | Pitted Team | Pass
Inventory Management | 2.01.11 | Count quantity in eaches | Count stock units in lowest pack quantity (each) | Pitted Team | Pass
Inventory Management | 2.01.12 | Count quantity in non-each pack | Count stock units in selected pack quantity | Pitted Team | Pass
Inventory Management | 2.01.13 | Count quantity that is expected in location | No variance is created | Pitted Team | Pass
Inventory Management | 2.01.14 | Count quantity other than what is expected in location | User is asked to confirm counted quantity for a second time | Pitted Team | Pass
Inventory Management | 2.01.15 | Confirm variance when counting quantity other than what is expected in location | Variance is captured | Pitted Team | Pass
Inventory Management | 2.01.16 | Select Next Item/Location to skip counting an item once scanned | Zero is counted for an item - variance is created | Pitted Team | Pass
Inventory Management | 2.02 | Adjust Inventory - Location Entry |  |  | 100%
Inventory Management | 2.02.01 | Scan Invalid location | Error message | Pitted Team | Pass
Inventory Management | 2.02.02 | Scan valid location with no stock in it | Brought to inventory adjustment menu | Pitted Team | Pass
Inventory Management | 2.02.03 | Scan valid location with stock in it | Brought to inventory adjustment menu | Pitted Team | Pass
Inventory Management | 2.03 | Adjust Inventory - Consume by Item |  |  | 100%
Inventory Management | 2.03.01 | Consume by Item --> Select Back | Brought to inventory adjustment menu | Pitted Team | Pass
Inventory Management | 2.03.02 | Consume by Item --> Scan Invalid Item and click Next | Error message | Pitted Team | Pass
Inventory Management | 2.03.03 | Consume by Item --> Scan Valid Item that exists in location and click Next | User is prompted to enter quantity of item to consume | Pitted Team | Pass | Used loc H9-9. Consumed 3pcs of S5-619
Inventory Management | 2.03.04 | Consume by Item --> Scan Valid Item that does not exists in location and click Next | Error message | Pitted Team | Pass
Inventory Management | 2.03.05 | Consume by Item --> Enter non-numeric qty of item to consume | Error message | Pitted Team | Pass
Inventory Management | 2.03.06 | Consume by Item --> Enter a qty that is higher than available qty to consume | Error message | Pitted Team | Pass
Inventory Management | 2.03.07 | Consume by Item --> Enter a negative quantity in the quantity input section of the screen | Error message | Pitted Team | Pass
Inventory Management | 2.03.08 | Consume by Item --> Enter a quantity that is lesser than the available quantity in the quantity input section of the screen | Quantity entered is added to consume item list | Pitted Team | Pass
Inventory Management | 2.03.09 | Consume by Item --> Enter a quantity that is exactly the allowed quantity in the quantity input section of the screen | Quantity entered is added to consume item list | Pitted Team | Pass
Inventory Management | 2.03.10 | Consume by Item --> Enter a non integer (decimal value) in the quantity input section of the screen | Error message | Pitted Team | Pass
Inventory Management | 2.03.11 | Consume by Item --> Select Confirm after Scanning Valid Items and | User is shown list of all items/quantities to be consumed along with reason code selection & option to add a note | Pitted Team | Pass
Inventory Management | 2.03.12 | Consume by Item --> Select Back after reviewing items to consume | User may start over and recreate list to consume | Pitted Team | Pass
Inventory Management | 2.03.13 | Consume by Item --> Select Reason Code and Submit after reviewing items to consume | Stock is deleted and Inventory Ledger record is created with corresponding reason code for item/location/quantity deleted | Pitted Team | Pass
Inventory Management | 2.04 | Adjust Inventory - Consume All in Location |  |  | 100%
Inventory Management | 2.04.01 | Consume All in Location --> For location with no stock | There are NO Stock Units in the "Review" screen so nothing will get consumed | Pitted Team | Pass
Inventory Management | 2.04.02 | Consume All in Location --> For location with stock that has open pick tasks against it | Receive error message since there is an incomplete Pick Tasks for at least (1) Stock Unit | Pitted Team | Pass | tested on location 57.04.02 which had open tasks against it.
Inventory Management | 2.04.03 | Consume All in Location --> For location with stock that has no open pick tasks | User is directed to the Review screen to display all Stock Units in the Location to Consume All | Pitted Team | Pass
Inventory Management | 2.04.04 | Consume All in Location --> Select Back after reviewing items to consume in location | User is directed back to the "Options" screen to determine which Adjust Inventory process to select | Pitted Team | Pass
Inventory Management | 2.04.05 | Consume All in Location --> Select Reason Code and Commit after reviewing items to consume in location | Receive confirmation message that all Stock Units in Location has been consumed > no Stock Units are available in Location > IGL record created with Reason Code | Pitted Team | Pass | consumed all inventory in H9-9
Inventory Management | 2.05 | Adjust Inventory - Create Inventory |  |  | 100%
Inventory Management | 2.05.01 | Scan Invalid Item | Receive error message that the Item could not be found | Pitted Team | Pass
Inventory Management | 2.05.02 | Scan valid Item | User is directed to the "Attribute" screen to input a Container (if applicable) and to specify the Qty | Pitted Team | Pass | entered S5-619. MW
Inventory Management | 2.05.03 | Create Inventory for Each pack | Since all Items will only have a Pack "Each" - this will add the Stock Unit to the listbox via "ScanItem" screen | Pitted Team | Pass
Inventory Management | 2.05.04 | Enter non-numeric qty of inventory to create | User remains in the "Attribute" screen with a warning message "For input string: xxxx | Pitted Team | Pass
Inventory Management | 2.05.05 | Enter a negative quantity of inventory to create | Receive error message "Quantity must be greater than 0" | Pitted Team | Pass
Inventory Management | 2.05.06 | Enter a non integer (decimal value) of inventory to create | User remains in the "Attribute" screen with a warning message "For input string: xxxx | Pitted Team | Pass
Inventory Management | 2.05.07 | Add multiple items to inventory list to be created for single item locations | Error message | Pitted Team | Pass | Entered S5-619, and tried to add DD110, but got error message. MW
Inventory Management | 2.05.08 | Add additional items to inventory list to be created for multi item locations | User is brought to AttributeScreen to enter in pack & location for item being added | Pitted Team | Pass
Inventory Management | 2.05.09 | Select Confirm | User is directed to the "Review" screen for type "Add Stock" to display all Items/Containers > user to select a Reason Code | Pitted Team | Pass
Inventory Management | 2.05.10 | Select Back after reviewing items to create | User is directed back to the "Options" screen to determine which Adjust Inventory process to select | Pitted Team | Pass | was not directed to "Options" screen. it completed task. | Optoins screen is the screen where you're able to select the type of adjust inventory process
Inventory Management | 2.05.11 | Select Reason Code and Commit after reviewing items to create | Receive confirmation message that all Stock Units in Location have been created > Stock Units are available in Location > IGL record created with Reason Code | Pitted Team | Pass | received message: "1 Each, are created as new. Item(s): [S5-619/1/SF]"
Inventory Management | 2.06 | Directed Replenishments |  |  | 15.38%
Inventory Management | 2.06.01 | Directed Replen, scan valid container to use for replenishments when replenishment tasks are available to complete | Brought to replenishment summary screen | Pitted Team | Pass
Inventory Management | 2.06.02 | Directed Replen, scan valid container when there are no open replenishment tasks to complete | Screen message - nothing to replenish | Pitted Team | Pass
Inventory Management | 2.06.03 | Scan the correct item barcode in the item scan section of the picking screen | Item scan accepted | Pitted Team | Ready to Test
Inventory Management | 2.06.04 | Enter a quantity that is lesser than the required quantity in the quantity input section of the picking screen (Non Grocery Mode) | Quantity entered is decremented from the quantity to pick - remaining quantity is prompted to pick | Pitted Team | Ready to Test
Inventory Management | 2.06.05 | Enter a quantity that is exactly the required quantity in the quantity input section of the picking screen (Non Grocery Mode) & no more replenishment tasks left | Quantity is picked and user is prompted to scan location & item qty to replenish for pick face location | Pitted Team | Ready to Test
Inventory Management | 2.06.06 | Picking Exception - No Stock | Replenishment Task is set to a status "Exception" > IF there are other Reserve Locations that have eligible stock then will create a new Replenishment Task and will prompt the user to the new location - If not, then the Stock Unit at the Location will be placed in a "On Hold" status > a Cycle Count will get generated with a type "Picking Audit" > if there are more Replenishment Tasks, user is directed to another tasks | Pitted Team | Ready to Test
Inventory Management | 2.06.07 | Select "Cart Is Full" on picking screen | User is prompted to begin putaway of items on cart to storage locations | Pitted Team | Ready to Test
Inventory Management | 2.06.08 | Scan the correct item barcode in the item scan section of the replenishment screen | User is directed to specify the Replenish Qty | Pitted Team | Ready to Test
Inventory Management | 2.06.09 | Enter a quantity that is lesser than the required quantity in the quantity input section of the picking screen (Non Grocery Mode) | Quantity entered is decremented from the quantity to replenish - remaining quantity is prompted to replenish | Pitted Team | Ready to Test
Inventory Management | 2.06.10 | Enter a quantity that is exactly the required quantity in the quantity input section of the picking screen (Non Grocery Mode) | Quantity is replenished and user is prompted to replenish next item/location | Pitted Team | Ready to Test
Inventory Management | 2.06.11 | Exception on Replenishment - Location Full | Replenishment Task is set to a status of Destination Full > A new (reverse) replenishment task is created to return the stock to the source reserve location | Pitted Team | Ready to Test
Inventory Management | 2.06.12 | Finish putaway of cart when more replenishment tasks are available to complete | User is presented summary screen of remaining tasks and can start a new replenishment cycle | Pitted Team | Ready to Test
Inventory Management | 2.06.13 | Finish putaway of cart when no more replenishment tasks are available to complete | "Nothing to replenish" | Pitted Team | Ready to Test
Inventory Management | 2.07 | Product Conversion (Work Order) |  |  | 0%
Inventory Management | 2.07.01 | User goes into the "Product Conversion w/ Workorder and enters in the correct kitting location without any open workorders available | Error message: "There are no open workorders to build" | Pitted Team | Ready to Test
Inventory Management | 2.07.02 | User goes into the "Product Conversion w/ Workorder and enters in the correct kitting location with open workorders available | User is brought to the next screen: "Work Order List" and is able to choose from of a list of open workorders to complete | Pitted Team | Ready to Test
Inventory Management | 2.07.03 | User selects available workorder | User is brought to the "Work Order Details" with a summary of the workorder and a list of components and an output SKU | Pitted Team | Ready to Test
Inventory Management | 2.07.04 | User selects "Pause WO" button | User is brought back to the "Work Order List" screen, with the workorder still being available to be completed | Pitted Team | Ready to Test
Inventory Management | 2.07.05 | User selects "End WO" button wihtout any other available WOs | User is brought back to the initial screen with message "There are no open workorders to build." Previous WO will be in a "Partial Complete" status | Pitted Team | Ready to Test
Inventory Management | 2.07.06 | User selects "End WO" button wiht available open WOs | User is brought back to the "Work Order List" screen and is able to select next open WO to complete | Pitted Team | Ready to Test
Inventory Management | 2.07.07 | User selects "Start WO" | User is brought to: "Build Product" with a view of details for the workorder | Pitted Team | Ready to Test
Inventory Management | 2.07.08 | User enters in quantity to build that's larger than the quantity for the workorder | Error message: "Cannot build more than X" | Pitted Team | Ready to Test
Inventory Management | 2.07.09 | User enter in a quantity less than the quantity to build for the workorder | User is brought back to the "Work Order Details" screen with the quantity build & quantity to build values being updated to reflect the amount that was built and is prompted to continue building out the item until the quantity built reaches the conversion # | Pitted Team | Ready to Test
Inventory Management | 2.08 | Kit to Stock (Non-Workorder) |  |  | 0%
Inventory Management | 2.08.01 | User enter in correct kitting location & kitted item | Brings user to next screen "Kit Item Config" | Pitted Team | Ready to Test
Inventory Management | 2.08.02 | User enters correct kitting location but not a kitted item | Error Message: "Item entered is not a kit item" | Pitted Team | Ready to Test
Inventory Management | 2.08.03 | User enters in quantity to build greater than the suggested quantity shown on the screen | Error Message: "No more than suggested number of kits can be built." | Pitted Team | Ready to Test
Inventory Management | 2.08.04 | User enters in quantity to build less than or equal to the suggested quantity shown on the screen | Brings user to next screen "Kitting Summary" | Pitted Team | Ready to Test
Inventory Management | 2.08.05 | User clicks "Next" on the screen with kit summary | User is brought back to the "Kit Item Config" with a new message on the bottow of the scrren "New kit items "X" created." and the suggested quantity should reflect how many left can be built. User is able to continue to build kits with the remainding components left in the kitting location | Pitted Team | Ready to Test
Inventory Management | 2.08.06 | User clicks "Done" on the "Kit Item Config" screen | User is brought back to the main menu screen for product conversion | Pitted Team | Ready to Test
Outbound I | 3.01 | Order Management |  |  | 0%
Outbound I | 3.01.01 | User pulls in order where order has stock in the facility | Order should be routed to its according facility based on the parameters set in order routing | PittedTeam | Ready to Test
Outbound I | 3.01.02 | User pulls in order where order has no stock in the facility | Order should be backordered, and Pitted can go in and cancel the order or force allocate | PittedTeam | Ready to Test
Outbound I | 3.01.03 | User pulls in order where there are some order lines that are able to be fulfilled and some that don't have available stock in the facility | Lines that are availble to be fulfilled are routed to its facility, the other lines are backordered, and Pitted can go in and cancel the order lines | PittedTeam | Ready to Test
Outbound I | 3.01.04 | Partially cancel a CoLine | Noncancelled order line quantities will be routed to its according facility if there are enough stock units to fulfill the customer order line | PittedTeam | Ready to Test |  | Test with order: CO36726, Partially cancel 8 units of item SCS-244. Reprocess customer order
Outbound I | 3.01.05 | Fully cancel CoLine | Cancelled coLines will be backorders, Pitted can go in and cancel. The other lines associated with the same coHeader will be routed to its according facility | PittedTeam | Ready to Test |  | Test with order: CO36723, Cancel order line with the item T-016 on the orer
Outbound I | 3.01.06 | Cancel an entire CoHeader | CoHeader will be put into a back ordered status, Pitted can go in and cancel the order | PittedTeam | Ready to Test |  | Test with order: CO36727
Outbound I | 3.01.07 | Pull in UK order | Order should route to UK facility regardless if there is available stock in the PHX facility | PittedTeam | Ready to Test
Outbound I | 3.01.08 | Pull in order where there is stock for one orderline has stoclk in PHX facility and another orderline where there is no stock in PHX but there are availble stock in UK | Order should not be split between facilities, and orderlines withut stock in PHX will be cancelled, the rest will be routed to PHX | PittedTeam | Ready to Test
Outbound I | 3.01.09 | Force allocate coLine using Force Allocate Process Action Link Button | Regardless of available stock, order should be routed to the according facility | PittedTeam | Ready to Test |  | Test with order: CO36728, force allocate to PHX facility
Outbound I | 3.02 | Build & Release Wave |  |  | 60%
Outbound I | 3.02.01 | User manually waves a single order from the order entity using the correct process action link | Order is waved based on its parameters |  | Pass | TESTED ORDER 29588 AND PASSED | 29565: Orders have to have "POI?" field check in order to be waved. This field will be automatically checked for all new orders pulled in the system. For testing, you can manually run POI through the process action drop down or manually checking the box. 29628: Order will wave as Walmart since the order source is Walmart. WEB1168401: Order needs to be run through POI so that the order profile is stamped, ince the field is stamped then it will wave occirdoing to the profile
Outbound I | 3.02.02 | User manually waves multiple orders from the order entity | Orders are waved based on their parameters |  | Pass |  | Orders need to be ran through POI so that the field is checkd, and then the order will be waved
Outbound I | 3.02.03 | User manually runs Build and Release Wave scheduler | Orders that are not club orders should be waved based on their parameters |  | Pass
Outbound I | 3.02.04 | User manually waves club orders (Build and Release - Club) through order entity | only club orders should be waved |  | Needs Info | I couldn't find any club orders to wave, and I am not sure how to filter this by sku | Club orders are any orders that have the exact same SKU, quantity, and number of lines. The profile is set so that there needs to be at least 25 of these identical orders, but you are able to lower the threshold for testing purposes in Pick Wave Profile --> Identical --> max number of orders
Outbound I | 3.02.05 | User manually rus "Waving - Identicals" scheduler | only club orders should be waved |  | Needs Info | I couldn't find any club orders to test | Club orders are any orders that have the exact same SKU, quantity, and number of lines. The profile is set so that there needs to be at least 25 of these identical orders, but you are able to lower the threshold for testing purposes in Pick Wave Profile --> Identical --> max number of orders
Outbound I | 3.02 | Undo Release Wave |  |  | 50%
Outbound I | 3.02.01 | User manually unrelease wave through Pick Waves entity for a wave in 'Released' status | Orders on the wave are successfully rolled back | Pitted Team | Pass | TESTED ORDER 29588 AND PASSED | PAL Button is called "Undo Release" on the Pick Wave Entity (Found in Distribution Application Menu)
Outbound I | 3.02.02 | User manually unrelease wave through Pick Waves entity for a wave in not 'Released' status | Order fails to roll back since work group for the wave is active | Pitted Team | Failed | tested order Single Small-240917_5 message"pick wave single small Single Small-240917_5 not released" | is wave supposeed to fail? Test should be passed if expected outcome is what happens
Outbound II | 3.03 | Singles Picking |  |  | 100%
Outbound II | 3.03.01 | Enter in picking LPN that does not exist in the system | New container is created in the system & user is able to pick items into new container | Pitted Team | Pass | TESTED ORDER 29588 AND PASSED
Outbound II | 3.03.02 | Enter in location not on the picking screen | Error message: "The location [x] does not match the required location." | Pitted Team | Pass | testing on order 28530. mw / tested on Single Small-240924_1 GSZ
Outbound II | 3.03.03 | Enter in location on the picking screen | Takes user to the item selection picking screen to enter in the SKU | Pitted Team | Pass | testing on order 28530. mw / Single Small-240924_1 GSZ
Outbound II | 3.03.04 | Enter in SKU not on picking screen | Error message: "The SKU [x] could not be found. Please enter a valid SKU." | Pitted Team | Pass | testing on order 28530. mw / Single Small-240924_1 GSZ
Outbound II | 3.03.05 | Enter SKU on picking screen | Takes user to the quantity picking sreen | Pitted Team | Pass | testing on order 28530. mw / Single Small-240924_1 GSZ
Outbound II | 3.03.06 | Enter in a quantity greater than 1 | Error Message: "The quantity that you entered [x] is more than the quantity that is required [x]. | Pitted Team | Pass | testing on order 28530. mw/ Single Small-240924_1 GSZ
Outbound II | 3.03.07 | Enter in quanntity on screen | If there are more pick tasks on the wave, it will take the user to the next location to complete the next task. If the task is the last one on the wave, it willt take the user back to the picking menu screen with a message"Picking LPN [x] staged to [Shipping]." | Pitted Team | Pass | testing on order 28530. mw/ Single Small-240924_1 GSZ
Outbound II | 3.03.08 | Select "stage" on item input screen | Picking cart will be staged to shipping and user will be prompted to scan new picking cart to finish the pick wave | Pitted Team | Pass | I don't see a "stage" button on item input screen. Only exception. mw
Outbound II | 3.03.09 | Select Exception and choose "No Stock" | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item | Pitted Team | Pass | GSZ
Outbound II | 3.03.10 | Suspend Task | The task is now moved to the end of the queue, it is picked last | Pitted Team | Pass | GSZ
Outbound II | 3.03.11 | Suspend Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated | Pitted Team | Pass | GSZ
Outbound II | 3.03.12 | End Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore | Pitted Team | Pass | GSZ
Outbound II | 3.04 | Multis Picking |  |  | 100%
Outbound II | 3.04.01 | Enter in location not on the picking screen | Error message: "Please scan a valid location" | Pitted Team | Pass | GSZ
Outbound II | 3.04.02 | Enter in location on the picking screen | Takes user to the item selection picking screen to enter in the SKU | Pitted Team | Pass | GSZ
Outbound II | 3.04.03 | Enter in SKU not on picking screen | Error message: "Please scan a valid item." | Pitted Team | Pass | GSZ
Outbound II | 3.04.04 | Enter SKU on picking screen | Takes user to the quantity picking sreen | Pitted Team | Pass | GSZ
Outbound II | 3.04.05 | Enter in a quantity greater than the one shown on the screen | Error Message: "Quantity entered is greater than required." | Pitted Team | Pass | GSZ
Outbound II | 3.04.06 | Enter in quanntity that's less than what is on the screen | user is asked to put the initial quantity into a bin and then brought back to scan the location, quantity, and bin for the reamaining quanitites on the wave | Pitted Team | Pass | GSZ
Outbound II | 3.04.07 | Enter in quanntity on screen | User is brought to the bin selection picking screen | Pitted Team | Pass | GSZ
Outbound II | 3.04.08 | User enters a bin that has preexisting stock units in it | User is brought to the next pick task and is asked to scan the next location if there are available pick tasks. | Pitted Team | Pass | GSZ
Outbound II | 3.04.09 | User enters a bin that doesn't have any preexisting stock units in it | Error Message: "Scanned bin [x] contains other orders | Pitted Team | Pass | GSZ
Outbound II | 3.04.10 | Enter suggested Bin number | Item & stock units are moved to the bin. User is brought to the next task if available, else it will bring the user to the Picking Menu screen to select another wave to complete if available | Pitted Team | Pass | GSZ
Outbound II | 3.04.11 | Enter a bin that is not the suggested bin number | Error Message: The suggested bin is [x]. | Pitted Team | Pass | GSZ
Outbound II | 3.04.12 | User selects 'New Bin' | Message: "New bin created for Order [x]. and user is able to select another bin to put item into if there is not existing stock in the new bin | Pitted Team | Pass | GSZ
Outbound II | 3.04.13 | Suspend Task | The task is now moved to the end of the queue, it is picked last | Pitted Team | Pass | GSZ
Outbound II | 3.04.14 | Suspend Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated | Pitted Team | Pass | GSZ
Outbound II | 3.04.15 | End Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore | Pitted Team | Pass | GSZ
Outbound II | 4.01 | Singles Packing |  |  | 100%
Outbound II | 4.01.01 | Scan a container that doesn't exist in the sytem | Error Message: Scanned container [x] does not exist or data issue | Pitted Team | Pass | GSZ
Outbound II | 4.01.02 | Scan container that has a multi's order in the bin | Takes user to ites screen --> Error message: Order [x] has more than one order line: x. | Pitted Team | Pass | GSZ
Outbound II | 4.01.03 | Scan container that was used to pick single orders | Takes user to Item screen where they can see all the items associated with the container | Pitted Team | Pass | GSZ
Outbound II | 4.01.04 | Scans an item that is not in the container | Error message: The item could not be found | Pitted Team | Pass | GSZ
Outbound II | 4.01.05 | Scan an item that is in the container | Takes user to the Enter Bin Dimensions Screen and is prompted to select or scan the carton type to pack the item into | Pitted Team | Pass | GSZ
Outbound II | 4.01.06 | User selects a bin from the drop down or scans a barcode associated with the carton type | User is taken to the Rate Shop Parameters screen and is able to select No Change or Rate Shop dependent on if the Ship Via field has "Rate Shop - [X]" or an exisitng shipping service | Pitted Team | Pass | GSZ
Outbound II | 4.01.07 | User selects Rate Shop (if ship via is Rate - Shop [X] | User is able to select the best rate and close out the shipment | Pitted Team | Pass | GSZ
Outbound II | 4.01.08 | User selects "No Change" if the ship via is a valid shipping service | User is taken back to the Scan Container Screen and is able to select a new container to start packing proces with a message saying "Order [x] is shipped" | Pitted Team | Pass | GSZ
Outbound II | 4.02 | Multis Packing |  |  | 100%
Outbound II | 4.02.01 | Scan a container that doesn't exist in the sytem | Error Message: Scanned container [x] cannot be found | Pitted Team | Pass | GSZ
Outbound II | 4.02.02 | Scan a container that has an order that is split across multiple picking bins | Error Message: "Order is split into different containers. [x] Please use repack to merge before packing." | Pitted Team | Pass | GSZ
Outbound II | 4.02.03 | Scan container with order that's been repalletized or is only in one picking bin | User is taken to the "ItemsInOrderScreen" and is prompted to select the items in the bin to pack out | Pitted Team | Pass | GSZ
Outbound II | 4.02.04 | Scans an item that is not in the container | Error message: The item could not be found on this order | Pitted Team | Pass | GSZ
Outbound II | 4.02.05 | Scan an item that is in the container | User is able to grocery scan each item that is available in the bin (qty will deprecate as user scans each unit) | Pitted Team | Pass | GSZ
Outbound II | 4.02.06 | Use 'pack remainder button' | User is able to bulk pack the remaining items in the bin and is brought to the dimension screen to select the carton to put the packed items into | Pitted Team | Pass | GSZ
Outbound II | 4.02.07 | Use 'start new box' button | User is taken to the dimension screen to pack out the items that they have already selected, and after selected carton type for initial items, user is brought back to the items in order screen and is able to select the rest of the items to pack out into a new container | Pitted Team | Pass | GSZ
Outbound II | 4.02.08 | User selects a carton in the system | user is brought to the rate shop parameters screen where they are able to choose 'no change' or 'rate shop' | Pitted Team | Pass | GSZ
Outbound II | 4.02.09 | User selects Rate Shop (if ship via is Rate - Shop [X] | User is able to select the best rate and close out the shipment | Pitted Team | Pass | GSZ
Outbound II | 4.02.10 | User selects "No Change" if the ship via is a valid shipping service | User is taken back to the Scan Container Screen and is able to select a new container to start packing proces with a message saying "Order [x] is shipped" | Pitted Team | Pass | GSZ
Outbound II | 4.03 | Repalletize |  |  | 100%
Outbound II | 4.03.01 | Enter LPN number that is not in the shipping locaiton | Error Message: The source container [x] could not be found | Pitted Team | Pass | GSZ
Outbound II | 4.03.02 | User enters LPN that exists in the shipping location | User is brought to the Items in Source Pallet screen and is prompted to enter in the items being moved and the destination location | Pitted Team | Pass | GSZ
Outbound II | 4.03.03 | User enters in an item that does not exist in the source location | Error Message: The item [x] could not be found in the container. | Pitted Team | Pass | GSZ
Outbound II | 4.03.04 | User enters a destination location not in shipping | System will generate a container and move stock units, pick tasks, and pick details from source location to destination location | Pitted Team | Pass | GSZ
Outbound II | 4.03.05 | User enters destintaion location in shipping and has the same order associated as the source location | User is brought to the Packs In Source Pallet For Selected Item and is prompted to enter in a quantity to move | Pitted Team | Pass | GSZ
Outbound II | 4.03.06 | User enters quantity that is greater than what is availble in the source container | Error Message: A total quantity of [x] for the selected pack is in the source container [x]. | Pitted Team | Pass | GSZ
Outbound II | 4.03.07 | User enters in a quantity less than what is available in the source container | User is brought back to the Items in Source Pallet screen and is able to select the same item and move the remaining quanitites. | Pitted Team | Pass | GSZ
Outbound II | 4.03.08 | User enters the exact number of units in the source location and there are no more remaining items to select from the source location | User is brought back to the Pallet to Pick From screen to select a new source location to repack | Pitted Team | Pass | GSZ
|  | User enters the exact number of units in the source location and there are remaining items to select from the source location | User is brought back to the Items in Source Pallet and is able to select more items to move from source to destination location | Pitted Team | Pass | GSZ
Outbound II | 4.03.09 | User attempts to repack items from one order into a container associated with a different order | Error Message: The Ship To postal code for the destination container must be the same as the source container. | Pitted Team | Pass | GSZ
Outbound II | 4.04 | Assign Trip to Container |  |  | 0%
Outbound II | 4.04.01 | user inputs a location not in the location input screen | error message: The door [x] could not be found | Pitted Team | Ready to Test
Outbound II | 4.04.02 | user selects or scans available location from the location input screen | user is brought to the pallets assigned to trip screen | Pitted Team | Ready to Test
Outbound II | 4.04.03 | user inputs an invalid or non existing shipping container into the pallet | error message: The container [x] could not be found. | Pitted Team | Ready to Test
Outbound II | 4.04.04 | user inputs valid shipping carton into the pallet | pallet is added to the listbox | Pitted Team | Ready to Test
Outbound II | 4.04.05 | User rescans the same container they scanned onto the pallet | the container is removed from the pallet listbox | Pitted Team | Ready to Test
Outbound II | 4.04.06 | user selects 'close trip' after building pallet | user is brought to the rate shop parameters screen and is able to select 'no change' or 'rate shop' | Pitted Team | Ready to Test
Outbound II | 4.04.07 | User selects Rate Shop (if ship via is Rate - Shop [X] | User is able to select the best rate and close out the shipment | Pitted Team | Ready to Test
Outbound II | 4.04.08 | User selects "No Change" if the ship via is a valid shipping service | User is taken back to the Location Input Screen and is able to select a new container to start packing proces with a message saying "Order [x] is shipped" | Pitted Team | Ready to Test
Outbound II | 4.05 | Void and Reprocess Shipment |  |  | 0%
Outbound II | 4.05.01 | user enters a valid order number, shipment numbner, or tracking number | error message: Please enter either a valid Tracking, Shipment, or Order number. | Pitted Team | Ready to Test
Outbound II | 4.05.02 | user enters an invalid order number, shipment numbner, or tracking number | user is brought to the Void Containers Confirmation Screen and is able to select container to void shipment | Pitted Team | Ready to Test
Outbound II | 4.05.03 | user selects a valid container to void shipment | user is brought back to the Identifier Entry Screen with a message noting the containers in which the system created to put the voided items into. User is able to input another new order/shipment to void | Pitted Team | Ready to Test
Outbound II | 4.06 | Rollback After Picking |  |  | 0%
Outbound II | 4.06.01 | user enters invalide LPN Number | error message: The selected container could not be found. Please enter a valid container number. | Pitted Team | Ready to Test
Outbound II | 4.06.02 | user enters valid LPN Number | user is brough to the Select PickDetail To RollBack Screen and is able to select the item to rollback | Pitted Team | Ready to Test
Outbound II | 4.06.03 | user selects valid item to roll back | user is brought to the Select PickDetail Qty To RollBack Screen and is prompted to select the qty to cancel | Pitted Team | Ready to Test
Outbound II | 4.06.04 | user enters in quantity greater than what is available to cancel | error message: The entered quantity should be less than or equal to the picked quantity. | Pitted Team | Ready to Test
Outbound II | 4.06.05 | user enters qty less than what is available | user is brough to the RollBack Location Screen and is prompted to select/scan location where the item exists and then brought back to the quantity screen with the scanned qty deprecated from the availlable qty | Pitted Team | Ready to Test
Outbound II | 4.06.06 | user enters a location that doesn't exist in the warehouse | error message: The location [x] could not be found. Please enter a valid location | Pitted Team | Ready to Test
Outbound II | 4.06.07 | user selects a valid location in the warehouse that isn't populated in the location listbox | item is moved to the location the user inputted | Pitted Team | Ready to Test
Outbound II | 4.06.08 | user rolls back all remaining items in the container | user is brought back to the RollBack Order screen and is able to select a new container | Pitted Team | Ready to Test
Integrations | 5.01 | Shopify ECOMM |  |  | 0%
Integrations | 5.01.01 | User pulls in item from Shopify | Creates items in channel listings & populates expected item fields (reference helpsite) | PittedTeam | Ready to Test
Integrations | 5.01.02 | User pulls in item in active status from Shopify | ensure only active items are pulling in | PittedTeam | Ready to Test
Integrations | 5.01.03 | Order Pull | Ony orders in paid & unfiilfulled status are pulled in | PittedTeam | Ready to Test
Integrations | 5.01.04 | User attempts to pull in order after updates are made | Previous order is voided & new order is created with updates from Shopify, ensure that the channel listing exists for the sales order | PittedTeam | Ready to Test
Integrations | 5.01.05 | User attempts to pull in customer returns | returns is created & ensure that the channel listing exists for the return | PittedTeam | Ready to Test
Integrations | 5.01.06 | Send a shipnotice to shopify | Tracking number sends and order marked as fulfilled | PittedTeam | Pass | Successful test with order SO29725 // DSID: 15765
Integrations | 5.02 | Shopify UK |  |  | 0%
Integrations | 5.02.01 | User pulls in item for Shopify | Item creates if the item didn't exist in ECOMM Shopify, ensure that no updates are made if item already existed, only creates a channel listing | PittedTeam | Ready to Test
Integrations | 5.02.02 | User pulls in item in active status from Shopify | ensure only channel listings for active items are being created | PittedTeam | Ready to Test
Integrations | 5.02.03 | Order Pull | Ony orders in paid & unfiilfulled status are pulled in | PittedTeam | Ready to Test
Integrations | 5.02.04 | User attempts to pull in order after updates are made | Previous order is voided & new order is created with updates from Shopify, ensure that the channel listing exists for the sales order | PittedTeam | Ready to Test
Integrations | 5.03 | Shopify WS |  |  | 0%
Integrations | 5.03.01 | User pulls in item for Shopify | Item creates if the item didn't exist in ECOMM Shopify, ensure that no updates are made if item already existed, only creates a channel listing | PittedTeam | Ready to Test
Integrations | 5.03.02 | User pulls in item in active status from Shopify | ensure only channel listings for active items are being created | PittedTeam | Ready to Test
Integrations | 5.03.03 | Order Pull | Ony orders in paid & unfiilfulled status are pulled in | PittedTeam | Ready to Test
Integrations | 5.03.04 | User attempts to pull in order after updates are made | Previous order is voided & new order is created with updates from Shopify, ensure that the channel listing exists for the sales order | PittedTeam | Ready to Test
Integrations | 5.04 | Amazon Vendor Central |  |  | 0%
Integrations | 5.04.01 | User runs stage EDI | ensure that successful docstores are created for orders pulled into stage EDI | PittedTeam | Ready to Test
Integrations | 5.04.02 | User runs process EDI | ensure that successful docstores are created for orders pulled into Deposco | PittedTeam | Ready to Test
Integrations | 5.04.03 | PO Acknowledgemnet | Whenever stage & process are ran for orders, an acknowledgement is sent to AMZ to avoid duplicate order pulls | PittedTeam | Ready to Test
Integrations | 5.05 | Amazon Seller Central |  |  | 25%
Integrations | 5.05.01 | User pulls in Item from ASC touchpoint | ensure only channel listings are created | PittedTeam | Ready to Test
Integrations | 5.05.02 | User pulls in sales order | ensure orders are being pulled into system | PittedTeam | Ready to Test
Integrations | 5.05.03 | Order acknowledgemnet | any orders that are pulled into system is sending an order acknowledgement to Amazon to avoid duplicate orders | PittedTeam | Ready to Test
Integrations | 5.05.04 | Ship Notice | test if docstores generates for tracking (tracking will not export currently in sandbox environment, no orders will be updated) | PittedTeam | Pass | Successful test with order SO29728 // DSID: 15779
Integrations | 5.06 | Walmart |  |  | 0%
Integrations | 5.06.01 | User pulls in item from Walmart | items are not created from item pulls, and ensure channel listings are created | PittedTeam | Ready to Test
Integrations | 5.06.02 | User pulls in sales order | Ensure order is coming in from Walmart | PittedTeam | Ready to Test
Integrations | 5.06.03 | Ship Notice | test if docstores generates for tracking (tracking will not export currently in sandbox environment, no orders will be updated) | PittedTeam | Ready to Test
Integrations | 5.07 | Orderful |  |  | 0%
Integrations | 5.07.01 | Customer Order Pull | Ensure that orders are created in the system | PittedTeam | Ready to Test
Integrations | 5.07.02 | Customer Order Acknowlodgment | Ensure that acknowledgements are sent back to Orderful for every order pulled in to avoid duplicate orders | PittedTeam | Ready to Test
Integrations | 5.07.03 | Export Ship Notice | check docstore for successful payloads | PittedTeam | Ready to Test
Integrations | 5.08 | Quickbooks Desktop |  |  | 0%
Integrations | 5.08.01 | Import Customer | Ensure TP is created with type of customer | PittedTeam | Ready to Test
Integrations | 5.08.02 | Import Vendor | Ensure TP is created with type of vendor | PittedTeam | Ready to Test
Integrations | 5.08.03 | Import Item | Ensure channel listings is created, no items will be created | PittedTeam | Ready to Test
Integrations | 5.08.04 | Import PO | Ensure PO is related and verify channel listing | PittedTeam | Ready to Test
Integrations | 5.08.05 | PO Receipts | Ensure for every receivied PO, a receipt is sent back to QBD | PittedTeam | Ready to Test
Integrations | 5.08.06 | Export Invoice | For every sales orders that are shipped, ensure that invoices are created & sent to QBD | PittedTeam | Ready to Test
Shipping | 6.01 | UPS |  |  | 0%
Shipping | 6.01.01 | Orders are shipped via UPS Next Day Air | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.02 | Orders are shipped via UPS 2nd Day Air | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.03 | Orders are shipped via UPS Surepost 1lb or Greater | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.04 | Orders are shipped via UPS Ground | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.05 | Orders are shipped via UPS 3 Day Select | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.06 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.01.07 | Ship an International Order | Shipping Account changes. Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02 | FEDEX |  |  | 0%
Shipping | 6.02.01 | Orders are shipped via FedEx Ground | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02.02 | Orders are shipped via FedEx First Overnight | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02.03 | Orders are shipped via FedEx Home Delivery | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.02.04 | Orders are shipped via FedEx Priority Overnight | Tracking number and shipping label is generated |  | Ready to Test
Shipping | 6.02.05 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03 | STAMPS (USPS) |  |  | 0%
Shipping | 6.03.01 | Orders are shipped via USPS First Class Mail | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.02 | Orders are shipped via USPS Priority Mail Express | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.03 | Orders are shipped via USPS Priority Mail | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.04 | Orders are shipped via USPS Ground Advantage | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.03.05 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.04 | EPOST |  |  | 0%
Shipping | 6.04.01 | Orders are shipped via EPG Courier Service | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.04.02 | Orders are shipped via EPG ePacket Service | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.04.03 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.05 | Royal Mail |  |  | 0%
Shipping | 6.05.01 | Orders are shipped via Royal Mail | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.05.02 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.06 | DHL |  |  | 0%
Shipping | 6.06.01 | Orders are shipped via DHL Express Worldwide | Tracking number and shipping label is generated | PittedTeam | Ready to Test
Shipping | 6.06.02 | Ship orders with every carton type (22) | Tracking number and shipping label is generated | PittedTeam | Ready to Test

## UAT Test Cases - End to End (hidden)
Spellbinders End to End Test Cases
Scenario | Status | Team | Owner | Notes
Inbound Admin
Create a PO Through DE | Pass | Pitted
Create a PO Through PO Entry | Pass | Pitted
Add a note through PO entry to an existing PO | Pass | Pitted
Generate a PO Report | Fail | Pitted |  | Changes to report needed
Create a return through CreateRMA | Ready to Test | Pitted
Create a return label through Deposco | Ready to Test | Pitted
Inbound
Receive PO full | Ready to Test | Pitted
U | Ready to Test | Pitted
Receive an item that requires Item Labels | Ready to Test | Pitted
Blind Receive a customer return from a web order | Ready to Test | Pitted
Receive a customer return for a wholesale | Ready to Test | Pitted
Partially Unrecieve a PO | Ready to Test | Pitted
Unreceive a full PO | Ready to Test | Pitted
Receive a PO that is designated for a Workorder, direct putaway | Ready to Test | Pitted
Putaway
Putaway single item containers | Ready to Test | Pitted
Putaway mixed item containers | Ready to Test | Pitted
Putaway containers to reserve locations | Ready to Test | Pitted
Putaway containers to pickable locations | Ready to Test | Pitted
Putaway loose stock | Ready to Test | Pitted
Outbound - Singles
Fulfill a Single Wave (Happy Path) | Ready to Test | Pitted
Exception a Pick on a Single Wave | Ready to Test | Pitted
Suspend a task on a Single Wave | Ready to Test | Pitted
Stage the container for a singles wave after it is full | Ready to Test | Pitted
Pack a Singles order | Ready to Test | Pitted
Pack a Singles O | Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
| Ready to Test | Pitted
Fulfill multi unit web order | Ready to Test | Pitted
Fulfill Wholesale order
Fulfill Club order
Fulfill international order
Fulfill singles exception repick
Fulfill multi exception repick
Exception a pick task for a single unit order
Exception a pick task for a multi unit order
Exception a pick task for web order
Exception a pick task for club order
Cancel an order that has not yet been released
Cancel an order that has been released but not picked
Cancel an order that has been picked but not packed or shipped
Cancel an order that has been packed but not shipped
Roll back an order that has been shipped and cancel it
Roll back an order that has not been shipped and re-ship

## Design Notes (hidden)
Day 1
Target and Walmart Trading Partners with labels
Packslip at order level
No BOL
Company field for custom packaging, to add notes via automations
No serial, lot or exp date tracking in any move processes
No limits to over receiving
Send email when stock has arrived (entity mod)
Send email when stock is received (rules)
how to handle serial ranges in pallet receiving | Will only be capturing numbers at packing
may have duplicate upc | Team will clean up this data
update warehouse lookup querty to remove dupes | Done
Will capture serial at packing not receiving due to serial ranges
Product conversion w/o workorder add to inventory
Lot tracking after product conversion with workorder | Only requires lot tracking of built product
Add cycle count variance api sql
how long does it take from start to finish for a cycle count? Replenishment?
Gabb has ICC and IMM id (sim card and phone serial number)
Have two fedex accounts
Need to setup 2 snogo shopify accounts but have all others
Grab stock expiration date report builder from FSG, send once a week
Create receiving billing config
Determine if they can partially ship based on their company level params and have two different waves/orp
Send email when return or po is received to the customer
Reorder point field and report field to trigger once below reorder point
POI and Automations
Blank Ship Via | Set Current Status to "On Hold" for some customers and then reach out to Pat, some PITTED can select or rate shop for them. PITTED team needs to provide list of customer preferences
Order inserts and stickers
can we inventory inserts and help them decrement inventory in an automated why? Or just do adjust inventory/cycle count on a regular cadence to keep level accurate?
Add text field at the item level that PITTED team or customer will manage by adding the message that will appear. DEP team to add automation to add stamp this field to orderheader.note field and then create a customization in packing to display this note. "Add insert from P0101"
Zip code, state, line 1, line 2, etc | Set current status to "On Hold"
FIFO waving
Group by carrier and ship service level, then prioritize by clients | Do we want to mix customers in pickwaves?
Bulk wave - same carrier, qty, and SKU
POI Done field | add at end of automations and add to build wave delegator to not wave if it is not checked
Ship Via Translations
PITTED team to provide mappings from customer side to Deposco for cross references, PITTED team to setup by following helpsite instructions
Pat to send invoice examples from QBO
Setup QBO meeting with Leah, Pat and Tyler
software kitting for gabb phones- no kitting in deposco for gabb
K location is the kitting location in the warehouse
add ons like stickers are not counted during cycle counts
how do they know which orders need inserts? based on slack comms and customer basis (vip vs regular)
add notes at packing to "add inserts"
cone locations need barcodes
cones: red is damaged/on hold/blind PO, green is ready complete, yellow is in progress, orange is replens
staging lanes need barcodes
during picking, single sku per pick location
charge at each picks and case picks - pack roll up in deposco
inaccurate dims and weights -- new pack flag in receivnig
pitted's customers to add correct dims and weight through DE
no cubiscan
in receiving no default receiving location, need putaway
direct putaway for hazmat location
need to put restrictions for hazmat locations in move item process
returns: they create returns, blind RMA, create a return label
take pictures at PO/OL level, need to configure capturing pics
busy season: april- august, slow season: oct to dec
need Picking and Packing performance widgets by users
custom packaging used for some items
inventory for cartons- yes
capture serial at picking and validate at packing for gabb
after packing, stage to assigned ups/usps bins, needs barcode for those bins, add rules to throw an error if scanned wrong bin
Day 2
Waving:
Turn serial capture off in picking processes
Leave staging screen for user to scan at end of picking processes, no suggestion will be given. User will need to decide which staging location to put the picked cart in
Kitting:
MuskOx - set ship via for all orders to "ship outside system" in automations as client sends PITTED shipping labels they generate in Shopify
Limit wave list in picking processes to 1 wave (oldest or priority?)
Cart Slotting
Packing:
Want grocery scanning in all packing processes
Weird current scenario with description field on cartonTypes | Currently need a unique cartonType record for each carrier even though physical box
B2B orders should always allocate to a reserve location
B2B no grocery scan, all others grocery scan picking
Grocery scan at packing except soft close
only require one scan per location for batchpicks
populate weight in packing based on pack weight
Setup b2b picking with only 1 order per wave
Setup bulk picking with 100 orders per wave for singles
Start tabbing at carton type field in packing
Serial tracking for gabb, Naturade and mitra9 use lot and expiration dates, washiepro only uses lot
Setup rateshop packing in admin group so they can check rates. Do not allow select rates for this specific one
Test mail innovations rateshopping to see why rates don't return
Need SCAC, PRO, Shipping service used (need to expose in api)
Map carrier (scac) to shipment and shipping service they chose to the ship via | They will need to enter the freight shipping cost before eod
Pickable reserve zone for b2b orders where they can pick from. Setup separate scheduler to replenish from reserve to pickable reserve and keep current replen scheduler that replenishes from reserve to picking. Make all waves zone based with ecomms in picking zones and b2b wave in the pickable reserve zone (need pickable and reserve flags checked)
3pl billing meeting setup with Leah and Pat
Cycle count in the missing po receipts and add image on blind orders. Map timestamp somewhere on the order
Setup bulk packing process with bulk waving/picking
Do not consider pallets in any locations, cycle counts or replenishment process
Show client number of backorders and actual backorders
Gross revenue (Tyler to provide calculations) - Daily revenue across all activities performed
Carrier special services setup for hazmat items
Bulk waves split by carrier and max number of orders = 250
Take pictures at the po level and at the receipt line level to show damages for audits
Will be using bulk packing
Will decrement carton types at shipping
Add in rules to physical count to not allow cycle counts if pick tasks are present
Create automations to ensure all items have cycle count enabled unless intangible
Add specific rules in packing to prevent backorders from shipping if the company level flag does not allow partials

## Test Cases
Test Number | Scenario | Assignee | Status | DEP Test Data | Pitted Test Data | Due Date | Date Complete | Pitted Comments | Deposco Comments | In SOP Document?
Data Exchange
| Use 'Purchase Order Upload' data exchange to import purchase orders | Pitted Team | Pass | PO #demopo1 uploaded via DE | KC.TEST>DEMO.PO | 2025-02-11 | 2025-02-10
Pre-Receiving
| Cancel entire PO before receiving has started | Pitted Team | Pass | PO #7440 canceled and current status updated from 'New' to 'Canceled' | KC.TEST>DEMO.PO | 2025-02-11 | 2025-02-10
| Cancel some PO lines before receiving has started | Pitted Team | Pass | PO #7441--3 canceled and Orderline status updated from 'New' to 'Canceled' | KC.TEST>DEMO.PO - Canceld line item 2 AOBLKS | 2025-02-12 | 2025-02-10
| Cancel part of PO line before receiving has started | Pitted Team | Pass | Order line [7441--2] was partially canceled | KC.TEST>DEMO.PO - Canceld partial line item 1 SA2 | 2025-02-11 | 2025-02-10
| Cancel some PO lines after some receiving has been completed | Pitted Team | Pass | Order line [7444--3] was canceled after PO 7444 was partially received | KC.DEMO.2.ANTI- SA2 line canceled | 2025-02-11 | 2025-02-10
| Cancel part of PO line after some receiving has been completed | Pitted Team | Pass | Order line [7444--1] was partially canceled after PO 7444 was partially received | KC.DEMO.2.ANTI- AOBLKS recieved 5 but when I tried to cancel the last ten i recoeved this error There are no eligible order lines to cancel for the item [AOBLKS]. | 2025-02-11 | 2025-02-10
| Cancel part of PO while receiving is occurring | Pitted Team | Pass | PO #7445 The order cannot be canceled when it has a status of [Receiving] | The order cannot be canceled when it has a status of [Receiving] | 2025-02-11 | 2025-02-10
Receiving
| Receive Loose stock | Pitted Team | Pass | PO #fake received | KC.TEST.DEMO.PO | 2025-02-11 | 2025-02-11
| Receive a PO partially into LPN | Pitted Team | Pass | PO #6723 received partially | KC.TEST.DEMO.PO | 2025-02-11 | 2025-02-11
| Receive a PO into LPN using the 'New pallet' button | Pitted Team | Pass | PO #6723 received on different pallets | KC.TEST.DEMO.PO Two pallets | 2025-02-11 | 2025-02-11
| Receive a PO into LPN and Putaway to suggested locations | Pitted Team | Pass | PO #DesignPO3 received and putaway to pickloc3 | KC.TEST.DEMO.PO attempt LA2 to pickloc3 | 2025-02-11 | 2025-02-11 | jogier@deposco.com I tried moving LA2 to pickloc3 did not give me under the suggested and when I entered pickloc3 it said please enter within assigned zones
| Receive a PO into LPN and Putaway to non-suggested locations | Pitted Team | Pass | PO #6784 received and SKU SA2 putaway to pickloc1 | KC.TEST.DEMO.PO SA2 to pickloc1 | 2025-02-11 | 2025-02-11
| Receive a PO with Lot and expiration tracked products | Pitted Team | Pass | PO #DesignPO3: captured Lot Number for SKU 'SA2' and expiration date for SKU 'MA2+MBLU' | KC.TEST>DEMO.PO - Serial and LOT and EXP for AOBLKS | 2025-02-11 | 2025-02-10
| Scan an item which is not on the PO | Pitted Team | Pass | errror message: Please enter a valid SKU for 6723 | KC.TEST>DEMO.PO - Scanned Item1 | 2025-02-11 | 2025-02-10
| Over-receive a SKU on a PO | Pitted Team | Pass | PO #6723: SKU 'SA2' over-received 60 instead of 4 | KC.TEST.DEMO.PO over received item AOBLKS | 2025-02-11 | 2025-02-10
| Display OrderHeader Notes during receiving | Pitted Team | Pass | PO #6723: Order note with title 'Receiving' and body 'This is an important note' displayed on OrderHeader notes screen | KC.TEST.DEMO.PO | 2025-02-11 | 2025-02-10
| Display OrderLine Notes during receiving | Pitted Team | Pass | PO #6723: Orderline note with title 'Receiving' and body 'This is an Orderline note' displayed on Orderline notes screen for 6723--3 | KC.TEST.DEMO.PO | 2025-02-11 | 2025-02-10 |  | jogier@deposco.com Do you have an example on what this is supposed to look like. I just need confimation
| Receive a PO with new pack flag checked on the Pack | Pitted Team | Pass | PO #7446 received with Pack 'AOBLKS--Each--1' with new pack flag field checked, updated the dims and weight on pack | All skus recieved in PO's have dims. | 2025-02-11 | 2025-02-10 |  | jogier@deposco.com Do you have an example on what this is supposed to look like. I just need confimation
| Receive a Blind Order | Pitted Team | Pass | Blind Receipt #6710 received | Blind order 8800 | 2025-02-11 | 2025-02-10 | Straight forward
| Scan an item from a different BU on the Blind Order | Pitted Team | Pass | error message: Order [6710] only accepts items in Company [Anti-Ordinary]. Please enter an item for Company [Anti-Ordinary] or hit Finish and start a new order for this item | Tested scanning an item from Anti-ordianry and scanned a Muskox items and it allowed me to add them to a blind reciept 8800 | 2025-02-11 | 2025-02-10 | jogier@deposco.com Blind reciept 8800 | karina@pittedlogistics.com could you share what PO/Blind order this is?
| Receive a Blind RMA using Returns Receiving | Pitted Team | Pass | Blind RMA #6803 received | DEMO.TEST.KC tested Blind RMA | 2025-02-11 | 2025-02-10
| Receive a Customer Return and Putaway in a suggested location | Pitted Team | Pass | CR #6843 received to pickloc2 location | 9008 recieved into location pickloc2 | 2025-02-11 | 2025-02-10 | jogier@deposco.com We did not have an RMA to test and we were not shown on creating an RMA so I based off blind order
| Receive a Customer Return with Reason Code 'Damaged' | Pitted Team | Pass | CR #6860 received with 'Damaged' reason code to Damaged Location | 9008 recieved into damage SA2 | 2025-02-11 | 2025-02-10
| Unreceive by Pallet | Pitted Team | Pass | PO #7461 in 'test' pallet unreceived from the 'Unreceiving' location | L0025127 moved into unreceiving | 2025-02-11 | 2025-02-10
| Unreceive by loose stock | Pitted Team | Pass | PO #6723 unreceived | Unreceived KC.DEMO.2.ANTI Container L0025127 | 2025-02-11 | 2025-02-11
| Capture image and attach at the order level | Pitted Team | Pass | Tested with PO #TEST5, added images to orderheader and receiptlines |  | 2025-02-11 | 2025-02-10 |  | karina@pittedlogistics.com this is ready to be tested! You can reference PO# TEST5
| Capture image and attach to receipt line level | Pitted Team | Pass | Tested with PO #TEST5, added images to orderheader and receiptlines |  | 2025-02-11 | 2025-02-10
| Fully receive a PO and check for email | Pitted Team | Pass | Blind PO #7607 received to sara.kulkarni@deposco.com | Recieved email | 2025-02-11 | 2025-02-10
| Change PO status from "New" to "Arrived" and check if email sends | Pitted Team | Pass | Updated the current status of a PO to Arrived, and received an email from system@deposco.com | KC.TEST.DEMO.PO emailed recieved | 2025-02-11 | 2025-02-10 |  | karina@pittedlogistics.com Test with Anti-Ordinary POs, email is set to go to karina@pittedlogistics.com
| Fully receive a customer return and check for email | Pitted Team | Pass | RMA 7630 received to sara.kulkarni@deposco.com |  | 2025-02-11 | 2025-02-11
Move Item
| Move a SKU into destination location | Pitted Team | Pass | Item [MA2+MBLU] has been moved from [Receiving] to [pickloc2]. | Tried moving SA2 into pickloc2 location and it gave me the error | 2025-02-11 | 2025-02-10 | jogier@deposco.com unable to move item. There are stock units with serial numbers in location,Please contact system administrator | karina@pittedlogistics.com could you specify the error you are getting and location you are trying to move SA2 to?
Move Stock
| Build cart of multiple SKUs | Pitted Team | Pass | Cart #car01 built with SA2 and Item3 from the Staging and Receiving location |  | 2025-02-11
| Put SKUs into multiple locations | Pitted Team | Pass | SA2 moved to Pickloc3 location and Item3 moved to resloc1 | Moved SA2 and AOBLKS into test loc | 2025-02-11 | 2025-02-10
Move Container
| Move container into destination location | Pitted Team | Pass | Pallet 'test' moved to destination location 'Unreceiving' |  | 2025-02-11 | 2025-02-10
Adjust Inventory
| Consume all inventory in a location | Pitted Team | Pass | Consumed all stock in location R12-26-D due to reason code 'Stock Not Found' | Damage location consumed | 2025-02-13 | 2025-02-13
| Consume some quantity of a particular item in a location | Pitted Team | Pass | 50 units of SKU Item3 consumed in Location #pickloc2 due to Damaged Goods | 2 SA2 consumed in damaged location | 2025-02-14 | 2025-02-13
| Add a note while adjusting inventory | Pitted Team | Pass | 50 units of SKU Item3 consumed due to Damaged Goods, with a note of 'Mold' | 1 SA2 added damaged Note | 2025-02-13 | 2025-02-13
| Consume all inventory in a specific container (LPN) | Pitted Team | Pass | Consumed all SKUs in LPN #pk1 in Location #testloc2 | Consumed LPN L0025127 | 2025-02-13 | 2025-02-13
| Create inventory for a serial tracked item in a specific location | Pitted Team | Pass | Created 4 units of SKU OXM23W007-410-XXL/T in pickloc2 with unique serial numbers | Adjusted 2 OXM23W007-410-XXL/T units and only asked for a lot and exp date. | 2025-02-13
| Create inventory for a lot tracked item in a specific location | Pitted Team | Pass | Created 1 unit of SKU OXM23W007-410-XXL/T in pickloc2 with exp, and lot number | Adjusted OXM23W007-410-XXL/T with LPN L0023745 | 2025-02-13
| Create inventory for an expiration date tracked item in a specific location | Pitted Team | Pass | Created 1 unit of SKU OXM23W007-410-XXL/T in pickloc2 with exp and lot number | Adjusted OXM23W007-410-XXL/T with LPN L0023746 | 2025-02-13
Cycle Counts
| Use Create Cycle Count Action on selected locations via desktop ui | Pitted Team | Pass | Count by Location task created for Location #testloc2 with a low priority | Created location tasks for R01 locations | 2025-02-13 | 2025-02-13
| Use Create Cycle Count Action on selected items | Pitted Team | Pass | Count by Item task created for SKUs SA2 and SA2+SPRP | MA2+MBLU cycle count task created | 2025-02-13 | 2025-02-13
| Queue Location for Cycle Count through Handheld | Pitted Team | Pass | Cycle Count task created for Location #pickloc2 | Cycle count task created for pickloc1 and pickloc2 | 2025-02-13 | 2025-02-13
| Queue Item for Cycle Count through Handheld | Pitted Team | Pass | Cycle Count task created for SKU AOBLKS | Created for SA2 | 2025-02-13 | 2025-02-13
| Perform On Demand Cycle Count | Pitted Team | Pass | Cycle count peformed for SKUs at Location #pickloc3 | Counted pickloc2 itemnumber3 | 2025-02-13 | 2025-02-13
| Cycle count Lot and Expiration dates tracked SKUs | Pitted Team | Pass | Cycle count peformed for SKUs SA2 & AOBLKS at Location #pickloc3 | OXM23W007-410-XXL/T counted and provided exp and lot. | 2025-02-13 | 2025-02-13
| Generate a cycle count for a location (Scheduler) | Pitted Team | Pass | Successful |  | 2025-02-13
| Generate a cycle count for an item (Scheduler) | Pitted Team | Pass | Successful |  | 2025-02-13
| Recount the variance | Pitted Team | Pass | Recounted variance for R11-27-A | Picloc2 recounted created | 2025-02-13 | 2025-02-13
| Reject a Variance | Pitted Team | Pass | Rejected variance Item1 | rejected AOBLKS | 2025-02-13 | 2025-02-13
| Approve a Variance | Pitted Team | Pass | Accepted variance for Item2 | Accepted SA2 adjustments | 2025-02-13 | 2025-02-13
| Scan Item not existing in location | Pitted Team | Pass | Scanned gabbtestitem at Location #testloc1 as a blind count | scanned R02-02-A gabbitem | 2025-02-13 | 2025-02-13
| Do not count items in location and just hit 'Next Location' | Pitted Team | Pass | Goes to Next Location | skipped cycle counting | 2025-02-13 | 2025-02-13
Replenishments
| Add Storage Details using DE | Pitted Team | Pass | Added Storage details for SKU LA2 in Location# pickloc2 | R11-01-A Pack [AOBLKS] not found when processing entity Storage Business Key: Pack: AOBLKS, Location: R11-01-A | 2025-02-13 | 2025-02-13 |  | karina@pittedlogistics.com Item/SKU number is AOBLKS, the pack key would be AOBLKS--Each--1
| Add Storage Details manually in UA | Pitted Team | Pass | Added Storage details for SKU AOBLKS in Location# pickloc1 | Added storage details for P05-08-D | 2025-02-13 | 2025-02-13
| Create replenishment via 'FEFO and FIFO Replenishments ' scheduler | Pitted Team | Open | Replenishments Tasks created for AOLKS from Location #resloc1 to pickloc1 based on FEFO,FIFO |  | 2025-02-13
| Replenish a location in full | Pitted Team | Pass | SKU #CDS6CS replenished completely from resloc3 to pickloc3 with a message of 'Nothing to replenish' | SKU Morg finished with nothing to replenish | 2025-02-13 | 2025-02-13
| Replenish a location partially | Pitted Team | Pass | Prompted to pick up remaining SKUs for Itemnumber6 |  | 2025-02-13
| Click Cart is Full | Pitted Team | Pass | State is updated to 'full' |  | 2025-02-13
| Exception Destination Location when replenishing | Pitted Team | Pass | State updated to 'Destination Full' when exceptioned | Destination full | 2025-02-13 | 2025-02-13
| Create manual replenishment | Pitted Team | Pass | Manually replenished SKU #AOBLKS in Location #pickloc1 | Created Manual replenishment item morg to picloc2 | 2025-02-13 | 2025-02-13
| Use 'Unassign my tasks' button | Pitted Team | Pass | You have been unassigned from 16 replenishment task(s).' |  | 2025-02-13 | 2025-02-13
| Validate replenishments can come from a reserve location with pickable and reserve flags checked | Pitted Team
Kitting
| Use' Kit Header and Kit details' Data exchange template | Pitted Team | Pass | Kit header and kit details for Kit 3 uploaded through DE | Testt.kitting | 2025-02-13 | 2025-02-13
| Use 'Kitting workorder' Data exhange template | Pitted Team | Pass | Workorder 12 uploaded through DE | Workorder.text.kc | 2025-02-13 | 2025-02-13
| Create Kit Header and kit details manually in UA | Pitted Team | Pass | Kit header and kit details for TestKit2 added manually | KC.Kit.test | 2025-02-13 | 2025-02-13
| Move Input item into Kitting Workcell Location | Pitted Team | Pass | testkitem1 moved to Kitting Workcell Location | testkitem1 Unable to move item [Item1]. There are stock units with serial numbers in the location [Shipping]. Please contact system administrator. | 2025-02-13 | 2025-02-13
| Execute Workorder using Product Conversion with Work Order button | Pitted Team | Pass | Workorder 11 executed completely | testkititem2 completed | 2025-02-13 | 2025-02-13
| Execute a workorder partially, back out and finish it in a couple of minutes | Pitted Team | Pass | Workorder 12 executed partially-- | Work order 17 | 2025-02-13 | 2025-02-13
| Execute a workorder that does not have enough stock, but stock exists in reserve | Pitted Team | Pass | TestWO9 was successfully replenished then built |  |  |  |  | User will be allowed to enter the normal kitting process, but if there is not enough stock it will generate a replenishment and fork the user to replenish the stock. Once the stock is replenished they can continue to build the workorder
Automations and Post Order Import (POI)
| Run POI on a SO when 'Insert?' field is set to 'true' to add a note on SO | Pitted Team | Pass | A note added on SO #16586--5947427356885 | demoSO12 added note | 2025-02-18 | 2025-02-18
| Run POI on a SO when 'Sticker?' field is set to 'true' to add a note on SO | Pitted Team | Pass | A notes added on SO #16586--5947427356885 | Muskox Insert-Demokc | 2025-02-18 | 2025-02-18
| Run POI on a SO with missing Ship via | Pitted Team | Pass | SO #2938--5838255489095 on hold due to blank ship via | KC.DEMO.Order1 hold due to ship via | 2025-02-18 | 2025-02-17
| Run POI on a SO with missing Ship to information | Pitted Team | Pass | SO #2943--5843949486151 on hold for a missing Ship to Phone field | KC.DEMO.Order1 missing phone | 2025-02-18 | 2025-02-18
| Run POI on a Musk OX Order to set ship via to 'Ship Outside System' | Pitted Team | Pass | SO #16558--5943681646805 set to Ship Outside System | 13379 - set to ship outside the system | 2025-02-18 | 2025-02-18
| Did the 'POI Flag' check after running POI | Pitted Team | Pass | SO #2943--5843949486151 POI flag checked | demoSO flag checked | 2025-02-18 | 2025-02-18
Sales Orders Cancellations
| Cancel a Sales order | Pitted Team | Pass | SO #11399 canceled | Canceled 16605--5955121873109 | 2025-02-18 | 2025-02-17
| Cancel an Orderline on SO | Pitted Team | Pass | Ordeline 11399--1 canceled | Canceled line order for order 11444 | 2025-02-18 | 2025-02-17
Waving
| Build and release a wave that can be completely fulfilled | Pitted Team | Pass | SO #demoSO2 released completely | singles-Anti-Ordinary-Shopify-250217-15:29:59-1 | 2025-02-18 | 2025-02-17
| Troubleshoot a backordered wave | Pitted Team | Pass | SO #9462--6220685508909 backordered, undo release the order | KC.DEMO.Order1 missing information backordered fixed and then released the order. | 2025-02-18 | 2025-02-18
| Use the build and release scheduler | Pitted Team | Pass | Successful |  | 2025-02-18
| Manually select two or more orders and build and release | Pitted Team | Pass | SO #11420 and #11421 released into Batch-Musk Ox-Shopify-250213-13:24:25-1 | 9587--6225364320557 | 2025-02-18 | 2025-02-17
| Build and release a Singles wave | Pitted Team | Pass | SO #demoSO2 released to a Singles Pickwave | demoSO12 build and released into a picking wave | 2025-02-18 | 2025-02-17
| Build and release a Subscirption wave | Pitted Team | Pass | SO #demoSO6 released to a Subscription Pickwave | Subscription-Batch-Musk Ox-x-redo:1XOXM19W001-340-L:1-P | 2025-02-18 | 2025-02-17
| Build and release a Batch wave | Pitted Team | Pass | SO #11410 release into a Batch wave | 11444 released waved and then picked | 2025-02-18 | 2025-02-17
| Builld and release a Large Order (Freight wave) | Pitted Team | Pass | SO #11406 release into a freight wave |  | 2025-02-18
| Build and release a batch or singles order with no available stock in picking zone | Pitted Team | Pass | Stock will backorder | Order back ordered 16608--5955241083093 | 2025-02-18 | 2025-02-17
| Build and release freight wave with stock available in reserve zone and picking | Pitted Team | Pass | 11577 was waved with picking stock and stock in reserve. Chose stock in reserve first over the picking stock. 11578 chose remaining stock from reserve then forked to picking zone for remainder |  | 2025-02-18
Picking
| Pick a Singles Order using SingleScanPicking | Pitted Team | Pass | SO #demoSO2 picked into LPN #222 |  | 2025-02-18 | 2025-02-17 |  | Picked containing 11406 into bin12
| Pick a Batch Order using BatchPicking | Pitted Team | Pass | SO #11410 picking in LPN #226 | Pick Wave [Batch-Anti-Ordinary-Shopify-250123-23:40:15-1]. | 2025-02-18 | 2025-02-17 |  | 11144 picked to bin11
| Pick a Subscription Singles Order | Pitted Team | Pass | SO #demoSO6 picked in LPN #223 | Subscription-Batch-Musk Ox-x-redo: | 2025-02-18 | 2025-02-17
| Pick a Subscription Batch Order | Pitted Team | Pass | SO #demoSO8 | 8094 | 2025-02-19 | 2025-02-18
| Pick a Large Order using Freight Picking | Pitted Team | Pass | SO #11436 | Freight-Anti-Ordinary-250213-12:26:27-1 | 2025-02-18 | 2025-02-18
| Pick an Order to check the FEFO, Location pick sequence | Pitted Team | Pass | SO #7149--5903726444788 used FEFO, location pick sequence | Wave containing order 8094 | 2025-02-18 | 2025-02-17
| Pick a Kit to Stock Item | Pitted Team | Pass |  |  | 2025-02-18
| Pick a Kit to Order item | Pitted Team | Pass |  |  | 2025-02-18
| Create an exception | Pitted Team | Pass | Picking Audit created for SKU SA2 | 9469--6220878545197 | 2025-02-18 | 2025-02-17
| Scan incorrect item during picking - should receive error | Pitted Team | Pass | Error message: Please enter a valid SKU | Picked wrong sku for order 11406 gave me error message please enter valid sku | 2025-02-18 | 2025-02-17
| Suspend workgroup and unassign user | Pitted Team | Pass | Pickwave#: Singles-Anti-Ordinary-Shopify-250124-12:07:11-1 suspended | Batch-Anti-Ordinary-Shopify-250213-15:52:51-1 | 2025-02-18 | 2025-02-17
| Suspend workgroup and keep assigned user | Pitted Team | Pass | Pickwave#: Singles-Anti-Ordinary-Shopify-250124-12:07:11-1 workgroup suspended | Tulip 250213-shopify | 2025-02-18 | 2025-02-17
| Suspend task | Pitted Team | Pass | Pick task #89 suspended task | Pick task 44 Batch-Anti-Ordinary-Shopify-250213-15:52:51-1 | 2025-02-18 | 2025-02-17
Packing
| Pack a Singles Order using PackOrderByItem | Pitted Team | Pass | SO #11422 packed using PackOrderByItem | Packing is complete for the order [11445 | 2025-02-20
| Pack a Batch order using SingleScanPacking | Pitted Team | Pass | SO #11446 packed using SingleScanPacking | Singles-Anti-Ordinary-Shopify-250225-22:06:53-1 | 2025-02-20
| Pack Subscription Orders using Bulk Packing | Pitted Team | Pass | 2 orders on Subscription-Batch-Musk Ox-x-redo:1XOXM19W001-340-L:1-PITSLC-250218_11:25:12-1 packed using bulk packing |  | 2025-02-20
| Pack an order and capture serial number | Pitted Team | Pass | Captured serial number for SKU LA2+MVCP SO #8345--6004687798516 | Packed item1 for order 11305 | 2025-02-20
| Pack an order and confirm lot number | Pitted Team | Pass | Confirmed lot number for SO #8345--6004687798517 | confirmed lot for LA2 sku | 2025-02-20
| Pack an order and confirm exp date | Pitted Team | Pass | Confirmed exp date for SO #8345--6004687798517 | confirmed lot for LA2 sku | 2025-02-20
| Rateshopping using SingleScanPacking | Pitted Team | Pass | SO #7938--5919384797428 rateshopped | 11305 | 2025-02-20
| Pack a Large Order | Pitted Team | Pass | SO # | Pack order in cart20 | 2025-02-20
| Pack an Order using Softclose packing | Pitted Team | Pass | SO #demoSO10, complete but not shipped | Soft packed item SA2+SBLU 1 pallet | No longer needed
| Pack a pallet using assign trip button | Pitted Team | Pass | The trip [Freight-250217-1421-64] is closed | Assigned trip for Freight-250218-0147-74
| After you have closed the trip check SCAC and tracking number fields on shipment | Pitted Team | Pass | Shipment 238 and 239. SCAC and pro number are mapped to shipment
| Use the next carton Button | Pitted Team | Pass | Successful | bin40001 packed in two cartons | 2025-02-20
| Use the Pack remainder button | Pitted Team | Pass | Successful | bin40001 packed remainder | 2025-02-20
| Void and reprocess a shipment | Pitted Team | Pass | Shipment 174 voided | 1Z17Y2X10390302393 | 2025-02-20
| Rollback Order button | Pitted Team | Pass |  |  | 2025-02-20
| Scan a carton type and ensure it decrements from shipping supplies in PackOrderByItem | Pitted Team | Pass |  | mailer | 2025-02-20
| Scan a carton type and ensure it decrements from shipping supplies in SingleScanPacking | Pitted Team | Pass |  | mailer | 2025-02-20
| Scan a carton type and ensure it decrements from shipping supplies in BulkPacking | Pitted Team | Pass |  | mailer | 2025-02-20
Shipping
| Retrieve a shipping label | Pitted Team | Pass | Shipment 174 | 272_9434600208271110689395_1] for Shipment (272) | 2025-02-20 | 2025-02-24
| Retrieve a third party Label | Pitted Team | Pass |  | 13338-SH-01 | 2025-02-20 | 2025-02-25
| UPS Ground | Pitted Team | Pass | Shipment 120 | Singles-Anti-Ordinary-Shopify-250225-22:06:53-1 | 2025-02-20 | 2025-02-25
| UPS Next Day | Pitted Team | Pass |  | Singles-Anti-Ordinary-Shopify-250225-22:06:53-1 | 2025-02-20 | 2025-02-25
| UPS Expedited Mail Innovations - Domestic | Pitted Team | Pass | Shipment 107 | 8327--5998928822516 |  | 2025-02-25
| UPS 2nd Day Air | Pitted Team | Pass | Shipment |  |  | 2025-02-25
| UPS 3 Day select | Pitted Team | Pass | Shipment 88 | 8314--5996056281332 | 2025-02-20 | 2025-02-25
| UPS Next Day Air Saver | Pitted Team | Pass | Shipment 85 | 8327--5998928822516 | 2025-02-20 | 2025-02-25
| UPS Next Day Air AM | Pitted Team | Pass | Shipment 106 | 8329--5999065071860 | 2025-02-20 | 2025-02-25
| UPS Next Day Air | Pitted Team | Pass | Shipment 105 | 8159--5950907908340 | 2025-02-20 | 2025-02-25
| UPS Standard | Pitted Team | Pass | Shipment 93 |  | 2025-02-20 | 2025-02-25
| UPS Worldwide ExpeditedSM | Pitted Team | Pass | Shipment 100 | 8322--5997884276980 | 2025-02-20 | 2025-02-25
| UPS Worldwide ExpressSM | Pitted Team | Pass |  |  | 2025-02-20 | 2025-02-25
| UPS Worldwide Saver | Pitted Team | Pass | Shipment 104 |  | 2025-02-20 | 2025-02-25
| UPS Priority Mail Innovations - International | Pitted Team | Pass | Shipment |  | 2025-02-20 | 2025-02-25
| USPS Ground Advantage | Pitted Team | Pass | Shipment 90 |  | 2025-02-20 | 2025-02-25
| USPS Priority Mail | Pitted Team | Pass | Shipment | Singles-250116_1 | 2025-02-20 | 2025-02-25
| FedEx One Rate | Pitted Team | Pass | Shipment 147 | 5994886004980 | 2025-02-20 | 2025-02-20
| GLS rates are potentially being used | Pitted Team | Needs Info |  |  | 2025-02-20
| USPS Ground Service Advantage | Pitted Team | Pass |  | Singles-Anti-Ordinary-Shopify-250225-22:06:53-1 | 2025-02-20 | 2025-02-25
| USPS Priority Mail | Pitted Team | Pass |  | Singles-Anti-Ordinary-Shopify-250225-22:06:53-2 | 2025-02-20 | 2025-02-25
| Amazon Services to be used | Pitted Team | Needs Info |  |  | 2025-02-20
| Fedex Ground | Pitted Team | Pass | Shipment 151 |  | 2025-02-20 | 2025-02-25
| Fedex Home Delivery | Pitted Team | Pass | Shipment 143 | 8330--5999092924660 | 2025-02-20 | 2025-02-25
| Fedex Two day One rate | Pitted Team | Pass | Shipment 145 |  | 2025-02-20 | 2025-02-25
| Generate Hazmat UPS Shipping Label | Pitted Team | Open |  |  | 2025-02-20 | 2025-02-25
| ehub FedEx Two Day One Rate | Pitted Team | Open
| ehub UPS 2nd Day Air | Pitted Team | Open
| ehub UPS 3-Day Select | Pitted Team | Open
| ehub UPS Ground | Pitted Team | Open
|  | Pitted Team | Open
|  | Pitted Team | Open
Integrations
| Manually pull an order | Pitted Team | Open | Shopify, Walmart, QBO and FBM
| Manually pull an item | Pitted Team | Open | Shopify, Walmart, QBO and FBM
| Manually pull a customer return | Pitted Team | Open | Shopify, Walmart
| Validate all item fields are pulling as expected | Pitted Team | Pass | Shopify, Walmart, QBO and FBM
| Validate order number and all order fields are pulling correctly | Pitted Team | Pass | Shopify, Walmart, QBO and FBM
| Validate all customer return fields are pulling correctly | Pitted Team | Open | Shopify, Walmart
| Push order acknowledgements | Pitted Team | Open | FBM
| Export billing invoices to Pitted QBO | Pitted Team | Pass
| Validate Stamps Manifest generates and sends | Pitted Team | Open
| Create a sales order | Pitted Team | Open | Deposco API (Gabb and Velvet only)
| Create a purchase order | Pitted Team | Open | Deposco API (Gabb and Velvet only)
| Create a customer return | Pitted Team | Open | Deposco API (Gabb and Velvet only)
| Pull shipment info | Pitted Team | Open | Deposco API (Gabb and Velvet only)
| Pull inventory | Pitted Team | Open | Deposco API (Gabb and Velvet only)
3PL Billing
| Per Order | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | 359 Anti-Ordinary | 2025-02-20
| Per Item | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | 357 Anti-Ordinary | 2025-02-20
| Per Pallet | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | 352 Anti-Ordinary Pallet Storage | 2025-02-20
| Per Carton | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | Gabb | 2025-02-20
| Returned Order Per Shipment | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | RMA.BILLING.TEST | 2025-02-20
| Shipping | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | 359 Anti-Ordinary | 2025-02-20
| Missing PO | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | 354 Anti-Ordinary Missing PO | 2025-02-20
| Outbound Pallet | Pitted Team | Open | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Returned Order Per Item | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | RMA.BILLING.TEST | 2025-02-20
| Pallet Storage | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| XL Bin Storage | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Large Bin Storage | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | 364 Anti-Ordinary Large Bin Storage | 2025-02-20
| Medium Bin Storage | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Small Bin Storage | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time | N/A do not have these bin sizes | 2025-02-20
| AMZ 2 Month Assembly (500+) | Pitted Team | Invalid | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| AMZ 2 Month Assembly (499-) | Pitted Team | Invalid | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Attached Label Fee | Pitted Team | Pass | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Sticker Fee | Pitted Team | Open | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Shade + Screw bag + Mount | Pitted Team | Invalid | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Threading Rings | Pitted Team | Invalid | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Screw Bags | Pitted Team | Invalid | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Insert Fee | Pitted Team | Open | Ensure billable transactions are generated. Billable transactions are created for all transactions of the previous day at 4 am mountain time |  | 2025-02-20
| Ensure invoices are creating for each customer | Pitted Team | Pass |  |  | 2025-02-20
| Adhoc transactions to be validated once added by Pat | Pitted Team | Pass |  | 411 | 2025-02-20
| Set "Exclude from billing" field to "Exclude" | Pitted Team | Needs Info | No transactions should be generated for the following: Sticker Fee Attached Label Fee Insert Fee Outbound Pallet Per Item Per Order Shipping
| Non admin users receive an error if they try to change the exclude from billing field | Pitted Team | Needs Info | If your user is not in the admin group they should receive an error if they try to change this field
Reports
| Velvet Packing Slip | Pitted Team | Open
| Generic Packing Slip | Pitted Team | Open
| Item Labels | Pitted Team | Open
| UPS Manifest | Pitted Team | Open
| Customer return label | Pitted Team | Open
Misc
| Run "Assign Mail Innovations Shipping Costs" scheduler for shipments < 1 pound | Pitted Team | Open | Will set any shipments shipping cost based off of zipcodes and zones template pat sent for any order with ship via = UPS Expedited Mail Innovations - Domestic
| Run "Assign Mail Innovations Shipping Costs" scheduler for shipments >= 1 pound | Pitted Team | Open | Will set any shipments shipping cost based off of zipcodes and zones template pat sent for any order with ship via = UPS Expedited Mail Innovations - Domestic
| Run action "Email Return Label and Create Return" | Pitted Team | Open | Will email you the return shipping label in a pdf file
| Ship an order in zone 9 for mail innovations | Pitted Team | Open

## UAT Test Cases
Test Number | Scenario | Assignee | Status | Pitted Test Data | In SOP Document?
Data Exchange
| Use 'Purchase Order Upload' data exchange to import purchase orders | Pitted Team | Pass | Uploaded Purchase Orders
| Add Storage Details using DE | Pitted Team | In Progress
| Use' Kit Header and Kit details' Data exchange template | Pitted Team | Pass | Added Bundle kit header
| Use 'Kitting workorder' Data exhange template | Pitted Team | Pass | Added 42 workorder
Pre-Receiving
| Cancel entire PO before receiving has started | Pitted Team | Pass | KC.TEST.PO.4
| Cancel some PO lines before receiving has started | Pitted Team | Pass | KC.TEST.PO.4
| Cancel part of PO line before receiving has started | Pitted Team | Pass | KC.TEST.PO.4
| Cancel some PO lines after some receiving has been completed | Pitted Team | Pass | KC.TEST.PO.6
| Cancel part of PO line after some receiving has been completed | Pitted Team | Pass | KC.TEST.PO.6
| Cancel part of PO while receiving is occurring | Pitted Team | Pass | KC.TEST.PO.6
| Cancel PO in "Arrived" status | Pitted Team | Pass | KC.TEST.PO.5
Receiving
| Receive Loose stock | Pitted Team | Pass | KC.TEST.PO.6
| Receive a PO partially into LPN | Pitted Team | Pass | KC.TEST.PO.1 using Pallet
| Receive a PO into LPN using the 'New pallet' button | Pitted Team | Pass | KC.TEST.PO.2
| Receive a PO into LPN and Putaway to suggested locations | Pitted Team | Pass | KC.TEST.PO.2
| Receive a PO into LPN and Putaway to non-suggested locations | Pitted Team | Pass | KC.TEST.PO.2
| Receive a PO with Lot and expiration tracked products | Pitted Team | Pass | KC.TEST.PO.2
| Scan an item which is not on the PO | Pitted Team | Pass | KC.TEST.PO.2
| Over-receive a SKU on a PO | Pitted Team | Pass | KC.TEST.PO.2
| Display OrderHeader Notes during receiving | Pitted Team | Pass | KC.TEST.PO.3
| Display OrderLine Notes during receiving | Pitted Team | Pass | KC.TEST.PO.3
| Receive a PO with new pack flag checked on the Pack | Pitted Team | Pass | KC.TEST.PO.3
| Receive a Blind Order | Pitted Team | Pass | 13851
| Scan an item from a different BU on the Blind Order | Pitted Team | Pass | 13851
| Receive a Blind RMA using Returns Receiving | Pitted Team | Pass | 13853
| Receive a Customer Return and Putaway in a suggested location | Pitted Team | Pass | V
| Receive a Customer Return with Reason Code 'Damaged' | Pitted Team | Pass | 13851
| Unreceive by Pallet | Pitted Team | Pass | 13851
| Unreceive by loose stock | Pitted Team | Pass | KC.TEST.PO.3
| Capture image and attach at the order level | Pitted Team | Pass | KC.TEST.PO.3
| Capture image and attach to receipt line level | Pitted Team | Pass | KC.TEST.PO.3
| Fully receive a PO and check for email | Pitted Team | Pass | KC.TEST.PO.3
| Change PO status from "New" to "Arrived" and check if email sends | Pitted Team | Pass | KC.TEST.PO.1
| Fully receive a customer return and check for email | Pitted Team | Pass | 13853
| Email and print a return label | Pitted Team | Pass | 13830
Move Item
| Move a SKU into destination location | Pitted Team | Pass | SGS-NPKLEO-R
| Hazmat location or zone restrictions? | Pitted Team | In Progress
Move Stock
| Build cart of multiple SKUs | Pitted Team | Pass | cart1
| Put SKUs into multiple locations | Pitted Team | Pass
Move Container
| Move container into destination location | Pitted Team | Pass | L0020557
Adjust Inventory
| Warehouse Lookup | Pitted Team | Pass | Scanned Receiving, bin10, LA2
| Consume all inventory in a location | Pitted Team | Pass | R01-02-D
| Consume some quantity of a particular item in a location | Pitted Team | Pass | MORG
| Add a note while adjusting inventory | Pitted Team | Pass | R02-01-D
| Consume all inventory in a specific container (LPN) | Pitted Team | Pass | phone
| Create inventory for a serial tracked item in a specific location | Pitted Team | Pass | MORG
| Create inventory for a lot tracked item in a specific location | Pitted Team | Pass | MORG
| Create inventory for an expiration date tracked item in a specific location | Pitted Team | Pass | MORG
Cycle Counts
| Use Create Cycle Count Action on selected locations via desktop ui | Pitted Team | Pass
| Use Create Cycle Count Action on selected items | Pitted Team | Pass
| Queue Location for Cycle Count through Handheld | Pitted Team | Pass
| Queue Item for Cycle Count through Handheld | Pitted Team | Pass | SA2
| Perform On Demand Cycle Count | Pitted Team | Pass | pickloc3
| Cycle count Lot and Expiration dates tracked SKUs | Pitted Team | Pass
| Generate a cycle count for a location (Scheduler) | Pitted Team | Pass | R01-02-D
| Generate a cycle count for an item (Scheduler) | Pitted Team | Pass | SA2+SBLU
| Recount the variance | Pitted Team | Pass | SA2+SBLU
| Reject a Variance | Pitted Team | Pass | SA2+SBLU
| Approve a Variance | Pitted Team | Pass | SA2+SBLU
| Scan Item not existing in location | Pitted Team | Pass
| Do not count items in location and just hit 'Next Location' | Pitted Team | Pass
Replenishments
| Add Storage Details manually in UA | Pitted Team | Pass | done
| Create replenishment via 'FEFO and FIFO Replenishments ' scheduler | Pitted Team | Pass | VTP-PUDGYTRUCKERHATXAWFO-PINK
| Replenish a location in full | Pitted Team | Pass | pickloc3
| Replenish a location partially | Pitted Team | Pass | pickloc2
| Click Cart is Full | Pitted Team | Pass
| Exception Destination Location when replenishing | Pitted Team | Pass | VTP-PUDGYTRUCKERHATXAWFO-PINK
| Create manual replenishment | Pitted Team | Pass | cart12
| Use 'Unassign my tasks' button | Pitted Team | Pass | done
Kitting
| Create Kit Header and kit details manually in UA | Pitted Team | Pass | Bundle Kit header
| Move Input item into Kitting Workcell Location | Pitted Team | Pass
| Execute Workorder using Product Conversion with Work Order button | Pitted Team | Pass | workorder 42
| Execute a workorder partially, back out and finish it in a couple of minutes | Pitted Team | Pass | workorder 43
| Execute a workorder that does not have enough stock, but stock exists in reserve | Pitted Team | Open
Automations and Post Order Import (POI)
| Run POI on a SO when 'Insert?' field is set to 'true' to add a note on SO | Pitted Team | Pass | demoSO1
| Run POI on a SO when 'Sticker?' field is set to 'true' to add a note on SO | Pitted Team | Pass | demoSO1
| Run POI on a SO with missing Ship via | Pitted Team | Pass | demoSO1
| Run POI on a SO with missing Ship to information | Pitted Team | Pass | demoSO1
| Run POI on a Musk OX Order to set ship via to 'Ship Outside System' | Pitted Team | Pass | demoSO1
| Did the 'POI Flag' check after running POI | Pitted Team | Pass | demoSO1
Sales Orders Cancellations
| Cancel a Sales order | Pitted Team | Pass | S15
| Cancel an Orderline on SO | Pitted Team | Pass | S15--2
Waving
| Build and release a wave that can be completely fulfilled | Pitted Team | Pass
| Troubleshoot a backordered wave | Pitted Team | Pass
| Use the build and release scheduler | Pitted Team | Pass | Batch-Anti-Ordinary-Shopify-250305-12:48:08-1
| Manually select two or more orders and build and release | Pitted Team | Pass
| Build and release a Singles wave | Pitted Team | Pass | Singles-Anti-Ordinary-Shopify-250305-12:44:21-1
| Build and release a Subscirption wave | Pitted Team | Pass
| Build and release a Batch wave | Pitted Team | Pass
| Build and release a Partial wave | Pitted Team | Pass | Partial-Anti-Ordinary-Shopify-250305-10:15:43-1
| Builld and release a Large Order (Freight wave) | Pitted Team | Pass | Freight-Velvet Caviar-250305-10:40:50-1
| Build and release a batch or singles order with no available stock in picking zone | Pitted Team | Pass
| Build and release freight wave with stock available in reserve zone and picking | Pitted Team | Pass
Picking
| Pick a Singles Order using SingleScanPicking | Pitted Team | Pass | 6805--5893742264564
| Pick a Batch Order using BatchPicking | Pitted Team | Pass | 13879
| Pick a Subscription Singles Order | Pitted Team | Pass
| Pick a Subscription Batch Order | Pitted Team | Pass
| Pick a Large Order using Freight Picking | Pitted Team | Pass | SO9
| Pick an Order to check the FEFO, Location pick sequence | Pitted Team | Pass | Batch-Tulip Home Goods-Shopify-250305-15:11:04-1
| Pick a Kit to Stock Item | Pitted Team | Pass
| Pick a Kit to Order item | Pitted Team | Pass
| Create an exception | Pitted Team | Pass
| Scan incorrect item during picking - should receive error | Pitted Team | Pass | done
| Suspend workgroup and unassign user | Pitted Team | Pass | done
| Suspend workgroup and keep assigned user | Pitted Team | Pass | done
| Suspend task | Pitted Team | Pass | done
Packing
| Pack a Singles Order using PackOrderByItem | Pitted Team | Pass | Order 13829
| Pack a Batch order using SingleScanPacking | Pitted Team | Pass
| Pack Subscription Orders using Bulk Packing | Pitted Team | Pass | Subscription-Batch-Musk Ox-x-redo:1XOXM19W001-340-L:1-PITSLC-250305_17:53:07-1
| Pack an order and capture serial number | Pitted Team | Pass
| Pack an order and confirm lot number | Pitted Team | Pass | item7
| Pack an order and confirm exp date | Pitted Team | Pass | item34
| Rateshopping using SingleScanPacking | Pitted Team | Invalid
| Pack a freight Order | Pitted Team | Pass | ATTC
| Pack a pallet using assign trip button | Pitted Team | Pass
| After you have closed the trip check SCAC and tracking number fields on shipment | Pitted Team | Pass
| Use the next carton Button | Pitted Team | Pass | tested with S13
| Void and reprocess a shipment | Pitted Team | Pass | 343 shipment number
| Rollback Order button | Pitted Team | Pass
| Scan a carton type and ensure it decrements from shipping supplies in PackOrderByItem | Pitted Team | Pass
| Scan a carton type and ensure it decrements from shipping supplies in SingleScanPacking | Pitted Team | Pass
| Scan a carton type and ensure it decrements from shipping supplies in BulkPacking | Pitted Team | Pass
| Added Gabb IMEI and ICC Number at packing | Pitted Team | Pass | bin 15019 for gabb
Shipping
| Retrieve a shipping label | Pitted Team | Pass | Pass
| Retrieve a third party Label | Pitted Team | Pass
| UPS Ground | Pitted Team | Pass | 364
| UPS Next Day | Pitted Team | Pass
| UPS Expedited Mail Innovations - Domestic | Pitted Team | Pass
| UPS 2nd Day Air | Pitted Team | Open
| UPS 3 Day select | Pitted Team | Open
| UPS Next Day Air Saver | Pitted Team | Open
| UPS Next Day Air AM | Pitted Team | Open
| UPS Next Day Air | Pitted Team | Open
| UPS Standard | Pitted Team | Open
| UPS Worldwide ExpeditedSM | Pitted Team | Open
| UPS Worldwide ExpressSM | Pitted Team | Open
| UPS Worldwide Saver | Pitted Team | Open
| UPS Priority Mail Innovations - International | Pitted Team | Open
| USPS Ground Advantage | Pitted Team | Open
| USPS Priority Mail | Pitted Team | Open
| FedEx One Rate | Pitted Team | Open
| GLS rates are potentially being used | Pitted Team | Open
| USPS Ground Service Advantage | Pitted Team | Failed | 13810
| USPS Priority Mail | Pitted Team | Open
| Amazon Services to be used | Pitted Team | Open
| Fedex Ground | Pitted Team | Open | 348
| Fedex Home Delivery | Pitted Team | Open | 362
| Fedex Two day One rate | Pitted Team | Open | 363
| Generate Hazmat UPS Shipping Label | Pitted Team | Open
| ehub FedEx Two Day One Rate | Pitted Team | Open
| ehub UPS 2nd Day Air | Pitted Team | Open
| ehub UPS 3-Day Select | Pitted Team | Open
| ehub UPS Ground | Pitted Team | Open
Integrations
| Manually pull an order | Pitted Team | Open
| Manually pull an item | Pitted Team | Open
| Manually pull a customer return | Pitted Team | Open
| Validate all item fields are pulling as expected | Pitted Team | Open
| Validate order number and all order fields are pulling correctly | Pitted Team | Open
| Validate all customer return fields are pulling correctly | Pitted Team | Open
| Push order acknowledgements | Pitted Team | Open
| Export billing invoices to Pitted QBO | Pitted Team | Open
| Validate Stamps Manifest generates and sends | Pitted Team | Open
| Create a sales order | Pitted Team | Open
| Create a purchase order | Pitted Team | Open
| Create a customer return | Pitted Team | Open
| Pull shipment info | Pitted Team | Open
| Pull inventory | Pitted Team | Open
| Item pull and check if LWH gets overriden to 0 | Pitted Team | Open
3PL Billing
| Per Order | Pitted Team | Open
| Per Item | Pitted Team | Open
| Per Pallet | Pitted Team | Open
| Per Carton | Pitted Team | Open
| Returned Order Per Shipment | Pitted Team | Open
| Shipping | Pitted Team | Open
| Missing PO | Pitted Team | Open
| Outbound Pallet | Pitted Team | Open
| Returned Order Per Item | Pitted Team | Open
| Pallet Storage | Pitted Team | Open
| XL Bin Storage | Pitted Team | Open
| Large Bin Storage | Pitted Team | Open
| Medium Bin Storage | Pitted Team | Open
| Small Bin Storage | Pitted Team | Open
| AMZ 2 Month Assembly (500+) | Pitted Team | Open
| AMZ 2 Month Assembly (499-) | Pitted Team | Open
| Attached Label Fee | Pitted Team | Open
| Sticker Fee | Pitted Team | Open
| Shade + Screw bag + Mount | Pitted Team | Open
| Threading Rings | Pitted Team | Open
| Screw Bags | Pitted Team | Open
| Insert Fee | Pitted Team | Open
| Ensure invoices are creating for each customer | Pitted Team | Open
| Adhoc transactions to be validated once added by Pat | Pitted Team | Pass | 13815
| Set "Exclude from billing" field to "Exclude" | Pitted Team | Open
| Non admin users receive an error if they try to change the exclude from billing field | Pitted Team | Open
Reports
| Velvet Packing Slip | Pitted Team | Pass | S13
| Generic Packing Slip | Pitted Team | Pass | 9632--6226688344365
| Item Labels | Pitted Team | Open
| UPS Manifest | Pitted Team | Pass | trip Freight-250305-1726-165
| Customer return label | Pitted Team | Open
| Email and Print Manifest | Pitted Team | Pass | "trip Freight-250305-1726-165"
Misc
| Run "Assign Mail Innovations Shipping Costs" scheduler for shipments < 1 pound | Pitted Team | Open
| Run "Assign Mail Innovations Shipping Costs" scheduler for shipments >= 1 pound | Pitted Team | Open
| Run action "Email Return Label and Create Return" | Pitted Team | Open
| Ship an order in zone 9 for mail innovations | Pitted Team | Open

## UAT Notes
Day One |  |  |  | Priority
Process | Change | Status | Description
Move Process | Can we move in bulk or need to scan 1/1 if it is lot/serial tracked (move stock & move item) | Complete | move item: need to scan 1 by 1, not for move stock | 1
Integrations | Tyler updated Gabb ehub to the prod api token | Complete | Resolved- missing ship vendor code in General.ShippingServiceWithOpenTrip
Integrations | For sure need amazon shipping through ehub, maybe GLS. Nothing required for go live | Complete | Setup in production
Cancel Order | Why are reason codes not populating in dropdown? |  |  | 10
Inventory | Make a new cycle count button for Gabb so we do not require counting serials and lots during that process | Complete | Not needed if we capture at picking | 1
Branding | update button color and logos | In Progress |  | 2
Kitting | Workorder replenishments not triggering | Complete | Working as expected | 1
Billing | Can we bill for stock that is in reserve older than a year | Complete |  | 1
Integrations | Upload the QBO company id's | Complete |  | 1
Receiving | Gabb is using phoenix for their returns. See if they can use the Deposco api | Complete | They will use deposco api to send returns
API | Ship gabb test order from paul | Complete
Shipping | Will ship hazmat through fedex, ups and usps
Picking | No need to have container numbers per each carton in receiving. Will received mixed items on one carton then move it to reserve. Test if this container is removed from the stock when moved to picking location | Complete | pallet receiving to resloc1, then move container to pickloc1, container gets stripped | 1
Ehub | Reach out about GLS ship vias | Complete | No Customers currently using GLS, but pitted does want this as an option
Move item | Hazmat locations to be added, validations for hazmat skus
Day Two
Shipping | Test rateshop profiles to only rateshop mail innovations and see if we can return those rates instead of using my custom logic - and international rates | Complete | Does not map to shipping cost
Waving | Karina/Pat to provide which customers are ok with partial shipments and how to handle (fill and kill) | Complete | Pat will own manually checking this
Waving | Karina/Pat to provide customers max number of orders so we can automatically split them | Complete |  | 1
Waving | Shields & Elan pure- 54 orders for a wave (sub and batch) singles= 300 | Complete |  | 1
POI | Ship via set to FTL or LTL- to identify the freight orders | Complete
Packing | Can we make a call to ups ground in attc? | Open |  | 1
Kitting | Capture lot and exp date // make a new kitting button for gabb that does not require capture | Complete |  | 10
Build and Release scheduler | 6am, 12pm,2pm Mon-Friday, 300 orders for build and release scheduler | Complete |  | 1
Shipping | usps parcel select mail innovations test | Complete
picking | evaluate if lot and serial tracked at item level | Complete | Added to sspicking, need to add to batchpicking
picking | add rules to sspicking to capture imei and icc | Complete | Tested and validated onsite
Mail innovations | Check logic to see why specific shipments are not being stamped | Complete | Adjusted query to use inner joins and use "Like" instead of only one ship via
Item Tracking | Will confirm lot and exp date in picking. Must be captured in receiving or kitting processes and then captured in cycle count process
Packing | Notes will be shown to packers instead of pickers per Karina | Complete |  | 1
Scanner | Scanners must have keystroke output > action key character = "Tab". Was previously "Line feed". Callout is these barcodes are too close to eachother and hard to scan | Complete
Picking | Add validation that imei is 15 characters and iCC is 20 characters | Complete | Need to add into batchpicking
Picking | Test gabb batch picking logic with multiple pick bins and orders for the same item (not being picked into the same container) | Complete |  | 1
Picking | test picking from mixed pallet that the stock is removed from pallet once cart is scanned | Complete | It lets you pick into that mixed pallet from which stock was removed | 1
Exceptions | See why single scan picking does not allow for exceptions | Complete
ATTC | Freight packing slip |  |  | 3
Packing | Will not be printing packing slips for everyone. Only print one for freight orders through assign trip to container process | Complete | switched off rules for sspacking and POBI for generic packing slip | 1
Packing | Throw error in packing whenever the packer scans the bin and total weight = 0 or any packs = 0 | Complete | Carrier will throw error
picking | See if gabb orders can work like subscriptions where we group like orders and have it stamp on the wave number | Complete
packing | get serial scan logic to work for imei so they can expand gabb picks | Complete
packing | take pack remainder button off | Complete
Shipping | test shipping serial/ot tracked item where lot is empty. Check for error showing | Complete |  | 1
ATTC | check empty string error in assign trip to container | Complete | Resolved
Day Three
Data Exchange | carton type DE | Complete
Receiving | UPC labels to be updated to 2.65x1 and adjust the field on the label | Complete
Manifest | need to add Dims of container,Item SKu,qty to manifest
Trip | Add BOL file to trip | Complete
KIitting | Review workorder replenishments without storage details | Complete | Working as expected | 1
New to Arrived | need to get Email approved | Complete | On pitted to upload dkin and spf files | 1
Return for gabb | Map item attributes from SL to OL on the returns | Open |  | 5
PO received email | Add a column in email to show the variance order pack ty - received pack qty (Business rules) | Complete | Will send email whether it is closed or partially closed | 2
Unreceiving | Figure out why unreceiving is not working even after moving stock to it | Complete
Item Tracking | Determine where every item tracking attribute will be captured/confirmed. Cycle counts should capture/confirm and replenishments should not, but we need to validate if attributes move with replenished stock | Complete |  | 1
Dashboards | Create revenue dashboards and reference google sheet karina created for reports
Billing | Update kitting queries to have the quantity look at sum of workorder details built quantity instead of wo.quantity | Complete |  | 1
Billing | Create new config which bills stock > 1 year old | Complete |  | 1

## Go Live Notes
Day 1 | Description | Status
Widget | Pallet locations being used (Stock in location /empty pallet location) | Complete
Billing | Will call billing query
Tracking | Ensure all lot/serial tracked items are flagged | In Progress
ShipNotice | make a throttle group for ship notices | Complete
PII | Test PII logic | Complete
Order Pulls | Every 30 mins (add throttle group) | Complete
Inventory | Setup filter queries and sync inventory every 2 hours | Complete
Kits | Crosscheck all kit to order components
Waving | Subscription waving profiles (5) based on the batchsize on company | Complete
Reporting | Backorders by client widget | Complete
Packs | Weights for 300 or more packs to be added in
Packing | test 8 ounces, 0.5 pounds while packing out
Shipping label | Default to use all customer names instead of pitted logistics for every ship service | Complete
New pack flag | auto calculating weight on OrderBatch-Elan Pure-Shopify-250317-18:13:05-1 due to the new pack flag rule | Complete | One item was missing weight
Item Attributes | Pitted needs to add insert/sticker/serial/exp tracking on all needed SKUs | Complete
Widget | Orders shipped by day per week | Complete
Field Mapping | Create lookup field mapping for shipping services | Complete
Field Mapping | Create lookup field mapping for carton types | Complete
Day 2
Field Mapping | Pack Import - check to ensure packs have right company | Complete
Hazmat | Add carrier special services for all hazmat items
Storage | Verify the 38 storage records with missing packs | Complete
Integrations | Best way to handle shopify order cancellations? | Complete | Added multiple sales order pulls
Automations | Pat to add sticker and insert flags for items to create order notes | Complete
stock | Karina to re upload stock using new fm | Complete
POI | Do not consider intagnble items on orderlines when setting batch for order summary | Complete
Storage | reupload missing storage records | Complete
Day 3
Replens | How can we sort by pick sequence to optimize picking and putaway?
Manifests | Team will manually print stamps and fedex manifests at pickup | Note
Rules Packing | Add error at container scan post to throw error if weight of any packs are 0 | Complete
Shipping | Test ups mail innovations international | Complete
Ship Vias | How to handle translations for blank ship vias | Complete
Order Priority | Create order priority pickwaves | Complete
Cartons | Create items and stock in shipping supplies location to decrement | Complete
Integrations | Walmart 404 error for items
Cycle Counts | Determine cycle count profile frequency
Packing Scans | Create location barcodes for staging after picking
Freight | Pick and pack a freight order
Day 4
Integration Alerts | Alert when there are failed order pulls | Complete
FBA | Setup autopick for FBA orders | Complete | Setup in ua and ready to be tested
Shipping | Ship international order
Freight | Assign trip to container packing slip printing and rules adjustment to print at container hist level | Complete
Karina | Revenue reports - show by department and by customer. |  | Need pat/karina to assign department to the billing configs
Did not do | Bulk (subscriptions) picking, bulk packing, freight picking, freight packing, FBA upload
QBO | Check on shipping carrier and aging stock configs added to QBO
Freight packing slip | update packing slip to pass in Ch.number and test ATTC | Complete
Order Pulls | Adjust automations to only add a note if poi has not run on the order yet | Complete
Stamps | Getting shipping manifest to run correctly
POI | check for insert and sticker notes
Day 5
BatchPicking | Final screen in batchpicking is setting serial and lot for non-serial and lot tracked items | Complete | Adjusted rules to not do this
Picking | Trim empty space in the IMEI field | Complete | Done in picking, but need to verify logic in packing
Packing | Leading space is preventing scans | Complete | Can adjust logic to only consider 16 characters
Shipping | Validate Gabb ehub for production | Complete
Trim long order summaries |  | Complete
eHub | ehub fedex one rate error | Complete
items | flag cycle count field

## GoNo-Go Decision
Pitted Logistics Go vs No-Go Decision Evaluation
Factors | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Due Date | Comment | Pitted Team Tested | DEP Team Tested
| Deposco Setup | 80 |  |  |  | 79
Deposco Setup | Printer Details | 10 |  | Pitted | 100% | 10 | Are all printers configured in Deposco and test prints received? |  |  | FALSE | FALSE
Deposco Setup | Printer Resources | 10 |  | Pitted | 100% | 10 | Are all print stations setup in Deposco? |  |  | FALSE | FALSE
Deposco Setup | Printer Assignments | 10 |  | Pitted | 100% | 10 | All reports assigned to printers and resources in Deposco? |  |  | FALSE | FALSE
Deposco Setup | RF Scanners/Handheld Devices | 10 |  | Pitted | 100% | 10 | All scanners purchased, Deposco app installed, auto-send features enabled? |  |  | FALSE | FALSE
Deposco Setup | Label Printers | 10 |  | Pitted | 100% | 10 | Are all printers setup on the network? Are printer supplies on-hand (ribbons, labels, etc.)? |  |  | FALSE | FALSE
Deposco Setup | Document Print Parameters - orientation, print speed, etc | 10 |  | Pitted | 100% | 10 | Are all printers setup on the network? Supplies on hand? |  | 300dpi | FALSE | FALSE
Deposco Setup | Critical and High Issues Resolved A) B) | 10 |  | DEP/Pitted | 90% | 9 | Have all High and Critical issues from the issues list been resolved? |  | Gabb imei and icc capture | FALSE | FALSE
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release - Cycle Counts - Replenishments | 10 |  | DEP/Pitted | 100% | 10 | All jobs have been scheduled and enabled? |  |  | FALSE | FALSE
| Warehouse Prep | 35 |  |  |  | 31.5
Warehouse Prep | Location Labels | 10 |  | Pitted | 100% | 10 | Are all locations, receiving areas, shipping docks, etc. labeled? |  |  | FALSE | FALSE
Warehouse Prep | Label Carts/Equipment for Moving of Inventory | 10 | Y | DEP/Pitted | 80% | 8 | Procure Carts for moving of inventory and label them |  |  | FALSE | FALSE
Warehouse Prep | Item inventory barcoded and labeled to scan | 5 |  | DEP/Pitted | 70% | 3.5 | Item inventory barcoded and labeled to scan |  |  | FALSE | FALSE
Warehouse Prep | RF Network connectivity | 10 |  | Pitted | 100% | 10 | Is the connectivity strong and cover all necessary scan areas? |  |  | FALSE | FALSE
| Standard Operating Procedure Documentation | 70 |  |  |  | 15.5
Standard Operating Procedures | Receiving/Unreceiving | 5 |  | Pitted | 10% | 0.5 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Create Customer Returns | 5 |  | Pitted | 100% | 5 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Putaway | 5 |  | Pitted | 100% | 5 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Cycle Counting | 5 |  | Pitted | 100% | 5 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Adjust Inventory | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Kitting/Workorders | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Picking | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Picking | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Bulk Packing | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Singles Packing | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Multis Packing | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | LTL Shipping (Wholesale) | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Exceptions in Packing | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
Standard Operating Procedures | Replenishments | 5 |  | Pitted | 0% | 0 | Pitted SOP's written and shared with appropriate team members? |  |  | FALSE | FALSE
| Training & Testing | 50 |  |  |  | 49
Training & Testing | Business Scenarios Definition | 10 |  | DEP/Pitted | 100% | 10 | Define all Business scenario including exception processes Unit and End to End Test Case Definition |  |  | FALSE | FALSE
Training & Testing | Process Training and Testing - Receiving - Putaway - Replenishments - Cycle Counting - Parcel Picking - Parcel Packing - Bulk Packing - Wholesale Picking - LTL Shipping - Shipping | 10 |  | Pitted | 90% | 9 | Unit and End to End Test Case Execution |  | Batchpicking for gabb needs to be finalized | FALSE | FALSE
Training & Testing | User Acceptance Testing | 10 |  | Pitted | 100% | 10 | Execute all defined business scenarios within Deposco |  |  | FALSE | FALSE
Training & Testing | Supervisor/Administrator | 10 |  | Pitted | 100% | 10 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | End-user | 10 |  | Pitted | 100% | 10 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
Training & Testing | Customer Training | 10 | Y | Pitted | 0% | 0 | Have all customers been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? |  |  | FALSE | FALSE
| Configurations/Master Data | 80 |  |  |  | 76
Configurations | Inventory Validation | 10 |  | Pitted | 100% | 10 | Is there a plan for inventory to be created in production environment for cutover? Has the plan been tested/validated? |  | Per Karina, team will do a full cycle count of the warehouse | FALSE | FALSE
Configurations | Items | 10 |  | Pitted | 100% | 10 | Are all items setup in production or have plan to do so? Are all of the units of measure defined for each item? |  |  | FALSE | FALSE
Configurations | Zones | 10 |  | Pitted | 100% | 10 | Have all of the Zone and Zone Location records been set up in production or have a plan to do so? Has the pick flow been tested? |  |  | FALSE | FALSE
Configurations | Locations | 10 |  | Pitted | 100% | 10 | Are the location types, zones, and location masters configured accurately in production or have a plan to do so? |  |  | FALSE | FALSE
Configurations | Menu Structures | 10 |  | Pitted | 100% | 10 | Have the appropriate menu levels been created for the different departments in production or have a plan to do so? |  |  | FALSE | FALSE
Configurations | Packs | 10 |  | Pitted | 100% | 10 | Have all valid pack types been entered into production or have a plan to do so? |  | We do have other packs besides eaches, but not needed for go live | FALSE | FALSE
Configurations | Containers | 10 | Y | Pitted | 80% | 8 | Have all containers (pallets, carts, transient bins) been created in production or have a plan to do so? |  |  | FALSE | FALSE
Configurations | Kit/Component Relationships | 10 | Y | Pitted | 80% | 8 | Are all KitHeaders/KitDetails for Kit to Stock and Item/Component for Kit to Order relationships been uploaded in production or have a plan to do so? |  | Pat to finish | FALSE | FALSE
Configurations | Carton Types | 10 | Y | Pitted | 0% | 0 | Upload all carton types to be used as well as associated items, packs and inventory into the shippingsupplies location |  |  | FALSE | FALSE
| Cutover and Conversion Plans | 10 |  |  |  | 5
Cutover and Conversion Plans | Cutover plan developed | 10 | Y | DEP/Pitted | 50% | 5 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions. |  |  | FALSE | FALSE
| Data Exchange Interfaces - Imports/Exports with Deposco | 85 |  |  |  | 50
Interfaces - Imports to Deposco | Carton Types | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Locations/Zones/Storage Details | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Items/Packs/UPCs | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Containers | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Workorders | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Kit/Component Relationships | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Sales Order | 5 |  | DEP | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  | Karina to email us current csv file | FALSE | FALSE
Interfaces - Imports to Deposco | Mail Innovations Cost Updates | 10 |  | DEP | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Interfaces - Imports to Deposco | Purchase Order | 10 |  | DEP | 90% | 9 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Integrations | 590 |  |  |  | 565
Integrations with Deposco | Amazon Seller Central - Order Acknowledgement | 0 |  | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  | Connected but not validated | FALSE | FALSE
Integrations with Deposco | Walmart - Item | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Walmart - Sales Order | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Walmart - Ship Notice | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Walmart - Inventory Sync | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Orderful - Ship Notice | 0 |  | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  | Connected but not validated | FALSE | FALSE
Integrations with Deposco | Orderful - Export Inventory Sync | 0 |  | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  | Connected but not validated | FALSE | FALSE
Integrations with Deposco | Orderful - Export customer order acknowledgement | 0 |  | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  | Connected but not validated | FALSE | FALSE
Integrations with Deposco | Amazon Seller Central - Order Acknowledgement | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Amazon Seller Central - Item | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Amazon Seller Central - Ship Notice | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Amazon Seller Central - Inventory Notice | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Amazon Seller Central - Sales Order | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Quickbooks Online - Import item | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Quickbooks Online - Export Ship Notice | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Quickbooks Online - Import Sales Order | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Quickbooks Online - Inventory Sync | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Quickbooks Online - Export Billing Invoice | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Shopify - Customer Return | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Shopify - Item | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Shopify - Sales Order | 10 |  | Pitted | 100% | 10 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Shopify - Ship Notice | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Shopify - Outbound Inventory Sync | 10 | Y | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | UPS - Rates - Shipping Label | 10 | Y | Pitted | 80% | 8 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Stamps - Rates - Shipping Label | 10 | Y | Pitted | 80% | 8 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | eHub - Rates - Shipping Label | 10 | Y | Pitted | 10% | 1 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
Integrations with Deposco | Fedex - Rates - Shipping Label | 10 | Y | Pitted | 80% | 8 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| 3PL Billing | 180 |  |  |  | 260
Billing with Deposco | Anti-Ordinary Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Bison Paddles Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Brazilian Flame Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Cascade Cocoa Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Elan Pure Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Gabb Wireless Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Krado Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Luxe Pickleball Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Mitra 9 Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Musk Ox Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Naturade Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Outstanding Foods Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Pudgy Penguins Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Shield Systems Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Sno-Go Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Tulip Home Goods Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Velvet Caviar Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Billing with Deposco | Washie Pro Transaction and Invoice Profiles and Configs | 10 |  | Pitted | 100% | 10 | Are the invoicing and transaction profiles accurate? Are all prices updated on billing configs? |  |  | FALSE | FALSE
Integrations with Deposco | Royal Mail - Rates - Shipping Label | 0 |  | Pitted | 0% | 0 | Is the interface accurate and does it meet the customer's production needs? |  | Connected but not validated | FALSE | FALSE
| Interfaces - Exports From Deposco | 0 |  |  |  | 0
Interfaces - Exports From Deposco | Shipment Confirmation from Deposco to Email* | 0 |  | DEP/Pitted |  | 0 | Is the interface accurate and does it meet the customer's production needs? |  |  | FALSE | FALSE
| Reports and Labeling | 30 |  |  |  | 30
Reports and Labeling | Shipping Labels | 10 |  | Pitted | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Packing Slips | 10 |  | Pitted | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Item Label | 10 |  | Pitted | 100% | 10 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
Reports and Labeling | Carton Type Label | 0 | Y | Pitted | 0% | 0 | Does the report print from the application accurately and timely? |  |  | FALSE | FALSE
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | DEP/Pitted | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback? |  | Can't really roll back to extensiv | FALSE | FALSE
| Total Weighted Score: | 911
| Total Possible Score: | 1220
| Total Percentage: | 74.67%
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Go Live Success Criteria
Pitted Project Tracker - Success Criteria
Orientation - Success Criteria/Goals
Goal | Solution
Automate orders | No paper or manual processes and flexible enough to accomodate all customer, brand or product requirements
Streamline cycle counting, replenishment, returns, serial tracking, & rate shopping processes | All will be automated and done within Deposco
Provide customers with exceptional experience and provide enterprise-level system support model | Need to train customers on Deposco and create SOP's so they can be independent
Onboard new customers in an expedited fashion | Integrations and API access for customers, eHub success and saying yes to new customers to open marketing floodgates
Ensure time it takes to bill/invoice back customers is efficient and avoid leaving revenue uncaptured or on the table | Automatically pushing invoices to QBO as well as mapping mail innovations prices to shipments
Provide reporting/visibility/dashboards for Pitted Team and Pitted customers in form of a Portal | Customer portal is created and team can create reports to filter per tenant as needed

## Cutover Plan
Logistics Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | Verified | TEAM | Owner | DUE DATE
1 | Create Production Environment | Create ticket to stand up prod environment | TRUE | TRUE | DEP | Josiah | 2025-03-01
2 | Set up remaining printers in Deposco | Set up and get test print in Deposco for remaining printers | TRUE | TRUE | Pitted | Josiah | 2025-03-01
3 | Set up printer assignements | Set up printer assignments for new printers | TRUE | TRUE | DEP | Josiah | 2025-03-01
4 | Set up UPS Account | Set up and verify UPS account in Production environment | TRUE | TRUE | Pitted | Josiah | 2025-03-10
5 | Set up STAMPS Account | Set up and verify STAMPS account in Production environment | TRUE | TRUE | Pitted | Josiah | 2025-03-10
6 | Set up eHub Account | Set up and verify ePost Account in Production environment | TRUE | TRUE | Pitted | Josiah | 2025-03-10
7 | Set up Shopify | Set up and verify Ecomm Shopify in Production environment | TRUE | TRUE | Pitted | Josiah | 2025-03-10
8 | Set up Walmart Integration | Set up and verify Walmart Integration in Production environment | TRUE | TRUE | Pitted | Josiah | 2025-03-10
9 | Set up Quickbooks Online | Set up and verify Quickbooks Online in Production environment | TRUE | TRUE | Pitted | Josiah | 2025-03-10
10 | Adjust QBO URL to production | Adjust QBO URL to production | TRUE | TRUE | DEP | Josiah | 2025-03-10
11 | Adjust event stream subscribers to their new IP names | shipNotice, receiptNotice, coTransRoutingQueued, purchaseOrderCreated, purchaseOrderUpdated | TRUE | TRUE | DEP | Josiah | 2025-03-10
12 | Review Shipping translations | Review rate shop and service translations in automations | TRUE | TRUE | Pitted | Josiah | 2025-03-10
13 | Master Data Check - Item UPC | Look through item UPCs in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
14 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions, weight | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
15 | Master Data Check - Locations | Look through Locations in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
16 | Master Data Check - Zones | Look through Zones in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
17 | Master Data Check - Storage Records | Upload and validate through Storage Records in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
18 | Master Data Check - Components | Look through components in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
19 | Master Data Check - Trading Partners | Look through trading partner in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
20 | Master Data Check - Carton Types | Look through carton types in production environment | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-14
21 | Upload POs to production | Upload any outstanding POs in Deposco/Validate PO upload | FALSE | FALSE | Pitted | Josiah | 2025-03-14
22 | Upload Workorders to production | Upload any outstanding Workorders in Deposco/Validate WO upload | TRUE | TRUE | Pitted | Josiah | 2025-03-14
23 | Review Scheduler Frequencies | Go through each scheduler and integration and confirm cron is as expected | TRUE | TRUE | Pitted | Josiah | 2025-03-14
24 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | TRUE | TRUE | Pitted | Josiah | 2025-03-17
25 | Turn on Order Pull in Deposco | Turn on scheduler for all Instances to bring in orders | TRUE | FALSE | DEP | Josiah | 2025-03-17
26 | Test Order Pull | Pull sample of orders from each marketplace into Deposco | TRUE | FALSE | DEP/Pitted | Josiah | 2025-03-17
27 | Finalize Shipping through old system | Finish up as much of the weekend back log | TRUE | FALSE | Pitted | Josiah | 2025-03-17
28 | Validate Inventory | First pass at inventory number, calculate pack quantities | TRUE | FALSE | DEP/Pitted | Josiah | 2025-03-17
29 | Upload Inventory to Deposco | Inventory is pushed to Deposco | TRUE | FALSE | Pitted | Josiah | 2025-03-17
30 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE | FALSE | DEP | Josiah | 2025-03-17
31 | Test Inventory Push | Send an inventory push from Deposco to each marketplace to sync systems | FALSE | FALSE | DEP/Pitted | Josiah | 2025-03-17
32 | Cycle Counts | Perform periodic cycle counting in pick face and back stock locations | TRUE | TRUE | Pitted | Josiah | 2025-03-17
33 | Turn on Ship Notice Push | Turn on Ship Notice Push | TRUE | TRUE | DEP | Josiah | 2025-03-17
34 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
35 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
36 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
37 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
38 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
39 | Smoke Test - Wholesale Picking |  |  | FALSE | DEP/Pitted | Josiah | 2025-03-17
40 | Smoke Test - International Picking |  |  | FALSE | DEP/Pitted | Josiah | 2025-03-17
41 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
42 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
43 | Smoke Test - Wholesale Packing | Pack an international order, order is shipped outside system | FALSE | FALSE | DEP/Pitted | Josiah | 2025-03-17
44 | Smoke Test - International Packing | Pack an international order, order is shipped outside system |  | FALSE | DEP/Pitted | Josiah | 2025-03-17
45 | Test ShipNotice Push | Fulfll an order from each marketplace to validate ship confirmations | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
46 | Ensure Mail Innovations ship rate cost fields move | Ensure Mail Innovations ship rate cost fields move | TRUE | TRUE | DEP | Josiah | 2025-03-17
47 | Carrier special services enabled | Carrier special services enabled for ups, fedex and stamps |  | FALSE | DEP | Josiah | 2025-03-17
48 | Validate 16 oz v 1 pound mail innovations scenarios | Need to see how to handle these when setting prices | TRUE | TRUE | DEP/Pitted | Josiah | 2025-03-17
49 | Channel Xrefs created for all curent customers for QBO | Needed to be able to map to these companies from Deposco | TRUE | TRUE | DEP | Josiah | 2025-03-17
50 | Channel xref SOP added to new client onboarding document | All new clients must have an xref created for them for invoices to push to QBO |  | FALSE | Pitted | Pat | 2025-03-17
51 | Setup RateShop Profiles per customer | Validate we can rateshop service and setup rateshop profiles | TRUE | TRUE | Pitted | Pat | 2025-03-17
52 | Hazmat storage restrictions | Have hazmat locations been setup and is anything else needed to support this? |  | FALSE | Pitted | Karina | 2025-03-17
53 | Item reorder points set | Set reorder point field on items to have reporting for clients |  | FALSE | Pitted | Karina | 2025-03-17
54 | Upload Resources | Upload/create all printer resources and assign correct printers | TRUE | TRUE | Pitted | Karina | 2025-03-17
55 | Validate all lot/serial/exp date tracked items are flagged | Need to determine capture points as well as which items should be flagged with serial and lot | TRUE | TRUE | Pitted | Karina | 2025-03-17
56 | Add waving logic for batch and singles | Set 54/300 etc for each customer | TRUE | TRUE | Pitted | Karina | 2025-03-17
57 | "Exclude from billing" filter is added to all order based billing queries | "Exclude from billing" filter is added to all order based billing queries | TRUE | TRUE | DEP | Josiah | 2025-03-17
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Custom Fields Needed
Field | DESCRIPTION | Purpose | Report | Severity | Status | Stored? | Current Field | Planned Deposco Field

## UK - Shopify (hidden)
UK - Shopify
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments | Links
Item | Pulls items and creates channel listings in Deposco |  |  |  | DSID: 17430 |  |  | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Item_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____3
Sales Order | Creates customer orders that route through bright order and then create a sales/fulfillment order |  |  |  | DSID: 17431 |  | Think of the customer order as intangible and the sales order is what you will actually pick/pack/ship | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Order_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____5
Ship Notice | Pushes tracking info to shopify |  |  |  | DSID: 17434 |  |  | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Ship_notice_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____6
Inbound Inventory Sync | Deposco pulls inventory FROM shopify |  |  |  | Not needed |  | We will use this one for the UK facility | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Incoming_inventory_sync_from_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____9
Outbound Inventory Sync | Deposco sends inventory TO shopify |  |  |  | DSID: 17440 |  | Tihs will not be used for the UK facility since we will not physically have the stock
Customer Return | This is not in scope |  |  |  | Not needed |  | This is not in scope
Customer | This is not in scope |  |  |  | Not needed |  | This is not in scope | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Customer_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____4

## Ecomm - Shopify (hidden)
Ecomm - Shopify
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments | Links
Item | Pulls items and creates channel listings in Deposco |  |  |  |  | DSID: 17447 |  | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Item_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____3
Sales Order | Creates customer orders that route through bright order and then create a sales/fulfillment order |  |  |  |  | DSID: 17449 | Think of the customer order as intangible and the sales order is what you will actually pick/pack/ship | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Order_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____5
Ship Notice | Pushes tracking info to shopify |  |  |  |  | DSID: 17456 |  | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Ship_notice_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____6
Inbound Inventory Sync | Deposco pulls inventory FROM shopify |  |  |  |  | Not needed | This will not be used since we will have the systematic and physical stock
Outbound Inventory Sync | Deposco sends inventory TO shopify |  |  |  |  | DSID: 17460 | This will be used to push our inventory/stock to shopify | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Outgoing_inventory_sync_to_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____8
Customer Return | This is not in scope |  |  |  |  | Not needed | This is not in scope
Customer | This is not in scope |  |  |  |  | Not needed | This is not in scope | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Customer_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____4

## Wholesale - Shopify (hidden)
Wholesale - Shopify
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments | Links
Item | Pulls items and creates channel listings in Deposco |  |  |  |  | DSID: 17441 |  | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Item_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____3
Sales Order | Creates customer orders that route through bright order and then create a sales/fulfillment order |  |  |  |  | DSID: 17442 | Think of the customer order as intangible and the sales order is what you will actually pick/pack/ship | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Order_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____5
Ship Notice | Pushes tracking info to shopify |  |  |  |  | DSID: 17444 |  | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Ship_notice_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____6
Inbound Inventory Sync | Deposco pulls inventory FROM shopify |  |  |  |  | Not needed | This will not be used since we will have the systematic and physical stock
Outbound Inventory Sync | Deposco sends inventory TO shopify |  |  |  |  | DSID: 17446 | This will be used to push our inventory/stock to shopify | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Outgoing_inventory_sync_to_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____8
Customer Return | This is not in scope |  |  |  |  | Not needed | This is not in scope | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Customer_return_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____7
Customer | This is not in scope |  |  |  |  | Not needed | This is not in scope | https://docs.deposco.com/docs/html/Content/Integrations/Web_stores/Shopify/Customer_integration_with_Shopify.htm?tocpath=Integrations%7CWeb%20store%20integrations%7CShopify%7C_____4

## Quickbooks (hidden)
Quickbooks Online
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments
Import Purchase Order | Not needed
Import Item | Needed | [5 empty] | DSID: 17669
Import Sales Order | Not needed
Import Customer | needed | [5 empty] | DSID: 17670 - channel xref is overriding when we pull from wholesale and ecomm. Need this to make two separate xrefs
Import Vendor | needed | [5 empty] | DSID: 17671
Ship Notice | needed | [5 empty] | DSID: 17820
Export Purchase Order | needed | [5 empty] | DSID: 17812 - have to manually run poi to actually push it over. Triggers updates first when it is created | added purchaseOrderCreate event | Users need to manually run poi currently to trigger this
Export Purchase Order updates | needed | [5 empty] | DSID: 17859 - This is triggering when the order is created | added purchaseOrderUpdate event | Must send updates through DE to trigger updateEvent
Inventory Sync | Needed | [5 empty] | DSID: 17806
Export Bill (Receipt Notice) | Needed | [5 empty] | DSID: 17905
Ship notice testing with rules
Invoice | DSID: 19698
Sales Receipt | DSID: 19691
Kibana Logs: | https://logs.deposco.com/_dashboards/goto/92ba47b4111690271209e7a1f826cb5f

## Amazon Vendor Central (hidden)
Amazon Vendor Central
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments
Advanced Shipment Notice (856) | Push back shipment info
Full Inventory Sync (856) | This is not in scope
Stage EDI | Needed
Process EDI | Needed
Purchase Order Acknowledgement | Not needed | [5 empty] | Maybe need this, ask Mike
Ship Notice | This is not in scope
Routing Request | This is not in scope

## Amazon Seller Central (hidden)
Amazon Seller Central
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments
Items | Pull in items and channel listings |  |  |  | DSID: 17570
Customer Order | Pull in sales orders and create customer orders |  |  |  | DSID: 17572
ShipNotice | Push back shipment info on a scheduled basis |  |  |  | DSID: 17590 | failed due to fedex2 but did push to amz
Inventory Sync | Sync inventory from deposco to amazon |  |  |  | DSID: 17573
Order acknowledgement | This is not in scope |  |  |  | Ask Mike

## Walmart (hidden)
Walmart
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments
Item | Pull in items and channel listings | [5 empty] | DSID: 17561
Customer order | Pull in sales orders and create customer orders | [5 empty] | DSID: 17565
Ship notice | Push back shipment info on a scheduled basis | [5 empty] | DSID: 17595
Inventory sync | Sync inventory from deposco to Walmart | [5 empty] | DSID: 17569 | Did not push because of test site, but doc store did generate
Customer returns | This is not in scope

## Orderful (hidden)
Orderful
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments
Customer Order (850 PO) | Pull in customer orders to fulfill |  |  |  |  | dsid: 15920
Ship Notice (856 ASN) | not needed
Export Inventory Sync (846) | not needed
Export customer order acknowledgement | This is not in scope | [5 empty] | Not needed, let orderful do this
Inbound ASN | This is not in scope
Inbound Transfer Order | This is not in scope
Export Invoice | This is not in scope
Export Inventory Sync | This is not in scope
Inventory Advice | This is not in scope

## Shipping Integrations (hidden)
Shipping
Touchpoint | DESCRIPTION | Custom Mapping Needed? | Deposco Field | Quickbooks Field | Pitted Testing Data | Pitted Comments | DEP Comments
UPS | DSID: 17433
Fedex | DSID: 17455
Stamps | DSID: 17458
Royal Mail
Epost
DHL Express

## Future ItemsParking Lot
Pitted Logistics Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | Pitted Comments
Amazon FBA
Etsy
Fedex
Defined cycle count profiles

## Billing Estimations
Billing Config | Unique Query? | Estimation In Hours
Per Order Fee | Query 1 | 2
Description: Order Fee per Order Shipped
Logic: Deposco will count the number of orders fully shipped to calculate the fee.
This will be included on the monthly invoice
Billing Config Type: Per Order
Per Each Item | Query 2 | 2
Description: Total units shipped per order
Logic: Deposco will charge a fee using the set price multiplied by the total units shipped for an order with a pack type of ‘Each’.
This will be included on the monthly invoice
Billing Config Type: Per Each Item
Assumptions
Cases and Pallets shipped are excluded from this charge
Pitted Logistics team will rename the associated billing item to “Per Each Item” in QBO
Per Pallet | Query 3 | 3
Description: Billing per pallet received/built
Logic: Deposco will charge a fee using set price x pallet received on receiptline
This will be included on the monthly invoice
Billing Config Type: Per Pallet
Assumptions
Pitted Logistics team will rename the associated billing item to “Per Pallet” in QBO
Per Carton | Query 4 | 2
Description: Billing per carton received that is NOT received to a pallet
Logic: Deposco will charge a fee using set price x number of cartons received not on a pallet.
This will be included on the monthly invoice
Billing Config Type: Per Carton
Assumptions
Pack type of carton is created in Deposco
Pitted Logistics team will rename the associated billing item to “Per Carton” in QBO
Returned Order Per Shipment | Query 5 | 2
Description: Billing per customer return received
Logic: Deposco will charge a fee using set price x number of customer returns received
This will be included on the monthly invoice
Billing Config Type: Returned Order Per Shipment
Assumptions
Pitted Logistics team will rename the associated billing item to “Returned Order Per Shipment” in QBO
Returned Order Per Item | Query 5 | 2
Description: Billing per unit received on a customer return
Logic: Deposco will charge a fee using set price x number units received on a return
This will be included on the monthly invoice
Billing Config Type: Returned Order Per Item
Assumptions
Pitted Logistics team will rename the associated billing item to “Returned Order Per Item” in QBO
Pallet Out | Query 6 | 3
Description: Bill per pallet shipped
Logic: Deposco will charge a fee using the set price multiplied by the total units shipped for an order with a pack type of ‘Pallet’.
This will be included on the monthly invoice
Billing Config Type: Pallet Out
Assumptions
Pack type of “Pallet” is created
Pitted Logistics team will rename the associated billing item to “Pallet Out” in QBO
Pallet Storage | Query 7 | 6
Description: Billing for stock in a pallet location
Logic: Deposco will charge a fee using set price x number of locations where custom attribute 1 = “Pallet”
This will be included on the monthly invoice
Billing Config Type: Per Pallet
Assumptions
Pitted Logistics team will rename the associated billing item to “Pallet Storage” in QBO
This will run daily and be divided by days of month
Missing PO Storage Fee | Query 8 | 2
Description: Billing for stock in the “Missing Purchase Order” receiving location
Logic: Deposco will charge a fee using set price x 1 for every client that has stock units in this location
This will be included on the monthly invoice
Billing Config Type: Missing PO Storage Fee
Assumptions
Pitted Logistics team will rename the associated billing item to “Missing PO Storage Fee” in QBO
Monthly XL Bin Storage | Query 7 | 0.25
Description: Billing for stock in an XL Bin location
Logic: Deposco will charge a fee using set price x number of locations where custom attribute 1 = “XL Bin”
This will be included on the monthly invoice
Billing Config Type: XL Bin Storage
Assumptions
Pitted Logistics team will rename the associated billing item to “XL Bin Storage” in QBO
This will run daily and be divided by days of month
Monthly Large Bin Storage | Query 7 | 0.25
Description: Billing for stock in a Large Bin location
Logic: Deposco will charge a fee using set price x number of locations where custom attribute 1 = “Large Bin”
This will be included on the monthly invoice
Billing Config Type: Large Bin Storage
Assumptions
Pitted Logistics team will rename the associated billing item to “Large Bin Storage” in QBO
This will run daily and be divided by days of month
Monthly Medium Bin Storage | Query 7 | 0.25
Description: Billing for stock in a Medium Bin location
Logic: Deposco will charge a fee using set price x number of locations where custom attribute 1 = “Medium Bin”
This will be included on the monthly invoice
Billing Config Type: Medium Bin Storage
Assumptions
Pitted Logistics team will rename the associated billing item to “Medium Bin Storage” in QBO
This will run daily and be divided by days of month
Monthly Small Bin Storage | Query 7 | 0.25
Description: Billing for stock in a Small Bin location
Logic: Deposco will charge a fee using set price x number of locations where custom attribute 1 = “Small Bin”
This will be included on the monthly invoice
Billing Config Type: Small Bin Storage
Assumptions
Pitted Logistics team will rename the associated billing item to “Small Bin Storage” in QBO
This will run daily and be divided by days of month
Per Completed Assembly | Query 9 | 3
Description: Billing per workorder completed
Logic: Deposco will charge a fee using set price x number of workorders completed
This will be included on the monthly invoice
Billing Config Type: Per Completed Assembly
Assumptions
Pitted Logistics team will rename the associated billing item to “Per Completed Assembly” in QBO
Per Completed Assembly Component | Query 10 | 4
Description: Billing per workorder completed
Logic: Deposco will charge a fee using set price x input quantities required x quantity to build
This will be included on the monthly invoice
Billing Config Type: Per Completed Assembly Component
Assumptions
Pitted Logistics team will rename the associated billing item to “Per Completed Assembly Component” in QBO
Per Insert | Query 11 | 2
Description: Billing per insert in order
Logic: Deposco will charge a fee using set price x orders with a note of “Insert” in the body
This will be included on the monthly invoice
Billing Config Type: Per Insert
Assumptions
Pitted Logistics team will rename the associated billing item to “Per Insert” in QBO
Assembly 5 count sticks | Query 9 | 2
Description: Billing per completed workorders with kitheader = Assembly 5 count sticks
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 5 count sticks
This will be included on the monthly invoice
Billing Config Type: Assembly 5 count sticks
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 5 count sticks” in QBO
Kitheader name will be “Assembly 5 count sticks”
Assembly 10 count sticks | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 10 count sticks
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 10 count sticks
This will be included on the monthly invoice
Billing Config Type: Assembly 10 count sticks
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 10 count sticks” in QBO
Kitheader name will be “Assembly 10 count sticks”
Assembly 20 count sticks | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 20 count sticks
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 20 count sticks
This will be included on the monthly invoice
Billing Config Type: Assembly 20 count sticks
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 20 count sticks” in QBO
Kitheader name will be “Assembly 20 count sticks”
Assembly 30 count sticks | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 30 count sticks
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 30 count sticks
This will be included on the monthly invoice
Billing Config Type: Assembly 30 count sticks
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 30 count sticks” in QBO
Kitheader name will be “Assembly 30 count sticks”
Assembly 4 Pack Cans - Single Flavor | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 4 Pack Cans - Single Flavor
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 4 Pack Cans - Single Flavor
This will be included on the monthly invoice
Billing Config Type: Assembly 4 Pack Cans - Single Flavor
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 4 Pack Cans - Single Flavor” in QBO
Kitheader name will be “Assembly 4 Pack Cans - Single Flavor”
Assembly 4 Pack Cans - Variety Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 4 Pack Cans - Variety Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 4 Pack Cans - Variety Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 4 Pack Cans - Variety Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 4 Pack Cans - Variety Pack” in QBO
Kitheader name will be “Assembly 4 Pack Cans - Variety Pack”
Sticker Charge | Query 11 | 0.25
Description: Billing per sticker charge
Logic: Deposco will charge a fee using set price x orders with a note of “Sticker” in the body
This will be included on the monthly invoice
Billing Config Type: Sticker Charge
Assumptions
Pitted Logistics team will rename the associated billing item to “Sticker Charge” in QBO
Attached Label Fee | Query 11 | 0.25
Description: Billing per attached label
Logic: Deposco will charge a fee using set price x orders with a note of “Attached Label” in the body
This will be included on the monthly invoice
Billing Config Type: Sticker Charge
Assumptions
Pitted Logistics team will rename the associated billing item to “Sticker Charge” in QBO
Carton Out | Query 6 | 0.5
Description: Bill per carton shipped
Logic: Deposco will charge a fee using the set price multiplied by the total units shipped for an order with a pack type of ‘Carton’.
This will be included on the monthly invoice
Billing Config Type: Carton Out
Assumptions
Pack type of “Carton” is created
Pitted Logistics team will rename the associated billing item to “Carton Out” in QBO
Assembly 3 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 3 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 3 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 3 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 3 Pack” in QBO
Kitheader name will be “Assembly 3 Pack”
Assembly 6 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 6 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 6 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 6 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 6 Pack” in QBO
Kitheader name will be “Assembly 6 Pack”
Assembly 4 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 4 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 4 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 4 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 4 Pack” in QBO
Kitheader name will be “Assembly 4 Pack”
Assembly 8 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 8 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 8 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 8 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 8 Pack” in QBO
Kitheader name will be “Assembly 8 Pack”
Assembly 10 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 10 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 10 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 10 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 10 Pack” in QBO
Kitheader name will be “Assembly 10 Pack”
Assembly 12 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 12 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 12 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 12 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 12 Pack” in QBO
Kitheader name will be “Assembly 12 Pack”
Assembly 16 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 16 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 16 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 16 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 16 Pack” in QBO
Kitheader name will be “Assembly 16 Pack”
Assembly 24 Pack | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 24 Pack
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 24 Pack
This will be included on the monthly invoice
Billing Config Type: Assembly 24 Pack
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 24 Pack” in QBO
Kitheader name will be “Assembly 24 Pack”
Assembly 2 Month Kit Amazon (Quantity 500+) | Query 12 | 3
Description: Billing per completed workorders with kitheader = Assembly 2 Month Kit Amazon (Quantity 500+)
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 2 Month Kit Amazon (Quantity 500+) and workorder build quantity >= 500
This will be included on the monthly invoice
Billing Config Type: Assembly 2 Month Kit Amazon (Quantity 500+)
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 2 Month Kit Amazon (Quantity 500+)” in QBO
Kitheader name will be “Assembly 2 Month Kit Amazon (Quantity 500+)”
Assembly 2 Month Kit Amazon (Quantity < 500) | Query 12 | 0.5
Description: Billing per completed workorders with kitheader = Assembly 2 Month Kit Amazon (Quantity < 500)
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly 2 Month Kit Amazon (Quantity < 500) and workorder build quantity < 500
This will be included on the monthly invoice
Billing Config Type: Assembly 2 Month Kit Amazon (Quantity < 500)
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly 2 Month Kit Amazon (Quantity < 500)” in QBO
Kitheader name will be “Assembly 2 Month Kit Amazon (Quantity < 500)”
Assembly Threading Rings | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly Threading Rings
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly Threading Rings
This will be included on the monthly invoice
Billing Config Type: Assembly Threading Rings
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly Threading Rings” in QBO
Kitheader name will be “Assembly Threading Rings”
Assembly Screw Bags | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly Screw Bags
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly Screw Bags
This will be included on the monthly invoice
Billing Config Type: Assembly Screw Bags
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly Screw Bags” in QBO
Kitheader name will be “Assembly Screw Bags”
Assembly Shade + Screw Bag + Mount | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly Shade + Screw Bag + Mount
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly Shade + Screw Bag + Mount
This will be included on the monthly invoice
Billing Config Type: Assembly Shade + Screw Bag + Mount
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly Shade + Screw Bag + Mount” in QBO
Kitheader name will be “Assembly Shade + Screw Bag + Mount”
Assembly Bagging Shades | Query 9 | 0.5
Description: Billing per completed workorders with kitheader = Assembly Bagging Shades
Logic: Deposco will charge a fee using set price x completed workorders with kitheader = Assembly Bagging Shades
This will be included on the monthly invoice
Billing Config Type: Assembly Bagging Shades
Assumptions
Pitted Logistics team will rename the associated billing item to “Assembly Bagging Shades” in QBO
Kitheader name will be “Assembly Bagging Shades”
AdHoc Billing Billing Configs
AdHoc Billing Charges
Pitted Logistics team will manage the creation and deduction of ad hoc charges in Deposco except for Customer Credit. Each ad hoc charge will have an individual billing item in QBO for the integration purpose.
Per 20 ft Floor Loaded Container
Pitted Logistics will generate a charge per 20 ft floor loaded container received
Billing Config Type: Per 20 ft Floor Loaded Container
Assumptions
Pitted Logistics team will rename the associated billing item to “Per 20 ft Floor Loaded Container” in QBO
Mixed Cartons
Pitted Logistics will generate a charge per mixed cartons received
Billing Config Type: Per Mixed Carton
Assumptions
Pitted Logistics team will rename the associated billing item to “Per Mixed Carton” in QBO
UPC Labeling - Receiving
Pitted Logistics will generate a charge per missing or damaged upc labels on received product(s)
Billing Config Type: UPC Labeling - Receiving
Assumptions
Pitted Logistics team will rename the associated billing item to “UPC Labeling - Receiving” in QBO
Non-compliant pallets
Pitted Logistics will generate a charge per broken, non-standard GMA, or outside of weight/dim requirements
Billing Config Type: Non-compliant pallets
Assumptions
Pitted Logistics team will rename the associated billing item to “Non-compliant pallets” in QBO
UPC Labeling - Assembly
Pitted Logistics will generate a charge per upc label applied on finished assemblies
Billing Config Type: UPC Labeling Assembly
Assumptions
Pitted Logistics team will rename the associated billing item to “UPC Labeling Assembly” in QBO
UPC Labeling
Pitted Logistics will generate a charge per upc label applied on non assemblies
Billing Config Type: UPC Labeling
Assumptions
Pitted Logistics team will rename the associated billing item to “UPC Labeling” in QBO
Phone Enrollment
Pitted Logistics will generate a charge per phone enrollment
Billing Config Type: Phone Enrollment
Assumptions
Pitted Logistics team will rename the associated billing item to “Phone Enrollment” in QBO
Software or Firmware Update
Pitted Logistics will generate a charge per software/firmware update
Billing Config Type: Software or Firmware Update
Assumptions
Pitted Logistics team will rename the associated billing item to “Software or Firmware Update” in QBO
Failed Phone Enrollment
Pitted Logistics will generate a charge per failed phone enrollment
Billing Config Type: Failed Phone Enrollment
Assumptions
Pitted Logistics team will rename the associated billing item to “Failed Phone Enrollment” in QBO
Failed Software or Firmware Update
Pitted Logistics will generate a charge per failed software or firmware update
Billing Config Type: Failed Software or Firmware Update
Assumptions
Pitted Logistics team will rename the associated billing item to “Failed Software or Firmware Update” in QBO
Re-label
Pitted Logistics will generate a charge for re-labeling product
Billing Config Type: Relabel
Assumptions
Pitted Logistics team will rename the associated billing item to “Relabel” in QBO
Labeling
Pitted Logistics will generate a charge for labeling product
Billing Config Type: Labeling
Assumptions
Pitted Logistics team will rename the associated billing item to “Labeling” in QBO
Tag Removal
Pitted Logistics will generate a charge for tag removal
Billing Config Type: Tag Removal
Assumptions
Pitted Logistics team will rename the associated billing item to “Tag Removal” in QBO
FNSKU Labeling
Pitted Logistics will generate a charge for FNSKU labeling
Billing Config Type: FNSKU Labeling
Assumptions
Pitted Logistics team will rename the associated billing item to “FNSKU Labeling” in QBO
FBA Orders will be manually imported to Deposco with an order source of “FBA”
Special Projects: Man Hours
Pitted Logistics will generate a charge for man hours
Billing Config Type: Special Projects: Man Hours
Assumptions
Pitted Logistics team will rename the associated billing item to “Special Projects: Man Hours” in QBO