## Schedule
REACT Project Tracker - Key Dates, Documents, and Milestones
Orientation - Success Criteria/Goals
Goal |  | Metric | Status
Improve inventory accuracy and visibility specific to serial tracking across systems |  |  | Open
Meet FDA Requirements 100% of the time |  |  | Open
Design and build a scalable solution that allows React to launch Columbus without additional config/design conversations needed |  |  | Open
Meet internal order cycle SLAs: Parcel = 24 hours, Freight = 72 hours |  |  | Open
Orientation - Baseline Education Demo Sessions
Topic | Description | Delivery Date
Deposco User Exerience | Review Application Menu and General Navigation, Layouts and View, and User, Groups, and Permissions | 2025-02-20
Master Data / Data Exchange | Review key master data requirements and Data Exchange for master data imports | 2025-02-20
Design - Documentation
Document | Description | Delivery Date | Completion Date
Onsite Design Agenda | LINK | 2025-02-12 | 2025-02-12
Master Design Document | LINK | 2025-03-14
Configuration and Validation - Delivery and Unit Testing Schedule
Topic | Description | Config Delivery Date | Unit Testing % Complete | Unit Testing Due Date
Integrations | Netsuite and Shipping Carriers - data requirements, troubleshooting steps etc. | 2025-05-30 | 0% | 2025-06-09
Order Orchestration | Sourcing, Routing, Exception and Backorder Management | 2025-05-09 | 0% | 2025-05-16
Inbound | General Receiving(PO, Blind Receipt, Customer Return, ITO), Move Item, Move Stock, Move Container | 2025-05-23 | 78.26% | 2025-05-30
Inventory Management | Cycle Counts, Adjust Inventory, Replenishments, Product Conversion | 2025-05-02 | 20% | 2025-05-09
Outbound 1 | Outbound Order Management, Waving, Picking | 2025-05-09 | 66.67% | 2025-05-16
Outbound 2 | Packing Shipping | 2025-05-16 | #DIV/0! | 2025-05-30
Reporting | Report Builder, Dashboard Widgets | 2025-05-30 | #DIV/0! | 2025-06-09
Validation - User Acceptance Training / End to End Testing
Task/Activity | Description | Completion % | Start Date | End Date
End to End Testing | Testing all process flows with live data end to end | 42.5% | 2025-06-16 | 2025-06-20
UAT Onsite | https://docs.google.com/document/d/1y-C0k5Bnwa-0iYv8dxaTs-nS03Zqd2235P1PDUAkAro/edit?tab=t.0 | 100% | 2025-06-23 | 2025-06-27
SOP Documentation | SOP Creation Tool Recommendation: https://www.tango.ai/ Google Drive Folder for completed SOPs: LINK | 0% | Ongoing | 2025-06-23
Go/No-Go Decision | Complete evaluation of Go/No-Go Decision Plan - End of UAT | 0% | Ongoing | 2025-06-13
Deploy - Go Live
Task/Activity | Description | Completion % | Start Date | End Date
Cutover Steps | Cutover Plan delivered with steps to complete. Ownership and due dates assigned. | 0%
Deposco Onsite Support | Travel booked for cutover and go-live week. | 0% | 2025-07-07 | 2025-07-11
Project Closeout | Agreement of final deliverables provided. | 0% | TBD - Pending OH Facility

## RHWDV Task Tracker
REACT Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | DEP Comments | REACT Comments
Orientation | Setup UPS Parcel Carrier Accounts | UPS: Client utilizes Deposco UPS Registration Wizard to setup UPS account DEP team to send documentation | Task | 2.High | TRUE | TRUE | Completed | DEP/REACT | Lanie
Orientation | Setup FedEx Parcel Carrier Accounts | FedEx: Clients configures FedEx account and Meter # within Deposco CompanyConfig UI screen DEP team to send documentation | Task | 2.High | TRUE | TRUE | Completed | DEP/REACT | Lanie
Orientation | Setup NetSuite Socket | Client utilizes Deposco help site guides to setup existing socket connections DEP team to send documentation | Task | 2.High | TRUE | TRUE | Completed | DEP/REACT | Rhea
Orientation | Data Exchange Demo and Overview | Deposco to provide a loom demo on Data Exchange application | Task | 2.High | TRUE | TRUE | Completed | DEP | Lanie
Orientation | Hardware Overview | REACT to check current hardware against Deposco requirements/order any necessary hardware | Task | 2.High | TRUE | TRUE | Completed | DEP/REACT | Mitch
Orientation | Schdule On Site Design | REACT and Dep to confirm dates for on site design session with team | Task | 2.High | FALSE | FALSE | Completed | DEP/REACT | Full Team
Orientation | Setup Deposco Distro List | Deposco sets up email group in following format: <tenant code> + @deposco.com | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Setup Client Mavenlink Account | Setup SX with tenant code and General / Project Management tasks | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Setup Tenant Support Slack Group | Setup Slack group with tenant as <tenant code> + "- Support" (e.g. DEP - Support) | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Setup Confluence and JIRA Project | Setup client confluence and JIRA Project | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Client UA Env. | Deposco to setup client UA environment with client code chosen by client during signning. Socket team adds socket connections and total # of connections to UA env. | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Company & Facility | Deposco to coordinate with client to update: - Company.code value (likely same as tenant code) - Company address info - Facility.number (needed for print server setup since it uses the facility.number) - Facility address info (needed for shipping since ship from info is pulled from user.facitliy for parcel carriers) | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Setup Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network - DONE 2) Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team DEP team to send documentation | Task | 3.Medium | TRUE | TRUE | Completed | REACT | Derek |  |  |  | Derek to work with Richard
Orientation | General Application and UI Overview | Deposco to schedule a demo on Help Site, UI Navigation (Menus/Views/Layouts/Searching), Settings and User Management, Handheld Menu Access | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Rhea
Orientation | Schedule recurring project calls | Weekly status call Bi-weekly executive steering call | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Hannah
Design | Deliver Onsite Design Agenda | Deliver onsite design agenda | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Mitch
Orientation | Location - Master Data Gathering | Collect location master data following the DE template for which information is needed | Task | 4.Low | FALSE | FALSE | Completed | REACT | Derek
Orientation | Create Specialized Process Flows | Client creates process flows for unique processes expected to address systemically within Deposco. Examples are work order handling, cartonization, inbound/outbound audit, quality assurance, and/or new processes outlined as "add-ons" within initial project SOW | Task | 5.NTH | FALSE | FALSE | Closed | REACT | REACT Team
Orientation | Create Inbound Process Flows | Client creates process flows for inbound handling of product (unloading, receiving, putaway) | Task | 5.NTH | FALSE | FALSE | Closed | REACT | REACT Team
Orientation | Create Order Management Process Flows | Client creates process flows for order management inclusive of order pre-processing, order validations, order orchestration, and DOM logic | Task | 5.NTH | FALSE | FALSE | Closed | REACT | REACT Team
Orientation | Create Outbound Process Flows | Client creates process flows for outbound handling of product (replenishments, picking, packing, staging, loading) | Task | 5.NTH | FALSE | FALSE | Closed | REACT | REACT Team
Design | Master Design Document Delivery | Deliver master design document for client team to review | Task | 2.High | FALSE | FALSE | Completed | DEP | Mitch
Design | Review and Sign Master Design Document | Client to review document and make notes in google doc to be reviewed together with Deposco team and eventually signed via Docusign. | Task | 1.Blocker | FALSE | FALSE | Completed | DEP/REACT | Full Team
Design | Open Design Decisions to Make - React | 1. Will Deposco need to provide EDI orders with more information? (meeting on Monday) 2. Can Bin Tracking be turned off/are inventory statuses necessary? 3. Will orders with express services get a higher priority or will Deposco need to prioritize certain services? 4. What field will the customer's account number be stored in for the order? 5. What field will the priority be stored in for the order? 6. Volume and weight where batch orders will go from small to large? | Task | 2.High | FALSE | FALSE | Completed | REACT | Full Team
Design | Open Design Decision to Make - Deposco | 1. Serial Receiving by LPN flow design | Task | 2.High | FALSE | FALSE | Resolved | DEP | Full Team
Configuration | Deliver Inbound Configuration | Via demo sessions or loom videos | Task | 3.Medium | TRUE | TRUE | Completed | DEP | Lanie
Configuration | Deliver Inventory Management Configuration | Via demo sessions or loom videos | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Implementation Lead
Configuration | Deliver Outbound Configuration Pt 1 | Via demo sessions or loom videos | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Implementation Lead
Configuration | Deliver Outbound Configuration Pt 2 | Via demo sessions or loom videos | Task | 3.Medium | TRUE | TRUE | Completed | DEP | Lanie
Configuration | Deliver Integration Configuration Training | Via demo sessions or loom videos | Task | 3.Medium | TRUE | TRUE | Completed | DEP | Lanie
Configuration | Deliver Reports and Metrics | Based on requirements from design | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Lanie |  |  | 6/17 - pending UAT
UAT | Inbound Receipt API | Finalize and test inbound receipt API | Task | 1.Blocker | TRUE | TRUE | Validation | REACT | REACT Team |  | 2025-07-11
Configuration | Data Exchange Setup | Create data exchange templates | Task | 3.Medium | TRUE | TRUE | Completed | DEP | Lanie |  | 2025-05-28
Configuration | Integrations - Inventory Transfer | Confirm that information Deposco provides is satisfactory for NetSuite e.i. Department, etc. | Task | 2.High | TRUE | TRUE | Completed | REACT | Jim |  | 2025-07-07
Configuration | Integrations - Ship Notice | Confirm that information Deposco provides is satisfactory for NetSuite e.i. Department, etc. | Task | 2.High | TRUE | TRUE | Completed | REACT | Jim |  | 2025-07-07
Validation | Printer Testing | All printers get a successful print test from Deposco | Task | 1.Blocker | TRUE | TRUE | In Progress | REACT | REACT Team |  | 2025-07-15
UAT | Set up ZPL Label Printers | Need to add to Network first | Task | 1.Blocker | TRUE | TRUE | Completed | REACT | REACT Team |  | 2025-07-11
UAT | Validate Item Label Printer | Calibrate item label printer to print item and lot labels correctly. | Task | 1.Blocker | FALSE | TRUE | Open | REACT | REACT Team |  | 2025-07-15
UAT | Labeling | Label all current stock with SKU/Serial labels | Task | 1.Blocker | FALSE | TRUE | Open | REACT | REACT Team |  | 2025-07-15
Configuration | Integrations - Item | Resolve all item failures, configure which items to pull in | Task | 2.High | TRUE | TRUE | Resolved | REACT | REACT Team |  | 2025-07-07
Configuration | Integrations - Inventory Adjustment | Need department field in inventory adjustments | Discussion | 2.High | TRUE | TRUE | Resolved | DEP/REACT |  |  | 2025-07-07 | Not a requirement to stamp in current state, Claudia to go to finance to resolve
Configuration | Integrations - Inventory Adjustment | Confirm account is based on item (COGS and COGS ID) | Discussion | 2.High | TRUE | TRUE | Resolved | DEP/REACT
Configuration | Integrations - Inventory Adjustment | Confirm that inventory status is not needed for lot/serial or items that arn't lot/serial tracked | Discussion | 2.High | TRUE | TRUE | Resolved | DEP/REACT
Configuration | Master Data - Packs | Upload all case and pallet packs and their dimension via Data Exchange | Task | 1.Blocker | TRUE | TRUE | In Progress | REACT | REACT Team |  | 2025-07-07
UAT | Create Locations | Need locations for each rack in aisle in "shipping" location | Task | 1.Blocker | TRUE | TRUE | Open | REACT | Mark |  | 2025-07-07
UAT | Labeling | Label all picking Containers | Task | 1.Blocker | FALSE | TRUE | Open | REACT | Mark |  | 2025-07-07
UAT | Inbound User Experience | How to get the user to know inbound shipment vs PO | Discussion | 1.Blocker | FALSE | TRUE | Open | DEP/REACT | Full Team |  | 2025-07-18
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | In Progress | REACT | Mark |  | 2025-07-07
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | In Progress | REACT | Mark |  | 2025-07-07
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | In Progress | REACT | Mark |  | 2025-07-07
UAT | Suggested Putaway for MC | Give all empty locations not on hold F,G,.. | Task | 2.High | FALSE | TRUE | Completed | DEP | Mitch |  | 2025-07-07 | Need to import suggested location rules to override suggested location box
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | In Progress | REACT | Mark |  | 2025-07-07
Validation | Deliver Onsite UAT Agenda | Deposco team to deliver agenda for onsite UAT | Task |  | TRUE | TRUE | Completed | DEP | Lanie |  | 2025-06-18
UAT | Manipulate BOD | Do we have a field that we can use during allocation that is able to be manipulated | Question | 2.High | FALSE | TRUE | Completed | DEP | Mitch |  | 2025-07-07 | Need rules to stamp BOD on item tracking
Validation | Unit Test Cases - Integrations | Complet test cases for Integrations on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | In Progress | REACT | Mark |  | 2025-07-07
Validation | End to End Test Case Execution | Complete end to end test cases | Task | 2.High | TRUE | TRUE | In Progress | REACT | Mark |  | 2025-07-07
UAT | Inbound TOs | Bring in inbound TOs from NS | Task | 2.High | FALSE | TRUE | Completed | DEP | Mitch |  | 2025-07-07
UAT | UN3481 Test | Make sure API includes check box for battery DSID: 4103 - shipped air correctly, ground is erroring in PFC but shipping label request is coming back correct | Task | 2.High | FALSE | TRUE | In Progress | DEP | Lanie |  | 2025-07-07 | Tested using Fedex Ground and Fedex Express (no hazmat indication on Payload to or from Fedex) Order: Hazmat_test Test shipping costs Test Label 7/29 - working, need to verify that label data is correct with REACT, Mitch & Lanie sync week of 8/11
UAT | Migration Timing | Need to pull receipts and push serials to be able to ship right away. | Discussion | 2.High | FALSE | FALSE | Open | DEP | Mitch |  | 2025-07-07
UAT | Correcting the wrong lot in receipt | Scenario where we want to change the lot apon receipt, how would this procedure affect NetSuite | Question | 2.High | FALSE | FALSE | Open | DEP | Mitch |  | 2025-07-07
Design | Design Decisions to be made - DEP |  | Task |  | FALSE | FALSE | Completed
Design | Design Decisions to be made - REACT |  | Task |  | FALSE | FALSE | Completed
UAT | Case/Pallet qtys changing | BMC Lot controlled items change case and pallet quantities | Discussion | 1.Blocker | FALSE | FALSE | Completed | DEP/REACT |  |  |  | SOP to
UAT | Building ASNs in Deposco | Current state there is a process in Syspro | Discussion | 2.High | FALSE | FALSE | Completed | DEP/REACT
Configuration | Master Data - Storage Details | Upload all Storage Details via Data Exchange | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team |  | 2025-07-07
UAT | Moving to SSPick -> Multi Sortation | With current rack situation, moving to picking 5/6 orders together | Discussion | 2.High | FALSE | FALSE | Completed | DEP/REACT |  |  |  | Going to demo for Mark and team
Configuration | Master Data - Each Packs | REACT To let DEP know the dimensions fields in NS (for each packs) | Task | 3.Medium | TRUE | TRUE | In Progress | REACT | Brie |  | 2025-07-07
Configuration | Master Data - Container | Upload all picking containers via Data Exchange | Task | 3.Medium | TRUE | TRUE | Open | REACT | REACT Team |  | 2025-07-07
Configuration | Master Data - Location <> Zones | Upload all location/zone relationship via Data Exchange | Task | 3.Medium | TRUE | TRUE | Open | DEP | Mitch |  | 2025-07-11 | F%A
UAT | PFC | Pack From Container skipping final serial scan if scanning item and then serials | Issue | 3.Medium | FALSE | FALSE | In Progress | DEP | Rebecca |  | 2025-07-07 | 7/29 - edge case scenario that appears like a bug, RT was not able to reproduce but Mitch will advise then create ticket
UAT | Complete Config for Multi Sortation | Approved to continue with setting up multi bin sortation at packing | Task | 2.High | FALSE | FALSE | Completed | DEP
UAT | HI & AK orders | Come through as FedEx Ground, may need to change via automation | Discussion | 3.Medium | FALSE | FALSE | Resolved | REACT | REACT Team |  | 2025-07-07 | Currently setting them to Fedex 2Day, need to confirm that is correct shipVia
UAT | Repenishment Flow | Scenario where we want to replen a location with a full pallet we would want to move the current stock to another location and replenish the stock | Discussion | 2.High | FALSE | FALSE | Completed | DEP
UAT | Putaway Flow in General | Discuss putaway logic based on LPNs needed | Discussion | 2.High | FALSE | FALSE | Completed
Configuration | Master Data - Carton Types | Upload all Carton Types via Data Exchange | Task | 3.Medium | TRUE | TRUE | Open | REACT | REACT Team |  | 2025-07-07
UAT | COHs | COHs coming in from NS without ship from facility | Issue | 2.High | FALSE | FALSE | Completed | DEP
UAT | LPN Label | 4x6 Stock and description as labels, number, lot, LPN as barcodes (rename) | Task |  | FALSE | FALSE | Completed | DEP
UAT | Print LPN button | enter LPN and print 4x6 label | Task |  | FALSE | FALSE | Completed | DEP
UAT | Allocate full pallet quantities | Mitch to test SU.allocated order to be able to choose which stock to pick | Task | 2.High | FALSE | FALSE | Completed | DEP
UAT | Lot Label | Number (BC), Description, Lot (BC), Pack Type, Pack Quantity (need to add) | Task |  | FALSE | FALSE | Completed | DEP
UAT | Map sales description to short description | Want to map short description to sales description in NetSuite, add this description to labels | Task | 3.Medium | FALSE | FALSE | Completed | DEP
UAT | Receive Serials | Bulk receipt of serials for migration from Syspro | Question | 2.High | FALSE | FALSE | Completed | DEP
UAT | COHs Split | Orders in NetSuite are split amoungst multiple locations | Issue | 2.High | FALSE | FALSE | Completed | DEP
UAT | Move lot label | move printing process to invManagement button |  |  | FALSE | FALSE | Completed | DEP
UAT | COHs | COHs coming in with too long PO# (Contract Number) | Task | 2.High | FALSE | FALSE | Completed | DEP |  |  |  | No issue with prod data so far
UAT | Replen | Grab based on BOD | Question | 3.Medium | FALSE | FALSE | Open | DEP | Mitch |  | 2025-07-07
UAT | Packing slip | have different packing slip | Question | 2.High | FALSE | FALSE | Completed |  |  |  |  | Move forward with original packing slip
UAT | Lots | Need to fulfill based expiration date | Task | 2.High | FALSE | FALSE | Completed
UAT | Need future date on label | Once every 2 weeks they need to go into FedEx and change the ship date | Task | 5.NTH | FALSE | FALSE | Completed |  |  |  |  | SOP to not ship until ready for label
UAT | Map priority from NetSuite | REACT to send Dep field in NetSuite | Task | 3.Medium | FALSE | FALSE | Open | REACT | REACT Team |  | 2025-07-07
UAT | Numeric Lots | Would like functionality to have FIFO based on lots vs born on date | Discussion | 3.Medium | FALSE | FALSE | Completed | DEP/REACT |  |  |  | REACT will stage to location and pick from that location for large or LTL orders that would require full pallets
UAT | LPN Nomenclature | Look into a sepecific nomenclature to help track LPNs (facility, date, number, etc) | Discussion | 3.Medium | FALSE | FALSE | Ongoing | DEP/REACT | Mark |  | 2025-07-07 | REACT to Use pregenerated labels
| Kit Touchpoint | Need to test the Cogs Account in Kit Item touchpoint mapping | Task | 2.High | FALSE | FALSE | Completed |  |  |  |  | DSID: 3888
UAT | put locations on hold | Put A-E on hold | Discussion | 3.Medium | FALSE | FALSE | Completed | DEP/REACT | Lanie |  | 2025-07-07
UAT | Location Updates | Add pick sequence to all locations | Task | 3.Medium | TRUE | TRUE | Completed | DEP | Mitch |  | 2025-07-11
UAT | Back Ordered COs | Add reprocess schedulers for COHs | Task | 4.Low | FALSE | FALSE | Completed
UAT | COHs | Getting stuck in allocated | Issue |  | FALSE | FALSE | Completed
UAT | Create SOP for Special Service | DEP and REACT to create a procedure for creating new carrier special service records for new UN3480 and UN3481 items | Discussion | 3.Medium | FALSE | FALSE | Open | DEP/REACT | Full Team |  | 2025-07-07
UAT | Failed Kit Scheduler | DSID: 3931 has bad request items that failed to be created |  |  | FALSE | FALSE | Completed |  |  |  |  | old data
UAT | Staging Full Pallet Order | For JAP orders, may use for other orders but wave orders to a specific slot | Task | 3.Medium | FALSE | TRUE | Completed | DEP | Mitch |  | 2025-07-11
UAT | Location Updates | look into making all locations LPN controlled | Task | 3.Medium | FALSE | FALSE | Completed | DEP
UAT | Mixed Pallets of Lots | Have pallets of mixed lots, Mitch to look into Pallet picking logic | Task | 3.Medium | FALSE | FALSE | Open | DEP | Mitch |  | 2025-07-07
UAT | Fedex Labels | PO#, and NS sales order number needed on labels | Task | 3.Medium | FALSE | FALSE | Completed
UAT | Test post cancelation of COH | Test scernario where someone modifies order to switch a line to Woodenville | Task | 3.Medium | FALSE | FALSE | Open | REACT | REACT Team |  | 2025-07-07
UAT | Lot and Expiration Tracked | Deposco makes lot numbered items expiration date tracked | Question | 3.Medium | FALSE | FALSE | Open | DEP | Mitch |  | 2025-07-07
UAT | Prevent LPN movement with 0 stock | Cannot Delete because container is associated with RL | Task | 3.Medium | FALSE | FALSE | Open | DEP | Lanie |  | 2025-07-07 | 7/29 - lanie to check with mitch on if he has rules for this once he's back
UAT | Unnecessary Hazmat Code | 788 items have a hazmat code of "No" that is being added from NetSuite when it is not a labeled as a hazmat item | Question | 3.Medium | FALSE | FALSE | Completed
UAT | Netsuite Adjustment Sync | Check what happens when we push a ITF for more than NS thinks we have because an adjustment has not gone through yet | Task | 3.Medium | FALSE | FALSE | Open | REACT | REACT Team |  | 2025-07-07
UAT | Split Japan Pallets | Special SOP for Japanese Pallets | Discussion | 4.Low | TRUE | FALSE | Completed | DEP/REACT
UAT | Order Info | Provide Deposco with order information | Task | 5.NTH | FALSE | FALSE | Completed | REACT
UAT | Items with no Pallet quantity | Some items do not have a consistent pallet quantity | Discussion | 5.NTH | FALSE | FALSE | Completed | DEP/REACT |  |  |  | Not an issue since items wont have full pallet orders
UAT | Add height attribute to location entity | Would like putaway logic to factor in the height of the rack and the height of the pallet to only allocate locations where the pallet can fit | Task | 5.NTH | FALSE | FALSE | Completed | DEP |  |  |  | Not moving forward with
UAT | Non Tracked Adjustment | Not on history table in Netsuite | Question | 5.NTH | FALSE | FALSE | Completed | DEP/REACT |  |  |  | Non issue
UAT | Grocery Scan just lot | This grocery scans now for serials and allows you to enter quantity for lots | Question | 5.NTH | FALSE | FALSE | Completed | DEP
UAT | Test Mutli Bin with RTS |  | Task |  | FALSE | FALSE | Completed | DEP
UAT | Order: Fortlift1 - Outbound_612788 | Battery configuration error when trying to pack item PRT-01198-000; Logs say this failed because it could not find a carrier special service set up, this worked when shipping air |  |  | FALSE | FALSE | Completed
UAT | AV | Orders come in with wrong ZIP Codes, do not want it changed, would rather go on hold | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Lanie |  | 2025-07-07 | 7/29 - not started, will look at EOW or early next week
UAT | Orders coming in without Phone Number | automation | Task | 3.Medium | FALSE | FALSE | Completed | DEP | Lanie |  | 2025-07-07 | 7/29 - not started, will look at EOW or early next week
UAT | NetSuite Zone Channel Lookup | Create channel lookups for each Zones in Deposco thats tied to a NetSuite Location | Task | 3.Medium | TRUE | TRUE | In Progress | DEP | Mitch |  | 2025-07-11 | NC, QUAR, INSPEC, 3B, No QUAR IN SB3
Configuration | Master Data - Item's ABC Classification | Get mapping done for ABC classification, DEP to map data | Task | 4.Low | FALSE | FALSE | Open | DEP | REACT Team |  |  | custitem_cycle_count_class
Validation | Train End Users | During UAT and any additional training as needed | Task | 4.Low | TRUE | TRUE | Open | REACT | Mark |  | 2025-07-07
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task | 4.Low | TRUE | TRUE | Ongoing | DEP/REACT | Full Team |  | 2025-07-16
Configuration | Master Data - Location Updates | Upload Location data (Pick Sequence) | Task | 5.NTH | TRUE | FALSE | Open | REACT | REACT Team |  | 2025-06-20
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task |  | FALSE | FALSE | Open | DEP | Hannah |  | 2025-07-07
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task |  | FALSE | FALSE | Open | DEP | Hannah |  | 2025-07-07
Deployment | Execute Cutover Plan Steps |  | Task |  | FALSE | FALSE | Open | DEP/REACT | Full Team |  | 2025-07-07
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task |  | FALSE | TRUE | In Progress | DEP | Lanie |  | 2025-07-16
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | TRUE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## RHCOL Task Tracker
RHCOL REACT Task Tracker
1-Blocker (Blocking progress on current project phase within next week)
2-High (Critical to current project phase and our path to completion)
3-Medium(Impacting completion of current project phase but able to work around or deal)
4-Low (No impact to path to compleltion of current project phase)
5- NTH (Nice to Have)
Project Phase | TITLE | DESCRIPTION | TYPE | SEVERITY | UAT Critical? | Go Live Critical? | STATUS | TEAM | OWNER | Start Date | Due Date | DEP Comments | REACT Comments
Orientation | Setup FedEx Parcel Carrier Account | FedEx: Clients configures FedEx account and Meter # within Deposco CompanyConfig UI screen DEP team to send documentation Only needed if COL uses a different shipping account than Woodenville | Task | 1.Blocker | TRUE | TRUE | Open | REACT | REACT Team
Orientation | Setup NetSuite Socket | Add COL Location/Facility Cross References and add schedulers to pull orders for COL facility These have been configured without the right location names/ids - Jim to fill out proper values and test. | Task | 1.Blocker | TRUE | TRUE | Open | REACT | Jim
Orientation | Setup Print Client (Windows) | Multi-Step: 1) Deposco Devops team sets up client print sever file with company and warehouse code decided during signing. Windows print server file and instructions provided to client to complete setup on their server/network - DONE 2) Client completes setup of windows print server on their network. 1 label printer and 1 document printer set and validated in Deposco through PrinterDetail config and validation. Printer assignments are setup at later time with implementation team DEP team to send documentation | Task | 1.Blocker | TRUE | TRUE | Open | REACT | REACT Team
Orientation | Order Hardware | Order all necessary hardware: - WIFI - Handhelds - Printers - Carts | Task | 1.Blocker | TRUE | TRUE | Open | REACT | REACT Team
Validation | Printer Testing | All printers get a successful print test from Deposco | Task | 1.Blocker | TRUE | TRUE | Open | REACT | REACT Team
Orientation | Set up inbound ZPL Label Printers | Need to add to Network first | Task | 1.Blocker | TRUE | TRUE | Open | REACT | REACT Team
Orientation | Set up outbound ZPL Label Printers | Need to add to Network first | Task | 1.Blocker | TRUE | TRUE | Open | REACT | REACT Team
Orientation | Setup Users | Deposco guides client super user through user setup with Message Center import or copying admin user from user UI. Client can choose to setup only super users or all users during this phase. Password reset emails are sent to client users to complete final step for Deposco access | Task | 2.High | FALSE | TRUE | Validation | DEP | Mitch
Configuration | Integrations - Inventory Transfer | Confirm that information Deposco provides is satisfactory for NetSuite e.i. Department, etc. | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Configuration | Integrations - Ship Notice | Confirm that information Deposco provides is satisfactory for NetSuite e.i. Department, etc. | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Configuration | Integrations - Inbound Shipment Pull | Confirm that information Deposco provides is satisfactory for NetSuite e.i. Department, etc. | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Configuration | Integrations - Inbound Shipment Receipt Pull | Confirm that information Deposco provides is satisfactory for NetSuite e.i. Department, etc. | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Configuration | Integrations - Item | Resolve all item failures, configure which items to pull in | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Orientation | Master Data - Packs | Upload all case and pallet packs and their dimension via Data Exchange | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Validation | Unit Test Cases - Inbound | Complete test cases for Inbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | In Progress | REACT | Kenny
Validation | Unit Test Cases - Inventory Management | Complete test cases for Inventory Management processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | Open | REACT | Kenny
Validation | Unit Test Cases - Outbound Pt 1 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | Open | REACT | Kenny
Validation | Unit Test Cases - Outbound Pt 2 | Complete test cases for Outbound processes on Test Cases - Unit tab | Task | 2.High | TRUE | TRUE | Open | REACT | Kenny
Validation | End to End Test Case Execution | Complete end to end test cases | Task | 2.High | TRUE | TRUE | Open | REACT | Kenny
Configuration | Update Suggested Putaway for MC |  | Task | 2.High | FALSE | TRUE | Open | DEP | Mitch
UAT | Labeling | Label all picking Containers | Task | 2.High | FALSE | TRUE | Open | REACT | Kenny
Configuration | Master Data - Storage Details | Upload all Storage Details via Data Exchange | Task | 2.High | TRUE | TRUE | Open | REACT | REACT Team
Design | Inbound User Experience | How to get the user to know inbound shipment vs PO | Discussion | 2.High | FALSE | TRUE | Open | DEP/REACT | Full Team
Configuration | Master Data - Locations | Create all locations | Task | 2.High | TRUE | TRUE | Open | REACT | Kenny
Orientation | Data Exchange Updates | Update data exchange templates | Task | 3.Medium | TRUE | TRUE | Open | DEP | Mitch
Configuration | Master Data - Each Packs | REACT To let DEP know the dimensions fields in NS (for each packs) | Task | 3.Medium | TRUE | TRUE | In Progress | REACT | Brie
Configuration | Master Data - Container | Upload all picking containers via Data Exchange | Task | 3.Medium | TRUE | TRUE | Open | REACT | REACT Team
Configuration | Master Data - Location <> Zones | Upload all location/zone relationship via Data Exchange | Task | 3.Medium | TRUE | TRUE | Open | DEP | Mitch
Configuration | Master Data - Carton Types | Upload all Carton Types via Data Exchange | Task | 3.Medium | TRUE | TRUE | Open | REACT | REACT Team
Validation | Train End Users | During UAT and any additional training as needed | Task | 3.Medium | TRUE | TRUE | Open | REACT | Kenny
Validation | Fill out Go/No-Go Decision Document | Fill out throughout UAT and use to make final decision on go live readiness | Task | 2.High | TRUE | TRUE | Ongoing | DEP/REACT | Full Team
Orientation | Label Warehouse Locations | Physically label each location in warehouse |  | 2.High | FALSE | FALSE | Open | REACT | Kenny
Validation | Schedule final Go/No-Go Decision Meeting | Schedule final call to review go/no-go document and make final decision for go live date | Task | 4.Low | FALSE | FALSE | Open | DEP | Hannah
Deployment | Schedule end of day check in calls for go live week | Schedule time to meet with full team end of each day of go live week to review progress | Task | 4.Low | FALSE | FALSE | Open | DEP | Hannah
Deployment | Deliver Cutover Plan | With columns for asignee and execution dates | Task | 4.Low | FALSE | TRUE | Open | DEP | Mitch
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | TRUE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Recordings
REACT Demo Videos
Delivery Date | Category | Config Code | Subcategory | LINK
Baseline Education
| Deposco User Exerience | N/A | General UI Demo | REACT & Deposco - General UI Demo - 2.20.25 - Recording.mp4
| Master Data / Data Exchange | N/A | Data Exchange Walk through | https://www.loom.com/share/b34ac0674dac40be8bd9defca2dea310?sid=584a22c8-4e10-422c-8e44-967b5fa901fb
Process Demos
Integrations
| Inbound/Putaway | InB1.1 | LPN Receiving w/ Data Exchange | https://www.loom.com/share/c9fb3b08888d40348ddc78d2870c3072
| Inbound/Putaway | InB2.1 | Stock Receiving | https://www.loom.com/share/bdc1afd5b84148b48a7d7d453850dee5?sid=8007d339-bb46-4e8c-ad7f-57e77bc6b1a6
| Inbound/Putaway | InB2.3 | Returns Receiving | https://www.loom.com/share/b8d0d84bbc724f1c8812942c7a5c04bd
| Inbound/Putaway | InB3.1 | Unreceiving | https://www.loom.com/share/9e3c2931aed14a8b83a10302d382281b?sid=3159d33c-16b9-4f5d-b830-7c207376fed4
| Inbound/Putaway | InB4.1 | Print Item Label | https://www.loom.com/share/ce849befddea41d699e216c46910bb2a?sid=a7b0b235-fda9-4653-9952-6693008c9523
| Inbound/Putaway | InB5.1 | Move Container | https://www.loom.com/share/03b7b80e660744efb999a4ae9e0ac5b7
| Inventory Management | IM1.1 | Kitting | https://www.loom.com/share/7534c273dd9a455e82d6b6bada3b8172?sid=c9961bf1-2b66-45d0-87a6-413e129ad593
| Inventory Management | IM2.1 | Cycle Count Creation | https://www.loom.com/share/532f1145cc4c443c813f49b2ce8d444d
| Inventory Management | IM2.2 | Cycle Counting | https://www.loom.com/share/91690472113d45b7813eed7643cb9523
| Inventory Management | IM3.1 | Replenishment | https://www.loom.com/share/4666f475d84f46f987d56a2ac289f3d2?sid=6e9b0212-4be7-43b3-a7a4-74507cb0fd03
| Inventory Management | IM3.2 | Replenishment Creation | https://www.loom.com/share/e301709481d04dbdb9e4ee01104b7192?sid=915c037e-be33-4c66-aa58-4c34abfa8eed
| Inventory Management | IM4.1 | Adjust Inventory | https://www.loom.com/share/c0989b79f285498aa99f47f10c20fa80
| Outbound I | OutB1.1 | Bright Order | https://www.loom.com/share/580fb634e1c5454e8b448e92df6489c6
| Outbound I | OutB2.1 | Outbound Order Management | https://www.loom.com/share/88d2dae56fd14c5f86d59c3211b833eb
| Outbound I | OutB3.1 | OFPs/Order Processing/Waving | https://www.loom.com/share/437b11590520423f94e951bfdeb5897b
| Outbound I | OutB4.1 | Single Order Picking | https://www.loom.com/share/b65beacceefb4dccaf19bc6a8a682ecc
| Outbound I | OutB4.2 | Multis Picking | https://www.loom.com/share/78fdb1ea42a84aee9a8755aa38dd5983
| Outbound II | OutB5.1 | Large Order Packing | https://www.loom.com/share/4bfc61605363401db0db7d418f6549a1?sid=a61c2b79-aee9-4635-bd06-853cd52c84c9
| Outbound II | OutB5.2 | Multi Order Packing | https://www.loom.com/share/4a6bc41f43614b4cb43f53534574e9f6?sid=8a7e1d5f-9869-4c46-ada2-e64a77fc6c16
| Outbound II | OutB5.3 | Pack From Container | https://www.loom.com/share/fed1ba18fc634c9ab224ad9b05625a74?sid=93c08128-7eea-45f3-99b8-a19313e6bd7d
| Outbound II | OutB5.4 | Assign Trips | https://www.loom.com/share/54d02820acc849d183fa224d9abcdcfb?sid=9e7f41cf-61a8-4369-be67-b56b53ab211e
| Outbound II | OutB5.5 | Build Pallet | https://www.loom.com/share/0750d994c45d448194edb9783933481f?sid=745a8392-ddb0-431a-bc60-8c439cdcef88
| Outbound II | OutB6.1 | Rate Shopping | https://www.loom.com/share/8572e16abcf54f8a9b7153c4ea189b8e?sid=9cba7c0f-e95c-4f8f-b61a-5fe9a80a0d2e
| Outbound II | OutB7.1 | Void Shipment & Roll Back Order | https://www.loom.com/share/9c08171ef9914843965898c1629e89a4?sid=cb61d7e4-f713-4adc-90d9-34b7e1468e83
Reporting
Miscellaneous Demos
Testing/Training Support
| User Creation |  |  | https://www.loom.com/share/f0d7cac988e145dd88f7a3e5f7bce116
| Integration Overview |  |  | https://www.loom.com/share/a87d26b36d764e1c9d5720e2b0d612ee

## DEP Config Tasks
Product / Task Group | Task | SOW Notes | In Scope | Post Design - Configuration Notes | Owner | Status | % Complete | Hours
Bright Warehouse Configuration (T&M)
Inbound | Pre Receiving | InB1.1 | FALSE | DE Needed for Inbound Shipment | Mitch | In Progress | 0%
Inbound | Button #1 LPN Receiving | InB1.1 | FALSE | Used for receiving LPNs uploaded via DE with an associated inbound shipment or to receive POs with LPNs tied. Product is already validated and only the LPN should be scanned. Receiving V2 Process Order Types: PO, TOs, Blind Orders, Inbound Shipments, Customer Returns LPN Required = False Bulk Count Disallow Over receiving Disallow item not on order Display order notes with title “Receiving Note” Serial capturing for Lot, Serial and Exp Date Always stage to receiving | Lanie | To-Do | 0% | 3
Inbound | Button #2 Stock Receiving | InB2.1 | FALSE | Used for receiving loose stock. Product is not validated and therefore the products need to be individually scanned. Receiving V2 Process: Order Types: PO, TOs, Blind Orders, Inbound Shipments, Customer Returns LPN Required = True Bulk Count Disallow Over receiving Disallow item not on order Display order notes with title “Receiving Note” Serial capturing for Lot, Serial and Exp Date Always stage to receiving | Lanie | To-Do | 0% | 3
Inbound | Button #3 Build Pallet | InB1.2 | FALSE | Used to add stock to an existing LPN or create a new LPN: Need to be able to add stock to a new LPN Need to be able to create a new LPNs and add stock Add rules to print 4x6 LPN label | Lanie | To-Do | 0% | 1
Inbound | Returns | InB2.3 | FALSE | Used for Customer Returns Stage to receiving Rules to capture image of product and store it on the Return in Deposco Reason codes not needed | Mitch | To-Do | 0% | 2
Inbound | Unreceiving | InB3.1 | FALSE | Do not cancel lines for unreceived items | Lanie | To-Do | 0% | 0.5
Inbound | Print Item Label | InB4.1 | FALSE | Used to print item label when needed during receiving Use PrintReport process Input of report should be Item Number, Lot/Expiration/Serial, and number of copies | Lanie | To-Do | 0% | 2
Inbound | Putaway | InB5.1 | FALSE | 3 Processes: Move Container Move Item Move Stock Need Item Tracking Suggested Locations: Only Suggest locations where the I.ItemType = Z.Name 1. Empty Higher Locations First (Pick Sequence in 2,000s) 2. Empty Lower Locations Next (Pick Sequence in 1,000s) | Mitch | To-Do | 0% | 3
Inventory Management | Item Tracking | N/A | FALSE | Serial Tracked Items Lot Tracked Items Exp Tracked Items |  |  | 0% | N/A
Inventory Management | Kitting | IM1.1 | FALSE | Product Conversion with WorkOrder Process Change 'Back' button in WorkOrderDetailsScreen to "Partially Complete" No Replens Need Item Tracking | Lanie | Complete | 0% | 3 | https://www.loom.com/share/7534c273dd9a455e82d6b6bada3b8172?sid=c9961bf1-2b66-45d0-87a6-413e129ad593
Inventory Management | Cycle Count Creation | IM2.1 | FALSE | - Schedulers Needed: 1. A Items: every 90 days (Priority: 5) 2. B Items: every 180 days (Priority: 10) 3. C Items: every 356 days (Priority: 15) EX) ECC - Item Category A Cycle Count 4. 10 Locations per Day based on last counted date (Priority: 10) EX) BLNTS - Quarterly Full Count (Last 50 Counted) - 9900 5. Full physcial count (Priority: 5, Disable Scheduler) - Exceptions in Picking - Item PAL - Location PAL | Rhea | Complete | 0% | 2 | https://www.loom.com/share/3af1a9db2d404225addc8eaa2081ead0
Inventory Management | Cycle Counting | IM2.2 | TRUE | Need to show Lot Number on item selection screen Will have manager approve Do not show 0 variances Will count by LPN Blind Count Bulk Count (except for serial tracked) Need Item Tracking | Rhea | Complete | 0% | 2 | https://www.loom.com/share/b6a541ae4c644da0ba7f07390fd3fbdb
Inventory Management | Replenishment | IM3.1 | FALSE | Need Item Tracking Base Replenishment Process DeleteExistingRecords allow overreplen | Lanie | Complete | 0% | 4 | https://www.loom.com/share/4666f475d84f46f987d56a2ac289f3d2?sid=6e9b0212-4be7-43b3-a7a4-74507cb0fd03
Inventory Management | Replenishment Creation | IM3.2 | FALSE | 2 Schedulers RHWDV and RHCOL Scheduler Base Queries Full Case Picking Storage -> Split Case Picking | Lanie | Complete | 0% | 2 | https://www.loom.com/share/e301709481d04dbdb9e4ee01104b7192?sid=915c037e-be33-4c66-aa58-4c34abfa8eed
Inventory Management | Adjust Inventory | IM4.1 | TRUE | Move to Admin Group Reason Codes: 1 - Damaged 2 - Expired 3 - Lost / Found 4 - Misship 5 - Supplier correction IGNORE_PICK_TASKS = true Need Item Tracking | Rhea | Complete | 70% | 2 | https://www.loom.com/share/c0989b79f285498aa99f47f10c20fa80
Outbound | Bright Order Config | OutB1.1 | FALSE | Sourcing Groups: RHWDV SG - Contains only the RHWDV Facility RHCOL SG - Contains only the RHCOL Facility Sourcing Profiles: Select based on ship from facility on the OL Routing Profiles: 1 single default profile Back order lines Rule Settings: Complete Single Source Only, Rank, All Lines Immediate Routing Type Consider inventory using ATP Routing Selection Profile: All orders go through default routing profile | Mitch | In Validation | 90% | 12
Outbound | Outbound Order Management | OutB2.1 | FALSE | POI: FedEx Address Validation: - Validate Address - Set Residential Flag Sales Order Updates: - Stamp total each quantity for each line on ol.customAttribute1 - Stamp total case quantity for each line on ol.customAttribute2 - Stamp total pallet quantity for each line on ol.customAttribute3 - Stamp true on oh.customAttribute7 (POI Done) Automations (REACT Owned): - Translations: - Ship to Country Translations - Shipping Service Translations Sales Order Updates: - Default Freight Terms Type to Prepaid - Set Freight Terms Type to Third Party if oh.billToAccount number is populated - Default oh.DutiesPaidBy to 'DDU' - Stamp customAttributeX = 'Hazmat' if any item on the order has a Hazmat item | Mitch | In Progress | 0% | 8
Outbound | Waving Profiles | OutB3.1 | FALSE | General Waving: Allocation: Priority>Created Date Backorder Management: All stock on order to fulfill. Pick Strategy: [Biggest Pack First]>[FIFO]>[Location Pick Sequence] Schedulers: Runs at 8:00 AM, 11:45 AM, and 2:00 PM daily Profiles (Details in DD) Need Priority and Partial Release: - Large - Small Multis - Large Multis - Hazmat - Exception Repicks Everything Below Lets Present to REACT in the Loom Scheduler Setup and How to change with OFP Previewing a Profile Processing a Profile Unreleasing a Wave General Overview of how waving works with OFP | Rhea | In Progress | 0% | 6
Outbound | Unrelease Config | OutB3.1 | FALSE | Order drops from Wave Released and Back Ordered Status | Rhea | Complete |  | 0.5
Outbound | Button #1: Single Order Picking (SSPicking) | OutB4.1 | FALSE | Split Screen Scan Serial Number Grocery Scan if pick quantity <= 5 Notes show with title of 'Picking Note' Lot, Exp, Serial Tracking Exception, Suspend Task, Suspend Workgroup, Stop Workgroup Waves strart with "Large" Sort by Priority and then Created Date | Rhea | Complete | 0% | 3 | Mitch Lantz how will we validate when there are multiple stock unit serials in the location, or will there always be 1 serial per sku? for example with item1, I wasn't sure which serial to enter when picking as there are 5 different serials for item 1 SU's in pickloc1
Outbound | Button #2: Hazmat Order Picking (SSPicking) | OutB4.1 | FALSE | Split Screen Scan Serial Number Grocery Scan if pick quantity <= 5 Notes show with title of 'Picking Note' Lot, Exp, Serial Tracking Exception, Suspend Task, Suspend Workgroup, Stop Workgroup Waves strart with "Hazmat" Sort by Priority and then Created Date | Rhea | Complete | 0% | 0.5
Outbound | Button #3: Small Batch Picking (Batch Picking) | OutB4.2 | FALSE | Split Screen Scan Serial Number Grocery Scan if pick quantity <= 5 Notes show with title of 'Picking Note' Lot, Exp, Serial Tracking Exception, Suspend Task, Suspend Workgroup, Suspend Workgroup and Keep Assigned User Waves strart with "Small Multis" Sort by Priority and then Created Date | Rhea | To-Do | 0% | 3
Outbound | Button #4: Large Batch Picking (Batch Picking) | OutB4.2 | FALSE | Split Screen Scan Serial Number Grocery Scan if pick quantity <= 5 Notes show with title of 'Picking Note' Lot, Exp, Serial Tracking Exception, Suspend Task, Suspend Workgroup, Suspend Workgroup and Keep Assigned User Waves strart with "Large Multis" | Rhea | Complete | 0% | 0.5
Outbound | Button #5: Repick Picking (Batch Picking) | OutB4.3 | FALSE | Split Screen Scan Serial Number Grocery Scan if pick quantity <= 5 Notes show with title of 'Picking Note' Lot, Exp, Serial Tracking Exception, Suspend Task, Suspend Workgroup, Suspend Workgroup and Keep Assigned User Waves strart with "Repick" Sort by Priority and then Created Date | Rhea | Complete | 0% | 0.5
Outbound | Button #1 Large Order Packing (SSPacking) | OutB5.1 | FALSE | Soft Close Print LPN Label (SPA as reference for rules) Bulk Counting Serial Tracking (Exp, Lot, Serial) | Lanie | In Validation | 0% | 4 | https://www.loom.com/share/4bfc61605363401db0db7d418f6549a1?sid=a61c2b79-aee9-4635-bd06-853cd52c84c9
Outbound | Button #2 Multi Order Packing (SSPacking) | OutB5.2 | FALSE | Hard Close Bulk Count Rate Shopping Serial Tracking (Exp, Lot, Serial) Print 1 Packing Slip Per Order Rules if container is scanned that was exceptioned (SPA as reference) | Lanie | In Validation | 0% | 2 | https://www.loom.com/share/4a6bc41f43614b4cb43f53534574e9f6?sid=8a7e1d5f-9869-4c46-ada2-e64a77fc6c16
Outbound | Pack From Container | OutB5.3 | FALSE | Hard Close Bulk Count Rate Shopping Serial Tracking (Exp, Lot, Serial) Print 1 Packing Slip Per Order Shipp | Lanie | In Validation |  | 4 | https://www.loom.com/share/25bf41a9b76f428395e7f380888a6762?sid=f1c04183-d3e0-47b5-a0bb-67de9b9b2c59
Outbound | Button #3 Assign Trip to Container | OutB5.4 | FALSE | Hard Close Print 1 Packing Slip Per Order Dont allow multiple orders per trip VALIDATE_ORDERS_COMPLETE VALIDATE_NO_MISSING_CONTAINERS | Lanie | In Progress | 0% | 4
Outbound | Button #4 Build Pallet | OutB5.5 | FALSE | Used to add stock to an existing LPN or create a new LPN: Need to be able to add stock to a new LPN Need to be able to create a new LPNs and add stock Add rules to print 4x6 LPN label Serial Tracking (Exp, Lot, Serial) | Lanie | In Validation |  | 1 | https://www.loom.com/share/0750d994c45d448194edb9783933481f?sid=745a8392-ddb0-431a-bc60-8c439cdcef88
Outbound | Rate Shopping v2 | OutB6.1 | FALSE | Profiles: 1. Standard - Select cheapest Method 2. 2 Day - Select cheapest Method 3. 1 Day - Select cheapest Method | Lanie | In Validation | 0% | 4 | https://www.loom.com/share/8572e16abcf54f8a9b7153c4ea189b8e?sid=9cba7c0f-e95c-4f8f-b61a-5fe9a80a0d2e
Outbound | Void Shipment | OutB7.1 | FALSE |  | Lanie | In Validation |  |  | https://www.loom.com/share/61f655b14e3d487695599cbfdee00936?sid=3f421558-4951-4af6-9837-9d723daa103f
Outbound | Roll Back After Picking | OutB7.1 | FALSE |  | Lanie | In Validation |  |  | https://www.loom.com/share/61f655b14e3d487695599cbfdee00936?sid=3f421558-4951-4af6-9837-9d723daa103f
Other | Shipping Documents/Labels |  | FALSE |  |  |  | 0%
Bright Socket Configuration (T&M)
Configure | Netsuite - Order |  | FALSE | Custom Mappings: - Map custitem19 to OH. |  |  | 0%
Configure | Netsuite - Item |  | FALSE |  |  |  | 0%
Configure | UPS |  | FALSE |  |  |  | 0%
Configure | FedEx |  | FALSE |  |  |  | 0%
Bright Performance Configuration (T&M)
Standard Dashboard and Reporting | Global Reports |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Company Reports/Report Builder |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Report Scheduling |  | FALSE |  |  |  | 0%
Standard Dashboard and Reporting | Dashboards |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Report Models |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Report Scheduling |  | FALSE |  |  |  | 0%
Dashboard and Reporting add-on | Data Archive |  | FALSE |  |  |  | 0%
Bright Order Configuration (T&M)
Configure - Order Orchestration | Preprocessing |  | FALSE | N/A |  |  | 0%
Configure - Order Orchestration | Order Sourcing |  | FALSE | N/A |  |  | 0%
Configure - Order Orchestration | Order Routing |  | FALSE |  |  |  | 0%
Configure - Order Orchestration | Order Release |  | FALSE |  |  |  | 0%
Configure - Order Processing | Order Management |  | FALSE |  |  |  | 0%
Configure - Order Processing | Order Exception Management |  | FALSE |  |  |  | 0%
Configure - Enterprise Inventory | Enterprise Inventory Management |  | FALSE |  |  |  | 0%
Configure - INventory Segmentation | Manage Segments |  | FALSE |  |  |  | 0%

## Test Cases - Unit
REACT Unit Test Cases |  |  | Category | % Complete
|  |  | Integrations | 0%
|  |  | Order Orchestration | 0%
|  |  | Inbound | 78.26%
|  |  | Inventory Management | 20%
|  |  | Outbound 1 | 66.67%
|  |  | Outbound II | 56.6%
|  |  | Other WMS | #DIV/0!
|  |  | Reporting | #DIV/0!
|  |  | TOTAL | 46.05%
Category | Subcategory | Config Code | Test Scenario | Expected Outcome | Owner | Status | Completed By | Columbus Completed By | Test Data | Comments | Deposco Comments
Integrations
Integrations |  | Netsuite - Item Pull | Execute: scheduled run at 00:00:00 nightly |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Execute: manual run with no entries into pop-ups |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Execute: manual run with "refNumberToPull " populated with one valid product ID |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Execute: manual run with "refNumberToPull" populated with multiple valid product IDs |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Execute: manual run with "refNumberToPull" populated with one invalid product ID |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Execute: manual run with "refNumberToPull" populated with mix of valid/invalid product IDs |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: Pull valid item with defined subsidiary |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: Pull valid item outside of defined subsidiary |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: Pull valid item of specified item type |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: Pull valid item of non-specified item type |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: Pull valid item where "Sent to Deposco" is true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: Pull manual run for validi item where "Sent to Deposco" is false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: "How do you want to handle missing items?" set to "Create or Update Item, Update Links If Found" - Pull item that DOES already exist in Deposco |  |  | Ready to Test
Integrations |  | Netsuite - Item Pull | Data: "How do you want to handle missing items?" set to "Create or Update Item, Update Links If Found" - Pull item that DOES NOT already exist in Deposco |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Execute: scheduled run at 01:00:00 nightly |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Execute: manual run with no entries into pop-ups |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Execute: manual run with "refNumberToPull " populated with one valid customer ID |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Execute: manual run with "refNumberToPull" populated with multiple valid customer IDs |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Execute: manual run with "refNumberToPull" populated with one invalid customer ID |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Execute: manual run with "refNumberToPull" populated with mix of valid/invalid customer IDs |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Data: Pull valid Customer with defined subsidiary |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Data: Pull valid Customer outside of defined subsidiary |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Data: Pull valid Customer of specified Category Id |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Data: Pull valid Customer of non-specified Category Id |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Data: Pull valid Customer where "Sent to Deposco" is true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Data: Pull valid Customer where "Sent to Deposco" is false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Criteria: Use Internal Id = True -- Create Customer |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Criteria: Use Internal Id = True -- Update Customer |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Criteria: Use Internal Id = False -- Create Customer |  |  | Ready to Test
Integrations |  | Netsuite - Customer Pull | Criteria: Use Internal Id = False -- Update Customer |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Execute: manual run with "NetSuite Order Number" populated with one valid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Execute: manual run with "NetSuite Order Number" populated with multiple valid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Execute: manual run with "NetSuite Order Number" populated with one invalid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Execute: manual run with "NetSuite Order Number" populated with mix of valid and invalid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull SO in status Pending Fulfillment |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull SO NOT status Pending Fulfillment |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull order with matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull order without matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull order with matching location id |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull order without matching location id |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull order with "Sent to Deposco" = true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Sales Order Pull | Data: Pull order with "Sent to Deposco" = false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Execute: manual run with "NetSuite Order Number" populated with one valid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Execute: manual run with "NetSuite Order Number" populated with multiple valid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Execute: manual run with "NetSuite Order Number" populated with one invalid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Execute: manual run with "NetSuite Order Number" populated with mix of valid and invalid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Data: Pull PO in status Pending Receipt |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Data: Pull PO NOT status Pending Receipt |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Data: Pull order with matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Data: Pull order without matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Data: Pull order with "Sent to Deposco" = true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Purchase Order Pull | Data: Pull order with "Sent to Deposco" = false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Execute: manual run with "refNumberToPull" populated with one valid order ID |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Execute: manual run with "refNumberToPull" populated with multiple valid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Execute: manual run with "refNumberToPull" populated with one invalid order ID |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Execute: manual run with "refNumberToPull" populated with mix of valid and invalid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Data: Pull RMA in status Pending Receipt |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Data: Pull RMA NOT status Pending Receipt |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Data: Pull order with matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Data: Pull order without matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Data: Pull order with "Sent to Deposco" = true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - RMA Pull | Data: Pull order with "Sent to Deposco" = false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with one valid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with multiple valid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with one invalid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with mix of valid and invalid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Data: Pull ITO in status Pending Receipt |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Data: Pull ITO NOT status Pending Receipt |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Data: Pull order with matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Data: Pull order without matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Data: Pull order with "Sent to Deposco" = true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Inbound Transfer Order Pull | Data: Pull order with "Sent to Deposco" = false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Execute: scheduled run every 15 minutes |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with one valid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with multiple valid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with one invalid order ID |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Execute: manual run with "refNumberToPull" populated with mix of valid and invalid order IDs |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Data: Pull OTO in status Pending Fulfillment |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Data: Pull ITO NOT status Pending Fulfillment |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Data: Pull order with matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Data: Pull order without matching subsidiary id |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Data: Pull order with "Sent to Deposco" = true in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Outbound Transfer Order Pull | Data: Pull order with "Sent to Deposco" = false in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship full order at one time - single tracking number |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship full order at one time - multiple tracking numbers |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship partial order - single tracking number |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship partial order - multipile tracking numbers |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship kit to order products on full order at one time - single tracking number |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship kit to order products on full order at one time - multiple tracking numbers |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship order that was manually marked as fulfilled in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Data: Ship quantity greater than quantity order line in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Execute: Re-generate ship notice for failed transaction |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Execute: Re-process ship notice event for failed transaction |  |  | Ready to Test
Integrations |  | Netsuite - Ship Notice | Execute: Scheduled re-process of ship notice event for failed transactions that have been retied less than 3 times |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Adjustment | Execute: scheduled run Friday at 23:00:00 |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Adjustment | Execute: manual run of scheduler |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Adjustment | Data: Summarize quantities = true -- Multiple adjustment records created for same item/location |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Adjustment | Data: Summarize quantities = true -- Single adjustment records created for each item/location |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Adjustment | Data: No adjustments found |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Adjustment | Data: Adjustments found |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Transfer | Execute: scheduled run Daily at 22:00:00 |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Transfer | Execute: manual run of scheduler |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Transfer | Data: No transfers found |  |  | Ready to Test
Integrations |  | Netsuite - Inventory Transfer | Data: Transfer found |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Execute: Scheduled run every x minutes |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Execute: Manual run |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Data: No receipts found |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Data: Receipts found |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Data: Receipts found for PO manually received in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Data: Order partilly received when job runs |  |  | Ready to Test
Integrations |  | Netsuite - PO Receipt | Data: Order fully received when job runs |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Execute: Scheduled run every x minutes |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Execute: Manual run |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Data: No receipts found |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Data: Receipts found |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Data: Receipts found for PO manually received in Netsuite |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Data: Order partilly received when job runs |  |  | Ready to Test
Integrations |  | Netsuite - RMA Receipt | Data: Order fully received when job runs |  |  | Ready to Test
Integrations |  | FedEx - Rate Shop | Retrieve rates for all relevant Ship Vias: |  |  | Ready to Test
Integrations |  | FedEx - Rate Shop
Integrations |  | FedEx - Shipping Label | Retrieve shipping label for all relevant Ship Vias: FedEx Ground, FedEx Home Delivery etc. |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve domestic shipping label |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve international shipping label |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label using Prepaid Freight Terms Type |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label using Collect Freight Terms Type |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label using Third Party Freight Terms Type |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label for Saturday Delivery shipment |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label for Residential shipment |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label for shipment where Insurance is required |  |  | Ready to Test
Integrations |  | FedEx - Shipping Label | Retrieve shipping label for shipment where Delivery Signature is required |  |  | Ready to Test
Integrations |  | FedEx - Shipping Documents | Retrieve Commercial Invoice for international shipment |  |  | Ready to Test
Order Orchestration
Order Orchestration |  | Preprocessing - Data Validations | Ship Via missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | NOT Ready to Test
Order Orchestration |  | Preprocessing - Data Validations | Ship To Address info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | NOT Ready to Test
Order Orchestration |  | Preprocessing - Data Validations | Trading Partner missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | NOT Ready to Test
Order Orchestration |  | Preprocessing - Data Validations | Line Item info missing on CO | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | NOT Ready to Test
Order Orchestration |  | Preprocessing - Data Validations | Multiple data validations are triggered on CO | Order goes to Review status until all data is fixed and re-processing has been run (scheduled or manual) |  | NOT Ready to Test
Order Orchestration |  | Preprocessing - Data Validations | Duplicate order warning is triggered | Order goes to Review status until data is fixed and re-processing has been run (scheduled or manual) |  | NOT Ready to Test
Order Orchestration |  | Preprocessing - Data Validations | No data validation is triggered | Order is either Back Ordered or Released automatically upon creation |  | NOT Ready to Test
Order Orchestration |  | Order Sourcing - Sourcing Group Selection | Order line location id matches Woodinville Facility | Sourcing Group Woodinville is assigned |  | NOT Ready to Test
Order Orchestration |  | Order Sourcing - Sourcing Group Selection | Order line location id matches Columbus Facility | Sourcing Group Columbus is assigned |  | NOT Ready to Test
Order Orchestration |  | Order Sourcing - Sourcing Group Selection | Order line location id matches no facility | Order goes to Review with CoNotice message that sourcing could not be completed |  | NOT Ready to Test
Order Orchestration |  | Order Routing - Routing Selection Profile | Order meets no matching Routing Selection Criteria | Order goes to Back Order |  | NOT Ready to Test
Order Orchestration |  | Order Release - Available Inventory | Full Inventory not available in either facillity to fulfill CO | CO Back Orders |  | NOT Ready to Test
Order Orchestration |  | Order Release - Available Inventory | Full Inventory is available in both facilities to fulfill CO | CO lines for Woodinville Sourcing release to Woodinville and CO lines for Columbus release to Columbus |  | NOT Ready to Test
Order Orchestration |  | Order Release - Available Inventory | Inventory for Woodinville Sourcing lines is available in Woodinville Facility but inventory for Columbus lines NOT available in Columbus | CO Back Orders |  | NOT Ready to Test
Order Orchestration |  | Order Release - Available Inventory | Inventory for Columbus Sourcing lines is available in Columbus Facility but inventory for Woodinville lines NOT available in Woodinville | CO Back Orders |  | NOT Ready to Test
Order Orchestration |  | Order Release - Available Inventory | Inventory for Columbus Sourcing lines is available in Columbus and inventory for Woodinville lines is available in Woodinville | CO Releases |  | NOT Ready to Test
Order Orchestration |  | Order Management - Scheduled Routing | Scheduled re-route attempt on orders in Back Order status | Orders in Back Order automatically re-routed ever x hours. Order either stays in Back Order or moves to Released if inventory now available. |  | NOT Ready to Test
Order Orchestration |  | Order Exception Management - Reprocess | Manual Reprocess CO in Review status | Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | NOT Ready to Test
Order Orchestration |  | Order Exception Management - Reprocess | Scheduled Reprocess CO in Review status | Orders in Review automatically reprocessed every x hours. Order either stays in Review if data has not been fixed or moves to Back Ordered/Released if data has been fixed. |  | NOT Ready to Test
Order Orchestration |  | Enterprise Inventory Management | Inventory by Facility | Reports execute timely and accurately for all skus |  | NOT Ready to Test
Inbound
Inbound | Stock Receiving |  | Scan item not on PO/RMA | "Unable to find order line for item: XYZ" | REACT Team | Pass | MSchumacher | KDuby | Order MS PO Test 1 | "Unable to find order line for item: PRT-00850-000"
Inbound | Stock Receiving |  | Scan item on PO/RMA | User is then moved to the Pack Quantity screen where they are prompted to enter the quantity to receive | REACT Team | Pass | MSchumacher |  | Order MS PO Test 1 | "Receive Qty:" and pack quantity screen appears
Inbound | Stock Receiving |  | Receive lot tracked product by item | User is prompted for the lot number received in the Item capture screen | REACT Team | Pass | MSchumacher | KDuby | MS PO Test 3 | Lot and expiry appear
Inbound | Stock Receiving |  | Receive serial tracked product by item | User is prompted for the serial numbers received in the Item capture screen | REACT Team | Pass | MSchumacher |  | Order MS PO Test 1 | Entered 5 test serial numbers
Inbound | Stock Receiving |  | Receive expiration date tracked product by item | User is prompted for the exp date received in the Item capture screen | REACT Team | Pass | MSchumacher | KDuby | MS PO Test 3 | Lot and expiry appear
Inbound | Stock Receiving |  | Enter quantity less than quantity on PO/RMA, select finish | Line and Order go into a partial reciept status, user is able to go in and receive the rest | REACT Team | Pass | MSchumacher | KDuby | MS PO Test 3 | good - goes from Receiving when in progress to Partial Receipt status
Inbound | Stock Receiving |  | Enter quantity equal to quantity on PO/RMA | Line and Order go into a Received status | REACT Team | Pass | MSchumacher | KDuby | Order MS PO Test 1
Inbound | Stock Receiving |  | Enter quantity greater than quantity on PO/RMA | Message displays in HH - "You can only receive up to the max amount X of Each." | REACT Team | Pass | MSchumacher |  | MS PO Test 3 | "You can only receive up to the max amount 1.6666666666666667 of Pallet." Attempted to receive 2 pallets worth
Inbound | Stock Receiving |  | Receiving a PO Line in case pack quantities | Line correctly updates to received the amount of amount received x case quantity | REACT Team | Pass | MSchumacher |  | MS PO Test 3 | Received 10x cases of 2 = 20 (120-20 = 100 open)
Inbound | Stock Receiving |  | Receiving a PO Line in pallet pack quantities | Line correctly updates to received the amount of amount received x pallet quantity | REACT Team | Pass | MSchumacher |  | MS PO Test 3 | Received 1x pallet of 60 = 60
Inbound | LPN Receiving/DE |  | Upload an inbound shipment to attach all of the serial information to a PO | Inbound shipment created with shipment lines created for each serial | REACT Team | Pass | DRakestraw |  | INBSHIP:INBSHIP1276 Order: Sam - LG3600 - PI-3BM-H2522 | Completed Data Exchange successfully / Is there a way to receive the whole Inbound at once without picking the LPN each time? |  | Would like the contract and/or SN to be searchable
Inbound | LPN Receiving |  | Scan LPN not on PO/RMA | Fail error "LPN [XYZ] does not exist on this shipment." | REACT Team | Pass | DRakestraw |  | INBSHIP:INBSHIP1276 Order: Sam - LG3600 - PI-3BM-H2522 | Yup |  | Would like to be able to export details from certain pages (IE. SNs on a container or contract)
Inbound | LPN Receiving |  | Scan LPN on PO/RMA | LPN Is received and order and order line update as expected | REACT Team | Pass | DRakestraw |  | INBSHIP:INBSHIP1276 Order: Sam - LG3600 - PI-3BM-H2522 | Uh-huh
Inbound | LPN Receiving |  | Receive serial tracked product by LPN | LPN Received and user is not prompted for serials, serials are created on the stock unit and receipt lines | REACT Team | Pass | DRakestraw |  | INBSHIP:INBSHIP1276 Order: Sam - LG3600 - PI-3BM-H2522 | SNs are on the stock unit. Inbound partially received.
Inbound | Returns Receiving |  | Take a picture of the product on the item capture screen | Picture is captured and appears on the | REACT Team | Needs Info | MSchumacher |  | MARKRMA061825 | Two pictures captured, not sure where they are stored
Inbound | Returns Receiving |  | Receive a return | RMA is updated, stock is created in the returns location | REACT Team | Needs Info | BDaw |  | MITCHRMA1--1 Number 398 | SN entered with 123456789123456789, Is there a way if it's an RMA on an order that shipped from this warehouse to link it to it's original outbound order?
Inbound | Build Pallet |  | Add loose stock to an LPN using a random LPN label | LPN is created and accurate amount of stock is placed on LPN in receiving | REACT Team | Pass | BDaw |  | PO 609133, LPNBD123
Inbound | Print Item/Serial Label |  | Go to Report and Metrics > Report Tab > REACT - Item-Serial Label> Enter in item and PO | A label shows for every serial received onto that PO | REACT Team | Pass | DRakestraw |  | Worked, but not needed for most receipts, product has SNs. Can we print an individual SN?
Inbound | Print Item Label |  | Go to Report and Metrics > Report Tab > REACT - Item Label > Enter in item and PO | An accurate label shows | REACT Team | Pass | DRakestraw |  | Worked, but not needed for most receipts, product has SNs. Can we print an individual SN?
Inbound | Print Item/Lot Label |  | Go to Report and Metrics > Report Tab > REACT - Item-Lot Label > Enter in item and PO | An accurate label shows | REACT Team | Needs Info | DRakestraw |  | Worked, but not needed for most receipts, product has SNs. Can we print an individual SN? | How do we connect INBSHIP to PO in Production? What does the receipt info look like so we know how to create the receipt flow back to NS via Celigo? | This is done through data exchange
Inbound | Move Container |  | Move an LPN from receiving to an LPN Controlled location | Container and stock move accurately and container stays with the stock in the new location | REACT Team | Pass | BDaw |  | LPNBD123 moved to BD LPN Location
Inbound | Move Container |  | Move an LPN from receiving to a non LPN Controlled location | Container and stock move accurately and container does not stay with the stock in the new location | REACT Team | Ready to Test | BDaw |  | LPN00345 moved to BD LPN No Location, Container Number still displaying under StockUnit |  | brie.daw@reacthealth.com Can you test this again? Just updated config
Inventory Management
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a single reserve location (enough to refill storage to maximum capacity) | Scheduler runs successfully. Replenishment task created to pull enough stock from reserve location to refill storage location to maximum capacity. | REACT Team | Ready to Test |  |  |  | Would like a summary of item and qty in a location when searching for the location.
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a single reserve location (but NOT enough to refill storage to maximum capacity) | Scheduler runs successfully. Replenishment task created to pull all stock from reserve location to refill storage location with remaining units. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a multiple reserve locations (each with enough stock to refill storage to maximum capacity) | Scheduler runs successfully. Replenishment task created to pull enough stock from the reserve location with the lowest pick sequence to refill storage location to maximum capacity. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a multiple reserve locations (only one with enough stock to refill storage to maximum capacity) | Scheduler runs successfully. Replenishment task created to pull enough stock from the reserve location full quantity to refill storage location to maximum capacity. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is below the storage minimum and additional stock exists in a multiple reserve locations (neither with enough stock to refill storage to maximum capacity alone) | Scheduler runs successfully. Multiple replenishment tasks created to pull enough stock from the each reserve location to sum up to the amount that will refill storage location to maximum capacity. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is below the storage minimum but NO additional stock exists in a reserve location | Scheduler runs successfully. No replenishment tasks created. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Execute replenishment scheduler when stock for a storage location is greater than or equal to the storage minimum | Scheduler runs successfully. No replenishment tasks created. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Generate Replenishment Task for serialized product | Replenishment tasks generated per serial number to be replenished - each task with quantity of 1 and serial number to pull associated. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Generate Replenishment Task for lot tracked product | Replenishment tasks generated per lot number to be replenished - each task with corresponding lot and quantity associated. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Generate Replenishment Task for expiration date tracked product | Replenishment tasks generated per expiration date to be replenished - each task with corresponding expiration date and quantity associated. | REACT Team | Ready to Test
Inventory Management | Replenishment Creation | IM3.2 | Generate Replenishment Task for products with no lot, serial, or expiration date tracking. | Replenishment tasks generated per pull location and item. | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull requested quantity on replenishment task | Quantity entered is moved to replenishment cart for putaway | REACT Team | Pass |  |  | Replenishment ID: 75
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull more than requested quantity on replenishment task | Quantity entered is moved to replenishment cart for putaway | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Perform exception for full quantity to pull | Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Perform exception for partial quantity to pull | Quantity entered is moved to repelnishment cart for putaway. Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull from LPN Controlled Location | User is prompted to enter LPN from which they pull inventory | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull from Non-LPN Controlled Location | User is prompted to enter only the sku and quantity to pull | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull serialized products | User is prompted first to enter the sku and quantity, then to confirm the serial number to pull | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull lot tracked products | User is prompted first to enter the sku and quantity, then to confirm the lot number to pull | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Pull expirationd date tracked products | User is prompted first to enter the sku and quantity, then to confirm the expiration date to pull | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Complete all pull tasks before moving to put tasks | User is automatically prompted to begin putaway | REACT Team | Pass |  |  | Replenishment ID: 75
Inventory Management | Replenishment | IM3.1 | Replenishment Pull - Select Cart Full to put away already pulled products before pulling more | Direct user to complete the replenishments that have already been picked, once completed, direct user back to replenishment task screen to continue with replenishment process | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Replenish to an LPN Controlled Location | User is prompted to enter putaway location, sku, LPN, and quantity | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Replenish to a Non-LPN Controlled Location | User is prompted to enter putaway location, sku, and quantity | REACT Team | Pass |  |  | Replenishment ID: 75
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Replenish serialized products | User is prompted first to enter the location, sku and quantity, then to confirm the serial number to put away | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Replenish lot tracked products | User is prompted first to enter the location, sku and quantity, then to confirm the lot number to put away | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Replenish expiration date tracked products | User is prompted first to enter the location, sku and quantity, then to confirm the expiration date to put away | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Perform exception for full quantity to put | Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process. Task is created to put stock back to source reserve location. | REACT Team | Ready to Test
Inventory Management | Replenishment | IM3.1 | Replenishment Put - Perform exception for partial quantity to put | Quantity entered is put away. Cycle count will be created for location that was exceptioned. If "Suspend Task" is chosen, the task will be moved to end of replenishment task process. Task is created to put remaining stock back in source reserve location. | REACT Team | Ready to Test
Inventory Management | Kitting | IM1.1 | Create Workorder Manually | Workorder with correct kit and quantity is created for kitting location | REACT Team | NOT Ready to Test
Inventory Management | Kitting | IM1.1 | Attempt to complete workorder when insufficient inventory exists in kitting workcell to create any quantity of output sku | Error message: Workcell doesn't have enough inventory to build. | REACT Team | NOT Ready to Test
Inventory Management | Kitting | IM1.1 | Attempt to complete a workorder when insufficient inventory exists in kitting workcell to complete entire workorder, however enough exists to build some quantity of output skus. | User is allowed to build as many outputs as the input quantities allow. Workorder remains in "Active" status and partial quantity of kit is successfully created, item components quantity is decremented properly | REACT Team | NOT Ready to Test
Inventory Management | Kitting | IM1.1 | Attempt to build quantity greater than workorder quantity with sufficient inventory available of input skus in kitting workcell. | Receive an error for attempting to build quantity over workorder quantity | REACT Team | NOT Ready to Test
Inventory Management | Kitting | IM1.1 | Attempt to build quantity equal to the workorder quantity with sufficient inventory available of input skus in kitting workcell. | Receive message that workorder has been completed. Output item quantity in Kit location increases by correct amount and item componenet is decremented | REACT Team | NOT Ready to Test
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for A movers when there are A classified items that have have not been counted in 90 days. | Cycle count tasks generated for A classified items that have not been counted in 90 days | REACT Team | Pass | DRakestraw |  | Cycle Count ID 343
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for B movers when there are B classified items that have have not been counted in 180 days. | Cycle count tasks generated for B classfieid items that have not been counted in 180 days | REACT Team | Pass | NMaldonado |  | Cycle count ID 352
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for C movers when there are C classified items that have have not been counted in 365 days. | Cycle count tasks generated for C classified items that have not been counted in 365 days | REACT Team | Pass | NMaldonado |  | Cycle count ID 353
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for A movers when there are NO A classified items that have have not been counted in 90 days. | No cycle count tasks created | REACT Team | Pass | DRakestraw |  |  | How do we account for tasks in process, so we're not creating the same task over and over if we run the flow and the task is pending completion?
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for B movers when there are NO B classified items that have have not been counted in 180 days. | No cycle count tasks created | REACT Team | Pass | NMaldonado
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for C movers when there are NO C classified items that have have not been counted in 365 days. | No cycle count tasks created | REACT Team | Pass | NMaldonado
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for "Last 10 Counted" when 10 or more locations have Cycle Count = true | Ten cycle count tasks are created. Locations that are chosen have the furthest away "Last Counted Date" | REACT Team | Ready to Test
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count task scheduler for "Last 10 Counted" when less than 10 locations have Cycle Count = true | Cycle count tasks created for all locations where cycle count = true. | REACT Team | Ready to Test
Inventory Management | Cycle Count Creation | IM 2.1 | Execute cycle count scheduler for full physical count | Count task created for all items/locations | REACT Team | Pass | NMaldonado |  | Cycle count ID's 354-363
Inventory Management | Cycle Count Creation | IM 2.1 | Use Process Action Link to create count by location for location where Cycle Count = true | Count task created for location | REACT Team | Pass | NMaldonado |  | Cycle count ID 367
Inventory Management | Cycle Count Creation | IM 2.1 | Use Process Action Link to create count by location for location where Cycle Count = false | No cycle count tasks created | REACT Team | Pass | NMaldonado
Inventory Management | Cycle Count Creation | IM 2.1 | Use Process Action Link to create count by item for item where Cycle Count = true | Count task created for every location in which the item exists | REACT Team | Pass | NMaldonado |  | Cycle count ID's 364-366
Inventory Management | Cycle Count Creation | IM 2.1 | Use Process Action Link to create count by item for item where Cycle Count = false | No cycle count tasks created | REACT Team | Pass | NMaldonado
Inventory Management | Cycle Count Execution | IM2.2 | Count location with one item | 1 item will display in CC item listbox when user scans location in Handheld | REACT Team | Pass |  |  | HB-P15C
Inventory Management | Cycle Count Execution | IM2.2 | Count location with multiple items | Multiple items will display in CC item listbox when user scans location from CC task | REACT Team | Pass
Inventory Management | Cycle Count Execution | IM2.2 | Count exact quantity that actually exists in the location systematically | No variance is recorded in 'Approve Variances' and cycle count task status goes to COMPLETE | REACT Team | Ready to Test |  |  | ID = 295 | cycle count task did not go into completed status
Inventory Management | Cycle Count Execution | IM2.2 | Count different quantity than what actually exists in the location systematicall | Variance recorded in 'Approve Variances' - must be approved my admin user. SU wil reflect original QTY until this variance is approved | REACT Team | Ready to Test |  |  |  | Add variance dollar amount? Variance % of qty expected?
Inventory Management | Cycle Count Execution | IM2.2 | Skip counting an item in a location by hitting "Next Location" before all items are counted | CC task for location will be complete status | REACT Team | Ready to Test
Inventory Management | Cycle Count Execution | IM2.2 | Scan an item that does not systematically exist in a location when counting | Item does not exist in this location - Error Message | REACT Team | Ready to Test
Inventory Management | Cycle Count Execution | IM2.2 | Count items in an LPN controlled location | Will be prompted to scan for LPNS | REACT Team | Ready to Test
Inventory Management | Cycle Count Execution | IM2.2 | Count items in a Non-LPN controlled location | Will not be prompted to scan in LPNS | REACT Team | Ready to Test
Inventory Management | Cycle Count Execution | IM2.2 | Count serial tracked items | Will have to enter serial/sku via grocery scanning process instead of QTY entry | REACT Team | Ready to Test
Inventory Management | Cycle Count Execution | IM2.2 | Count lot tracked items | Lot required | REACT Team | Ready to Test
Inventory Management | Cycle Count Execution | IM2.2 | Count expiration date tracked items | Expiration date required | REACT Team | Needs Info |  |  |  | Don't require Expiration during cycle count (cycle count confirms qty, SKU, LOT, not Expiration).
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - consume one item one quantity | SU quantity decrements by 1 in location entered on Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - consume one item quantity > 1 | SU quantity decrements by quantity entered in Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - consume multiple units of multiple items | Multiple inventory records decremented in start location on Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - consume serial tracked item | Serial number required | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - consume lot tracked item | Lot number required when entering item details on Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - consume expiration date tracked item | Expiration date entry is required when entering Inv details in Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - scan item that does not exist in adjustment location | Error | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by item - select reason code for adjustment | 5 reason code options will display - Damaged, Expired, Lost/Found, Misship, Supplier Correction | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume all in location - location has stock units | All Stock Units will be consumed - item Numbers of consumed SU's will display in success message | REACT Team | Ready to Test |  |  | Damages
Inventory Management | Adjust Inventory | IM 4.1 | Consume all in location - location has no stock units | Will return to location screen | REACT Team | Ready to Test | MSchumacher |  | (handheld)No error, goes back to location prompt |  | This is updated. It should take you back to location screen, no error will appear
Inventory Management | Adjust Inventory | IM 4.1 | Consume all in location - select reason code for adjustment | All Stock Units will be consumed - item Numbers of consumed SU's will display in success message | REACT Team | Ready to Test | MSchumacher |  | (handheld)Completed, scrapped out all as damaged (1 LG3800, 106 + 5 PRT-00850-000)
Inventory Management | Adjust Inventory | IM 4.1 | Consume by LPN - scan LPN that does not exist in adjustment location | Error | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by LPN - consume 1 LPN | LPN(s)in start location will decrease by 1 | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by LPN - consume multiple LPNs | LPN(s) in start location will decrease by qty entered | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Consume by LPN - select reason code for adjustment | 5 reason code options will display - Damaged, Expired, Lost/Found, Misship, Supplier Correction | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Create Inventory - Create inventory for one unit of one item | Inventory created in start-off location with QTY 1 | REACT Team | Ready to Test | DRakestraw |  |  | Attempted multiple times via handheld, might be a permissions issue, but cannot create inventory. Created inventory via data exchange.
Inventory Management | Adjust Inventory | IM 4.1 | Create Inventory - Create inventory for multiple units of one item | Inventory created in start-off location with QTY entered in Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Create Inventory - Create inventory for multiple units of multiple items | Multiple inventory records created in start location on Handheld | REACT Team | Ready to Test
|  |  | Created invenotry via Data Exchange - multiple units or multiple items |  | REACT Team | Pass | DRakestraw |  | Transmission ID 24
Inventory Management | Adjust Inventory | IM 4.1 | Create Inventory - Create inventory for serial tracked items | Serial number required when entering item details on Handheld | REACT Team | Ready to Test
Inventory Management | Adjust Inventory | IM 4.1 | Create Inventory - Create inventory for lot tracked items | Lot number required when entering item details on Handheld | REACT Team | Needs Info | MSchumacher |  | Unclear ID? did not appear on approve variances
Inventory Management | Adjust Inventory | IM 4.1 | Create Inventory - Create inventory for expiration date tracked items | Expiration date entry is required when entering Inv details in Handheld | REACT Team | Ready to Test
Outbound 1
Outbound 1 | Order Management - AV | OrdMngt1.1 | Process order that has a residential address | Sales Order goes to status "Hold - AV" and Order Header Note created with suggested address changes - POI Done flag is set to true | REACT Team | NOT Ready to Test | DRakestraw |  | CO12951 & CO13239 | Order released without going to Hold - AV / / order changed to sourced but not released CO12951 after updating the ship from facility
Outbound 1 | Order Management - AV | OrdMngt1.1 | Process order that has a commercial address | Sales Order goes to status "Hold - AV" and Order Header Note created indicating no suggestions could be found - POI Done flag is set to true | REACT Team | Pass | DRakestraw |  | DR LG3700 3 - AV Test Fail | Order went to AV Hold
Outbound 1 | Order Management - AV | OrdMngt1.1 | Process order that fails address validation | Sales Order goes to status "Hold - AV" | REACT Team | NOT Ready to Test | DRakestraw |  |  | Order released with bad address
Outbound 1 | Order Management - AV | OrdMngt1.1 | Process order that passes address validation | Sales Order stays in New status, 'POI Done' field is set to true | REACT Team | NOT Ready to Test | DRakestraw |  |  | No issues with bad address
Outbound 1 | Order Management - POI | OrdMngt2.1 | POI runs successfully | POI Done' field is set to true | REACT Team | Pass | DRakestraw
Outbound 1 | Order Management - POI | OrdMngt2.1 | POI fails | POI Done' field is set to false. Waving does not run on the order. | REACT Team | Pass | DRakestraw
Outbound 1 | Order Management - POI | OrdMngt2.1 | Run POI on an order that can be fulfilled using each packs | POI Done flag is set to true, order line's 'Each Quantity' field is properly updated to the correct amount | REACT Team | Pass | DRakestraw |  | DR LG3700 + LG3600 Pallet Case | EA qty updated to "1"
Outbound 1 | Order Management - POI | OrdMngt2.1 | Run POI on an order that can be fulfilled using Case packs | POI Done flag is set to true, order line's 'Case Quantity' field is properly updated to the correct amount | REACT Team | Pass | DRakestraw |  | DR LG3700 + LG3600 Pallet Case | Added a case pack config, it worked well
Outbound 1 | Order Management - POI | OrdMngt2.1 | Run POI on an order that can be fulfilled using Pallet packs | POI Done flag is set to true, order line's 'Pallet Quantity' field is properly updated to the correct amount | REACT Team | Pass | DRakestraw |  | DR LG3700 + LG3600 Pallet Case
Outbound 1 | Order Management - POI | OrdMngt2.1 | Run POI on an order where the bill to account number is blank | Freight Terms type is set to prepaid, Duties Paid By is set to DDU, | REACT Team | Pass | DRakestraw |  | DR LG3700 3 - AV Test Fail | Added fields
Outbound 1 | Order Management - POI | OrdMngt2.1 | Run POI on an order where the bill to account number is set | Freight Terms type is set to third party, Duties Paid By is set to DDU, | REACT Team | Pass | DRakestraw |  | DR v2 LG3700 + LG3600 Pallet Case
Outbound 1 | Order Processing | OB3.1 | Select 'Preview/Process" order preview for order that has not completed POI, ('POI Done' field is set to false) | Will not show anything. No orders will show as the OFP will only process orders that have completed POI check | REACT Team | Pass | DRakestraw |  | A unique pick wave was not created for DRakeLarge 1, DRakeLarge 2 originally - POI set to false, still worked when manually set to False ML - Make sure the orders have gone through POI, select actions Post Order Import. This sets the POI Check to true allowing the order to go through waving
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Small Multis Profile (check OFP for logic) and there is stock available in a picking location. Select preview for the Small Multi profile under order processing. | Orders go into a released status, Pick Wave is in a 'Pending Release' status and is not available for picking |  | Pass | DRakestraw
Outbound 1 | Order Processing | OB3.1 | Take a preview and select cancel | Orders go back into a new status and wave no longer exists |  | Pass | DRakestraw |  | OFP run result id 246
Outbound 1 | Order Processing | OB3.1 | Take a preview and select Process | Pick Wave and Work Group go into released status and are available in the handheld to be picked |  | Pass | DRakestraw |  | Small Multis_250514_15:55:51_1
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Small Multis Profile (check OFP for logic) and there is no stock available in a picking location. Select process for the Small Multi profile under order processing. | Order(s) not able to be allocated appear under the back ordered section of the preview |  | Pass | DRakestraw |  | All lines showed backordered, with item actually backordered reflected correctly.
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Small Multis Profile (check OFP for logic) and there is no stock available in a picking location. Select process for the Small Multi - Partial profile under order processing. | Order(s) without adequate stock are put on wave just for the stock that could be allocated. |  | Pass | DRakestraw |  | Small Multis_Partial_250514_17:07:27_1 DRakeSmall 3700 + Filter --> Filter backlogged
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Large Multis Profile (check OFP for logic) and there is stock available in a picking location. Select process for the Large Multi profile under order processing. | Pick Wave, Work Group, Orders go into released status and are available in the handheld to be picked |  | In Progress | DRakestraw |  | DR IOH200 Large | Order hitting Large OFP instead of large multis | Fixed will discuss on call
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Large Profile (check OFP for logic) and there is stock available in a picking location. Select process for the Large profile under order processing. | Pick Wave, Work Group, Orders go into released status and are available in the handheld to be picked |  | Pass | DRakestraw |  | 2 orders for 1 pallet were released.
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Hazmat Profile (check OFP for logic) and there is stock available in a picking location. Select process for the Hazmat profile under order processing. | Pick Wave, Work Group, Orders go into released status and are available in the handheld to be picked |  | Pass | DRakestraw |  | DRake PRT-00011-001 HZMT | Attempted to create item with hazmay checked true, I could not. Copied Sticker1 item and renamed to PRT-00011-001 to try and find Hamzat field, but couldn't. Reconfigured the item tab to pull in Hazmat - UN3480.
Outbound 1 | Order Processing | OB3.1 | Create Order(s) that will hit the Exception Profile (check OFP for logic, must pick an order and exception part of it) and there is stock available in a picking location. Select process for the Exception profile under order processing. | Pick Wave, Work Group, Orders go into released status and are available in the handheld to be picked |  | In Progress | DRakestraw |  | DR LG3700, LG3600, Filter - Pallet Case; 609104 worked as expected | Created inventory after backordering part of the order - the initial order wasn't captured in the exception repick process, I assume because it was already on part of a pick wave.
Outbound 1 | Manual Waving | OB3.1 | Wave a non priority order manually using the Build and Release Wave PAL on the order header | Order gets placed on the correct wave and is released and able to be picked |  | Pass | DRakestraw |  | DRakeLarge 3700 & LG3800 Pallet
Outbound 1 | Manual Waving | OB3.1 | Wave a priority order manually using the Build and Release Wave PAL on the order header | Order gets placed on the correct wave and is released and able to be picked |  | Pass | DRakestraw |  | Most of them are 0
Outbound 1 | Manual Waving | OB3.1 | Wave an order manually using the Build and Release Wave - Partial PAL on the order header. Make sure that only part of the order has enough stock to allocate to it | Order is placed on a wave, goes into a back ordered status and all stock that is able to be allocated gets waved. |  | Pass | DRakestraw |  | DR v2 LG3700 + LG3600 Pallet Case
Outbound 1 | Unreleasing | OB3.1 | Unrelease an entire wave | All orders go back to new status and the wave is deleted |  | Pass | DRakestraw |  | Completed multiple times
Outbound 1 | Unreleasing | OB3.1 | Unrelease a single order from a wave | Only the order that was unreleased goes back to new status and the wave is still released |  | Pass | DRakestraw |  | Completed multiple times
Outbound 1 | Single Order Picking | OB4.1 | Enter in location not on the picking screen | Error message: "The location [x] does not match the required location." |  | Pass | DRakestraw |  | 609221
Outbound 1 | Single Order Picking | OB4.1 | Enter in location on the picking screen | Takes user to the item selection picking screen to enter in the SKU |  | Needs Info | DRakestraw |  | 609221 | Item image doesn't display
Outbound 1 | Single Order Picking | OB4.1 | Enter in SKU not on picking screen | Error message: "The SKU [x] could not be found. Please enter a valid SKU." |  | Pass | DRakestraw |  | 609283 | Passed on second attempt using 609283
Outbound 1 | Single Order Picking | OB4.1 | Enter SKU on picking screen | Takes user to the quantity picking sreen |  | Pass | DRakestraw |  | 609283 | Took me to qty screen, worked as expected | Items should grocery scan if the quantity is less than 5. This order was for 1 unit so it did not require a quantity input | Went through the de-pick process.
Outbound 1 | Single Order Picking | OB4.1 | Enter in a quantity greater than quantity prompted | Error Message: "The quantity that you entered [x] is more than the quantity that is required [x]. |  | Ready to Test | DRakestraw |  | Moved on to 609259 - this took me to the qty screen - worked as expected | Error message: "Quantity entered is greater than required."
Outbound 1 | Single Order Picking | OB4.1 | Enter in quantity on screen | If there are more pick tasks on the wave, it will take the user to the next location to complete the next task. If the task is the last one on the wave, it willt take the user back to the picking menu screen with a message"Picking LPN [x] staged to [Shipping]." |  | In Progress | DRakestraw |  | 609259 - Item1 - Pickloc2 - no containers in that loc | Forced me to enter a bin, hit enter, then guessed "123", took me to enter location screen. Went back through the prompts, can't get past bin screen. no bin for this item and loc. Suspended work group.
Outbound 1 | Single Order Picking | OB4.1 | Wave an order that will give you multiple pick tasks pick one and then select "stage" on item input screen when picking the other. | Picking cart will be staged to shipping and user will be prompted to scan new picking cart to finish the pick wave |  | In Progress | DRakestraw |  | Small Multis_250519_10:53:57_1 | Build and release wave put the wave into planned status, had to manually change to release. Clicked "stage" in item input screen, said nothing to stage and went back to the location screen. Same thing happened when I input the item and clicked "stage" in the qty screen. | This order was already on a partial wave when it was released, which would be why it was planned. The order is backordered and the lines are exceptioned
Outbound 1 | Single Order Picking | OB4.1 | Select Exception and choose "No Stock" | Order will be placed on 'Back Order', location/stock unit will be placed in 'Hold' status, and a cycle count task will be created for the location/item |  | Pass | DRakestraw |  | Small Multis_250519_10:53:57_1 | Clicked exception from location enter screen on the LG3F002 pick task. Took me back to the picking menu. Entire order went on back order. Work group 286 went on exception. Inventory in HB-L24B went on Exception (pick task 2225)
Outbound 1 | Single Order Picking | OB4.1 | Suspend a pick Task | The task is now moved to the end of the queue, it is picked last |  | In Progress | DRakestraw |  | Large_250519_09:26:43_1 | Errror: Multiple orders were found that are associated with a single pick task, which is not a valid scenario for single scan picking. Please contact your Deposco representative. | There are commas in this order which messed up the waving on the backend.
Outbound 1 | Single Order Picking | OB4.1 | Suspend a Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated |  | In Progress | DRakestraw |  | 609230 | Order pick asking for a BIN where none exists. I hit enter to try and go through it, but got an error. Suspended the work group - Large Multis_250508_12:53:23_1 -- work order 123 shows suspended. | You should hit the Suspend Workgroup and keep assigned user button on the exception screen to complete this task
Outbound 1 | Single Order Picking | OB4.1 | End a Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore |  | In Progress | DRakestraw |  | Large_250516_15:58:55_1 | Tried backing out of the work group using the back button. Got as far as entering the Location, tried backing out, ran into this error: Please stage the container since the container includes picked items. -- clicked on handheld menu and it let me out. Did something similar on Small Multis_250520_09:46:07_1 | To suspend a workgroup, you will need to hit the suspend workgroup button on the exception screen to back out of a pick wave
Outbound 1 | Single Order Picking | OB4.1 | Wave and pick an item that is serial tracked | User is prompted for Serial Number after selecting the quantity |  | Needs Info | DRakestraw |  | Small Multis_250520_09:46:07_1 | Location > Item > Bin > SN (skipped qty)
Outbound 1 | Single Order Picking | OB4.1 | Wave and pick an item that is lot tracked | User is prompted for Lot Number after selecting the quantity |  | Needs Info | DRakestraw |  | Small Multis_250520_09:53:23_1 | Location > Item > Bin > it showed the LOT, but didn't have a manual entry field. I couldn't progress. Request: scan the LOT instead of clicking confirm on handheld. If under 5, scan the LOT 5 times instead of having to enter the location and item 5 times. Enter qty for anything above 1, but still scan LOT instead of hitting confirm. | Need to hit confirm to confirm that is the lot there. Was not a manual field because there is only one lot in that location. It will then prompt you to repeat the steps to pick the second item
Outbound 1 | Single Order Picking | OB4.1 | Wave and pick an item that is exp date tracked | User is prompted for Exp Date after selecting the quantity |  | Needs Info | DRakestraw |  | Small Multis_250520_09:58:20_1 | Location > Item > Bin > it showed the LOT and expiry, but didn't have a manual entry field. I couldn't progress. I hit confirm and it took me back to location. | Because it is grcoery scan below quantity of 5, the system requires you to input all values after you hit confrim the lot for the first item. It appears like you are repeating the same thing but you are actually picking the second item
Outbound 1 | Multis Picking | OB4.2 | Enter in location not on the picking screen | Error message: "Please scan a valid location" |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1
Outbound 1 | Multis Picking | OB4.2 | Enter in location on the picking screen | Takes user to the item selection picking screen to enter in the SKU |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1
Outbound 1 | Multis Picking | OB4.2 | Enter in SKU not on picking screen | Error message: "Please scan a valid item." |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1
Outbound 1 | Multis Picking | OB4.2 | Enter SKU on picking screen | Takes user to the quantity picking sreen |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1
Outbound 1 | Multis Picking | OB4.2 | Enter in a quantity greater than the one shown on the screen | Error Message: "Quantity entered is greater than required." |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1
Outbound 1 | Multis Picking | OB4.2 | Enter in quanntity that's less than what is on the screen | user is asked to put the initial quantity into a bin and then brought back to scan the location, quantity, and bin for the reamaining quanitites on the wave |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1 >> EUIEQ38K
Outbound 1 | Multis Picking | OB4.2 | Enter in quanntity on screen | User is brought to the bin selection picking screen |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1 >> EUIEQ38K
Outbound 1 | Multis Picking | OB4.2 | User enters a bin that has preexisting stock units in it | Error Message: "Scanned bin [x] contains other orders |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1 >> EUIEQ38K
Outbound 1 | Multis Picking | OB4.2 | User enters a bin that doesn't have any preexisting stock units in it | User is brought to the next pick task and is asked to scan the next location if there are available pick tasks. |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1 >> EUIEQ38K
Outbound 1 | Multis Picking | OB4.2 | Enter a bin that is not the suggested bin number | Error Message: The suggested bin is [x]. |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1 >> EUIEQ38K
Outbound 1 | Multis Picking | OB4.2 | Enter suggested Bin number | Item & stock units are moved to the bin. User is brought to the next task if available, else it will bring the user to the Picking Menu screen to select another wave to complete if available |  | Pass | DRakestraw |  | Small Multis_250512_14:57:25_1 >> EUIEQ38K
Outbound 1 | Multis Picking | OB4.2 | User selects 'New Bin' | Message: "New bin created for Order [x]. and user is able to select another bin to put item into if there is not existing stock in the new bin |  | Pass | DRakestraw
Outbound 1 | Multis Picking | OB4.2 | Suspend Task | The task is now moved to the end of the queue, it is picked last |  | Pass | DRakestraw
Outbound 1 | Multis Picking | OB4.2 | Suspend Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are still associated |  | Pass | DRakestraw |  | Small Multis_250520_10:16:50_1
Outbound 1 | Multis Picking | OB4.2 | End Work Group | User is able to back out of the wave and complete it at a later time, the pick wave and user are not associated anymore |  | Pass | DRakestraw |  | Small Multis_250520_10:16:50_1
Outbound 1 | Multis Picking | OB4.2 | Wave and pick an item that is serial tracked | User is prompted for Serial Number after selecting the quantity |  | Ready to Test | DRakestraw |  | See issue above with single order picking
Outbound 1 | Multis Picking | OB4.2 | Wave and pick an item that is lot tracked | User is prompted for Lot Number after selecting the quantity |  | Ready to Test | DRakestraw |  | See issue above with single order picking
Outbound 1 | Multis Picking | OB4.2 | Wave and pick an item that is exp date tracked | User is prompted for Exp Date after selecting the quantity |  | Ready to Test | DRakestraw |  | See issue above with single order picking
Outbound 1 | Multis Picking | OB4.2 | Wave an exception repick wave. Select the pick wave and select "Summary" | User is given the bin associated with the stock previously picked |  | Ready to Test | DRakestraw |  | Exception Repicks_250520_15:09:06_1 I completed the repick with this one, but I used the exception repick, I wasn't sure where to find a suspended task for example, not sure if that's what this line was intended to address.
Outbound II | Multis Packing | OB 5.2 | Enter wrong bin | Error message displays - The container [x] could not be found. | REACT Team | Pass | GBregu |  | The container [23] could not be found.
Outbound II | Multis Packing | OB 5.2 | Enter a bin that has no items in it | There are no items to pack and User should receive error message | REACT Team | Pass | GBregu |  | There are no items to pack. MITCHLPN013 & MitchLPN0048
Outbound II | Multis Packing | OB 5.2 | Enter a bin that does have stock | User is brought to 'Items in Order' Screen. LPN we are packing displays at the top of the screen | REACT Team | Pass | GBregu
Outbound II | Multis Packing | OB 5.2 | Select 'Pack Remainder' | Should not need to scan any items and user should be brought to the container dimension screen | REACT Team | Pass | GBregu
Outbound II | Multis Packing | OB 5.2 | Select 'Ship' without packing any items | User will receive error that says you need to pack items before shipping container | REACT Team | Pass | GBregu
Outbound II | Multis Packing | OB 5.2 | Select 'Ship' after packing any item from the items in order screen | User will be brought to the container dimenstion screen, after dimensions are inputted or carton is selected, user should be able to pack box successfully and then is returned to item in container screen to pack additional items, shipment should be created for that bin with status of "Shipped" | REACT Team | Pass | GBregu |  | VC2RLXIC shipped 390164160888 order: RHEATEST8
Outbound II | Multis Packing | OB 5.2 | Select 'Back' | User is brought back to scan container screen | REACT Team | Pass | GBregu
Outbound II | Multis Packing | OB 5.2 | Select 'Start new bin' without having item selected | User will get error to pack at least one item before starting new bin | REACT Team | Pass | GBregu
Outbound II | Multis Packing | OB 5.2 | Select 'Start new bin' with item selected | User will be brought to container dimension, once dimensions are entered or carton is selected, user will be brought back to items in container to pack items in new bin | REACT Team | Pass | GBregu
Outbound II | Multis Packing | OB 5.2 | Enter an item not in the container/ items in order screen | The item could not be found on this order | REACT Team | Pass | GBregu
Outbound II | Large Order Packing | OB 5.1 | Enter wrong bin | Error message displays in Handheld - 'Container [X] could not be found' | REACT Team | Pass | GBregu
Outbound II | Large Order Packing | OB 5.1 | Enter a bin that has no items in it | There are no items to pack and User should receive error message | REACT Team | Pass | GBregu
Outbound II | Large Order Packing | OB 5.1 | Enter a bin that does have stock | User is brought to 'Items in Order' Screen. LPN we are packing displays at the top of the screen | REACT Team | Pass | GBregu
Outbound II | Large Order Packing | OB 5.1 | Select 'Pack Remainder' | Should not need to scan any items and user should be brought to the container dimension screen | REACT Team | Pass | GBregu
Outbound II | Large Order Packing | OB 5.1 | Select 'Ship' without packing any items | User will receive error that says you need to pack items before shipping container | REACT Team | Pass | GBregu
Outbound II | Large Order Packing | OB 5.1 | Select 'Ship' after packing any item from the items in order screen | User will be brought to the container dimenstion screen, after dimensions are inputted or carton is selected, user should be able to pack box successfully and then is returned to item in container screen to pack additional items, shipment should be created for that bin with status of "Shipping" | REACT Team | Ready to Test | GBregu
Outbound II | Large Order Packing | OB 5.1 | Select 'Back' | User is brought back to scan container screen | REACT Team | Ready to Test | GBregu
Outbound II | Large Order Packing | OB 5.1 | Select 'Start new bin' without having item selected | User will get error to pack at least one item before starting new bin | REACT Team | Ready to Test | GBregu
Outbound II | Large Order Packing | OB 5.1 | Select 'Start new bin' with item selected | User will be brought to container dimension, once dimensions are entered or carton is selected, user will be brought back to items in container to pack items in new bin | REACT Team | Ready to Test | GBregu
Outbound II | Large Order Packing | OB 5.1 | Enter an item not in the container/ items in order screen | The item could not be found on this order | REACT Team | Ready to Test | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container - Scan/Enter container with mis-matching pick details | Error message displays in Deposco UI: Container [x] cannot be packed due to an error in picking. Items with Stock Units and not matching Pick Details: | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container - Scan/Enter container with no stock units | Error message displays in Deposco UI - Error scanning the container x | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container - Scan/Enter container with correct pick details | User is brought to items screen. This displays all the items from the order associated with scanned container | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container items screen - Scan/Enter item that doesn't exist | Error message displays in Deposco UI - [x] not found in system. Check the order and ensure you are packing the correct item and quantity. | REACT Team | Pass | GBregu |  | Order ID :609399
Outbound II | Pack from Container | OB 5.3 | Pack from Container items screen - Scan/Enter item not in the order associated with container | Error message displays in Deposco UI - [x] not found in container. Check the order and ensure you are packing the correct item and quantity. | REACT Team | In Progress | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container items screen - Scan/Enter SERIAL TRACKED item in items screen associated with order container | User will be prompted to enter serial number matching SKU before confirming item pack process | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container items screen - Scan/Enter NON-SERIAL TRACKED item in items screen associated with order container | Should be prompted to enter quantity if more than one unit is in container | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container items screen - Scan/Enter LOT tracked items in items screen asssociated with order container | Should be asked for the Lot Number after you can the item | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container - Scan/Enter container that does not exist | Error message displays in Deposco UI - Container [x] not found in the system. Scan a valid container number. | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container - Scan/Enter container that contains 'Ready to Ship' items | After entering item, 'ready to ship' box pre-populates in Deposco UI with RTS dimensions and weight pre-populated | REACT Team | Pass | GBregu
Outbound II | Pack from Container | OB 5.3 | Pack from Container - Scan/Enter container that contains lot tracked items with missing lot number in pick details | Error message displays in Deposco UI - Item [x] is lot tracked, however pick detail is missing lot number information. The container cannot be packed, return items to the picking container. | REACT Team | Pass | GBregu
Outbound II | Build Pallet | OB 5.5 | Select LPN from list | User will be brought to Carton Selection Screen | REACT Team | Pass | GBregu
Outbound II | Build Pallet | OB 5.5 | Scan LPN that does not exist in system | User will be brought to Carton Selection Screen | REACT Team | Ready to Test | GBregu |  | need to scan LPN ? I did enter to built a pallet
Outbound II | Build Pallet | OB 5.5 | Scan LPN that is not type Pallet | User will receive an error for being the wrong container type | REACT Team | Ready to Test |  |  | need to scan
Outbound II | Build Pallet | OB 5.5 | Select Carton from "Carton LPNs in Location" List |  | REACT Team | Pass | GBregu
Outbound II | Build Pallet | OB 5.5 | Scan Carton into "Selected Carton LPNs" List |  | REACT Team | Ready to Test
Outbound II | Build Pallet | OB 5.5 | Scan Carton not in Source Location | User will receive an error and be asked to move carton into source location | REACT Team | Ready to Test
Outbound II | Build Pallet | OB 5.5 | Select Finish | If User selected a previously existing pallet, the pallet should now have inner containers with the name of the cartons the user added If the User scanned a pallet that did not previously exist, a new container should be created with type Palllet and number scanned, and it should have inner containers with the names of the cartons the user added | REACT Team | Pass | GBregu |  | LPNgb // Inner containers NMBC5NQH & yy
Outbound II | Assign Trips to Container | OB 5.4 | Select Shipping Door | User will be brought to "Pallets Assigned to Trip" Screen | REACT Team | Needs Info | GBregu |  | Multiple shipping doors
Outbound II | Assign Trips to Container | OB 5.4 | Scan Pallet to Trip and Enter weight | User should see pallet added to the "Pallets" List with the weight and number of inner cartons on it | REACT Team | Ready to Test
Outbound II | Assign Trips to Container | OB 5.4 | Scan Container to Trip (Type being shipping or transient) and Enter Weight | User should see pallet added to the "Pallets" List with the weight and number of inner cartons on it | REACT Team | Ready to Test
Outbound II | Assign Trips to Container | OB 5.4 | Select Pallet in Pallet List | User will see the pallet removed from the pallet list | REACT Team | Ready to Test
Outbound II | Assign Trips to Container | OB 5.4 | Select Back after Adding pallets to trip, and select same shipping door | User should be brought back to shipping door screen, once they seelect the same shipping door, they should see the pallets they already added still remain in Pallet list | REACT Team | Ready to Test
Outbound II | Assign Trips to Container | OB 5.4 | Select Close Trip | User will be brought to Custom Details Input Screen to fill in trip information | REACT Team | Ready to Test
Outbound II | Assign Trips to Container | OB 5.4 | Close trip without added all the containers associated with an order | User will receive an error (after custom detail screen) prompting them with the missing container numbers | REACT Team | Ready to Test
Outbound II | Rate Shopping | OB 6.1 | Verify Rate Shop Profiles | Please go to Rate Shop Profile v2 entity and verify the profile and criteria is correct for each rule | REACT Team | Pass | GBREGU |  | I cannot update the shipping
Outbound II | Rate Shopping | OB 6.1 | Pack Order that should be Rate Shopped | After packed, "Ship Rate Quote" entity should have rows on the order | REACT Team | Pass | GBREGU |  | 612884 test case
Outbound II | Void Shipment | OB 7.1 | Enter Shipment number, Tracking Number or Order Number | Should receive message with container numbers that have been rolled back, Shipment status should be "Rolled Back" and shipping status on Order will go back to "Not Shipped" | REACT Team | Ready to Test
Outbound II | Rollback Order after Picking | OB 7.1 | Scan LPN | User will be taken to Select PickDetail Screen | REACT Team | Ready to Test
Outbound II | Rollback Order after Picking | OB 7.1 | Select Item and Next | User will be prompted to enter quantity to cancel | REACT Team | Ready to Test
Outbound II | Rollback Order after Picking | OB 7.1 | Select or Scan Location Number | User will be brought back to PickDetail Selection screen (if more items) and Order will go into backordered status | REACT Team | Ready to Test
Outbound II | Reset Sales Order | OB 7.1 | Navigate to Admin> 'Reset Sales Order' from Handheld menu. Enter the order number for sales order to be reset. The sales order has already completed POI and been released to a wave | Message displays in HH: 'Successfully reset order [x]'. The Pick wave that was associated with this order has now been dropped. The pick wave still exists, but goes to 'Planned' status and the resetted order is no longer on the wave. | REACT Team | Ready to Test
Outbound II | Reset Sales Order | OB 7.1 | Navigate to Admin> 'Reset Sales Order' from Handheld menu. Enter the order number for sales order to be reset. The sales order is NOT on a wave | Message displays in HH: 'Successfully reset order [x]'. Order status goes from 'Released' to 'New' | REACT Team | Ready to Test

## Test Cases - End to End
REACT End to End Test Cases |  | Category | % Complete
|  | Inbound | 0%
|  | Outbound | 0%
|  | Inventory Management | 0%
|  | TOTAL | 42.5%
Category | Scenario | Status | Team | Owner | Test Data | Notes
Inbound
Inbound | Receive PO full | Ready to Test | REACT
Inbound | Receive Partial PO | Ready to Test | REACT
Inbound | Unreceive full PO | Ready to Test | REACT
Inbound | Unrecieve partial PO | Ready to Test | REACT
Inbound | Receive a PO with PO where the LPN is specified (LPN) | Ready to Test | REACT
Inbound | Receive a PO with PO where the LPN is not specified (Item) | Ready to Test | REACT
Inbound | Putaway containers to an LPN location | Ready to Test | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Inbound |  | Hold | REACT
Outbound
Outbound | Fulfill "large" orders | Ready to Test | REACT
Outbound | Fulfill "Pallet" orders | Hold | REACT
Outbound | Fulfill multi unit orders | Ready to Test | REACT
Outbound | Fulfill Hazmat orders | Hold | REACT
Outbound | Fulfill domestic orders | Ready to Test | REACT
REACT
REACT
REACT
REACT
REACT
REACT
REACT
REACT
REACT
Inventory Management
Inventory Management | Perform scheduled cycle counts by location | Ready to Test | REACT
Inventory Management | Perform scheduled cycle counts by item | Ready to Test | REACT
Inventory Management | Perform on demand cycle counts by location | Ready to Test | REACT
Inventory Management | Perform scheduled replenishment tasks | Ready to Test | REACT
Inventory Management | Perform on demand replenishment tasks | Ready to Test | REACT
Inventory Management | Over-replenish | Ready to Test | REACT
Inventory Management | Perform exception during replenishment | Ready to Test | REACT
Integrations
NetSuite - Inventory Adjustment | Send an adjustment for a serial tracked item | Pass | DEP/REACT |  | DSID: 3884
NetSuite - Inventory Adjustment | Send an adjustment for a lot tracked item | Pass | DEP/REACT |  | DSID: 3893
NetSuite - Inventory Adjustment | Send an adjustment for a non tracked item | Pass | DEP/REACT |  | DSID: 3894
NetSuite - Inventory Transfer | Send a transfer for a serial tracked item | Pass | DEP/REACT |  | DSID: 3895
NetSuite - Inventory Transfer | Send a transfer for a lot tracked item | Pass | DEP/REACT |  | DSID: 3896
NetSuite - Inventory Transfer | Send a transfer for a non tracked item | Pass | DEP/REACT |  | DSID: 3897
NetSuite - Purchase Order | Bring in a PO with serial tracked items | Pass | DEP/REACT |  | DSID: 3914 (257896)
NetSuite - Purchase Order | Bring in a PO with lot tracked items | Pass | DEP/REACT |  | DSID: 3905 (257915)
NetSuite - Purchase Order | Bring in a PO with non tracked items | Pass | DEP/REACT |  | DSID: 3919 (257257)
NetSuite - PO Reciepts | Send back receipts to NS for serial tracked items | Pass | DEP/REACT |  | DSID: 3915 (257896)
NetSuite - PO Reciepts | Send back receipts to NS for lot tracked items | Pass | DEP/REACT |  | DSID: 3906 (257915)
NetSuite - PO Reciepts | Send back receipts to NS for non tracked items | Pass | DEP/REACT |  | DSID: 3986 (257978)
NetSuite - PO Reciepts | Send back partial receipts to NS for non tracked items | Pass | DEP/REACT |  | DSID: 3984 (257978)
NetSuite - Sales Order | Bring in a CO with serial tracked items | Ready to Test | DEP/REACT
NetSuite - Sales Order | Bring in a CO with lot tracked items | Pass | DEP/REACT |  | DSID: 3926, Look into shipfrom facility
NetSuite - Sales Order | Bring in a CO with non tracked items | Ready to Test | DEP/REACT
NetSuite - Ship Notice | Send back ship notice to NS for serial tracked items | Pass | DEP/REACT |  | DSID: 4004
NetSuite - Ship Notice | Send back ship notice to NS for lot tracked items | Pass | DEP/REACT |  | DSID: 3930
NetSuite - Ship Notice | Send back ship notice to NS for non tracked items | Fail | DEP/REACT |  | DSID: 3996 | Not bringing cost over to the sales order
NetSuite - Ship Notice | Send back a partial ship notice | Pass
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test
Ready to Test

## WHWDV GoNo-Go Decision
REACT Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 76.5
Deposco Setup | Label Printers | 10 |  | REACT | 100% | 10 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - One label printer on network, three missing. One that is on the network is malformatted
Deposco Setup | Document Printers | 10 |  | REACT | 100% | 10 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 |  | REACT | 100% | 10 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - React to validate
Deposco Setup | End users | 10 |  | REACT | 100% | 10 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live | 2025-06-20 | 7/7 - 3 end users in Woodenville created in system
Deposco Setup | Printer Details | 10 |  | REACT | 100% | 10 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - One label printer on network, three missing. One that is on the network is malformatted
Deposco Setup | Printer Resources | 10 |  | REACT | 100% | 10 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - Receiving setup, Pack Stations Missing
Deposco Setup | Printer Assignments | 10 | Y | REACT | 25% | 2.5 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - Receiving setup, Pack Stations Missing
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 50% | 5 | Have all Go-Live Critical issues from the task tracker been resolved? |  |  | 7/7 - No open issues high/critical but several open tasks high/critical.
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 |  | DEP | 90% | 9 | Have all jobs have been scheduled and enabled? |  |  | 7/7 - Scheduled jobs setup but not enabled. Will confirm at go live and will start with manual runs.
| Warehouse Prep | 40 |  |  |  | 19
Warehouse Prep | Location Labels | 10 |  | REACT | 90% | 9 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT |  | 6/4 - a few that may need QR codes, testing higher up locations with scanner 6/19 - need to label carts, bins, and anything else to help us move fast (tackle during onsite UAT)
Warehouse Prep | Container Labels | 10 | Y | REACT | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT |  | 6/4 - derek & mark to set this up 6/19 - tackle during onsite UAT
Warehouse Prep | Inventory Labels | 10 | Y | REACT | 0% | 0 | Are all inventory units labeled and scannable? | Recommend 100% by UAT |  | 6/4 - part of receiving process will be to place a label on these items, will happen over time 6/19 - tackle during onsite UAT - need printer to be live - will create LPNs and labels over time as inventory turns.
Warehouse Prep | Network Connectivity | 10 |  | REACT | 100% | 10 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT |  | 6/4 - two wireless access points to be installed
| Standard Operating Procedure Documentation | 65 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Kitting (Kit To Stock) | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | LTL Shipping (Wholesale) | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 28
Training & Testing | Test Case Scenarios Definition | 10 |  | DEP / REACT | 100% | 10 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and REACT to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | REACT | 40% | 4 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT |  | 7/7 - Requiring re-work post UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | REACT | 40% | 4 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT |  | 7/7 - Requiring re-work post UAT
Training & Testing | Supervisor/Administrator Training | 10 |  | REACT | 100% | 10 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT |  | 7/7 - Requiring re-work post UAT
Training & Testing | End-user Training | 10 | Y | REACT | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT |  | 7/7 - Pending above
| Production Master Data | 50 |  |  |  | 18
Master Data | Cutover Inventory Validation | 10 | Y | REACT | 10% | 1 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload into one location via Data Exchange, move them into locations over time. 6/19: discuss while onsite for UAT 7/7: Deposco to provide recommendation by EOW
Master Data | Items and Packs | 10 | Y | REACT | 50% | 5 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Pull into production via integration. How do we create packs from NS detail? 7/7: Items good from NS. Packs need to be uploaded via Data Exchange.
Master Data | Locations and Zones | 10 | Y | REACT | 50% | 5 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: anything on the ground is picakable, anything in a rack is storage/bulk, storage locations are pickable by LPN/pallet, replen to a pickable location (preferably in the same HB or closest HB) 7/7: Still some outstanding locations to be uploaded by Mark.
Master Data | Containers | 10 | Y | REACT | 50% | 5 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange 7/7: Should we allow LPN creation during picking/putaway by scanning existing container?
Master Data | Kit/Component Relationships | 0 | Y | REACT | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | REACT | 20% | 2 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / REACT | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date. |  | 2025-07-11 | 6/19: develop while onsite for UAT. 7/11: Deposco to deliver known cutover steps by EOW. React to add steps early next week as needed.
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 45
Interfaces - Imports to Deposco | Carton Types Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT |  | 6/19 - done in UA, need to congifure in production
Interfaces - Imports to Deposco | Items/Packs Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT |  | 6/19 - Create case and pallet upload template for upload into Deposco
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | REACT | 100% | 5 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Item Vendor Upload | 0 |  | REACT | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 80 |  |  |  | 62
Integrations with Deposco | Netsuite - Item - Pull | 10 |  | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Trading Partner - Pull | 0 | Y | REACT | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Sales Order - Pull | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order - Pull | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Customer Return - Pull | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Ship Notice - Push | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order Receipt - API Pull from DEP | 10 | Y | REACT | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 |  | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 0 |  | REACT | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 | Y | REACT | 80% | 8 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT |  | 7/7: Hazmat issues in task tracker
Integrations with Deposco | FedEx - Get Rate Shop Request | 0 |  | REACT | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 40 |  |  |  | 32
Reports and Labeling | Shipping Label | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Packing Slip Report | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: work with Brie's team while onsite for UAT to complete this work.
Reports and Labeling | Location Label | 0 |  | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Item Label | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Cartonized Container Label | 0 |  | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Carton Type Label | 0 | Y | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Container Label | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Generic BOL Report | 0 | Y | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | DEP / REACT | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 290.5
| Total Possible Score: | 480
| Total Percentage: | 60.52%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## WHCOL GoNo-Go Decision
REACT Go vs No-Go Decision Evaluation
Category | Detail | Weight | Critical? | Owner | % Cmp | Score | Analysis | Timeline | Due Date | Comments
| Deposco Setup | 90 |  |  |  | 0
Deposco Setup | Label Printers | 10 | Y | REACT | 0% | 0 | Are all label printers procured and setup on the network? Are printer supplies on-hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - One label printer on network, three missing. One that is on the network is malformatted
Deposco Setup | Document Printers | 10 | Y | REACT | 0% | 0 | Are all document printers procured and setup on the network? Supplies on hand? Settings correct? Windows test prints successful? | Recommend 50%+ by UAT Recommend 100% by Go Live
Deposco Setup | Scanners and Handheld Devices | 10 | Y | REACT | 0% | 0 | Are all scanners procured? Deposco app installed? Auto-send features enabled? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - React to validate
Deposco Setup | End users | 10 | Y | REACT | 0% | 0 | Are all end users configured with user profiles in the system? Logged in successfully? | Recommend 50%+ by UAT Recommend 100% by Go Live | 2025-06-20 | 7/7 - 3 end users in Woodenville created in system
Deposco Setup | Printer Details | 10 | Y | REACT | 0% | 0 | Are all printer details configured in Deposco and printer validations passed? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - One label printer on network, three missing. One that is on the network is malformatted
Deposco Setup | Printer Resources | 10 | Y | REACT | 0% | 0 | Are all print stations setup in Deposco as resources? Are users assigned appropriate resources? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - Receiving setup, Pack Stations Missing
Deposco Setup | Printer Assignments | 10 | Y | REACT | 0% | 0 | Are all reports assigned to printers and resources? | Recommend 50%+ by UAT Recommend 100% by Go Live |  | 7/7 - Receiving setup, Pack Stations Missing
Deposco Setup | Critical and High Issues Resolved A) B) | 10 | Y | DEP | 0% | 0 | Have all Go-Live Critical issues from the task tracker been resolved? |  |  | 7/7 - No open issues high/critical but several open tasks high/critical.
Deposco Setup | Scheduled Jobs A) Scheduler Tasks - Build and Release Wave - Create Replenishment Task - Create Inv Adjustments - Create Cycle Counts by Item - Create Cycle Counts by Location | 10 | Y | DEP | 0% | 0 | Have all jobs have been scheduled and enabled? |  |  | 7/7 - Scheduled jobs setup but not enabled. Will confirm at go live and will start with manual runs.
| Warehouse Prep | 40 |  |  |  | 0
Warehouse Prep | Location Labels | 10 | Y | REACT | 0% | 0 | Are all locations, receiving areas, shipping docks, etc. labeled and scannable? | Recommend 100% by UAT |  | 6/4 - a few that may need QR codes, testing higher up locations with scanner 6/19 - need to label carts, bins, and anything else to help us move fast (tackle during onsite UAT)
Warehouse Prep | Container Labels | 10 | Y | REACT | 0% | 0 | Are all carts and bins for moving of inventory procured, labeled, and scannable? | Recommend 100% by UAT |  | 6/4 - derek & mark to set this up 6/19 - tackle during onsite UAT
Warehouse Prep | Inventory Labels | 10 | Y | REACT | 0% | 0 | Are all inventory units labeled and scannable? | Recommend 100% by UAT |  | 6/4 - part of receiving process will be to place a label on these items, will happen over time 6/19 - tackle during onsite UAT - need printer to be live - will create LPNs and labels over time as inventory turns.
Warehouse Prep | Network Connectivity | 10 | Y | REACT | 0% | 0 | Is the internet connectivity strong and cover all necessary scan areas? | Recommend 100% by UAT |  | 6/4 - two wireless access points to be installed
| Standard Operating Procedure Documentation | 65 |  |  |  | 0
SOP Documents | Receiving/Unreceiving | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Create Customer Returns | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Putaway | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Cycle Counting | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Adjust Inventory | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Kitting (Kit To Stock) | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Picking | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Picking | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Singles Packing | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Multis Packing | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | LTL Shipping (Wholesale) | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Exceptions in Packing | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
SOP Documents | Customer Order Management | 5 |  | REACT | 0% | 0 | Have SOP's been written? Printed or shared with relevant team members? | Recommend 80% by UAT Recommend 100% by Go Live
| Training & Testing | 50 |  |  |  | 0
Training & Testing | Test Case Scenarios Definition | 10 | Y | DEP / REACT | 0% | 0 | Have all unit test cases and end-to end test cases been created and documented for the solution? | Recommend 100% by Design Doc Signature |  | DEP to deliver baseline scenarios and REACT to add/remove test cases as needed for their business.
Training & Testing | Unit Test Case Completion - Inbound - Inventory Management - Outbound - Integrations | 10 | Y | REACT | 0% | 0 | Have all unit test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT |  | 7/7 - Requiring re-work post UAT
Training & Testing | End to End Test Case Completion - Inbound - Inventory Management - Outbound All test cases performed with full integration involvement as will be in production. | 10 | Y | REACT | 0% | 0 | Have all end-to-end test cases passed or been marked invalid? Has test data been provided? | Recommend 100% by UAT |  | 7/7 - Requiring re-work post UAT
Training & Testing | Supervisor/Administrator Training | 10 | Y | REACT | 0% | 0 | Have all supervisors been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 90% by UAT |  | 7/7 - Requiring re-work post UAT
Training & Testing | End-user Training | 10 | Y | REACT | 0% | 0 | Have all end-users been trained and do they understand the process flow? Have they been informed of any procedure or policy changes? | Recommend 100% by end of UAT |  | 7/7 - Pending above
| Production Master Data | 50 |  |  |  | 7
Master Data | Cutover Inventory Validation | 10 | Y | REACT | 0% | 0 | Is there a plan in place to aquire accurate inventory levels in production at cutover? Has the plan been tested? | Recommend 100% by end of UAT |  | Options: Upload into one location via Data Exchange, move them into locations over time. 6/19: discuss while onsite for UAT 7/7: Deposco to provide recommendation by EOW
Master Data | Items and Packs | 10 | Y | REACT | 50% | 5 | Is there a plan in place to ensure all items are setup in production? All of the packs (units of measure) defined for each item? All UPC's for each item/pack? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Pull into production via integration. How do we create packs from NS detail? 7/7: Items good from NS. Packs need to be uploaded via Data Exchange.
Master Data | Locations and Zones | 10 | Y | REACT | 0% | 0 | Is there a plan in place to ensure all Locations and Zones are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: anything on the ground is picakable, anything in a rack is storage/bulk, storage locations are pickable by LPN/pallet, replen to a pickable location (preferably in the same HB or closest HB) 7/7: Still some outstanding locations to be uploaded by Mark.
Master Data | Containers | 10 | Y | REACT | 0% | 0 | Is there a plan in place to ensure all pallets, bins, and carts are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange 7/7: Should we allow LPN creation during picking/putaway by scanning existing container?
Master Data | Kit/Component Relationships | 0 | Y | REACT | 0% | 0 | Is there a plan in place to ensure all kit/component relationships are setup in production? Has the plan been tested and data validated? | Recommend 100% by end of UAT |  | Options: Copy from UA, Re-upload via Data Exchange, Re-pull via integration
Master Data | Menu Structures | 10 | Y | REACT | 20% | 2 | Have the appropriate menu levels been created for the different user groups and departments? Have they been validated to have the appropriate permissions for each job? | Recommend 100% by end of UAT |  | Options: Copy from UA, manually update in production
| Cutover Plan | 10 |  |  |  | 0
Cutover Plan | Cutover plan delivery | 10 | Y | DEP / REACT | 0% | 0 | Is the cutover plan developed including Deposco technical steps, operational decisions, cutover audit, and contingency plans? Need step by step for all technical data conversions along with assignee and expected completion date. |  | 2025-07-11 | 6/19: develop while onsite for UAT. 7/11: Deposco to deliver known cutover steps by EOW. React to add steps early next week as needed.
| Data Exchange Interfaces - Imports/Exports with Deposco | 45 |  |  |  | 45
Interfaces - Imports to Deposco | Carton Types Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Locations/Zones Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT |  | 6/19 - done in UA, need to congifure in production
Interfaces - Imports to Deposco | Items/Packs Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT |  | 6/19 - Create case and pallet upload template for upload into Deposco
Interfaces - Imports to Deposco | Inventory Upload | 5 |  | REACT | 100% | 5 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Item Vendor Upload | 0 |  | REACT | 0% | 0 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
Interfaces - Imports to Deposco | Container Upload | 10 |  | REACT | 100% | 10 | Is the Data Exchange accurate and does it meet production needs? | Recommend 100% by UAT
| Integrations with Deposco | 80 |  |  |  | 62
Integrations with Deposco | Netsuite - Item - Pull | 10 |  | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Trading Partner - Pull | 0 | Y | REACT | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Sales Order - Pull | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order - Pull | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Customer Return - Pull | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Ship Notice - Push | 10 | Y | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | Netsuite - Purchase Order Receipt - API Pull from DEP | 10 | Y | REACT | 0% | 0 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Shipping Label | 10 |  | REACT | 90% | 9 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | UPS - Get Rate Shop Request | 0 |  | REACT | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
Integrations with Deposco | FedEx - Get Shipping Label | 10 | Y | REACT | 80% | 8 | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT |  | 7/7: Hazmat issues in task tracker
Integrations with Deposco | FedEx - Get Rate Shop Request | 0 |  | REACT | 0% |  | Is the interface accurate and does it meet production needs? | Recommend 90% by UAT
| Reports and Labeling | 40 |  |  |  | 24
Reports and Labeling | Shipping Label | 10 | Y | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Packing Slip Report | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: work with Brie's team while onsite for UAT to complete this work.
Reports and Labeling | Location Label | 0 |  | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Item Label | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Cartonized Container Label | 0 |  | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Carton Type Label | 0 | Y | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Container Label | 10 | Y | REACT | 80% | 8 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
Reports and Labeling | Generic BOL Report | 0 | Y | REACT | 0% | 0 | Does the report print from the application accurately and timely? | Recommend 90% by UAT |  | 6/19: config while onsite for UAT to complete this work.
| Contingency Plans | 10 |  |  |  | 10
Contingency Plans | Contingency Plans | 10 |  | DEP / REACT | 100% | 10 | Is there a backwards migration strategy planned in case of emergency rollback?
| Total Weighted Score: | 148
| Total Possible Score: | 480
| Total Percentage: | 30.83%
| UAT Recommendation: |  | To achieve a "YES" UAT onsite recommendation
| Go Live Recommendation: |  | To achieve a "YES" go-live recommendation, two things must occur: (1) all items with a weight of 10 must have a % complete of at least 90%, and (2) the Total Percentage score at the bottom must have a % complete of at least 90%. Note, even if these conditions are met, if the score is not 100%, there could be issues when going live.

## Cutover Plan
REACT Cutover Plan
STEP | TITLE | DESCRIPTION | COMPLETED | TEAM | Owner | DATE
1 | Create Production Environment | Create ticket to stand up prod environment | FALSE | DEP
2 | Set up Shipping Accounts | Set up Shipping accounts in Production environment | FALSE | REACT
3 | Set up Netsuite | Set up Netsuite Instances in Production environment | FALSE | REACT
4 | Test Item Pull | Ensure all items come into Deposco as expected | FALSE | DEP/REACT
5 | Test Order Pull | Create a test order in Netsuite and bring order into Deposco | FALSE | DEP/REACT
6 | Test ShipNotice Push | Fulfill order in Deposco and ensure ship notice is sent to Netsuite | FALSE | DEP/REACT
7 | Test Inventory Push | Send an inventory push from Deposco to Netsuite | FALSE | DEP/REACT
8 | Test UPS Label | Fulfil an order using all UPS shipping services | FALSE | DEP/REACT
9 | Test STAMPS Label | Fulfil an order using all STAMPS shipping services | FALSE | DEP/REACT
10 | Master Data Check - Items | Look through items in production environment | FALSE | REACT
11 | Master Data Check - Item UPC | Look through item UPCs in production environment | FALSE | REACT
12 | Master Data Check - Item Vendor | Look through item vendor table in production environment | FALSE | REACT
13 | Master Data Check - Packs | Look through Packs in production environment, ensure every pack has dimensions | FALSE | REACT
14 | Master Data Check - Locations | Look through Locations in production environment, ensure every pack has dimensions | FALSE | REACT
15 | Master Data Check - Storage Records | Look through Storage Records in production environment, ensure every pack has dimensions | FALSE | REACT
16 | Review Scheduler Frequencies | Go through each scheduler and confirm cron is as expected | FALSE | DEP/REACT
17 | Cut Off Orders from Current System | Shipping Labels are printed and end of day process is done to have accurate inventory | FALSE | DEP/REACT
18 | Inventory Push to Netsuite | Inventory is pushed to Netsuite | FALSE | DEP/REACT
19 | Inventory Push to Deposco | Inventory is pushed to Deposco | FALSE | DEP/REACT
20 | Turn on Order Pull in Deposco | Turn on scheduler for both Netsuite Instances to bring in orders | FALSE | DEP/REACT
21 | Upload Stock | Once fulfillment is finalized, Upload current stock using DE | FALSE | REACT
22 | Validate Stock | Smoke test a few locations to make sure stock is accurate | FALSE | REACT
23 | Turn on Ship Notice Push | Turn on Ship Notice Push | FALSE | DEP
24 | Turn on Inventory Sync Push | Turn on Inventory Sync Push | FALSE | DEP
25 | Validate Each Handheld | Ensure each handheld is working in the Deposco app and is tabbing as expected | FALSE | REACT
26 | Validate Each Pack Station | Ensure each pack station is able to log into Depsoco and scanners are working as expected | FALSE | REACT
27 | Smoke Test - Waving | Wave a group of orders together, ensure everything behaves as expected | FALSE | DEP/REACT
28 | Smoke Test - Singles Picking | Pick a singles wave, ensure everything behaves as expected | FALSE | DEP/REACT
29 | Smoke Test - Multis Picking | Pick a Multis wave, ensure everything behaves as expected | FALSE | DEP/REACT
30 | Smoke Test - Singles Packing | Pack a singles wave, ensure everything behaves as expected | FALSE | DEP/REACT
31 | Smoke Test - Multis Packing | Pack a Multis wave, ensure everything behaves as expected | FALSE | DEP/REACT
32 | Smoke Test - International Packing | Pack an international order, order is shipped outside system | FALSE | DEP/REACT
33 | Smoke Test - Insured Packing | Pack an insured order, High Value report is printing outside system successfully | FALSE | DEP/REACT
34 | Smoke Test - Priority Packing | Pack a prioirty shipping order, ensure everything behaves as expected | FALSE | DEP/REACT
35 | Smoke Test - Hazmat Packing | Pack a hazmat item, ensure everything behaves as expected | FALSE | DEP/REACT
36 | Smoke Test - Receiving PO | Receive a typical PO with loose stock using Handheld and putaway according to recommendations | FALSE | DEP/REACT
37 | Smoke Test - Receiving Transfer Order | Receive a transfer order using handheld and putaway accoridng to recommendations | FALSE | DEP/REACT
38 | Smoke Test - Migrate from SysPro to Deposco | Complete a migration of serial numbers, lot numbers, and items from SysPro to Deposco | FALSE | DEP/REACT
39 | Smoke Test - Receive Inbound Shipment | Receive an inbound shipment by LPN and putaway according to recommendations | FALSE | DEP/REACT

## Future ItemsParking Lot
REACT Future Phase Initiatives
TITLE | DESCRIPTION | Date Opened | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEP Comments | REACT Comments
COC Image at Receiving | REACT would like a way to capture a COC document at receiving and send it to NS | 2025-02-19
Unipoint Integration | Potential Unipoint integration for quality management | 2025-02-19
Order Consolidation | Customer orders two orders within a few hours ensure they are on the same truck | 2025-02-20 |  |  |  |  | Not a requirement happens very infrequently
MHE/Packing Station Setup | REACT would like to potentially look at MHE options for their Columbus facility. | 2025-02-20
Future Order Functionality | To set planned release date in the future | 2025-03-10
DOM | Split fulfillments, automated sourcing etc. | 2025-03-10