## Mavenlink
Workspace | User Name | Performed | Task: Name | Time Entry: Notes | Hours | Weekending Date | Total Hours by Process
WTC001: Implementation - 001 - UPS Bright Suite | Claire Solomon | 2024-05-06 | Administration | Account setup | 1 | 2024-05-11
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-15 | Professional Services & Customer Success Intro Call | Internal Intro Call | 0.5 | 2024-05-18
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-28 | Administration | WTC Cap Map and Slide Review | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-28 | Administration | WTC Onside Design Agenda | 1 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-28 | Professional Services & Customer Success Intro Call | WTC Intro Call | 0.75 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-30 | Administration | Desing Booking Travel | 0.25 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-30 | Internal Meeting | WTC Meeting w Josiah and Keegan | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-30 | Receiving Build | Design Config and data prep | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-30 | Receiving Build | New Receiving Workflow config and test to use instead of old receiving process | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-31 | Put-Away | Putaway Processes initial set up | 0.66667 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-31 | Cycle Counting | Cycle Counting Initial Set up | 0.58333 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-05-31 | Replenishment | Replenishment Initial set up | 0.75 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-03 | Administration | WTC Demo email communication | 0.16667 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-03 | Client Meeting | WTC Demo General UI | 0.75 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-04 | Receiving Build | Receiving config w Josiah | 1 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-04 | Onsite Design | Design | 8 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-04 | Onsite Design | Master Design Document write and flow charts creation | 0.5 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-05 | Onsite Design | Design | 8 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-05 | Master Data | Master Data Pack cleanup | 0.75 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-06 | Onsite Design | Master Design Document modification + revision | 1 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-07 | Client Meeting | API call WTC | 0.5 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-10 | Write Functional Flow | MDD Document POI and Automations | 0.33333 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-11 | Write Functional Flow | MDD Cleanup | 0.16667 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-12 | Internal Meeting | Cubiscan Meeting WTC | 0.58333 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-17 | Internal Meeting | cubiscan call | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-18 | Internal Meeting | Internal Meeting | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-20 | Client Meeting | Client meeting | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-06-25 | Internal Meeting | Internal meeting WTC | 0.25 | 2024-06-29
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-09 | Internal Meeting | Internal Meeting | 0.5 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-10 | Internal Design Review | Jonathan Coment Review | 0.16667 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-11 | Client Meeting | Client Meeting to Review MDD | 1.1667 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-16 | Internal Meeting | Internal Meeting | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-18 | Client Meeting | Client Meeting | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-18 | Receiving Build | Receiving + Putaway build + testing and validating test scenarios | 3 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-24 | Internal Meeting | Internal Meeting | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-26 | Cycle Counting | Cycle Count Configuration | 2 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-26 | Cycle Counting | Cycle Count run through w Sara | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-26 | Cycle Counting | Task Tracker unit cases creation | 0.25 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Daniel Stenger | 2024-07-30 | Internal Meeting | Internal Meeting | 0.5 | 2024-08-03
Total Hours by Resource
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-15 | Sales Transition | Internal sales transition call | 0.5 | 2024-05-18
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-28 | Administration | Reviewing capability map in preparation for transition call | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-28 | Professional Services & Customer Success Intro Call | Intro call with team | 0.75 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-30 | Internal Design Review | Reviewing design tasks with daniel and keegan | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-30 | Pick Wave Management Build | Setup batch and singles pick waves and test orders correctly assign to them | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-30 | Picking Build | Adjusting exception screens xaml and testing exceptions generate cycle counts | 0.25 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-30 | Picking Build | Run through batch and singles picking making adjustments to xaml and adding validations | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-30 | Deposco API Support (D1 ERP) | Collect and test all necessary payloads | 1 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-30 | Deposco API Support (D1 ERP) | Review integrations diagram and grab all payloads needed to sync correctly to Deposco | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-05-31 | Deposco API Support (D1 ERP) | Testing payload for invAdjustment and creating test data | 0.5 | 2024-06-01 | Hours by Week per Resource
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-03 | Orientation Training Sessions and Support | General ui demo | 0.75 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-03 | Write Functional Flow | Creating design doc | 1 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-03 | Packing/Shipping | Soft close packing and attc setup/testing | 1.5 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-04 | Write Functional Flow | Adding inbound section to design doc | 1.25 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-04 | Onsite Design | Onsite design | 8 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-05 | Onsite Design | Onsite design | 8 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-07 | Client Meeting | ERP Api sync with Dev team and John | 0.5 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-10 | Administration | Followup email with takeaway items | 0.25 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-10 | Write Functional Flow | Review inbound and inventory flows | 0.5 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-10 | Write Functional Flow | Writing outbound functional flow and diagrams | 3.25 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-10 | Outbound Order Management Build | Automations to set ecomm orders | 1 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-10 | Pick Wave Management Build | Adjusting ecomm pick wave profile and testing | 0.25 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-10 | Picking Build | Adding name details to the batchpicking screen and adjuting xaml | 0.75 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-11 | Write Functional Flow | Editing and refining design document | 1.5 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-11 | Picking Build | Validating sspicking and batchpicking screen flows do not overlap from name override and test staging validations | 1 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-12 | Internal Meeting | cubiscan meeting | 0.5 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-12 | Write Functional Flow | Cubiscan design flow and discovery | 1.25 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-17 | Internal Meeting | Cubiscan design review with Luke and Sudeep | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-17 | Deposco API Support (Cubiscan) | documentation/discovery on api and implementation | 2 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-18 | Internal Meeting | Weekly team sync | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-18 | Write Functional Flow | Refining cubiscan flow | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-19 | Deposco API Support (Cubiscan) | Testing container api's and cubiscan warehouse flows | 3.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-06-20 | Client Meeting | Weekly external team sync | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-08 | Administration | Cap map and design doc review / followups with team design review | 0.5 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-09 | Internal Meeting | Weekly internal team sync | 0.5 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-09 | Write Functional Flow | Functional flow replies/review | 0.25 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-11 | Functional Flow Review with Client | Reviewing design doc | 1.25 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-16 | Internal Meeting | Weekly team sync | 0.5 | 2024-07-20 | Hours per week
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-18 | Client Meeting | WTC weekly sync | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-18 | Initial Environment Setup | Printer documentation and print testing | 0.25 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-23 | Internal Meeting | Sync with keegan on cubiscan ticket | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-24 | Internal Meeting | Weekly team sync | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-24 | Deposco API Support (Cubiscan) | Cubiscan/container api testing and estimation ticket | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Josiah Ogier | 2024-07-25 | Client Meeting | Weekly sync with John | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-15 | Sales Transition | Deposco <> WTC Internal Transition | 0.5 | 2024-05-18
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-28 | Internal Meeting | R and R review with JO | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-28 | Current State Documentation | solution review | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-28 | Professional Services & Customer Success Intro Call | PROs intro | 1 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-28 | System Requirements | packing router review | 1 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-28 | Testing Support | EVO <> DEP: Testing Office Hours | 0.75 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-30 | Administration | travel plan creation for design and sending email | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-05-30 | Internal Meeting | WTC - Onsite Design R & Rs | 0.5 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-06-10 | Internal Design Review | design doc review | 1 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-06-11 | Internal Design Review | design doc review - cubiscan and MDD | 1.25 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-06-12 | Internal Design Review | WTC - Cubiscan Review | 0.5 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-06-19 | Internal Design Review | cubiscan design review | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-06-20 | Client Meeting | WTC - Weekly Status (External) | 0.25 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-09 | Internal Meeting | WTC - Weekly Status Internal | 0.5 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-10 | Internal Meeting | reviewing ticket -WTCSUP-1 | 0.5 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-11 | Client Meeting | WTC - Weekly Status (External) | 0.25 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-11 | Functional Flow Review with Client | review on call with client | 0.75 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-15 | Internal Meeting | WTCSUP-1 ticket review | 0.25 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-16 | Internal Meeting | WTC - Weekly Status Internal | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-18 | Client Meeting | weekly status external | 0.25 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-23 | Internal Meeting | WTC Cubiscan ticket review | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-25 | Client Meeting | WTC - Weekly Status (External) | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Keegan McGuire | 2024-07-30 | Internal Meeting | WTC - Weekly Status Internal | 0.5 | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Sara Kulkarni | 2024-07-29 | Training: Inventory Management | Worked on different cycle counting test cases in the WTC UA | 0.5 | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-05-14 | Administration | Meeting times for Sales Transition and PROs Intro for BizDev | 0.25 | 2024-05-18
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-05-15 | Sales Transition | Sales Transition | 0.5 | 2024-05-18
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-05-28 | Administration | Next Steps email to WTC team post Intro Call | 0.25 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-05-28 | Professional Services & Customer Success Intro Call | PROs intro | 0.75 | 2024-06-01
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-03 | Administration | Budget review WE 6/1 | 0.5 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-04 | Onsite Design | Day 1 Design | 8 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-05 | Onsite Design | Day 2 Design | 8 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-07 | Client Meeting | Integration kick off with ERP One | 0.5 | 2024-06-08
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-10 | Administration | Travel expenses submission | 0.25 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-11 | Administration | Orientation Tasks and ML updates | 1.5 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-14 | Administration | Budget review WE 6/8 | 0.5 | 2024-06-15
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-17 | Internal Meeting | Cubiscan review | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-18 | Internal Meeting | weekly internal | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-20 | Administration | Weekly deck prep | 0.75 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-20 | Client Meeting | Weekly status | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-21 | Administration | Budget Review WE 6/14 | 0.5 | 2024-06-22
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-06-25 | Internal Meeting | Weekly internal | 0.25 | 2024-06-29
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-01 | Administration | Budget Review WE 6/21 | 0.5 | 2024-07-06
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-01 | Administration | Budget Review WE 6/28 | 0.25 | 2024-07-06
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-09 | Internal Meeting | Weekly internal | 0.5 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-11 | Functional Flow Review with Client | MDD Review | 1 | 2024-07-13
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-15 | Administration | Budget Review WE 7/5 | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-16 | Internal Meeting | Weekly Status | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-18 | Administration | ML Updates and slide deck prep | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-18 | Client Meeting | weekly status | 0.5 | 2024-07-20
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-24 | Internal Meeting | RevOps review - Socket swap | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-24 | Internal Meeting | Weekly internal | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-25 | Administration | ML Updates and Slide updates | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-25 | Client Meeting | Weekly External | 0.5 | 2024-07-27
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-30 | Administration | Budget Review WE 7/12 | 0.5 | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-30 | Administration | Budget Review WE 7/19 | 0.5 | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-30 | Internal Meeting | Weekly internal | 0.5 | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Shayne Schmidt | 2024-07-31 | Administration | Budget Review WE 7/26 | 0.5 | 2024-08-03
Formulas:
Weekending Date = [Performed]+7-WEEKDAY([Performed])

## Sheet3
SOW Label
Project Management |  | Burn through 9/28 | SOW Totals | Remaining
Bright Warehouse | SOW Label | 0 | 682 | 682
Project Management | Project Management | 0 | 100 | 100
Orientation | Bright Warehouse | 0 | 146 | 146
Bright Warehouse | Orientation | 0 | 28 | 28
Bright Socket | Bright Socket | 0 | 80 | 80
Bright Socket | Design | 0 | 100 | 100
Project Management | Bright Performance | 0 | 24 | 24
Design | Go Live | 0 | 204 | 204
Orientation
Design
Project Management
Orientation
Bright Warehouse
Design
Orientation
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Warehouse
Orientation
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Performance
Orientation
Bright Socket
Orientation
Bright Warehouse
Bright Warehouse
Bright Warehouse
Bright Warehouse
Design

## SX Hours
[11 empty] | 136.58 | ML | 422.744 | 682 | 259.256
Engagement ShortName | Activity | Task | Resource | Entry Date | Factored Entry Units | Usage Unit Type | Notes | Category Combination | Weekending Date |  | 286.164 | SX
WTC001: Implementation - 001 - UPS Bright Suite | Bright Performance Configuration (T&M) | UAT - Packing Slip and query adjustments | Daniel Stenger | 2025-01-17 | 2 | Hour | 2:00 WTC Packing slip recreation + query adjustments |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Bright Performance Configuration (T&M) | Reports & Dashboards | Mitchell Lantz | 2024-10-01 | 0.333 | Hour | Writing query with Daniel for stock in container report |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Bright Performance Configuration (T&M) | Reports & Dashboards | Daniel Stenger | 2024-09-06 | 2 | Hour | Schedulers to check onTime booleean and to update actual release date |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Bright Performance Configuration (T&M) | Reports & Dashboards | Daniel Stenger | 2024-09-04 | 2 | Hour | WTC Packing Carton Label query + label creation + testing 2:00 |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-15 | 1.5 | Hour | Widget to show ready to ship orders on pallets ready to close out |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-14 | 3 | Hour | Adding rules and testing to sum container weights on shipment and adjust ship via based on total sumShipping widget to determine pallets ready to ship |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Daniel Stenger | 2025-01-13 | 1.167 | Hour | WTC: 100 lbs testing 1:10 + customer communication |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Keegan McGuire | 2025-01-10 | 0.5 | Hour | WTC / Deposco - UPS Ground w Freight Pricing email thread review |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-08 | 2 | Hour | Follow the leader logic and testing to show previously scanned pallets |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Sara Kulkarni | 2025-01-08 | 1 | Hour | Created a test report model and Assigned Pallet dashboard widget to show the order number, container number, container weight, assigned pallet. ordered by oh.number and assigned pallet |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Sara Kulkarni | 2025-01-07 | 1 | Hour | WTC external call with Bruce and John to review the shipping solution |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-06 | 1.5 | Hour | Testing hundred weight rates with multi package ordersInternal sync with team on future solution for hundred weight |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Daniel Stenger | 2025-01-06 | 1.5 | Hour | 1:00 Rate shopping testing multiple containers and weight being > 150 pounds scenario 0:30 Freight Pricing investigation online |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Keegan McGuire | 2025-01-06 | 1 | Hour | shipping solution session, WTC - Shipping Solution - Alignment before Tues call |  | 2025-01-11 | Remaining | 259.256 | 422.744
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Sara Kulkarni | 2025-01-06 | 0.5 | Hour | WTC Internal sync to go over shipping solution alignment |  | 2025-01-11 | UAT
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-03 | 0.5 | Hour | Path forward scenarios |  | 2025-01-04 | Go Live/PGL | -140
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-03 | 0.5 | Hour | Meeting with ups on 100 weight config and discussion in shipping |  | 2025-01-04 | Open Config |  |  |  | Bright Socket
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-03 | 0.5 | Hour | Sync on pallet shipping and ups freight pricing solutions |  | 2025-01-04 |  | 119.256 |  | 0
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Daniel Stenger | 2025-01-03 | 0.417 | Hour | Rate shopping investigation |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Daniel Stenger | 2025-01-03 | 0.333 | Hour | Shipping meeting |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Sara Kulkarni | 2025-01-03 | 0.5 | Hour | WTC internal call to discuss the shipping solution |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Josiah Ogier | 2025-01-02 | 0.75 | Hour | Sync with Daniel and Keegan on pallet shipping flow |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Daniel Stenger | 2025-01-02 | 0.75 | Hour | pallet shipping internal meeting |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Keegan McGuire | 2025-01-02 | 1.75 | Hour | WTC - Weekly Status (External), WTC - Pallet Shipping - Workflow Review |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | UPS 100 Weight Solutioning | Sara Kulkarni | 2025-01-02 | 1 | Hour | WTC external call with John and Bruce to review the pallet shipping workflow in UA |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Shipping Carrier Configuration/Support | Daniel Stenger | 2024-11-26 | 0.333 | Hour | 0:20 paperless enabled documentation + client communication |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Deposco API Support (Cubiscan) | Daniel Stenger | 2024-11-07 | 2 | Hour | 2:00 Rate shop profile testing (after meeting with mark a ticket was created to auto select rate) |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Deposco API Support (Cubiscan) | Josiah Ogier | 2024-09-26 | 0.5 | Hour | Cubiscan setup emails and json api test |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Shipping Carrier Configuration/Support | Josiah Ogier | 2024-09-24 | 1 | Hour | Rateshopping setup |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Shipping Carrier Configuration/Support | Josiah Ogier | 2024-09-23 | 2.75 | Hour | UPS testing and test data creationStamps testing and test data creation |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Shipping Carrier Configuration/Support | Josiah Ogier | 2024-09-19 | 1 | Hour | Test case review with team and shipping carrier setup |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Deposco API Support (Cubiscan) | Josiah Ogier | 2024-09-19 | 0.25 | Hour | Sync with Nolan on cubiscan implementation timeline |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Bright Socket Configuration (T&M) | Deposco API Support (Cubiscan) | Nolan Pridgen | 2024-09-17 | 0.5 | Hour | WTC - reviewing cubican packing integration/MHE handling with WTC team |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2025-01-03 | 0.5 | Hour | Testing ups ground v ups ground w freight pricing label calls and test data |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Shipping - Staged Pack containers to a pallet | Josiah Ogier | 2025-01-02 | 0.5 | Hour | Testing logic to build pallet then ship using single container packing and potential options moving forward with rules |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-12-17 | 0.25 | Hour | Added tp code to listbox in single container packing |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Warehouse Lookup Query Modification | Josiah Ogier | 2024-12-10 | 2 | Hour | Adding PO inner query to find lines for item entered |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Shipping - Add Pallet text box during scontainer packing that maps what they ... | Josiah Ogier | 2024-11-26 | 2 | Hour | Testing script and metadata, adding screen elements for scanning palelt for shipping containers |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Shipping - Staged Pack containers to a pallet | Josiah Ogier | 2024-11-26 | 1 | Hour | Testing containers get stamped with scanned pallet during packing |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-11-13 | 0.5 | Hour | 0:30 bill receiver test. + customer communication and credentials retrieval |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-11-12 | 0.5 | Hour | Meeting w Imad to go over rate shopping enhancement and testing w WTC environment in their DEV environment |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | BatchPicking - add item.name to single screen picking | Sara Kulkarni | 2024-11-11 | 1 | Hour | WTC config UAT critical task: configured and Validated that item name is displaying in Single Screen Batch Process in Picking menu + tested that item name displays in the packing screens |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Shipping - Add Listbox showing all open containers for trading partner | Brian Jung | 2024-11-11 | 0.583 | Hour | SCPacking listbox override for Parent container with Daniel |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Descoped - Cartonization | Daniel Stenger | 2024-11-08 | 2 | Hour | 2:00 single container rules to stamp pcontainer numbers in pallet WIP |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Descoped - Cartonization | Daniel Stenger | 2024-11-07 | 2 | Hour | 2:00 single container rules to stamp pcontainer numbers in pallet |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Descoped - Cartonization | Daniel Stenger | 2024-11-06 | 0.5 | Hour | 0:30 Changes to the UCC number logic |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-10-11 | 0.25 | Hour | Testing ucc number generation for 20 characters |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Configuration (UI) | Daniel Stenger | 2024-10-08 | 1.583 | Hour | 1:15 Order comes down and tp.paymentTerms = COD then set ship via = ship outside system and set order packing note to say it is shipping outside and to use worldship 0:20 COD BR |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Putaway | Daniel Stenger | 2024-10-02 | 1.5 | Hour | 1.30 Only allow user to scan container that exists in the system |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-10-02 | 3.333 | Hour | 1:30 PDF PACKING SLIP + SINGLE CONTAINER PACKING BUSINESS RULES 1:50 New Carton Label Creation + testing + business rules to stamp carton sequence |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Putaway | Daniel Stenger | 2024-10-01 | 4 | Hour | 2:00 Changing Screen Listbox to add zones 2:00 Remove receiving from suggested listbox |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-10-01 | 1.667 | Hour | NEW PACKING SLIP CREATION30 Min Split Outbound Button 0:10 Changes to Packing XAML |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-09-27 | 1.5 | Hour | 1:30 Printing Rules |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Receiving | Daniel Stenger | 2024-09-27 | 0.333 | Hour | WTC 0:20 Receiving business rule change |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Receiving - Validation | Josiah Ogier | 2024-09-26 | 0.25 | Hour | Waving and picking video review |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-09-26 | 2.25 | Hour | 1:00 Automations setting 0:45 Postman Testing automations 0:30 Cross References Testing - Not working |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-09-25 | 2.167 | Hour | 0:40 Cross References set up 1:30 Troubleshooting API postman orders. Ship via not |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Sara Kulkarni | 2024-09-25 | 1.5 | Hour | loom videos of building and releasing waves of ecomm singles, ecomm ws, ws small and ws large and picking of the same. |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Receiving - Validation | Josiah Ogier | 2024-09-24 | 0.5 | Hour | Reviewing bruce tests in packing and emails |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-09-18 | 1 | Hour | Adding cubiscan down packing and testing outbound soft close packs |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-09-17 | 0.25 | Hour | Cubiscan payloads and email communication for cubiscan connection |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Sara Kulkarni | 2024-09-13 | 0.25 | Hour | WTC test cases after outbound demo on Thursday: staging after all picking |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Sara Kulkarni | 2024-09-13 | 0.25 | Hour | WTC test case for packing: entering dimensions and weight after packing, but not closing the packing process. |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Daniel Stenger | 2024-09-12 | 0.5 | Hour | 0:30 Picking staging testing cases + adding dims into soft close + testing |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Daniel Stenger | 2024-09-12 | 0.5 | Hour | 0:30 Batch Picking Bin config |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-09-04 | 0.25 | Hour | International shipping review of required item fields |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Daniel Stenger | 2024-09-03 | 2.333 | Hour | 1:00 Base config and testing Product Conversion 1:00 Meeting with Sara to go over Product Conversion config and test cases 0:20 Set up testing cases in tracker |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | NewScope - Kitting/Product Conversion | Sara Kulkarni | 2024-09-03 | 0.5 | Hour | Product conversion test cases for WTC |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-08-30 | 1.25 | Hour | Outbound demo |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-08-29 | 1 | Hour | Testing container logic in shipping process to show remaining containersPicking/packing/shipping demo prep |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Automation (POI) & Address Validation | Josiah Ogier | 2024-08-29 | 0.75 | Hour | Adding logic to set ecomm orders and testing |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Daniel Stenger | 2024-08-29 | 0.333 | Hour | Test cases review |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Putaway | Daniel Stenger | 2024-08-22 | 0.333 | Hour | Changing Move Stock Screen |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Sara Kulkarni | 2024-08-19 | 0.5 | Hour | Packing and shipping test cases |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Sara Kulkarni | 2024-08-16 | 0.5 | Hour | test cases for waving and picking |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Automation (POI) & Address Validation | Sara Kulkarni | 2024-08-16 | 0.5 | Hour | test cases for automation and POI |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-08-14 | 2 | Hour | Packing and shipping setup, testing and use cases |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Waving & Picking | Josiah Ogier | 2024-08-14 | 1.25 | Hour | Waving/picking setup, testing and use cases |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Automation (POI) & Address Validation | Josiah Ogier | 2024-08-14 | 0.75 | Hour | POI and automations setup, testing and use cases |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Replenishment | Daniel Stenger | 2024-08-08 | 1 | Hour | Training Inv Management |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Cycle Counting | Daniel Stenger | 2024-08-07 | 1.5 | Hour | Adjust inventory set up + testing Meeting w Sara to walk her over the config put in place |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Replenishment | Sara Kulkarni | 2024-08-07 | 0.25 | Hour | Ran Adjust inventory test cases in WTC UA |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Packing & Shipping | Josiah Ogier | 2024-08-06 | 0.5 | Hour | Container api updates testing |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Replenishment | Sara Kulkarni | 2024-08-05 | 0.5 | Hour | Ran replenishment test cases in WTC UA. |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Replenishment | Daniel Stenger | 2024-08-02 | 3.5 | Hour | Call w Sara to go over config and unit test cases Replens set up validating and testing |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Bright Warehouse Configuration (T&M) | Putaway | Daniel Stenger | 2024-08-01 | 1 | Hour | inbound demo |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-28 | 1 | Hour | Checking and email to WTC for progress around GNG and other tasksReview and slide deck for Office hours |  | 2025-02-01
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2025-01-28 | 0.5 | Hour | Office Hours |  | 2025-02-01
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2025-01-21 | 0.5 | Hour | Shayne/Keegan |  | 2025-01-25
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-20 | 0.5 | Hour | Budget Review WE 1/17 |  | 2025-01-25
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2025-01-17 | 1 | Hour | Weekly internal post UAT connection with Keegan |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-17 | 0.5 | Hour | Budget Review WE 1/10 |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2025-01-17 | 0.5 | Hour | Internal team sync |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2025-01-17 | 0.5 | Hour | Internal Meeting |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Daniel Stenger | 2025-01-17 | 0.25 | Hour | WTC: Jira ticket to wipe out environment 0:15 |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2025-01-17 | 0.083 | Hour | internal status meeting |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Sara Kulkarni | 2025-01-17 | 0.5 | Hour | WTC internal sync to discuss go live timeline and open items from UAT |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2025-01-16 | 1 | Hour | Post UAT Review and GNG review |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2025-01-16 | 0.75 | Hour | UAT remote support phone call with Josiah on go live timeline and invoicing challenges, talking through potential solutions |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2025-01-16 | 1 | Hour | Weekly Status (External) |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Sara Kulkarni | 2025-01-16 | 0.5 | Hour | WTC external sync to discuss no go/ go live discussion with John , bruce and Rich |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2025-01-14 | 0.5 | Hour | remote UAT support |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Daniel Stenger | 2025-01-09 | 0.167 | Hour | Booking Travel |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-08 | 0.75 | Hour | Agenda review and travel form review for WTC approval Budget Review WE 1/3 |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2025-01-07 | 0.5 | Hour | Weekly internal |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2025-01-07 | 1 | Hour | 100 weight and UAT prep |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-07 | 0.5 | Hour | Project updates and remaining budget review |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2025-01-07 | 1.5 | Hour | Weekly sync with John and BruceWeekly internal team sync |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2025-01-07 | 0.5 | Hour | 0:30 Meeting |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2025-01-07 | 1 | Hour | 1:00 external meeting |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Daniel Stenger | 2025-01-07 | 0.667 | Hour | 0:30 Draft Agenda 0:10 Repricing for trip investigation |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2025-01-07 | 2 | Hour | Weekly Status (External)Weekly Status (External) |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2025-01-07 | 1 | Hour | Weekly Status InternalWeekly Status Internal |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Sara Kulkarni | 2025-01-07 | 0.5 | Hour | WTC internal sync with team |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2025-01-06 | 0.5 | Hour | 100 Weigtt follow up |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2025-01-06 | 0.5 | Hour | 0:30 Internal Meeting |  | 2025-01-11
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2025-01-03 | 0.5 | Hour | Meeting with UPS around the shipping 100 weight for WTC |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2025-01-03 | 0.25 | Hour | Follow up discussion from the UPS 100 weight and solutioning |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-03 | 0.25 | Hour | Budget Review WE 12/27 |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2025-01-02 | 1 | Hour | Weekly External |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2025-01-02 | 0.5 | Hour | Pallet Shipping internal review |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2025-01-02 | 0.5 | Hour | Weekly Deck prep |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2025-01-02 | 0.75 | Hour | Weekly sync with John and Bruce |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2025-01-02 | 0.833 | Hour | 0:50 external meeting |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Daniel Stenger | 2025-01-02 | 0.25 | Hour | 0:15 Filling travel plan document and researching prices in delta and Marriott |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Sara Kulkarni | 2025-01-02 | 0.5 | Hour | WTC - Weekly Status (External) with Bruce and John |  | 2025-01-04
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-23 | 0.5 | Hour | Budget Review WE 12/20 |  | 2024-12-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-12-23 | 2 | Hour | Reviewing pallet shipping flow and setup trying to retrieve shipping labels with single pallet scans |  | 2024-12-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-20 | 1 | Hour | Budget Review WE 12/6 and 12/13 |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-19 | 0.5 | Hour | Slide deck prep |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-12-19 | 0.5 | Hour | Weekly External |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-12-19 | 0.5 | Hour | Weekly sync with john and Bruce |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-12-19 | 0.333 | Hour | WTC - Weekly Status (External) |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Working Sessions - Test Case Completion | Shayne Schmidt | 2024-12-18 | 1 | Hour | Working Session 2 |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-18 | 0.25 | Hour | Updates to the Project Plan for Working Sessions |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Working Sessions - Test Case Completion | Josiah Ogier | 2024-12-18 | 1 | Hour | Test case call with John and Bruce |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Working Sessions - Test Case Completion | Shayne Schmidt | 2024-12-17 | 1 | Hour | Working Session 1 |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-12-17 | 0.5 | Hour | Weekly Internal |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Working Sessions - Test Case Completion | Josiah Ogier | 2024-12-17 | 1.25 | Hour | External sync with John and Bruce to go through test cases |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-12-17 | 0.5 | Hour | Internal weekly sync with Shayne and Daniel |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Working Sessions - Test Case Completion | Daniel Stenger | 2024-12-17 | 1 | Hour | Testing Session |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-12-17 | 0.25 | Hour | Internal |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-12-16 | 0.25 | Hour | Review test cases document and add new items |  | 2024-12-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-12-12 | 0.5 | Hour | Weekly External |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-12 | 0.5 | Hour | Weekly Deck prep |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-12-12 | 0.25 | Hour | Weekly external sync with John and Bruce |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-12-12 | 0.5 | Hour | weekly external |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-12-10 | 0.5 | Hour | Weekly Internal |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-12-10 | 0.5 | Hour | Fedex setup sync with John |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-12-10 | 0.5 | Hour | Team weekly sync internal with Shayne |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-12-09 | 1 | Hour | Estimating Bruce requests and feasibility around warehouse lookup and packing voice prompts |  | 2024-12-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-05 | 0.5 | Hour | Slide deck prep for External |  | 2024-12-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-12-05 | 0.5 | Hour | Weekly External |  | 2024-12-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-12-05 | 0.5 | Hour | weekly team sync |  | 2024-12-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-12-05 | 0.083 | Hour | WTC - Weekly Status (External) |  | 2024-12-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-12-03 | 0.5 | Hour | Weekly Internal |  | 2024-12-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-12-03 | 0.5 | Hour | Budget Review WE 11/29 |  | 2024-12-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-29 | 1 | Hour | Weekly Deck Prep Budget Review WE 11/22 |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-11-29 | 0.75 | Hour | Weekly External |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-11-29 | 0.667 | Hour | Wtc 0:40 external meeting |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-11-29 | 0.5 | Hour | WTC - Weekly Status (External) |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-11-26 | 0.5 | Hour | Weekly Internal |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-11-26 | 0.5 | Hour | Weekly team sync |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-11-26 | 0.333 | Hour | Internal Meeting |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-11-26 | 0.25 | Hour | internal status meeting |  | 2024-11-30
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-22 | 0.5 | Hour | budget Review WE 11/15 |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-21 | 0.5 | Hour | Slide deck Prep |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-11-21 | 0.75 | Hour | Weekly External |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-11-21 | 1.75 | Hour | Creation of single container packing listbox to show all containers for trading partners that can be shipped and testing |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-11-21 | 0.5 | Hour | Weekly external sync |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-11-21 | 0.667 | Hour | 0:05 Field mapping customer communication 0:35 External Call |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-11-21 | 0.5 | Hour | WTC - Weekly Status (External) |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-20 | 0.5 | Hour | Budget Review WE 11/15 |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-11-19 | 0.5 | Hour | Weekly internal |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-11-19 | 0.5 | Hour | Weekly internal sync |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-11-19 | 0.5 | Hour | WTC - Weekly Status Internal |  | 2024-11-23
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-15 | 0.5 | Hour | Budget review WE 11/8 |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-11-14 | 0.5 | Hour | Weekly Status |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-14 | 0.5 | Hour | Weekly Deck Prep |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-11-14 | 0.5 | Hour | Weekly sync with John and Bruce |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-11-14 | 0.25 | Hour | Go/no-go task review and additions |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-11-14 | 0.5 | Hour | 0:30 External |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-11-14 | 0.5 | Hour | weekly status meeting |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-11-12 | 0.5 | Hour | Weekly internal |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-11-12 | 0.5 | Hour | Internal team sync |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-11-12 | 0.5 | Hour | 0:30 internal |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-11-12 | 0.5 | Hour | WTC - Weekly Status Internal |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-11-11 | 0.5 | Hour | Sync with Daniel on shipping listbox rules |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-11-11 | 0.5 | Hour | Rules Packing overview w Josiah |  | 2024-11-16
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-11-07 | 0.5 | Hour | Weekly External |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-11-07 | 0.167 | Hour | External Meeting |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-11-07 | 0.167 | Hour | 0:10 External Meeting |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-11-05 | 0.5 | Hour | Weekly Internal |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-05 | 0.25 | Hour | Review internally for Hours |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-11-05 | 0.25 | Hour | internal team sync |  | 2024-11-09
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-11-01 | 0.25 | Hour | Budget Review EOM OCT |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-10-31 | 0.5 | Hour | Weekly External |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-10-31 | 0.25 | Hour | External Meeting |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-10-31 | 0.25 | Hour | WTC - Weekly Status (External) |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-29 | 0.5 | Hour | Weekly internal |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-29 | 0.083 | Hour | Internal |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-28 | 0.5 | Hour | Budget Review WE 10/25 |  | 2024-11-02
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-25 | 0.5 | Hour | Budget Review WE 10/18 |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-10-25 | 0.5 | Hour | Weekly External |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-10-25 | 0.25 | Hour | Weekly sync with John |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-10-25 | 0.167 | Hour | External Meeting |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-22 | 0.5 | Hour | Weekly internal |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-22 | 0.25 | Hour | Alignment/Follow up for confirmed Go Live Scenario and approvals on onsite takeaways |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-22 | 0.25 | Hour | Internal meeting |  | 2024-10-26
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-17 | 0.5 | Hour | Slide deck prep |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-10-17 | 0.5 | Hour | Weekly external |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-10-17 | 0.5 | Hour | Weekly external sync |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-10-17 | 0.5 | Hour | 0:30 Client Call |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-10-17 | 0.5 | Hour | WTC - Weekly Status (External) |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-16 | 0.5 | Hour | Go Live scenarios communication and review |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-15 | 1 | Hour | 30m - Weekly internal 30m - Shayne/Keegan review for Go Live/Budget |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-10-15 | 0.5 | Hour | Weekly team sync |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-15 | 0.5 | Hour | 0:30 Internal Call |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-10-15 | 1.25 | Hour | Shayne / Keegan - WTC budget and timeline review, internal status meeting |  | 2024-10-19
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-11 | 0.5 | Hour | Budget Review WE 10/4 |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-10 | 0.25 | Hour | Updates for the Weekly External |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-10-10 | 0.5 | Hour | Weekly Status |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-10-10 | 0.5 | Hour | External Meeting |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-10-10 | 0.5 | Hour | WTC - Weekly Status (External) |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-10-09 | 0.25 | Hour | review project plan and hrs |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-08 | 0.5 | Hour | Weekly internal |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-08 | 0.5 | Hour | Budget Analysis to view what may be needed to get WTC to go live |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-08 | 0.5 | Hour | Internal Meeting |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-10-08 | 0.5 | Hour | Weekly Status Internal |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-07 | 0.5 | Hour | Shayne/Keegan |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-07 | 0.167 | Hour | Internal Meeting |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-10-07 | 0.25 | Hour | WTC - Weekly Status (External) |  | 2024-10-12
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-04 | 0.5 | Hour | Shayne/Keegan/Mike discussion on next steps |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-04 | 0.5 | Hour | Slide deck prep for External - Meeting pushed to Monday |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-10-04 | 0.5 | Hour | internal alignment on UAT open items and budget review |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-03 | 0.5 | Hour | Onsite post review |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-10-03 | 0.5 | Hour | Onsite sync and takeaways with team |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-03 | 0.5 | Hour | Post Onsite Internal Meeting |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-10-03 | 0.5 | Hour | WTC Internal - Post Onsite |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-02 | 0.5 | Hour | EOD Sync |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-10-01 | 0.5 | Hour | Weekly internal |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-10-01 | 0.25 | Hour | Budget Review EOM |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-10-01 | 0.75 | Hour | External EOD Sync |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-10-01 | 0.5 | Hour | Internal Meeting |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-10-01 | 0.5 | Hour | internal status meeting |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-10-01 | 0.5 | Hour | WTC EOD Sync |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-30 | 0.5 | Hour | Budget Review WE 9/27 |  | 2024-10-05
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-27 | 0.75 | Hour | Budget Review WE 9/21Updates to SOW003 - Adding in Rate Shopping |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-09-27 | 0.5 | Hour | Reviewing current process flows with team |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-09-27 | 0.5 | Hour | WTC 0:30 Call internal Process Flows review |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-26 | 0.5 | Hour | external deck prep |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-09-26 | 0.5 | Hour | Weekly External |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-09-26 | 0.75 | Hour | Creating onsite agenda for pre uat |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-09-26 | 0.5 | Hour | Weekly sync with John and Bruce |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-09-26 | 0.5 | Hour | External Meeting |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-09-26 | 0.5 | Hour | rateshopping internal convos |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-09-26 | 0.5 | Hour | WTC - Weekly Status (External) |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-09-24 | 0.5 | Hour | Weekly internal |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-24 | 0.25 | Hour | SOW003 creation and submission |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-09-24 | 0.5 | Hour | Weekly team sync |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-09-24 | 0.5 | Hour | Internal MEeting |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-09-24 | 1 | Hour | setup carriers with Rateshopping , WTC - Weekly Status Internal |  | 2024-09-28
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-20 | 0.75 | Hour | Budget Review WE 9/13 |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-09-19 | 1 | Hour | Weekly External, transitioned to Working session |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-19 | 0.5 | Hour | Weekly Status deck prep |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-09-19 | 0.5 | Hour | Weekly external sync with team |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-09-19 | 1 | Hour | WTC - Weekly Status (External) |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-09-18 | 0.5 | Hour | Shayne/Keegan catch up |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-09-18 | 0.5 | Hour | Refinements to tracker, added items |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-09-17 | 0.5 | Hour | Weekly Internal |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-09-17 | 1.5 | Hour | Keegan internal sync on timelinesWeekly team sync |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-09-17 | 1 | Hour | Updating task tracker with go/no go, tasks, parking lot and cutover plans |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-09-17 | 0.5 | Hour | Internal Meeting |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-09-17 | 1 | Hour | project plan review, Cubiscan build review |  | 2024-09-21
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-09-12 | 1.75 | Hour | Outbound and product conversion demosPacking questions review |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-09-12 | 1.667 | Hour | 1:10 demo 0:30 Weekly Meeting |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-09-12 | 0.5 | Hour | Weekly Status (External) |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-09-11 | 0.5 | Hour | Working Session |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-09-11 | 0.5 | Hour | Outbound question review |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-09-11 | 0.5 | Hour | External Meeting |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-09-11 | 0.5 | Hour | WTC - Unit Testing Working Session |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-09-10 | 0.5 | Hour | Weekly internal |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-09-10 | 0.5 | Hour | Weekly team sync |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-09-10 | 0.5 | Hour | Internal Meeting |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-09-10 | 0.5 | Hour | WTC - Weekly Status Internal |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-09 | 1 | Hour | Budget Review WE 9/6Weekly Deck review |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-09-09 | 0.5 | Hour | Weekly external |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-09-09 | 0.5 | Hour | Weekly meeting with bruce and john |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-09-09 | 0.583 | Hour | 0:35 External Meeting |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-09-09 | 0.5 | Hour | Weekly Status (External) |  | 2024-09-14
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-09-05 | 1.25 | Hour | Budget Review August 2024 |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-09-03 | 0.5 | Hour | Weekly internal |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-09-03 | 0.5 | Hour | Weekly team sync |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-09-03 | 0.333 | Hour | Internal Meeting |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-09-03 | 0.333 | Hour | weekly internal status |  | 2024-09-07
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-08-30 | 2.583 | Hour | Outbound Demo 1:20 1:15 Receiving Config Changes and new button config (need to add this to receiving bucket) |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-29 | 0.5 | Hour | Weekly updates and slide deck prep |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-08-29 | 0.5 | Hour | Weekly External |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-08-29 | 0.5 | Hour | Weekly sync with john and bruce |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-08-29 | 0.5 | Hour | External Meeting |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-08-29 | 0.5 | Hour | External status call |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-08-28 | 0.25 | Hour | Task tracker review and communication to team |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-08-28 | 0.333 | Hour | Receiving troubleshooting w Sara |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-08-27 | 0.5 | Hour | Weekly internal |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-08-27 | 0.5 | Hour | Weekly internal team sync |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Josiah Ogier | 2024-08-27 | 0.25 | Hour | Packing slip emails and replens help with John |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-08-27 | 0.5 | Hour | External Meeting |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-08-27 | 0.5 | Hour | WTC - Weekly Status Internal |  | 2024-08-31
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-22 | 0.5 | Hour | Weekly deck prep |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-08-22 | 0.5 | Hour | Weekly External |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-08-22 | 0.5 | Hour | External Meeting |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-08-22 | 0.25 | Hour | Ticket: 179842, Invalid Character for Inventory Adjustment Location - system working as expected |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-08-22 | 0.5 | Hour | WTC - Weekly Status (External) |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-08-20 | 0.5 | Hour | Weekly internal |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-08-20 | 0.5 | Hour | Internal weekly sync |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-08-20 | 0.5 | Hour | internal status meeting |  | 2024-08-24
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-15 | 0.5 | Hour | Weekly Deck prep |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-08-15 | 0.5 | Hour | Weekly External |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-08-15 | 0.5 | Hour | Weekly team sync |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Shayne Schmidt | 2024-08-13 | 0.5 | Hour | Weekly Internal |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-08-13 | 0.5 | Hour | weekly internal sync |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-08-13 | 0.5 | Hour | WTC - Weekly Status Internal |  | 2024-08-17
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-08 | 0.5 | Hour | SX updates and Slide deck prep |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-08-08 | 1.25 | Hour | Demo - Cycle Counts/ReplensWeekly External |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-08-08 | 1.25 | Hour | Cycle counts and replenishments demoWeekly sync |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-08-08 | 0.5 | Hour | Client Meeting |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-06 | 0.25 | Hour | Socket Swap SOW and Scheduling Demos |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Josiah Ogier | 2024-08-06 | 0.5 | Hour | Internal weekly sync |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Daniel Stenger | 2024-08-06 | 0.5 | Hour | Internal Meeting |  | 2024-08-10
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-02 | 0.5 | Hour | Budget Review - EOM July |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Administration | Shayne Schmidt | 2024-08-01 | 0.5 | Hour | ML Updates and slide deck prep |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Shayne Schmidt | 2024-08-01 | 0.5 | Hour | Weekly External |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Josiah Ogier | 2024-08-01 | 1.5 | Hour | inbound/putaway demoWeekly team sync |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Daniel Stenger | 2024-08-01 | 0.5 | Hour | Client meeting |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | External Meeting | Keegan McGuire | 2024-08-01 | 1.5 | Hour | WTC - Demo Inbound/Putaway, WTC - Weekly Status (External) |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Project Management (T&M) | Internal Meeting | Keegan McGuire | 2024-08-01 | 0.5 | Hour | external sync prep |  | 2024-08-03
WTC001: Implementation - 001 - UPS Bright Suite | Support (Non-billable) |  | Keegan McGuire | 2025-01-28 | 0.5 | Hour | Shayne/Keegan - WTC touchbase | Development Meeting | 2025-02-01
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Post UAT - Process Testing | Daniel Stenger | 2025-01-30 | 0.167 | Hour | 0:10 WTC wiping out all storage records |  | 2025-02-01
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Post UAT - Process Testing | Daniel Stenger | 2025-01-29 | 0.25 | Hour | Waving Troubleshoot + customer communication |  | 2025-02-01
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Onsite UAT | Josiah Ogier | 2025-01-16 | 6.5 | Hour | Onsite uat |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Onsite UAT | Daniel Stenger | 2025-01-16 | 6.5 | Hour | UAT |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Onsite UAT | Josiah Ogier | 2025-01-15 | 8 | Hour | Onsite uat |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Onsite UAT | Daniel Stenger | 2025-01-15 | 8.833 | Hour | UATOverriding screen elements to show available QTY |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Onsite UAT | Josiah Ogier | 2025-01-14 | 8 | Hour | Onsite UAT |  | 2025-01-18
WTC001: Implementation - 001 - UPS Bright Suite | Validate (T&M) | Onsite UAT | Daniel Stenger | 2025-01-14 | 8.5 | Hour | UAT |  | 2025-01-18

## Go Live Scenarios
| Thanksgiving impact as to why two Go live Dates |  | Jan 2025 Go Live
| Scenario 1a | Scenario 2 | Scenario 3
Config/Validation Completion | 2024-11-15 | 2024-11-15 | 2024-01-10
UAT | 11/20 and 11/21 | 11/20 and 11/21 | 1/15 and 1/16
GNG | 2024-11-26 | 2024-12-03 | 2024-01-21
Cutover | 12/2 and 12/3 | 12/6 and 12/9 | 1/24 and 1/27
Go Live | 2024-12-04 | 2024-12-10 | 2025-01-28
Post Go Live Support | 2024-12-09 | 2024-12-16 | 2024-02-03
Project Closeout | 2024-01-03 | 2024-01-03 | 2024-02-28
Risks | Right after Holiday Week | DEP AC on 12/12 | Hours for the project
| Cubiscan readiness | Cubiscan Readiness | Customer Engagement
| Any high volume risks? | Any high volume risks?
Addtional Notes | Team is onsite on Wed/Fri | Daniel is not available for Go Live | Cubiscan should be available and connected
| Could be back onsite the following Mon/Tues | Difference from go live of 10/15 to this date | Difference from go live of 10/15 to this date
| Daniel is not available for Go Live |  | Everything completed and ready for Go Live by 11/30, December could be a pause in communication/reduction of hours burned
Difference from go live of 10/15 to this date